 Programme Completion Review

Title: Mexico Bilateral Prosperity Programme (previously Mexico Bilateral Prosperity Fund)
Final Programme Spend £ (full life): £31.5m	Review Date: June 2022	April 2022
Programme Code: N/A	Start Date: April 2017	End Date: March 2022

Summary of Programme Performance

Year	2019	2020	2021	Close (2022)
Programme Score	A	A	B	B
Residual Risk Exposure Rating	Moderate	Moderate	Major	Minor

DevTracker Link to Business Case (and any addendum):	www.gov.uk/government/publications/prosperity-fund-mexico-programme
DevTracker Links to all logframes used during programme lifetime:

Mexico Bilateral Prosperity Programme: Financial Services Strand
Call for SMEs to Join the Caravana FinTech Initiative
Credit: Mexico Financial Services Programme

LIST OF ACRONYMS

ACROL – Anti-corruption and Rule of Law
APF – Agile Programming Fund
AMAFORE – Mexico’s Pension Fund Management Institution
BANXICO – Mexico’s Central Bank
CONAVIM – National Commission to Prevent and Eradicate Violence Against Women
CONEVAL – National Council for the Evaluation of Social Policy
COPARMEX – Mexican Employers’ Association
CONALEP – National College of Professional Technical Education
CNBV – National Banking and Securities Commission
CONSAR – National Retirement Savings System Commission
DAC – Development Assistance Committee
DFID – Department for International Development
DIT – Department for International Trade
FCDO – Foreign, Commonwealth and Development Office
Fintech – Financial Services Technology
GDP – Gross Domestic Product
GNI – Gross National Income
HMA – Her Majesty’s Ambassador
HMG – Her Majesty’s Government
IADB – Inter American Development Bank
IPA – Infrastructure and Projects Authority
ITT – Invitation to Tender
KPI – Key Performance Indicators
MoU – Memorandum of Understanding
MREL – Monitoring, Reporting, Evaluation, Learning
MSMEs – Micro, small and medium enterprises
ODA – Official Development Assistance
OECD – Organisation for Economic Cooperation and Development
OGD – Other Government Department
ORT – Mexico City’s Regulatory Body for Transport
OSJA – Overseas Security and Justice Assistance
PBR – Payment by results
PF – Prosperity Fund
PPP – Public Private Partnership
SEMOVI - Mexico City’s Ministry of Mobility
SESNSP – Executive Secretariat of the National System of Public Security
SDGs – Sustainable Development Goals
SLA – Service Level Agreements
SME – Small and medium-size enterprises
SoR – Statement of Requirements
SRO – Senior Responsible Officer
ToC – Theory of Change
VfM – Value for Money
WB – World Bank
WHO – World Health Organisation

A. Summary and Overview

Description of the programme and what it has achieved

The Mexico Prosperity Fund (PF)[1] Programme was originally planned in 2017 as a five-year, £60 million investment. It’s purpose was to support inclusive economic development in Mexico through poverty reduction and gender equality. Secondary benefits aimed to increase bilateral trade and investment between Mexico and the UK. The PF delivered through 4 strands: Anti-Corruption and the Rule of Law (ACROL), Energy[2], Future Cities and Financial Services. After nearly two years of design and mobilisation, the programme was launched formally by the Foreign Secretary in Mexico’s Palacio Nacional in August 2019. It formed a central element of the UK-Mexico Partnership for Sustainable & Inclusive Growth signed during that visit. Individual programmes were launched soon after with strong engagement from Mexican governments demonstrated through the large volume of project proposals and areas for partnership identified.
[1] The Prosperity Fund was re-named Prosperity Programme in 2021.
[2] Following an internal review on Paris Agreement alignment, the Energy strand became the Clean Energy strand.

The seismic impact of the pandemic on the UK economy forced the UK government to take tough but necessary decisions, and as announced in 2020, the UK moved to spending 0.5% of GNI as Official Development Assistance (ODA) in 2021. Following a thorough review, the FCDO’s programme budget was allocated in accordance with UK strategic priorities against the challenging financial climate of COVID-19.  Throughout the business planning process, the FCDO has strived to ensure that every penny of ODA spend brings maximum strategic coherence, impact and value for taxpayers’ money. The FCDO focuses on core HMG priorities for poverty reduction, including getting more girls into school, providing urgent humanitarian support to those who need it most, and tackling global threats like climate change, COVID-19 recovery and other international health priorities. Following the move to 0.5%, this Programme was closed earlier than planned.

This Programme Completion Review reflects that the Programme had limited time to deliver planned results, as well as reflecting the progress and achievements that have been possible. Where objectives have not been completed this does not necessarily reflect on the quality of Programme design or delivery.

The total bilateral PF investment in Mexico was £31,599,795.13 or 52.66% of the original Programme allocation. Despite the early closure, significant results were achieved. For example, through technical support provided by the Future Cities strand, 41,732 people have access to more affordable transport, 31,495 people can use low carbon transport such as new cycling lanes and 170,000 people in the city of Guadalajara benefit daily from the new public rapid bus service. The Financial Services strand provided technical support to the Mexican regulatory authority enabling the development of an advanced system for regulating the emerging FinTech market. The Anti-Corruption and Rule of Law strand successfully piloted a new homicide investigation model for the state of Tabasco and a second with a focus on embezzlement for the state of Jalisco. The Clean Energy strand met its targets in training government employees in Environmental Management Audit processes.

Results differed significantly across strands, with the Future Cities strand performing the strongest by meeting a number of outcome logframe level objectives within the programme life-cycle. Strands reached, predominantly, output and, in some case, intermediate outcome levels. On the backdrop of early closure, logframe targets for each strand were re-set in July 2021 against the output level only. When averaging the four strands, the programme scored a “B” meaning that it moderately did not meet expectations when using the Aid Management Platform and programme scoring calculator. When comparing the Programme’s targets at all levels of the logframe against results recorded at the end of the project life-cycle, however, they fall short of their objectives, bringing into question value for money of the investment spent and weakening sustainable impact.

The strands were clearly adversely affected by a number of external factors such as the COVID-19 pandemic and the subsequent UK government decision to reduce GNI spend on ODA to 0.5% and, with respect to the Clean Energy strand, the shift of the federal government away from renewable energy plans. Though strands adjusted to these challenges revising logframe indicators to capture new objectives and targets, the speed of change meant that in some cases, indicators were not fully aligned to capture results effectively.

The Prosperity Programme was classified as ODA, therefore all spending under the Programme needed to be fully ODA compliant. Improving the generation and sharing of potential commercial leads with the Department of International Trade was also an important element of the Programme. Although substantially less than the low scenario estimate of £235m calculated during the business case stage, the Programme generated at least double the value of its final ODA spend in Secondary Benefits. These continue to be captured and are currently valued at:

2019/20	£36.2m
2020/21	£12.7m
2021/22	£14m
Legacy	To be confirmed
Total	£62.9m +

Major lessons learned, evidence generated and recommendations

When contracting, it is important to consider the technical skills and networks of implementing partners [IPs] and their governance frameworks. IPs with strong brand recognition which delivered through an alliance of organisations had the best results. They were able to blend technical expertise and knowledge of the local environment with strong financial and contractual management processes. As a result, they were able to engage more effectively with stakeholders and drive outcomes. Single IPs, with a shorter history and footprint in in Mexico, were not as effective as they were reliant on sub-contractors for delivery of targets. It is recommended that in the tendering process Terms of Reference include guidance towards IPs operating through an alliance model and that due diligence processes are robust enough to capture operational expertise but at the same flexible enough to ensure that key local technical knowledge and footprint is not excluded.

It is important to build in mechanisms to support long-term sustainability of programme work. Anchoring technical work and products developed for a wide range of partner country institutions and participants, could drive greater impact and strengthen sustainability beyond the programme life-cycle. At the same time, legacy and sustained influence could be delivered through platforms and depositories that could retain outputs and make them accessible to new stakeholders and participants. Lastly, the majority of the impact level indicators were set to be measured and captured beyond the life-cycle of the project. Whilst there is a logic behind this approach, it introduces a risk that the highest level of results will not be captured. Logframes should therefore be developed wherein impact statements can be measured during the programme’s life-cycle unless resources are made available to ensure follow-up of results upon programme closure.

The creation of new brands and platofrms is high-risk. Related to the sustainability point above, the establishment from scratch of new entities like EPI Energia and AhorrandoAndo carries a higher risk than working with, and improving, existing providers – a strategy that a sister programme, Skills for Prosperity, opted for in Mexico. A new entity requires many years of support to fully identify and occupy its market niche. In the event of early budget reductions, new investments are unlikely to be sustainable and that was the case here. The skills and financial services training platforms, which absorbed significant resources in their design and initial application, are likely to disappear as competitive brands. An approach that took existing providers and made them more inclusive, more accessible, more relevant and higher quality would have led to different outcomes.

Alignment to government priorities builds strong partnerships and delivers better results. Co-designing outputs with partner government institutions ensured that logframes remained viable and relevant. Success in this area was reinforced when the stakeholder agreed on acceptance criteria and implementation responsibilities were shared. For example, the Future Cities strand worked closely along these lines with policy-makers and technical experts in the sub-national government of Jalisco to expand a social fare policy and scheme with budgets and implementation forecasts committed by the authorities. By contrast, when the Mexican government moved away from market liberalisation of the energy sector, the Clean Energy strand faced challenges which significantly delayed implementation. More broadly, the UK’s ODA portfolio in Mexico experienced a reduction in federal government engagement with the transition to the current administration.

Strand’s communication strategies should include a greater emphasis on development. It is recommended that future programmes’ communications plans include a more robust, comprehensive and continuous approach to development communications, capturing human-centred stories and images that show impact and lessons learned. For example, work in the strands was often highly technical in nature, which limited the type of audience it could reach. Presenting the problem in a simple visual form could have enabled the strands to tell the story to a wider audience more effectively.

How this report was conducted

This report was conducted as a desk-based review of final project report documentation submitted by the implementing partners that delivered the work on behalf of the UK Government in Mexico. Wider documentation and reports from the strands was also reviewed. At the same time, members of the Embassy Programme Team engaged in a series of working sessions in April and May where lessons learned were discussed, feedback and reflections from key stakeholders revised and outputs and knowledge products produced and evaluated. This review also takes into account the independent evaluation cycle reporting that was contracted for the lifetime of the Programme.

Actions following approval of this report

The British Embassy in Mexico can continue to follow-up on impact seeded by this Programme:

Each of the strands has developed outputs in the form of knowledge products that have been accepted by government stakeholders and are now in implementation. Examples of this are evident from the Financial Services strand which developed, together with the Mexican Regulatory Agency for Banking and Finance, a series of platforms to mitigate risk around FinTech operations and strengthen regulatory practices. At the same time, the Future Cities strand’s technical work informed new policy and the development of a new bike lane network across Mexico City, used daily by thousands of citizens as well as the legal framework for improvements to the travelcard system. These, and other examples, are still being monitored by the Embassy for learning purposes and with a view to producing future impact stories and communications materials.

Strands have also developed a wide range of outputs that, though complete and accepted by the government stakeholder, have not yet reached implementation. Examples of these can be seen in the Future Cities Data Mobility Center project work for the government of Nuevo León or in the financial education materials developed for the Mexican authority regulating and managing pensions where follow-up work with stakeholders is required to drive implementation. To do this, the strands have developed hand-over materials for Embassy policy teams and DIT (where relevant) to take forward these actions.

The Programme has also explored where strands and specific projects may add value to other donor funded projects both within the FCDO and with partner agencies. For example, there is a strong interest in building further on the work delivered by the Future Cities strand where it relates to micro-mobility and carbon emissions reductions that can play important roles in implementing city level climate action plans. This exploratory work should continue with actions taken to map all projects and potential connections to on-going areas of work across donor agencies in the region. For example, the Financial Services strand work on Open Banking will be taken forward by the IADB later this year. Based on demand and positive results to date, there is strong interest from both the public and private sectors in the continuation of the Caravana FinTech model. The Embassy is also working to secure adoption of the financial education tools developed through implementation agreements with the Mexican government authorities.

Otherwise, there are no outstanding administrative actions following approval of this report. All final payments and assets have been accounted for. All MoUs and commercial agreements have been exited or tightly defined to need no further follow-up action from the UK.
## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£60m	£31.5m
Timeframe	4 years	3 years
Outcomes	Improved conditions for growth in Mexico, through increased capacity and an improved environment for trade and economic growth. Achieved through progress against 4 specific intermediate outcomes: / 1. More productive and resilient men and women, businesses and government officials to support Mexico’s transition to a low carbon economy. / 2. Improved efficient urban development in Mexico’s cities that results in better, safer and more sustainable public services for citizens, particularly women and girls. / 3. More inclusive and competitive Financial Services sector, accessible to all sections of Mexican society and new international entrants. / 4. More efficient detection and investigation of serious and organised crime and corruption cases.P	Modest progress was made towards achieving the purpose of the Programme to improve conditions for growth in Mexico, through increased capacity and an improved environment for trade and economic growth. / Given its early exit and reduced scale, this Programme delivered a much lower impact against all intermediate outcomes while the sustainability of interventions delivered was much weaker than planned. / A positive aspect is that proof of concept in each strand was realised to a good degree, corroborated by findings throughout the evaluation cycles. / Another positive aspect to consider is the momentum generated by the project – the Embassy and other development partners could choose to follow through on some of the impact delivered if resources were made available.

Overall assessment of programme outcomes, sustainability and VfM

The original Programme outcomes were only partially achieved. Two major contextual changes impacted the ability of this Programme to meet its outcome and impact goals:

COVID-19: This had an almost immediate impact on Programme outputs. There were delays to delivery due to travel and other restrictions and difficult challenges placed on abilities of implementing partners. For example, many project deliverables and work products were conceived and designed for a face to face world. These included co-design processes with end participants, capacity and training workshops, as well as behavioural insights focused activities. At the same time, government participants had to reprioritise budgets originaly forecast to support implementation and rethink solutions as new challenges and problems arose. The social and economical fall out from the pandemic also affected a number of assumptions within the Theory of Change given the changing characteristics and scale of poverty in Mexico.

UK 2021 Spending Review (SR): The one-year SR announced in late 2020 came into effect in April 2021. COVID-19 deeply affected our resources for development work in Mexico resulting in reduced Programme activities. Programme budgets were drastically cut for the FY21-22 requiring work plans to be significantly revised. Unable to operate on a reduced budget, the ACROL strand, for example, closed during the third quarter of the 21-22 financial year with the other strands of the Programme delivering a slimmed down work plan with a focus on responsible closure. The remaining strands all closed in March 2022, one year early than planned.

Review of the original Value for Money (VfM) assessment:

Final Cost of Programme: April 2017 - March 2022			Original Allocations
Clean Energy	DAI (Europe) Limited, varied to DAI Global UK Ltd	£10,029,380.34	£24.95m
Future Cities	Pricewaterhouse Coopers LLP	£7,690,658	£9.97m
Financial Services	DAI (Europe) Limited, varied to DAI Global UK Ltd	£5,172,143.09	£9.7m
Anti-Corruption & Rule of Law	PA Consulting Services Limited	£4,400,655	£8.67m
Financial Audits	Contracts	£76,958.70	£0.88m
Admin & programme delivery costs	FCDO	1,940,000	£2.98m
Platform charges	FCDO	1,120,000	1.68m
Transition phase	Various implementing partners	1,170,000	1.17m
Total:		£31,599,795.13	£60m

Cost drivers and performance

The COVID-19 pandemic was a significant cost driver across all strands. Projects had been developed in a pre-pandemic world where co-design, fieldwork, face-to-face courses and infrastructure pilots, to name some examples, were integral elements. The COVID-19 crisis required the Embassy Programme Team and implementing partners to revise work plans. Simultaneously, government stakeholder priorities changed drastically, putting at risk the co-funding committed. In some cases, entire projects were forced to be placed on pause. The result of this was that more time and resources were applied to planning and stakeholder engagement activities just as implementation was on the cusp of beginning. Additionally, activities related to contract management with a focus on change control increased.

The outcome of the Spending Review which led to an 85% cut to the Programme and its early closure, had the largest detrimental impact on the VfM proposition as outlined in the Business Case and therefore represent a key cost driver overall. The cuts to budget created considerable uncertainty in programme delivery, additional time and resources spent on contract management activities, stakeholder engagement, and, indeed, new proposal writing as teams looked to offset loss by securing new funds through other sources. Most damaging was that, during this process, strands were in effect paused with only essential activities being carried out. Significant cuts also meant that many projects were forced to be abandoned or drastically scaled down. For example, the amount of investment initially made in the creation of the EPI Energía project for the Clean Energy strand has been lost as the timeframe and investment available were not enough to turn this into a sustainable business model as planned. The ACROL investment was also much weaker from a VfM perspective as only preliminary diagnostics and investigation models were developed and not the advanced ones needed by the government. The original plan was to work with them to support full implementation of those models using UK expertise. The Financial Services and Future Cities strands have better VfM elements although similarly the amount invested initially on financial education will only be maintaned if AMAFORE continues to deliver against the MoU signed with the British Embassy. Additionally, there was a significant reduction in programme staff during the final quarter of the FY21-22.

A valuable mechanism which has helped reduce the impact of some of these cost drivers has been the British Embassy’s use of virtual teams (VTs) comprising representatives from climate change, trade, economic, defence, development and political teams. The VTs have been extraordinarily effective in handling the impact of cuts with external stakeholders as well as supporting reprioritisation processes for each Programme strand.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

The overarching Theory of Change (ToC) for this Programme is provided in Table 1. Each intermediate outcome statement has separate outputs designed to deliver against that statement.

Separate ToCs and logframes were developed for each strand. In all cases the intermediate outcome statement from the overarching ToC became the impact statement for each separate strand. Additional outcome statements for secondary benefits were added. This is better illustrated in Table 2. There were no changes made to outcome level indicators identified for each strand throughout the timeframe of the Programme.

The main finding of the first cycle independent evaluation was that ‘the design of the Programme was sound and aligned well with both Mexico’s National Development Plan and the Prosperity Fund’s objectives’, and also that ‘emerging results were promising’. The first cycle evaluation and the 2020 Annual Review proposed new recommendations for the logframes servicing each strand and new iterations were agreed in March 2021. This was the last logframe to capture adjustments and articulate results that would be delivered under the full allocation ahead of budget and timeframe cuts.

Joint work with all four contracted implementing partners took place during July 2021 and new logframes were agreed for each strand which adjusted for budget reductions – for example removal of certain outputs or output indicators, but with an assumption that the Programme would continue for a further year. These logframes were not updated and instead were accepted as final for the rest of the Programme.

Table 1: Original Programme Level Theory of Change: What is the developmental problem?
Impact	Outcomes	Intermediate Outcome	Outputs
A relationship that promotes growth between UK and Mexico: / Higher rates of sustainable growth in Mexico / Greater investment flows / Greater trade flows	Improved conditions for growth in Mexico, through increased capacity and an improved environment for trade and economic growth	1. More productive and resilient men and women, businesses and government officials to support Mexico’s transition to a low carbon economy.	Larger pipeline of certified male and female specialists to meet industry demand and a local workforce that is resilient to economic shocks; / Incorporation of market ready local male and female-owned SMEs in the supply chain of MNCs in the energy sector; and / Increased levels of technical proficiency amongst regulators and male and female officials that uphold adherence to international standards in the Energy Sector.
		2. Improved efficient urban development in Mexico’s cities that results in better, safer and more sustainable public services for citizens, particularly women and girls	Improved governance, decision-making and planning mechanisms for urban mobility services within Mexico’s cities; / Adoption of strategies tested in successful pilots to deliver better urban mobility services, particularly for women and girls in Mexico’s cities.
		3. More inclusive and competitive Financial Services sector, accessible to all sections of Mexican society and new international entrants.	More financially literate male and female consumers who feel greater trust in Financial Services institutions and have the ability to use formal financial services / Supportive regulatory environment for the Fintech sector that works both for men and women. / Increased number of MSMEs procuring Fintech solutions that provide financing alternatives; and allowing for more accessible cashless transactions for men and women.
		4. More efficient detection and investigation of serious and organised crime and corruption cases	Agreement of standards and processes for identifying and investigating serious crime and corruption. / Scale up of a specialized training programme on identifying and investigating serious crime and corruption. / Greater recognition of the roles, responsibilities and handover points between different actors involved in the investigation or serious crime and corruption.

Table 2 – Final Outcome Statements for each Strand – improved on outputs first defined in the ToC
Clean Energy	Future Cities	Financial Services	Anti-Corruption & Rule of Law
Outcome 1: Male and female workers are able to secure better quality or higher paying jobs (both formal and informal), which contributes to improved resilience to economic shocks. / Outcome 2: More male and female owned SMEs take advantage of explanded opportunities in and integrations into local supply chains, including clean-energy technologies / Outcome 3: State- and national-level male and female government officials have increased levels of technical proficiency, which supports the development and implementation of more ambitious projects related to emission-reduction targets.	Outcome 1: Improved policy, governance and coordination of metropolitan mobility in Mexican cities that enables more sustainable, inclusive and safer mobility for citizens, particularly vulnerable groups including (but not limited to) women and girls / Outcome 2: Implemented mobility solutions result in improved metropolitan mobility in Mexican cities that are either more inclusive, more affordable, more efficient, safer or more sustainable for citizens, particularly vulnerable groups including (but not limited to) women and girls	Outcome 1: Greater access to and increased use of financial services for young adults. / Outcome 2: Supportive regulatory environment for the Fintech sector that works both for men and women / Outcome 3: Increased number of MSMEs and male and female users who adopt Fintech solutions and cashless transactions.	Outcome 1: Detection and investigation processes performance of ACROL´s crimes are strengthened in beneficiary institutions units. / Outcome 2: Scale up of a specialized training Programme on identifying and investigating ACROL crimes in beneficiary institutions, in which G&I considerations are mainstreamed. (Not PF funded) / Outcome 3: Improved coordination in the detection and investigation of Homicides, Embezzlement and Cyber Fraud in beneficiary institutions. / Outcome 4: Gender & Inclusion is mainstreamed through policy creation and implementation.
Secondary Benefits: Total value of contracts awarded to SMES by UK Companies was £300,925 by end of programme. [+ greater investment by UK firms at impact level – target to be set by DIT]	Secondary Benefits: Increase in tenders and contract bids submitted by UK and international companies to Mexico / Secondary Benefits: Opportunities for UK methodologies adopted across governments or policies, regulations and strategies	Secondary Benefits: At least 1 public sector institutions adopting / implementing the HCD financial education project / Secondary Benefits: 13 Export Wins leads participating in the new regulatory environment for the fintech sector / Secondary Benefits: 3 Mexican financial secondary dispositions based on the UK experience / Secondary Benefits: 4 ODI leads participating in the adoption programme	Secondary Benefits: £2m of export opportunities with public agencies are generated for which UK and international businesses are expressing interest in submitting a business proposal or tender. / Secondary Benefits: At least 1 UK and International-style regulation, practice or methodology is adopted as a result of programme interactions

## C: Detailed Output Assessment [aim for max. 1 page per output. Repeat for each output]

Strand 1: Clean Energy

Output Number and Title	1a) Establishment of 3 primary interventions to increase the skills of male and female workers to meet industry demand
Output Score	C – Substantially did not meet expectation.
Impact weighting (%)	45%	Impact weighting revised since last AR?		No

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
Number of women and men taking a training course	1091	610	465 – Substantially not met / The strand implemented eleven courses.
Number of courses taken per person (average)	1.5	1.4	1.2 – Moderately not Met
Number of training programmes provided on-site and online	13	34	17 – Substantially not met / The strand implemented seventeen activities. Due to the COVID-19 pandemic, all were implemented online, except for the Gender Awareness and Mentorship Event that was carried out in a hybrid modality.
Number of women and men taking mentorships	171	241	140 – Substantially not met / 87 women and 53 men participated in mentorship activities.
Number of women and men taking an acceleration programme	30	0	Substantially not met - Activity cancelled due to budget constraints.

Output Number and Title	2a) Establishment of the SMEs primary intervention to increase their capabilities to meet industry demand
Output Score	C – Substantially did not meet expectation.
Impact weighting (%)	45%	Impact weighting revised since last AR?		No

Output Indicator	Starting Target	Final Logframe Target	Final Result Achieved
Number of SMEs trained	118	115	142 – Moderately exceeds expectations
Number of SMEs registered in the Centre Systems (SRP)	106	0	Substantially not met - Activity cancelled due to budget constraints.
Number of SMEs participating in mentorships	65	65	Substantially not met – 42 SMEs are recorded in the logframe as participating in mentorships.
Number of SMEs participating in acceleration programmes	15	0	Substantially not met - Activity cancelled due to budget constraints.

Output Number and Title	3a) Establishment of partnerships within relevant government institutions that promote continuous improvement
Output Score	A – Met Expectation
Impact weighting (%)	10%	Impact weighting revised since last AR?			No

Output Indicator	Starting Target		Final Target	Final Result Achieved
Number of technical sessions with government institutions (local and national)	28		Output indicator revised in July 2021 (see better defined output indicators immediately below)
Revised 2021 indicator – / Number of government officials that receive training (tailored training)	-		Tailored Training: 20	60 - Exceeded / Two tailored courses designed for government institutions were delivered. The first one aimed to certify the Energy and Environment Agency (ASEA for its acronym in Spanish) regulators in the global certifications on Health, Security & Environment ISO 14001, and ISO 45001. The second aimed to facilitate the Federal Commission of Electricity (CFE for its acronym in Spanish) regulators a planning process for promoting Mini Hydroelectric Power Plants.
Revised 2021 indicator - Number of government officials that receive training (EPI course)	-		EPI Course: 15	11- Moderately not met. / 11 government officials are registered as having attended more than 50% of the course units.
Number of Partnerships with government institutions (local and national)	10		Output indicator revised in July 2021 (see better defined output indicators immediately below)
Revised 2021 indicator - Number of different government institutions that receive training (tailored training)	10		Tailored Training: 2	2 – Met / 11 - Met / Two tailored courses designed for government institutions were delivered. The first one aimed to certify Energy and Environment Agency (ASEA for its acronym in Spanish) regulators in the global certifications on Health, Security & Environment ISO 14001, and ISO 45001. The second aimed to facilitate Federal Comission of Electricity (CFE for its acronym in Spanish) regulators a planning process for promoting Mini Hydroelectric Power Plants. / Besides, government officials showed interest in EPI courses.
Revised 2021 indicator - Number of different government institutions that receive training (EPI course)			EPI Course: 3

Output Number and Title	4) Secondary Benefits - New 2021 output
Output Score	A – Output met expectation
Impact weighting (%)	10%			Impact weighting revised since last AR?		No

Output Indicator		Starting Target	Final Target		Final Result Achieved
New 2021 indicator - Number of UK technical and vocational institutions (UK experts) consulted in course design and/or implementation		0	2		Met - 2 / Quimera Energy Efficiency (QEE), a recognised British organisation dedicated to the optimisation of assets and the use of advanced technologies in energy saving, offered the attendees a direct knowledge of the use of different applications in EE with a global perspective and the company's portfolio of services. / Senergy's CEO participated as a panellist in "Women in the Solar Thermal Energy Sector" sharing important information about women's leadership. These activities showcased UK expertise and facilitated knowledge sharing and networking with the Mexican Energy sector.

Briefly describe this strand’s activities and achievements during the programme’s lifetime, and provide supporting narrative for the score.

The strand scores a C overall – Outputs substantially did not meet expectation.

The work to increase the skills of male and female workers to meet industry demand produced mixed results. Some courses in the portfolio, such as Solar Thermal and Energy Efficiency delivered solid results behind the development of a comprehensive curriculum. Others fell short in terms of reaching the target audience and generating new learning and impactful experience with high attrition. Whilst the strand was undoubtedly affected by the switch to on-line delivery as a result of the pandemic, along with the shift away from the EPI Energia framework due to Spending Review cuts, results achieved cannot solely be evaluated under this spectrum. For example, evaluation and impact assessment design and implementation, with a focus on “new knowledge acquisition” and testing of new skills could have been far more robust and ambitious.

The work with SMEs suffered from a lack of clear objectives, vision and a robust structure for delivery and implementation. The definition of “mentorships” for example could have been made stronger through a unified structure over a set period of time as opposed to individual sessions and an adapative model approach. Overall, far too many of the courses offered blended individual participants with SMEs andgovernment regulators, creating confusing and duplicated results, when a more specialised and focused approach approach would have been more suitable.

Developing tailored trainings through a co-design process proved a strong way to work and brought solid results. Thirty leading auditors and specialists in environmental management and safety operations from Mexico’s Safety, Energy and Environment Agency were certified. These certifications in regulation, supervision, inspection and verification in industrial, operational safety and environmental protection were granted by the British Standards Institution. A further thirty employees from the Federal Electricity Commission were trained on the methodology known as Metaplan, a technique to prepare a protocol for installing mini-hydro power plants in Mexico.

Secondary Benefits fell far short of expected targets included in the Business Case. This strand faced considerable challenges with setting stretching targets in this area. Although the investment climate proved to be very difficult to attract UK and other firms, more might have been achieved with a more focused strategy. A specific soft power Secondary Benefit output indicator was added as part of the 2021 strand logframe revision.

Assess the VfM of this strand based on performance over the past year, and over the lifetime of the programme.

Economy: The Programme spent £8.33m (£10.03m less £1.7m of excess profit) against its originally envisaged spend of £24.95m or 33% of its budget. Economy, from a VfM perspective, was weak as he strand significantly outspent the others, but delivered fewer results and outcomes. Monitoring of economy was further complicated by the overly complex and inefficient governance structure of the central delivery unit of the implementing partner, which included DAI Global, DAI Europe, DAI Sustainable Business Group and DAI Mexico. This contributed to high-cost administration and work meetings with low quality delivery.

Efficiency: The development of original education and training materials provided the strand with a range of products that could drive efficiency. This is now being seen in the transfer of projects (with some adjustments) into the Skills for Prosperity Programme as part of the agreement to re-invest the Clean Energy excess profit. Nevertheless, the planned creation of three physical centres called EPI Centros (in Mexico City, Guadalajara and Villahermosa) where participants could attend trainings and events was cancelled as a result of the COVID-19 pandemic and this impacted efficiency negatively. It was believed that the EPI Centros were essential for building up the brand of EPI Energia and the central framework of the strand’s implementation strategy. However, on a more positive note, the resulting shift towards delivery of on-line courses and training increased the strand’s geographical reach. On refection, working with an existing training provider and improving it, may have been a better option.

Effectiveness: Some programme components were more effective than others. However, overall, the strand was adversely affected by too many changes and adjustments forced upon it by external forces. Set up to work, primarily, at the federal level of government posed a risk given the priorities of the new administration. Greater outcomes can been found in the Intervention 1 portfolio where strong demand for training and opportunities within the clean energy sector were identified. Nevertheless, the switch to on-line modes of delivery hampered impact where blending technical theory with practical training was required. The strand was less successful in addressing the needs of SMEs and may have benefited more from a more tailored and practical approach to intervention design.

Equity: The switch to on-line was a limitation for reaching the most vulnerable groups of the population. Physical facilities for training delivery were proposed to host beneficiaries with vulnerabilities. Daycare, breastfeeding rooms and other facilities were planned to incentivise greater participation from women. The move to online training meant that these incentives had to be cancelled. However, the equity element of the online delivery model was still strong as evidenced by demand from female workers. The percentage of women participating in the strand’s training and events was 50%; a very high participation rate considering the overall participation of women in the energy sector is around 20%. Additionally, 3% of participants identified themselves as part of an indigenous group, 4% as Afro-Mexicans and 3% as single mothers. Most of the participants (54%) reported earning a monthly income of less than MXN 11,500.

Lessons learned through this output, and recommendations for future programming

Develop a better SWOT analysis before setting-up a new institution like EPI Energia. The investment made in the creation of a new institution will be lost as there was insufficient time to develop the sustainable business model that was planned. The success of the EPI Centros was predicated on having sufficient time to engage the private sector, especially SMEs, and, in so doing, ensure the sustainability of the institution.

In future, stakeholder engagement should be led by the Embassy team throughout the strand’s lifecycle. Originally, the implementing partner for the Clean Energy strand was meant to lead engagement with the Ministry of Energy and other government stakeholders. Due to the sensitivity of the government changing priorities, the Embassy Programme Team took on the lead role in the official stakeholder engagement for the strand. This shift delayed the transition to implementation and posed a risk to delivery.

Focus greater efforts towards the development and design of SLAs, KPIs and Milestones that contain qualitative, as well as quantative indicators and align better to delivering outcomes, and impact as encapsulated by the ToC.

Strand 2: Future Cities

Output Number and Title	1) Develop and deliver recommendations that aim to improve the governance and management of mobility in Mexican cities, including recommendations that address the basic and practical needs of vulnerable groups, including (but not limited to) women and girls
Output Score	A++ - Output substantially exceeded expectation
Impact weighting (%)	50%		Impact weighting revised since last AR?			No

Output Indicator		Starting Target		Final Target	Final Result Achieved
Number of recommendations (strategies or agreements) that aim to improve transport governance and management prepared for consideration by the relevant Authority		3		5	48 – Exceeded / Mexico City – 11 / Monterrey – 8 / Queratero – 5 / Hermasillo – 1 / C19 APF recommendations for restoring transport safely – 19
Number of stakeholders consulted regarding recommendations		9		29	312 – Exceeded
Number of deliverables (e.g. knowledge products, training, events) that support the capacity of authorities and others to improve mobility governance and management with respect to inclusivity		2		2	23 – Exceeded
Number of deliverables (e.g. knowledge products, training, events) that support the capacity of authorities and others to improve mobility governance and management with respect to climate mainstreaming		1		1	20 – Exceeded
Number of recommendations (strategies or agreements) that aim to improve transport governance and management prepared for consideration by the relevant Authority that have considered climate mainstreaming		1		1	33 - Exceeded

Output Number and Title	2) Identify and develop delivery plans for practical mobility solutions in pilot cities, prioritising those that support inclusive, safe and sustainable mobility, particularly for vulnerable groups, including (but not limited to) women and girls
Output Score	A++ - Output substantially exceeded expectation
Impact weighting (%)	40%	Impact weighting revised since last AR?				No

Output Indicator			Starting Target	Final Target	Final Result Achieved
Number of city proposals reviewed			12	12	12 – Met
Number of cities selected for the pilot			3	3	3 – Met / As part of the Inception Phase city selection process, the following 3 cities and 5 pilots were shortlisted: / Mexico City - 1. Neighbourhood Mobility; 2. G&I policy implementation (behaviour change); / Guadalajara - 1. Fare integration for social inclusion; 2. Safe bus stops pilot; / Hermosillo - Design of a suburban transportation system for Hermosillo metropolitan area.
Number of potential pilots identified that have a particular impact on women, girls and other vulnerable populations			5	6	8 - Exceeded / 8 pre-feasibility studies that were delivered for Mexico City, Guadalajara, Jalisco and Hermosillo. All pilots were selected where they had potential to prioritise impact on gender and/or inclusion.
Number of stakeholder groups engaged during pilot identification			15	25	28 – Exceeded
Number of delivery plans delivered to relevant authorities for practical mobility solutions			4	6	26 – Exceeded / A mixture of pre-feasibility studies and delivery plans springing from successful pilots, as well as a number of delivery plans for handling mobility and public transport during the COVID-19 pandemic
Number of delivery plans delivered to relevant authorities which meaningfully incorporate disadvantaged groups’ views into the consultation and design			2	2	3 – Exceeded
Number of stakeholders engaged during mobility solution development			60	60	232 – Exceeded
Number of deliverables (e.g. knowledge products, training, events) that support the capacity of authorities and others to improve mobility solutions with respect to inclusivity			1	1	34 – Exceeded
Number of deliverables (e.g. knowledge products, training, events) that support the capacity of authorities and others to improve mobility solutions with respect to climate mainstreaming			1	2	10 – Exceeded
Number of delivery plans delivered to relevant authorities that have considered climate mainstreaming			1	3	24 - Exceeded

Output Number and Title	3) Raising awareness of potential export opportunities linked to the programme for UK and international companies
Output Score	A++ - Output substantially exceeded expectation
Impact weighting (%)	10%		Impact weighting revised since last AR?			No

Output Indicator		Starting Target		Final Target	Final Result Achieved
Number of showcases or events (e.g. trade presentation, video demonstration, company roundtables, communication materials) or reports to raise awareness of potential export opportunities organised with non-ODA funds		12		8	8 – Met
The number of engaged participants in activities delivered for knowledge exchange between UK organisations / experts and Mexican authorities		70		70	239 – Exceeded / UK organisation participation included: Nottingham City Council, Transport for London (TfL), Ascendal, Citymapper, The Climate Bond Initiative, Greater Manchester Combined Authority, Glasgow City Council, University College London (UCL) & Behavioural Insights Team (BIT)

Briefly describe this strand’s activities and achievements during the programme’s lifetime, and provide supporting narrative for the score.

The strand scores an A++ overall – Output substantially exceeded expectation.

The objective of the Future Cities strand was to support urban development in Mexico’s cities that results in safer, resilient, more accessible and more sustainable mobility services for citizens, particularly for women and girls. The strand operated across 5 cities with project work falling under two intervention areas. The first focused on improving the governance and management of mobility across the implementing cities; and the second on designing practical mobility solutions through pilot interventions in cities to deliver more inclusive and safer mobility. Though targets may have been set conservatively in the logframe review in July 2021, the strand, nonetheless, undoubtably performed strongly. Key to success and achievement was the development of a portfolio of projects that were bottom-up, demand driven by the needs of sub-national and national governments, in line with the ToC and implemented through a co-design approach to project delivery. The implementing partners – set up as an Alliance of local and international organisations – had a proven track record in Mexico of high-quality interventions and a strong reputation in the mobility sector, facilitating strong buy-in, trust, and commitment from government partners. This in turn, further drove secondary benefits with a focus on soft-power and knowledge exchange.

Outputs 1, 2 and 3 worked cohesively together to deliver some impressive impact stories and drove results into outcomes. Examples include:

  - In March, 2021, the government of the state of Jalisco implemented a re-design of their social fare policy and programme with a $40 million pesos investment based on the technical work delivered by the strand. The new policy benefitted 11,732 women, heads of households, living in peripheral areas of the city of Guadalajara giving them access to free public transport and bike sharing programmes. The programme was continued in March 2022.

  - The strand collaborated with Mexico City’s Ministry of Mobility (SEMOVI for its acronym in Spanish) and the Regulatory Body for Transport (ORT for its acronym in Spanish) to strengthen the governance and operational structure of the city’s mobility sector. The strand’s technical recommendations to SEMOVI established a governance unit that specialises in the collection and revenue management of the travel card payment system. For the first time, public transport users have been able to purchase and top-up their integrated travel cards (TUMI) in stores, via smart-phones, and online through a new platform. Users have also been able to utilise their cards as payment on select concessionary buses as part of the actions to integrate non-government operated transport into the integrated network

  - In the state of Nuevo León, the strand supported the government by designing the governance and operational structure of a Mobility Management Centre (CGM for its acronym in Spanish) which aims to inform and support sustainable urban development policy and planning. Provisions for the establishment of the CGM have been included in the state’s planning instruments and legal framework, including the Sustainable Mobility and Accessibility Law, the Comprehensive Plan for Sustainable Urban Mobility of the Metropolitan Area, the 2040 Metropolitan Monterrey Programme, and the Mobility and Accessibility Institute’s bylaw. In December 2021, a public tender was launched with a value of £65 million for the purchase of traffic signals, cameras, sensors, and infrastructure, based on the programme’s technical designs.

  - Claudia Sheinbaum, Mexico City’s mayor announced that the temporary bicycle lanes installed on the largest avenue in the city would become permanent. The decision was taken based on recommendations from the strand that evaluated the temporary mobility measures implemented by the authorities to contain the COVID-19 pandemic. This decision is already having an impact on the lives of the people that use bicycles as their main means of transport – over 30,000 trips per day are made using the pop-up bike lane, representing a 275% increase in cyclists’ use since November 2020.

Assess the VfM of this strand based on performance over the past year, and over the lifetime of the programme

The strand spent a total of £8.3m (of which £604,387 was funded by BEIS in the final year of implementation) of its allocated budget of £9.97m. The strand has delivered at the outcome level of the logframe substantial and tangible results, despite closing a year early and suffering from significant budget reductions. VfM, therefore, is considered strong.

Economy: The lead implementing partner scored consistently high in their performance in management of resources through the Central Delivery Unit (CDU) governance and delivery framework. The CDU was able to expand, contract, pause and deliver at speed as budget reductions demanded and the pandemic impacted delivery. This meant that the strand could protect resources when needed and maximise return. At the same time, technical delivery teams from the Alliance of implementing partners were consistently selected with care and strong due diligence to ensure that the right mix of expertise and skills were in place at point of delivery.

Efficiency: The strand drove efficiency through its agile approach and openness to view and act upon opportunities as well as risk. For example, successes and results were achieved through the development of technical recommendations to inform new standards for bus stops that were released by the government of Jalisco in November, 2020. The work was outside the original scope of the Safe Bus Stop Corridor project, but seeing the opportunity the team were able to pivot, delivering important work with a focus on gender-informed design, technology and access.

Effectiveness: The demand driven characteristics of the portfolio of projects, together with the co-design and close working structures in place between implementing partners, participants, and government stakeholders, ensured that the business case remained viable and outputs drove outcomes consistently throughout the strand’s life-cycle.

Equity: The Future Cities strand aimed to build safer, resilient, more accessible and and more sustainable mobility services for citizens, particularly for women and girls. As a result, the participants impacted by the results of the strand were predominanetly women, girls, and those from low socio-economic backgrounds. Evidence of this has been presented through examples above.

Lessons learned through this output, and recommendations for future programming

Be realistic about abilities and differences between local administrations. The Future Cities strand had originally designed a programme active in up to three Mexican cities but ended up working in five. This required an increase in its Resource Pool that had to coordinate tightly at all levels of delivery, as well as careful monitoring and reporting of processes, engagement and results.

In order to maximise impacts and the adoption of recommendations amongst authorities and stakeholders, the strand re-introduced the City Manager role to continue dialogue with cities and authorities where the two intervention areas and the Agile Programming Fund projects had closed or were about to close. The City Managers kept recommendations and their implementation front of mind, and proved invaluable in the strand’s management of relationships with authorities, including maintaining relationships with authorities where stakeholders changed due to turnover or elections.

The strand used a highly effective and resilient adaptive management model that responded well to risks, opportunities and new information. This was highly effective when it became necessary to revisit the project’s resource allocation.

The legacy of the strand’s activities includes insightful diagnostics, instruments and public policy and governance recommendations. As part of the strand’s exit strategy, the legacy was considered and the decision was made to re-purpose the strand’s website into a legacy platform, where information and the most replicable tools per programme theme and project can be found. A brochure was also developed to showcase the strand’s key impacts and achievements. The hope and expectation is that by making these programme tools and insights public, they will continue to deliver value, practical guidance and a framework for future successful implementation of recommendations to authorities across cities in Mexico and beyond.

Strand 3: Financial Services

Output Number and Title	1) A human-centred design (HCD) financial education programme to build financial capabilities in vulnerable and poor young adults for the foundations of provisional savings
Output Score	C – Output substantially did not meet expectation
Impact weighting (%)	30%		Impact weighting revised since last AR?			No

Output Indicator		Starting Target		Final Target	Final Result Achieved
Number of institutions receiving HCD financial education		2		2	1 – Not Met / Recipient was CONALEP. After July 2021, implementation became the responsibility of AMAFORE through an MoU agreed with the British Embassy in Mexico. Any results achieved after June 2021 have therefore not been recorded as part of this PCR.
Level of satisfaction from training programmes		3.5		3.4	0- Not Met / After June 2021, this became the responsibility of AMAFORE through an MoU agreed with the British Embassy in Mexico. Any results achieved after June 2021 have therefore not been recorded as part of this PCR.
Number of male and female receiving behavioural design financial education interactions		11,000		1,200	119 – Substantially Not Met / 119 CONALEP students received training through online courses. / After June 2021, this became the responsibility of AMAFORE through an MoU agreed with the British Embassy in Mexico. Any results achieved after July 2021 have therefore not been recorded as part of this PCR.
% of male and female beneficiares under the income poverty line receiving behavioural design financial education interactions		65%		Indicator Cancelled after July 2021 review.
Number of activities linked to financial education (workshops )		32		Indicator Cancelled after July 2021 review.
Number of international (including UK) experts engaged in supporting HCD methodologies for strengthening financial inclusion and safeguarding users' transactions		6		6	6 - Met / Experts were representatives from: Ideas 42, BFA, IADB Invest, IFC-WB, CGAP and UK Public Health Rapid Support Team
Number of associations and institutions that will establish relationships with the British Embassy as a result of the intervention		4		4	4 - Met / In 2019 relationships were started with INAES and AMAFORE, which are organisations interested in financial inclusion that includes vulnerable populations and interested in learning from UK experience. / In 2021 CONDUSEF and the General Direction of Access to Financial Services of the CNBV also established a relationship with the strand.

Output Number and Title	2a) Rollout of regulated open Application Programming Interface (API) standards for data sharing within the Mexican Financial Services Sector that empower consumer choice for men and women
Output Score	B – Outputs Moderately did not met expectation
Impact weighting (%)	10%		Impact weighting revised since last AR?		No

Output Indicator		Starting Target	Final Target	Final Result Achieved
% of standards in the secondary regulation issued influenced by international best practice		100%	100%	100% - Met / During 2019 and 2020, Open Data secondary regulation and ATM API standards were published. All standards issued until Dec 2021 were based on international best practices, mainly from the UK / We expect further standards for transactional data for debit and consent APIs to also be published in the first half of 2022.
Number of international (including UK) experts engaged in the provision of professional services for Open Finance		7	7	6 – Moderately Not Met / In 2020 TESOBE (Germany), Accenture International (Ireland) and Open Vector (UK) were engaged in the provision of professional services for Open Finance. In 2021 Open Banking Delivery (UK) expert became engaged also. All facilitated through this programmes relationship with the IDB.

Output Number and Title	2b) A fintech-focused supervisory technology solution for regulators (SupTech/RegTech) to enable efficient reporting and reduced compliance costs
Output Score	B – Outputs moderately did not meet expectation
Impact weighting (%)	15%		Impact weighting revised since last AR?		No

Output Indicator		Starting Target	Final Target	Final Result Achieved
Percentage of fintechs and banks submitting regulatory reports based on suptech/regtech solutions		70%	30%	12% - Not Met / 13/109: 13 fintechs now use the suptech. / A further 10 fintechs are expected to join the suptech platform shortly. It is anticipated that all 51 banks in the country will join the platform within the next 2 years.
Degree of progress of Fintech basic analytics capabilities of the SupTech platform		100%	80%	80% - Met
Number of international (including UK) companies engaged in providing SupTech/RegTech solutions for automated reporting and compliance		1	2	2 - Met

Output Number and Title	2c) A functional regulatory sandbox environment for innovative Fintechs to safely test their products and services
Output Score	B – Outputs Moderately did not meet expectation
Impact weighting (%)	10%		Impact weighting revised since last AR?		No

Output Indicator		Starting Target	Final Target	Final Result Achieved
Number of projects submitted to the National Securities and Banking Commission seeking to test their products and services through the sandbox		20	11	5 – Not Met / The four projects submitted to the CNBV are: Clinch, Oikos, Arca Financiera and Tokenise. / 3 others also progressed; 1 successfully and 2 declined, though they are still hoping to join the sandbox.
Number of innovative models receiving technical assistance to participate in the regulatory sandbox		18	28	26 - Moderately not met
Level of satisfaction of Fintechs that received technical assistance in the process for applying to the Mexican regulatory sandbox		3.5	3.5	Indicator cancelled after July 2021 review. / In the evaluation that was made to the companies participating in the SBC 1.0, in 2020, the rating was 3.7 exceeding the 3.3 target.There was no time or resources to do the same exercise with the winning models of the SBCh 2.0 since it will take place after the closing of activities of the programme.
Number of international (including UK) start-ups engaged in the authorisation process through the Mexican regulatory sandbox		3	2	1 – Moderately not met / Tokenise (UK) are working towards authorisation. A second also participated but decided to opt out due to a change in their business model.

Output Number and Title	3) A programme for Fintech companies to support deployment of different solutions that empower MSMEs and vulnerable male and female individuals
Output Score	A – Output met expectation
Impact weighting (%)	35%	Impact weighting revised since last AR?			No

Output Indicator		Starting Target	Final Target	Final Result Achieved
Number of states participating in the Fintech Caravan (CF)		8	5	20 - Exceeded / Vastly enabled through the move to online events: participants were drawn from: Baja California, Campeche, CDMX, Chiapas, Coahuila, State of Mexico, Guanajuato, Guerrero, Hidalgo, Jalisco, Michoacán, Morelos, Nuevo León, Oaxaca, Puebla, Querétaro, San Luis Potosí, Tamaulipas, Veracruz and Yucatán
Number of Fintechs participating in the CF activities		12	7	22 - Exceeded
Number of CF activities linked to adoption		90	128	147 – Moderately Exceeded / Activities to facilitate the link between the supply side (Fintech solutions) and the demand side (MSMEs and vulnerable female and male users). The final event was designed especially for individuals with hearing disabilities.
Number of MSMEs participating in the CF adoption activities		1800	300	n/a – Indicator cancelled after July 2021 review / Results of this indicator could not be corroborated.
Number of male and female final users participating in the CF socialisation activities		3700	4700	1016– Substantially Not Met / Total numbers based on participants attending CF seminars and workshops.
Level of satisfaction of participants with CF activities		3.5	Indicator cancelled after July 2021 review
Number of international (including UK) companies engaged with CF activities (benefit partners and advisors)		3	2	16 - Exceeded / International companies partnered with the Caravana FinTech were: ADDEM Capital, Fundación Capital, Fintech Expert, ARKANGELES, Google, Ideas&Capital, AWS, IGNIA, Wild Entrepreneur, AMEXCAP, Impact Hub, Matteria: Talent Impact, BIVA, Iupana, E&M, & LinkedIn.
Percentage of beneficiaries of the socialization programme that are vulnerable.		15%	Indicator cancelled after July 2021 review
Number of associations and institutions at national and state level that will establish relationships with the British Embassy as a result of the intervention		8	6	11 - Exceeded / In 2020 Institutions of Queretaro that established relationships with the British Embassy were : SEDESU, SEJUVE, COPARMEX and TD2035. / In 2021 institutions from Campeche: SEDECO, CCE, and BANCAMPECHE, INMUJERES, / Additional insitutions engaged with were Fundación Bécar, Instituto Municipal de las Mujeres Querétaro y SEDECO Chiapas.

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

The strand scored a B overall – Outputs moderately did not meet expectations.

Despite good results recorded against some outputs, the strand fell far short of its targets and impact expected. The strand performed strongest in those outputs with a focus on building networks, knowledge exchange, sharing expertise and disseminating best practices related to Open Finance, RegTech (regulatory technology) and SupTech (supervisory technology). One example of this was the adoption of the ATM API Standard. These networks also opend up important channels, which resulted in solid secondary benefit wins totalling more than £15 million. Secondary benefits were a core priority of the Financial Services strand and the relationships formed with key partner government stakeholders are expected to bring additional secondary benefits after the project life-cycle.

The strand’s work on Financial Technology (FinTech) delivered strong results in a challenging context. A regulatory Sandbox Challenge 1.0 (SBC) was launched attracting 166 FinTechs from Mexico, Chile, Colombia, Peru, Kenya, Singapore, Ukraine, USA and the UK. The strand provided a policy briefing on SBC 1.0 to help CNBV and CONSAR with its management of a Sandbox 2.0. Morevoer, it supported the creation of 29 modules that will help the automation and efficiency of CNBV’s processes for SupTech, an important step in the development of the FinTech sector in Mexico.

The pandemic had an averse effect on strand delivery. At the same time it allowed projects, particularly, those of the Caravana FinTech, to reach a wider audience and geographical area as results show. Nevertheless, after analysis, it is clear that the projects failed to capitalise on these opportunities and to build sustainable and impactful relationships with key target populations, most significantly MSMEs. Improved design of deliverables along with indicators to measure effectively the impact of the strand on the target population would have brought higher impact and VfM.

Projects designed to build financial capabilities for vulnerable and poor male and female young adults focused on the design, development and implementation of the Financial Education Initiative for the Inclusion of Young Adults into Provisional Saving Systems. The initiative employed tools and educative contents through a Circuit of Digital Educative Interactions that was hosted in a microsite called “AhorrandoAndo”. AhorrandoAndo was piloted in 2021 in CONALEP Yucatan reaching 119 students, a number far lower than originally forecast. AhorrandoAndo has since been transferred to AMAFORE, however, it remains offline and requires susbstantial improvements to be competitive with other tools available. On refection, working with an existing provider and improving it, may have been a better option.

Assess the VfM of this strand based on performance over the past year, and over the lifetime of the programme

Economy & Efficiency: The strand spent a total of £5.17m of its allocated budget of £9.7m. Management of resources performance produced mixed results across its life-cycle. Outputs 2 and 3 and the projects with a focus on Open Finance and FinTech regulation performed strongest where the implementing partner had to manage the development of new software with a government partner required to test and feeback into the process. Despite the risk of costs spiralling, the projects delivered the products on time, against acceptance criteria, and with robust VfM. Nevertheless, as has been highlighted above with reference to the Clean Energy strand, the overly complex structure of the Central Delivery Unit reduced efficiency, coupled with a disconnection between local and central teams. For example, the strand was forced to return £225,000 as a result of the implementing partner reporting an excess profit in the final month of operations leaving no room for reinvestment. The team responsible for developing the technical elements of the strand were disconnected from the team managing the contract, including the financial reporting. The Embassy Programme Team found a number of challenges in understanding forecast and spend of specific deliverables and pieces of work within Milestones.

Effectiveness: The strand was more effective in some areas than others. The investment made in financial education did not deliver VfM. Though an MOU was signed with AMAFORE to facilitate continuity, the site remains offline and requires significant adjustments to be a viable product. At the same time, the Caravana FinTech initiative failed to reach the number of participants expected and did not build substantial relationships with MSMEs, a key target population. Though both projects were adversely affected by the pandemic, a more robust strategy, that relied less heavily on social media tools as a vehicle of knowledge exchange and impact, may have brought stronger and more reliable results. The work delivered through the Regulatory SandBox did not produce expected results and was hampered more by a lack of progress and appetite within the federal government regulatory authorities than by poor delivery. However, the development of the regulatory technical platforms to support increased efficiency in the regulation of FinTechs driven by demand from the government proved successful and in high demand.

Equity: Output 1 piloted the AhorrandoAndo initiative in April 2021 with 119 CONALEP students of Yucatan state. 70% of the families of these students lived under the Mexican poverty line, with an approximate monthly income of less than today’s £250 GBP (CONALEP Income Profile, Dec 2013). Moreover, 63% of CONALEP pilot participants were women compared to the overall 46% of female students of CONALEP’s alumni. In output 3, of the total of 562 participants attending Caravana Fintech events between October 2021 and February 2022, 64% were women; 36% were from vulnerable groups; and 72% were micro business owners.

Lessons learned through these outputs, and recommendations for future programming

The strand was adversely affected by changing priorities of the federal government, which forced two out of the three interventions to be adjusted. This was particularly damaging for the work on financial education for vulnerable populations. It is critical to consider alternatives and extend the scope of stakeholders when an activity has a planned direct collaboration with a government programme that suddenly comes under political pressure.

When the product being developed is software, it is important to set up the right programme management approach and framework to manage the work, even if this is different from the approach taken to other projects within the portfolio. An agile approach would have best suited the needs of the SupTech platform in which development, testing, and feedback loops were a constant theme.

It is critical that the design of deliverables align to the objectives of the project and that both acceptance criteria and logframe indicators capture the information that will deliver results against logframe targets. Deliverables should be developed for the participants, not the client, who is informed through reporting. Greater care is required when developing an Implementation Project Plan and logframe to ensure that the business case remains valid.

Strand 4: ACROL

Output Number and Title	1a,b,c) Standards, processes, guidelines and/or policies for investigation of serious crime (homicides), corruption and cyber-crime
Output Score	A – Outputs met expectation
Impact weighting (%)	15%		Impact weighting revised since last AR?		No

Output Indicator		Starting Target	Final Target	Final Result Achieved
Number of formal collaboration agreements in place with relevant institutions.		6	5	5 - Met. / ACROL signed Memoranda of Understanding with 5 institutions in: Tabasco (1), Jalisco (2) and CDMX (2). / The implementing partner signed 1 DA with CNBV. A sixth planned agreement was abandoned after cuts were made to the budget.
Number of toolkits (manuals, standards or protocols) created to reflect recommendations, which incorporate UK or international best practice		3	4	4 – Met. / Jalisco, Tabasco, CDMX and CNBV benefitted from toolkits provided by the UK government which incorporated best practice.

Output Number and Title	1d,e,f) Detailed outline of case building procedures for the detection and investigation of selected crimes
Output Score	A – Outputs met expectation
Impact weighting (%)	10%	Impact weighting revised since last AR?			No

Output Indicator		Starting Target	Final Target	Final Result Achieved
Number of sets of recommendations provided which incorporate UK or international best practice		6	6	5. Moderately not met. / Final sets of recommendations to improve investigations have been created for Tabasco and Jalisco authorities. Recommendations for CDMX are pending due to impacts of COVID-19 and SR results. The strand also started an analysis on financial cyber fraud.
Number of investigation models developed		3	2	2 – Met / Tabasco – Homicide / Jalisco – Embezzlement / CDMX – diagnostic and recommendations only

Output Number and Title	2a,b,c) Training needs analysis for the detection and investigation of selected crimes
Output Score	C
Impact weighting (%)	Output Cancelled	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Target	Final Result Achieved
Percentage of training topics analysed as a proportion of total agreed priority topics	50%	Indicator cancelled after decision to close strand

Output Number and Title	2d,e,f) Design and delivery of basic and specialised detection and investigation skills training programme on selected crimes
Output Score	C
Impact weighting (%)	Output Cancelled	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Target	Final Result Achieved
Number of basic training programmes designed to improve detection and investigations	6	2	Met / Training needs analysis were finalised, and capacity building packs were delivered to the beneficiaries in Tabasco and Jalisco
Number of specialised training programmes designed to improve detection and investigations	6	Indicator cancelled after decision to close strand
Percentage of trained operational personnel involved in the investigation of crimes of corruption	80%	Indicator cancelled after decision to close strand
Percentage of trained operational personnel involved in homicide investigation	80%	Indicator cancelled after decision to close strand

Output Number and Title	2g,h,i) Pilots of specific detection and investigation processes for selected crimes
Output Score	C
Impact weighting (%)	Output Cancelled	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Target	Final Result Achieved
Number of pilots designed	4	2	Met / Pilots were designed and delivered for Jalisco and Tabasco
Percentage of officials who perceived that their technical skill improved through participation in pilots	30%	Indicator cancelled after decision to close strand

Output Number and Title	2j,k) Scaling up of basic and/or specialised investigation skills training programme on selected crimes
Output Score	C
Impact weighting (%)	Output Cancelled	Impact weighting revised since last AR?	No

Output Indicator	Starting Target	Final Target	Final Result Achieved
Number of institutions interested in adopting and delivering training programmes	3	Indicator cancelled after decision to close strand

Output Number and Title	3a,b,c) Mapping of handover points between agencies working on selected crimes.
Output Score	A – Outputs met expectation
Impact weighting (%)	20%	Impact weighting revised since last AR?			No

Output Indicator			Starting Target	Final Target	Final Result Achieved
Number of recommendations provided to improve inter-agency coordination			3	3	3- Met. / Final sets of recommendations to improve inter-agency coordination were delivered in November 2020 for Tabasco (1) and Jalisco (1). From February to July, the strand carried out activities to define recommendations to the cybercrime component.

Output Number and Title	3d,e,f,i) Multi-agency working groups for detection and investigation of selected crimes involving multiple hand offs
Output Score	A – Outputs met expectation
Impact weighting (%)	15%	Impact weighting revised since last AR?			No

Output Indicator		Starting Target	Final Target	Final Result Achieved
Number of community of practice meetings held		44	8	8 - Met / Four Communities of Practice were established one for each crime - homicides, embezzlement and cyber-fraud and one focused on gender and inclusion

Output Number and Title	3g,j,k,l,m) Annual workshop for judges in selected states to socialise new standards and processes and share international best practice, learning events and SGB meetings.
Output Score	B – Outputs Moderately did not meet expectation
Impact weighting (%)	20%	Impact weighting revised since last AR?				No

Output Indicator			Starting Target	Final Target	Final Result Achieved
Number of events held as part of the judge`s annual visit			3	3	1 - Not Met
Number of learning events held			4	4	4 - Met / Virtual learning events on Cybersecurity, Homicide (2), and Embezzlement were held
Number of beneficiaries and public agencies attending knowledge sharing events aiming to showcase UK and international best practices, approaches and methods			20	21	21 – Moderately Exceeded / 21 learning events were held during 2020 sharing UK best practices with Mexico’s public agency servants.
Number of participants from government agencies and beneficiaries identified through the main programme attending non-ODA funded showcase events and trade shows aiming to raise awareness of UK and international best practices and technical solutions			100	100	85 – Not Met.

Output Number and Title	3h) Diagnosis and support to implement non-discrimination practices, policies and/or complaint procedures within beneficiary institutions
Output Score	A – Outputs met expectation
Impact weighting (%)	20%	Impact weighting revised since last AR?			No

Output Indicator			Starting Target	Final Target	Final Result Achieved
Number of pilots in which is identified the profile of the people involved to allow an investigation with a G&I perspective			4	2	Met: 2 pilots were reintroduced as targets and completed as part of the handover plan at end of project.
Number of priorization workshops held			6	6	Met. 6 workshops held
Number of G&I diagnostics delivered to key institutions			8	5	Met. 5 G&I diagnosis were delivered

Briefly describe the output’s activities and achievements during its lifetime, and provide supporting narrative for the score.

The strand scored an A overall – Outputs met expectations.

Despite these achievements the strand fell far short of its original targets due to early closure. This was due, in particular, to ending the original work planned for output 2.

Following the SR, the ACROL implementing partner concluded that it was no longer possible to meet the strand objectives and agreed with the Embassy Programme Team to close the strand while preparing a handover plan that would minimise reputational impact and still deliver VfM. The Exit Plan covered the transition period from May to November 2021. Thus, the logframe results above are those from March 2021.

The strand designed two new investigation models on homicide and embezzlement based on UK and international best practice. It also produced the first standards, processes and specific recommendations (including Gender and Inclusion considerations) for implementation. These were built on an extensive analysis of existing procedures, capabilities and coordination mechanisms in the selected regions. In Tabasco, the UK successfully tested and deployed the new homicide investigation model with an innovative social participation component. The strand had strong results in Tabasco, where the state authorities implemented organisational and operational changes, adopting the new model and expressing their commitment to continuation. In Jalisco, the strand successfully tested and deployed the new investigation model to tackle financial corruption crime beyond embezzlement that allows for macro-case prioritisation and integration. While the government partner accepted the work, deployment of the new investigation model remains pending. In Mexico City, the strand delivered a diagnostic report on homicide investigation and recommendations that if taken forward would form the basis of a new investigation homicide model.

To help improve the capacity of officials in government institutions, the strand completed an analytical report of the training needs to support implementation of the new investigation models for both Tabasco and Jalisco. The training needs analysis were finalised, and capacity building packages which included training sessions and materials with practical hands-on implementation were delivered to the government stakeholders in Tabasco and Jalisco. Both of the new investigation models for homicide and embezzlement detection and investigation were successfully piloted, leading to the update of the operating manuals in both regions to better reflect the practical needs of the investigation procedures.

The implementing partner established four communities of practice, which operated with high-level stakeholders (one for each crime - homicides, embezzlement and cyber-fraud, including one focused on gender and inclusion). The strand also delivered several knowledge sharing events with high attendance rates (100 + attendees), creating effective networks and relationships between Mexican agencies and their UK/international counterparts. In addition, the strand defined the nature of the cyber fraud crime phenomenon in Mexico and shaped an appropriate response: mapping the transfer points and relevant actors across legislation, public policy development, detection, investigation, prosecution and international collaboration.

The secondary benefits focus for the ACROL strand centred on demonstrating UK expertise in the field of anti-corruption and rule of law and identifying potential opportunities for UK business in building Mexican capability. COVID-19 measures led to the cancellation of several activities that would have helped identify economic leads, slowing the process as a result. However, the strand was able to adapt and create new opportunities. It facilitated participation of experts across all three crime types including the head of the Metropolitan Police Homicide Command, investigators from the National Crime Agency’s National Cyber Crime Unit, former officials from the Serious Fraud Office and the former Department for International Development and the CEO of the College of Policing.

Assess the VfM of this output based on performance over the past year, and over the lifetime of the programme

The strand spent a total of £4.4m of its allocated budget of £8.67m. Overall the strand delivered robust VfM in relation to planned impact.

Economy & Efficiency: Despite the impact of the budget cuts on this strand, a sensible exit plan was agreed between the British Embassy and the implementing partner which left a platform on which Mexican institutions and other donors and stakeholders can build. The shift to an on-line mode of working did not hamper efficiency, but instead enhanced the work delivering quality at a reduced cost.

Effectiveness & Equity: Co-design was a consistent element in the development of the investigation models resulting in strong buy-in from government partners and a high rate of acceptance of technical products. During the close down process, four learning events and four communities of practices were hosted. High-level stakeholders spoke of the impact of the work and gave their commitment to take it forward. The strand was instrumental in kick-starting the process to embed gender and inclusion at the operational and organisational levels of the partner agencies and launched the Gender and Inclusion Community of Practice to improve coordination.

Lessons learned through this output, and recommendations for future programming

An objective that had been set at the beginning of the strand was to reach gender equality within the Strand Governance Board (SGB). This proved to be a challenging task for two main reasons: i) senior presence of women in government institutions continues to be limited in comparison to men and ii) there were cases where female SGB representatives delegated their participation to male subordinates, resulting in an increased male presence. The inability to guarantee gender equality on the SGB is an important reminder of how essential it is to insist on governance mechanisms attaining agreed diversity and inclusion targets and taking effective action to achieve them.

The government takes a top-down approach to anti-corruption, leaving little room for other actors such as civil society and the private sector to contribute. This context complicated the design and early implementation of the ACROL strand. A further challenge is that the links to inclusive economic growth are indirect, which further complicated evidencing the strand’s contribution to achieving primary purpose.

A review of the output insdicators of this strand reveals some simplistic targets such as number of events or number of workshops held. In future, we must seek to challenge implementing partners with more meaningful targets such as number of workshop participants applying learning from workshops, etc.

D: Risk

Overview of programme risk during the past year and over the life of the programme, drawing on FCDO’s Risk Management Policy and Risk Appetite Statement and wider risk guidance.

The Programme had strong management systems and practices in place to manage risk, as concluded in previous Annual Reviews and independent evaluations. Risks were reviewed and discussed monthly at our Programme Management Committee, with SRO oversight.

An initial risk to the Programme was presented by the change in administration of the Government of Mexico and a set of policies and reforms that affected each of the sectors. This had not been adequately accounted for during design across all strands.

The next set of delivery, reputational, operational and VfM risks stemmed from the impact that COVID-19 had on both the Mexican and the UK economies and the resulting budget reductions and early programme closure. Initially, the Programme responded well to the risks posed by COVID-19. New challenges were properly addressed at the beginning of the pandemic and continued to be managed well throughout the Programme. Workplans were adapted to the changing contexts and this flexibility was key to ensuring delivery continued.

Reputational risks were a keen area of concern in the end phase of the Programme as the UK sought to exit responsibly with a steep cut of 85% of the budget in the final year. We assess that these cuts led to a more cautious engagement from the Government of Mexico on bilateral cooperation with the UK. The start of the Prosperity Programme initially led to a large boost in the UK’s relationship and visibility with many government and other stakeholders. However, the exact opposite has happened with the announcement of the budget reductions and then the subsequent communication on the Programme’s early closure. Stakeholder relationships have been managed carefully with regular communications and discussions, but the disappointment of government contacts remains considerable.

Additonal operational delivery risks also materialised in the final year. The Embassy Programme Team reduced in size by almost 50% due to natural attrition and planned redundancies. FCDO’s wider internal communications around staff workforce planning also affected morale and represented a key risk to manage in the final year. Mitigation measures and incentives were put in place to ensure that the British Embassy retained the capacity to close the Programme responsibly and account for the results and impact of UK investment.

Fiduciary and safeguarding risks have been managed well throughout the Programme. This included the handling of excess profits reported to FCDO by one implementing partner. These were generated inadvertently due to early closure of the Programme and ended up reducing final contract values.

E: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

Summarise the performance of partners and FCDO, notably on commercial and financial issues, and including VfM measures of economy and efficiency.

Performance by implementing partners and the Embassy Programme Team needs to be set against the volatile environment that has affected delivery brought about first by the COVID-19 pandemic and spending review cuts, and then early closure of the Programme. However, other factors also affecting the Programme’s evaluation.

The last SRM scorecard exercise was carried out in June 2021, just before a decision to close the Programme was communicated to implementing partners. [Note that the SRM scorecard only applies to two of our three implementing partners]. Future Cities – 70 | Financial Services – 52 | Clean Energy – 58 | ACROL – no scorecard.

On reflection, Prosperity Programme processes could have been improved to lessen bureaucracy and support effective decision-making. In the final year of implementation, for example, the Programme Team had to focus on managing processes for closing the Programme and ensuring that financial commitments and allocations were met. This meant that our influencing role with stakeholders to clear bottlenecks was much reduced. A further area that could have been strengthened was the capturing of impact stories demonstrating to key audiences that the Programme had some substantial successes.

KPIs could have been developed and evolved better over the life-cycle of the Programme to incorporate more qualitative indicators to balance against those predominantely focused on contract management elements and aligned better to logframe indicators.

FCDO exercised strong governance of the Programme through the creation of a number of internal and external governance mechanisms. These included:

The Programmes Strategy Advisory Board provided a venue for high-level discussions which included senior UK and Mexican authorities to ensure strategic oversight.This met quarterly throughout the Programme.

Strand Governance Boards (SGBs) ensured the collaboration of key stakeholders who are strategic decision-makers, thereby ensuring continued alignment to Mexican government priorities. The membership of the SGBs was at the working level and included key government agencies and actors to fulfil the board’s mandate. This was also a key mechanism for transparency and accountability.

An internal Programme Management Committee, chaired by the SRO and a forum for discussing risks, progress and opportunities on the Programme as a whole.

A Gender and Inclusion (G&I) Group. The G&I Advisers/Leads from each of the strand implementing partners met monthly with the Embassy Programme Gender Lead to discuss the effective integration of G&I priorties into all our work and activites.

Internal cross-pillar ‘Virtual teams’ which met monthly to discuss developments in each sector that the Programme was focused on to better coordinate policy, Programme and trade objectives. It was also a key forum for agreeing on changes to the Programme and exploring secondary benefit opportunities generated by the strands.

Programme-level approach to monitoring and evaluation

Monitoring and evaluaton of this Programme was contracted out to a third party consortium of Evaluation and Learning specialists from Tetratech International Development, NIRAS LTS International and Integrity. The evaluations were designed to feed into each of the Annual Reviews conducted for this Programme.

The first cycle evaluation covered the period from June 2017 (submission of the Business Case) through May 2019 - the mid-point in the inception phase. A second cycle evaluation was conducted to cover the first full year of implementation FY 2019/20. A third and final cycle evaluation took place just ahead of the announcement of cuts covering the period 2020/21.

Lessons Learned and Recommendations for Future Programming

Timely and clear stakeholder communications is vital to mitigate reputational risks. Constant and clear communication between implementing partners and the British Embassy was crucial during the SR to maintain the trust of key stakeholders and to mitigate reputational risks as fara as possible. Build development communications into the Programme from design through to every step of implementation and closure. The same is true for secondary benefit targets and objectives.

Ensure that there is capacity at the British Embassy to engage with high-level officials to accelerate Programme implementation. Understanding political sensitivities and internal government dynamics is critical to creating and maintaining Programme momentum. Early escalation of bottlenecks, when necessary is also useful. This became more challenging as departing team members were not replaced, and more staff time was diverted to managing cuts, contract variations, and the early closure of the Programme.

Fully employ adaptable and flexible programming approach from the outset to reduce risks and maintain impact. The COVID-19 outbreak, lockdown measures and SR outcome forced the Programme to be agile and adapt activities to a constantly changing environment. Most Programme interventions moved to virtual delvery, adapting communications, stakeholder engagement, contents and timelines to achieve quality impact.

Use of standardised financial templates that are not fit for purpose can consume working times unnecessarily and contribute to increased errors. Templates should be design and tested to reflect the nature and needs of the the Programme.

Date of last narrative financial report	November 2021 for the implementing partner that decided to exit early from this programme. / April 2022 for all remaining implementing partners.	Date of last audited annual statement	Future Cities: February 2021 / ACROL: February 2021 / Clean Energy & Financial Services: March 2021