## Data (hidden)
QuestionCode | QuestionText | AssessmentDate | TOARef | Sum of Score | Response | Evidence | Assessor Review | Assessor Reason | Supporting Comments | Evidence Comments
StraQuestion47 | The high level characteristics required of the capability under consideration are defined. |  |  | 0 |  | Example: Business Case Para 4.1 (https://sharepoint.com/...) Please use a full URL instead of a hyperlink. Alt+Enter for a new line.
StraQuestion48 | The high level characteristics of the system have been agreed by the capability sponsor. |  |  | 0
StraQuestion49 | The project has achieved consensus with stakeholders regarding the need. |  |  | 0
StraQuestion50 | The capability description is specific. |  |  | 0
StraQuestion51 | The draft user requirements have been derived from the capability description. |  |  | 0
StraQuestion32 | The degree to which security affects the delivery of the capability is understood. |  |  | 0
StraQuestion33 | The Authorisation boundary definition includes systems, organisations (MOD and other) and people. |  |  | 0
StraQuestion52 | There is agreement on where boundaries are with adjacent projects/capabilities between the relevant Senior Responsible Owners. |  |  | 0
StraQuestion53 | There is a high-level description of the assets in scope (more detailed as the project matures) |  |  | 0
StraQuestion34 | Assets include physical, virtual and data types. |  |  | 0
ManQuestion20 | Where there is a need, projects have a transition plan between the current and future architecture (answer Yes if no need). |  |  | 0
StraQuestion65 | The impact of the loss of assets is understood. |  |  | 0
StraQuestion35 | The impact of the loss of assets is reflected in the high level design and requirements. |  |  | 0
StraQuestion37 | Project interdependencies have been identified. |  |  | 0
StraQuestion54 | Interdependencies are reflected in the stakeholder list. |  |  | 0
StraQuestion36 | The project has documented how it supports the wider Defence purpose. |  |  | 0
FinQuestion13 | Activities to address requirements arising from interdependencies are reflected in funding requests and project plan. |  |  | 0
StraQuestion38 | The enterprise architecture has been captured diagramatically, reflects the interdepencies and has been used to inform the design. |  |  | 0
StraQuestion39 | Interdependencies have been identified using information lifecycle diagrams. |  |  | 0
StraQuestion55 | The capability owner has provided a clear and useful risk appetite (e.g. following Orange Book or NCSC guidance) |  |  | 0
StraQuestion40 | The project has generated a basic threat assessment for the type of capability to be provided. |  |  | 0
FinQuestion14 | Funding requested for the next phase of work identifies the range of security tasks. |  |  | 0
FinQuestion15 | Security resourcing has been estimated for each task. |  |  | 0
ManQuestion21 | Risks to delivering the capability within the available project budget, arising from security, have been identified. |  |  | 0
FinQuestion16 | Budgets for managing the identified delivery risks have been estimated and included within the proposal. |  |  | 0
FinQuestion17 | Security funding estimates are based on project need (not worked back from what is available) |  |  | 0
StraQuestion41 | Any risks that are proposed for acceptance by the SRO are within the risk appetite agreed for the project. |  |  | 0
StraQuestion66 | Any risks outside risk appetite have been escalated. |  |  | 0
ManQuestion64 | The SRO has accepted accountability for project risks. |  |  | 0
ManQuestion26 | The project has documented responsibility for their security obligations. |  |  | 0
EcoQuestion5 | The project can demonstrate active discussion with the SRO of security issues vis a vis costs, capability and time. |  |  | 0
FinQuestion11 | Key security governance roles (e.g. as defined by NIST) have been identified and budgeted accordingly. |  |  | 0
ManQuestion27 | The project has change management processes in place, and can demonstrate that they incorporate security. |  |  | 0
StraQuestion42 | The scope of the project and its authorisation boundaries are clearly defined. |  |  | 0
StraQuestion56 | The list of stakeholders encompasses indirect as well as direct dependencies (this should include commercial, political and regulatory stakeholders, such as HSE and ICO) |  |  | 0
StraQuestion57 | The project is aware of any programmes relying on it. |  |  | 0
StraQuestion58 | The project has identified the MOD and other policies that impact on security which apply to the project. |  |  | 0
StraQuestion59 | Any perceived conflicts between policies and capabilities have been identified. |  |  | 0
FinQuestion12 | Actions required to resolve conflicts between policies and capabilities have been scoped. |  |  | 0
ManQuestion28 | The project has planned to manage security risks through life using a formal framework (e.g. NIST 800-37) |  |  | 0
StraQuestion60 | The project has a risk assessment that enables key project management decisions. |  |  | 0
StraQuestion43 | Project can demonstrate the security risks have been well developed, for example by completing the Prepare Step or other appropriate framework. |  |  | 0
EcoQuestion6 | Cyber risks are integrated with other project risks. |  |  | 0
StraQuestion44 | Any risks impacting on other projects have been communicated to the affected SROs and stakeholders. |  |  | 0
ManQuestion22 | There is a process for escalating risks beyond the project. |  |  | 0
ManQuestion29 | Project can demonstrate that it is capturing risks, even when no solution has yet been determined. |  |  | 0
StraQuestion45 | The project presents the top risks associated with the project, and evidence to support them. |  |  | 0
EcoQuestion7 | The business case options for delivering the capability include a documented consideration of the cyber threats. |  |  | 0
EcoQuestion8 | The busienss case options for delivering the capability consider how improved security may support better project outcomes. |  |  | 0
EcoQuestion4 | Any transferred risks have been formally accepted by the recipient. |  |  | 0
FinQuestion18 | Risks outside of appetite have mitigations planned and cost estimated. |  |  | 0
FinQuestion19 | The project has budgeted for implementing formal risk management e.g. using NIST 800-37 or equivalent standards. |  |  | 0
StraQuestion61 | The project has identified the parties responsible for meeting the security requirements. |  |  | 0
ManQuestion23 | The project can demonstrates the separation between accountability and responsibility for risks. |  |  | 0
StraQuestion62 | Project can demonstrate that security risks have been used to influence project direction. |  |  | 0
EcoQuestion9 | Each option in the business case has considered secure engineering principles for confidentiality (NIST 800-160 vol 1 or an alternative standard) |  |  | 0
EcoQuestion10 | Each option in the business case has considered secure engineering principles for resilience (NIST 800-160 vol 2 or an alternative standard) |  |  | 0
ComQuestion1 | The project understands its likely supply chain opportunities and limitations. |  |  | 0
ComQuestion2 | Has the risk assessment included supply chain risks? |  |  | 0
ComQuestion3 | The NIST 800-37 section 2.8 Supply Chain risk management guidance (or equivalent) has been followed. |  |  | 0
ManQuestion30 | The project has registered the system on DART. |  |  | 0
StraQuestion63 | The project can demonstrate that it has used its agreed risk appetite to prioritise risks. |  |  | 0
StraQuestion46 | The project can show that the key security risks have been accepted by the SRO. |  |  | 0
ManQuestion24 | How data is transmitted, stored, processed, created and destroyed (the information lifecycles) have been considered throughout the life of the capability. |  |  | 0
ManQuestion31 | Project can demonstrate that there is a plan in place for continuously managing risks throughout the capability's lifetime. |  |  | 0

## Start here
Project Information
Project Name:
TOA Reference:
User's Name:
Email Address:
Date Of Completion:
Description
This tool has been developed to support you in assessing your project's achievement against the Secure by Design policy and Prepare Step. This tool is to be used by Project Teams to assess themselves against the requirements of Secure by Design and may be reviewed by CySAAS Assessors where they are required to provide a formal assessment of the project. All projects, whether self-assessed, or independently CySAAS assessed will be evaluated against the same criteria. Note this tool is OFFICIAL and it is recommended that no information above this classification is input. The reason for this classification is that it covers behaviours rather than technical capabilities.
Planning for Success
You should review the Assessment tab at your earliest opportunity, a project that delays this until immediately before their SOC submission is unlikely to demonstrate the required level of security maturity to progress. Read the statements, and understand the activities that you will need to plan and carry out to achieve the desired outcome, guidance is available on the Secure by Design portal. Determine the evidence that you will need to provide to the Assessor, and ensure that the production of any required evidence pack has been included in your project plans.
Using the Tool
To use the table, the Assessor must look at each of the compliance indicators in column F of the Assessment tab, and then determine whether they are compliant or not, according to the evidence they have seen. Evidence may be drawn from, but not limited to the following: • Discussions with stakeholders for security • Security or risk focused meetings • Security or risk focused documentation reviews • Reviews of risk registers • Reviews of architectural design patterns • Observing how security or risk is managed day to day • Use of security or risk technology • Risks or incidents that have been realised If you are content that the evidence shows the compliant behaviour, you should type 'Yes' in column G, otherwise leave it blank. If the evidence is unclear or inconclusive you should leave the answer blank. Once you have answered each row you must refresh the workbook using Ctrl+Alt+F5, this will update the output diagrams.
Interpreting the Results
You can review the output of the assessment on the Metrics tab, in the form of three radar plots. Although these plots are based on the same data set, they each present this data in a different context. The Policy plot allows you to identify areas of compliance against policy. You are compliant against each Policy Principle where the radar plot shows 100%. Where the radar plot shows a level below this, you are non-compliant. The Prepare plot allows you to assess how well you have progressed the Prepare Steps identified in NIST 800-37 and recommended by the Secure by Design guidance. The Pre-SOC plot allows you to understand how well you have incorporated security issues and considerations into the SOC documentation, and therefore provides a view of how well integrated security is to the rest of the project.

## Assessment
Question Code | Policy Principle | Policy Index | Prep Step Task | Green Book Case | Compliant Indicator | Score | Score_calc | Supporting Evidence | Project Comments (optional) | Assessor Review | Reason for Discrepancy | Supporting Comments (if disagreement) | Comment on Evidence (optional)
StraQuestion47 | Understand and define the context | 1 | Mission or Business Focus | Strategic | The high level characteristics required of the capability under consideration are defined. |  | 0 | Example: Business Case Para 4.1 (https://sharepoint.com/...) Please use a full URL instead of a hyperlink. Alt+Enter for a new line.
StraQuestion48 | Understand and define the context | 1 | Mission or Business Focus | Strategic | The high level characteristics of the system have been agreed by the capability sponsor. |  | 0
StraQuestion49 | Understand and define the context | 1 | Mission or Business Focus | Strategic | The project has achieved consensus with stakeholders regarding the need. |  | 0
StraQuestion50 | Understand and define the context | 1 | Mission or Business Focus | Strategic | The capability description is specific. |  | 0
StraQuestion51 | Understand and define the context | 1 | Requirements Definition | Strategic | The draft user requirements have been derived from the capability description. |  | 0
StraQuestion32 | Understand and define the context | 1 | Mission or Business Focus | Strategic | The degree to which security affects the delivery of the capability is understood. |  | 0
StraQuestion33 | Understand and define the context | 1 | Authorisation Boundary | Strategic | The Authorisation boundary definition includes systems, organisations (MOD and other) and people. |  | 0
StraQuestion52 | Understand and define the context | 1 | Authorisation Boundary | Strategic | There is agreement on where boundaries are with adjacent projects/capabilities between the relevant Senior Responsible Owners. |  | 0
StraQuestion53 | Understand and define the context | 1 | Asset Identification | Strategic | There is a high-level description of the assets in scope (more detailed as the project matures) |  | 0
StraQuestion34 | Understand and define the context | 1 | Information Types | Strategic | Assets include physical, virtual and data types. |  | 0
ManQuestion20 | Understand and define the context | 1 | Enterprise Architecture | Management | Where there is a need, projects have a transition plan between the current and future architecture (answer Yes if no need). |  | 0
StraQuestion65 | Understand and define the context | 1 | Information Types | Strategic | The impact of the loss of assets is understood. |  | 0
StraQuestion35 | Understand and define the context | 1 | Information Types | Strategic | The impact of the loss of assets is reflected in the high level design and requirements. |  | 0
StraQuestion37 | Understand and define the context | 1 | Authorisation Boundary | Strategic | Project interdependencies have been identified. |  | 0
StraQuestion54 | Understand and define the context | 1 | Authorisation Boundary | Strategic | Interdependencies are reflected in the stakeholder list. |  | 0
StraQuestion36 | Understand and define the context | 1 | Mission or Business Focus | Strategic | The project has documented how it supports the wider Defence purpose. |  | 0
FinQuestion13 | Understand and define the context | 1 | Requirements Definition | Financial | Activities to address requirements arising from interdependencies are reflected in funding requests and project plan. |  | 0
StraQuestion38 | Understand and define the context | 1 | Enterprise Architecture | Strategic | The enterprise architecture has been captured diagramatically, reflects the interdepencies and has been used to inform the design. |  | 0
StraQuestion39 | Understand and define the context | 1 | Information Life Cycle | Strategic | Interdependencies have been identified using information lifecycle diagrams. |  | 0
StraQuestion55 | Understand and define the context | 1 | Risk Assessment | Strategic | The capability owner has provided a clear and useful risk appetite (e.g. following Orange Book or NCSC guidance) |  | 0
StraQuestion40 | Understand and define the context | 1 | Risk Assessment | Strategic | The project has generated a basic threat assessment for the type of capability to be provided. |  | 0
FinQuestion14 | Plan the Security Activities | 2 | Requirements Definition | Financial | Funding requested for the next phase of work identifies the range of security tasks. |  | 0
FinQuestion15 | Plan the Security Activities | 2 | Requirements Definition | Financial | Security resourcing has been estimated for each task. |  | 0
ManQuestion21 | Plan the Security Activities | 2 | Risk Assessment | Management | Risks to delivering the capability within the available project budget, arising from security, have been identified. |  | 0
FinQuestion16 | Plan the Security Activities | 2 | Requirements Definition | Financial | Budgets for managing the identified delivery risks have been estimated and included within the proposal. |  | 0
FinQuestion17 | Plan the Security Activities | 2 | Requirements Definition | Financial | Security funding estimates are based on project need (not worked back from what is available) |  | 0
StraQuestion41 | Plan the Security Activities | 2 | Risk Assessment | Strategic | Any risks that are proposed for acceptance by the SRO are within the risk appetite agreed for the project. |  | 0
StraQuestion66 | Plan the Security Activities | 2 | Risk Assessment | Strategic | Any risks outside risk appetite have been escalated. |  | 0
ManQuestion64 | Plan the Security Activities | 2 | System Stakeholders | Management | The SRO has accepted accountability for project risks. |  | 0
ManQuestion26 | Plan the Security Activities | 2 | System Stakeholders | Management | The project has documented responsibility for their security obligations. |  | 0
EcoQuestion5 | Plan the Security Activities | 2 | System Stakeholders | Economic | The project can demonstrate active discussion with the SRO of security issues vis a vis costs, capability and time. |  | 0
FinQuestion11 | Plan the Security Activities | 2 | System Stakeholders | Financial | Key security governance roles (e.g. as defined by NIST) have been identified and budgeted accordingly. |  | 0
ManQuestion27 | Plan the Security Activities | 2 | Requirements Definition | Management | The project has change management processes in place, and can demonstrate that they incorporate security. |  | 0
StraQuestion42 | Plan the Security Activities | 2 | Authorisation Boundary | Strategic | The scope of the project and its authorisation boundaries are clearly defined. |  | 0
StraQuestion56 | Plan the Security Activities | 2 | System Stakeholders | Strategic | The list of stakeholders encompasses indirect as well as direct dependencies (this should include commercial, political and regulatory stakeholders, such as HSE and ICO) |  | 0
StraQuestion57 | Plan the Security Activities | 2 | System Stakeholders | Strategic | The project is aware of any programmes relying on it. |  | 0
StraQuestion58 | Plan the Security Activities | 2 | Requirements Definition | Strategic | The project has identified the MOD and other policies that impact on security which apply to the project. |  | 0
StraQuestion59 | Plan the Security Activities | 2 | Requirements Definition | Strategic | Any perceived conflicts between policies and capabilities have been identified. |  | 0
FinQuestion12 | Plan the Security Activities | 2 | Requirements Definition | Financial | Actions required to resolve conflicts between policies and capabilities have been scoped. |  | 0
ManQuestion28 | Implement Continuous Risk Management | 3 | Enterprise Architecture | Management | The project has planned to manage security risks through life using a formal framework (e.g. NIST 800-37) |  | 0
StraQuestion60 | Implement Continuous Risk Management | 3 | Risk Assessment | Strategic | The project has a risk assessment that enables key project management decisions. |  | 0
StraQuestion43 | Implement Continuous Risk Management | 3 | Risk Assessment | Strategic | Project can demonstrate the security risks have been well developed, for example by completing the Prepare Step or other appropriate framework. |  | 0
EcoQuestion6 | Implement Continuous Risk Management | 3 | Risk Assessment | Economic | Cyber risks are integrated with other project risks. |  | 0
StraQuestion44 | Implement Continuous Risk Management | 3 | Risk Assessment | Strategic | Any risks impacting on other projects have been communicated to the affected SROs and stakeholders. |  | 0
ManQuestion22 | Implement Continuous Risk Management | 3 | System Stakeholders | Management | There is a process for escalating risks beyond the project. |  | 0
ManQuestion29 | Implement Continuous Risk Management | 3 | Risk Assessment | Management | Project can demonstrate that it is capturing risks, even when no solution has yet been determined. |  | 0
StraQuestion45 | Implement Continuous Risk Management | 3 | Risk Assessment | Strategic | The project presents the top risks associated with the project, and evidence to support them. |  | 0
EcoQuestion7 | Implement Continuous Risk Management | 3 | Risk Assessment | Economic | The business case options for delivering the capability include a documented consideration of the cyber threats. |  | 0
EcoQuestion8 | Implement Continuous Risk Management | 3 | Risk Assessment | Economic | The busienss case options for delivering the capability consider how improved security may support better project outcomes. |  | 0
EcoQuestion4 | Define Security Controls | 4 | Requirements Allocation | Economic | Any transferred risks have been formally accepted by the recipient. |  | 0
FinQuestion18 | Define Security Controls | 4 | Requirements Definition | Financial | Risks outside of appetite have mitigations planned and cost estimated. |  | 0
FinQuestion19 | Define Security Controls | 4 | Risk Assessment | Financial | The project has budgeted for implementing formal risk management e.g. using NIST 800-37 or equivalent standards. |  | 0
StraQuestion61 | Define Security Controls | 4 | Requirements Allocation | Strategic | The project has identified the parties responsible for meeting the security requirements. |  | 0
ManQuestion23 | Define Security Controls | 4 | Requirements Allocation | Management | The project can demonstrates the separation between accountability and responsibility for risks. |  | 0
StraQuestion62 | Define Security Controls | 4 | Requirements Definition | Strategic | Project can demonstrate that security risks have been used to influence project direction. |  | 0
EcoQuestion9 | Define Security Controls | 4 | Risk Assessment | Economic | Each option in the business case has considered secure engineering principles for confidentiality (NIST 800-160 vol 1 or an alternative standard) |  | 0
EcoQuestion10 | Define Security Controls | 4 | Risk Assessment | Economic | Each option in the business case has considered secure engineering principles for resilience (NIST 800-160 vol 2 or an alternative standard) |  | 0
ComQuestion1 | Supply Chain | 5 | System stakeholders | Commercial | The project understands its likely supply chain opportunities and limitations. |  | 0
ComQuestion2 | Supply Chain | 5 | Risk Assessment | Commercial | Has the risk assessment included supply chain risks? |  | 0
ComQuestion3 | Supply Chain | 5 | Risk Assessment | Commercial | The NIST 800-37 section 2.8 Supply Chain risk management guidance (or equivalent) has been followed. |  | 0
ManQuestion30 | Assure, Verify and Test | 6 | System Registration | Management | The project has registered the system on DART. |  | 0
StraQuestion63 | Assure, Verify and Test | 6 | Risk Assessment | Strategic | The project can demonstrate that it has used its agreed risk appetite to prioritise risks. |  | 0
StraQuestion46 | Assure, Verify and Test | 6 | Risk Assessment | Strategic | The project can show that the key security risks have been accepted by the SRO. |  | 0
ManQuestion24 | Enable Through Life Management | 7 | Information Life Cycle | Management | How data is transmitted, stored, processed, created and destroyed (the information lifecycles) have been considered throughout the life of the capability. |  | 0
ManQuestion31 | Enable Through Life Management | 7 | Requirements Definition | Management | Project can demonstrate that there is a plan in place for continuously managing risks throughout the capability's lifetime. |  | 0
[10 empty] | Confirmed | Missing evidence.
[10 empty] | Questioned | Partially completed evidence
[10 empty] | Disputed | Evidence does not justify answer (or claimed maturity level)
Non-compliant with MOD policy
Not Applicable
N.B. To enter data, first save this workbook as a new file.
Enter "Yes" where there is evidence of a good behaviour; leave blank otherwise.
The definition of Yes =
User the Notes column to record the location of the evidence; you may be required to produce this by CySAAS or auditors.
During assessment, if you believe a good behaviour is not recognised by this tool, please let CySAAS know, for consideration for future updates.
The status of this tool is currently 'Beta'.
Note on I1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This should reference some documentary evidence to justify the self-assessment. This evidence should be made available to an assessor for any independent review.
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This may be used to clarify the self-assessment, or highlight parts of the supporting evidence. However, only referenced evidence can be used to justify the self-assessment not any compliance statements provided here.
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Testing an alternative to a Y/N response. Select from: Questioned - self-assessment partially validated Disputed - self-assessment not justified by the evidence Confirmed - self-assessment is supported by the evidence provided.
Note on L1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Select from current options: Missing evidence. Partially completed evidence Evidence does not justify claimed maturity level Non-compliance(s) with MOD policy Not Applicable
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Brief comment to justify any discrepancy
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Brief comment on a specific piece of evidence e.g. how it could be improved, or how well it justifies the self assessments, or where it is particularly good.

## Calculation (hidden)
Row Labels | Count of Policy Principle | Sum of Score_calc | Policy Principle | Score
Assure, Verify and Test | 3 | 0 | Assure, Verify and Test | 0%
Define Security Controls | 8 | 0 | Define Security Controls | 0%
Enable Through Life Management | 2 | 0 | Enable Through Life Management | 0%
Implement Continuous Risk Management | 10 | 0 | Implement Continuous Risk Management | 0%
Plan the Security Activities | 18 | 0 | Plan the Security Activities | 0%
Supply Chain | 3 | 0 | Supply Chain | 0%
Understand and define the context | 21 | 0 | Understand and define the context | 0%
Grand Total | 65 | 0
Row Labels | Count of Prep Step task | Sum of Score_calc | NIST Prepare Steps | Score
Asset Identification | 1 | 0 | Asset Identification | 0%
Authorisation Boundary | 5 | 0 | Authorisation Boundary | 0%
Enterprise Architecture | 3 | 0 | Enterprise Architecture | 0%
Information Life Cycle | 2 | 0 | Information Life Cycle | 0%
Information Types | 3 | 0 | Information Types | 0%
Mission or Business Focus | 6 | 0 | Mission or Business Focus | 0%
Requirements Allocation | 3 | 0 | Requirements Allocation | 0%
Requirements Definition | 13 | 0 | Requirements Definition | 0%
Risk Assessment | 20 | 0 | Risk Assessment | 0%
System Registration | 1 | 0 | System Registration | 0%
System Stakeholders | 8 | 0 | System Stakeholders | 0%
Grand Total | 65 | 0
Row Labels | Count of Green Book Case | Sum of Score_calc | 5 Case Business Model | Score
Commercial | 3 | 0 | Commercial | 0%
Economic | 7 | 0 | Economic | 0%
Financial | 9 | 0 | Financial | 0%
Management | 12 | 0 | Management | 0%
Strategic | 34 | 0 | Strategic | 0%
Grand Total | 65 | 0
Yes
No
Understand and define the context | 1
Plan the Security Activities | 2
Implement Continuous Risk Management | 3
Define Security Controls | 4
Supply Chain | 5
Assure, Verify and Test | 6
Enable Through Life Management | 7

## Metrics
SBD Policy compliance (JSP 440 Leaflet 5C) | Inclusion of Security in Green Book 5-Case Model
Prepare Step completion (NIST 800-37 Rev 2)
Select 'Refresh All' on the Data tab (or press Ctrl-Alt-F5) to update