TERMS OF REFERENCE
UK’s CPTPP Accession: Maximising the potentials of UK-Malaysia trade and investment
Background
The United Kingdom (UK) became a CPTPP member on 16 July 2023. Its accession provided bloc members with easier access to the fifth largest economy in the world and a market of 67 million consumers. For Malaysia, this will be its first free trade agreement with the UK and an opportunity to improve further bilateral trade and investment ties.
The United Kingdom (UK) – Malaysia bilateral trade in goods and services was valued at approximately £5.6bn in the four quarters to the end of 2022 (4Q22). The UK currently has a near-5% share of the Malaysian market in services (compared to less than 2% in goods), mainly in the travel, transportation, financial and other business services sub-sectors. Given the UK’s strengths especially in services, there is significant potential for growth in Malaysia and in UK players’ interest in utilising Malaysia as a hub in the wider region. Likewise, for Malaysian businesses and investors in the UK.

However, there have been limited studies conducted on the specific opportunities in Malaysia and in the UK for both nation’s goods and services trade and investments. Hitherto, studies have focused on the broad or aggregated benefits of trade to both countries’ economies. To fill this gap, research is now being proposed to focus on how the UK’s accession to the CPTPP could benefit the different UK and Malaysian trade and services exporters as well as investors.

Scope of the study
Based on the above, the Foreign, Commonwealth and Development Office (FCDO), Government of UK would like to invite proposals for an analysis of the market access and investment opportunities afforded to UK players across key goods and services sectors in Malaysia and vice versa, through the CPTPP. The analysis is expected to help promote, among other things, the economic and trade interests of the UK Government in Malaysia.

Specific themes that the study should address include:
1. The list of top beneficiaries (at least three sectors) in goods and services trade, both for the UK in Malaysia and vice versa. This should include quantitative estimation by sub-sector.
2. The list of top investment opportunities (at least three sectors) for both the UK in Malaysia and vice versa. This should include quantitative estimation by sub-sector.
3. The list of non-tariff measures not addressed in the CPTPP but could be barriers to fulfilling the opportunities, particularly but not limited to the sectors listed on item (1) and (2) above.

Methodology
The research should be done as a desk exercise, following appropriate empirical analysis methodology coupled with expert consultations where required. When performing quantitative estimations, international classification of the goods and services sector and sub-sectors such as HS Code (at least 6-digits) and EBOPS 2010 or CPC should be used. Any secondary data used should be from reputable and credible databases. Contextual analysis of risks and opportunities should be targeted towards UK policymakers and businesses. No primary data collection is envisaged, other than expert consultations, where needed.
Care should be taken to ensure that all data and literature that is reviewed meets accepted quality standards. Expert opinion should be drawn upon, but a clear distinction should be made between inferences drawn from published literature and those drawn from consultative processes.
Detailed methodology should be proposed by the research team at an early stage, drawing attention to specific sources of available data and information where relevant. This should include key policy documents and existing policy and/or commercial analysis.
Consultations with key BHC staff will be needed. These should be planned at an early stage of the study and continued throughout the study duration.

Recipient
The primary recipient of this project will be the British High Commission Kuala Lumpur (BHC), who will have full control of the output’s intellectual property. BHC may, at its own discretion, consider making available the output of this project to the wider policy and business community. The output of this project should not be published or shared with anyone except with written permission from the Economic Adviser, Political Counsellor (Bilateral) and DIT Country Director at BHC.

Time frame, deliverables and budget
The study should be completed, with all deliverables submitted and/or completed by 31 March 2024.
The deliverables should include:
- A technical report, responding to the review questions mentioned above, not exceeding 40 pages, and including a stand-alone Executive Summary. Details of quantitative data and analyses made should be presented as Annexure.
- A policy paper, not exceeding 4 pages, based on the technical report, targeted to a policymaking audience.
- A slide set based on the content of the technical report.
- At least one physical workshop to disseminate the findings. The target audience should include policymakers and businesses.

The timelines would be:
- An inception report: Within two weeks of the initiation of the study, including the agreed methodology.
- A review-ready early draft of the technical report within 20 weeks of the initiation of the study.
- A review-ready second draft of the technical report and early-draft of the slide set and policy paper: Within 25 weeks of the initiation of the study
- Final technical report, slide set and policy paper within 30 weeks of the initiation of the study
- Dissemination event: Within 31 weeks of the initiation of the study
- A short dissemination report before the end of the study

The budget for the study should not exceed £ 60,000 including management and administration costs, and any relevant local taxes.

Skills
Proposals will be accepted from organisations or a consortium of consultants. The proposed project team should collectively possess the following skills:
Sound knowledge of the Malaysian trade policies. Familiarity with the UK trade policies is preferred but not essential.
- Proven ability to conduct quantitative analysis and conceptualization in trade.
- Proven ability to undertake applied research and produce high quality review papers and policy briefs, meeting international standards within short timeframes
- Excellent written and spoken communication skills, and the ability to communicate to policy audiences
- Strong academic and policy networks in Malaysia, nuanced understanding of issues in the Malaysian context, demonstrated by previous work experience in the country and/or region.

Bidding

The technical proposal (maximum of 10 pages) should include an organisational profile, short CVs of members of the project team, the proposed methodology (including access to data sources), a clear workplan and comments on the ToR. A commitment that the proposed experts will be available – and the team will be mobilised at short notice – is needed due to the nature of the assignment. Indicative time allocations of key team members should be provided in the technical proposal. These should be consistent with figures indicated in the financial proposal. Detailed CVs may be provided as an Annexure (not counted in the 10 pages).

The technical and financial proposals will be assigned weights of 80% and 20% respectively – for the purpose of assessment.

Further, the following sub-weights will be assigned within the technical proposal:
- Strengths of the organisation: 10%
- Skills and past experience on similar assignments – of the Team Leader and key team members[1]: 15%
  [1] The proposal should clearly indicate the roles of the Team Leader and each team member.
- Understanding of issues in the TOR and methodology (including access to data sources): 40%
- Feasibility of the proposed workplan, and evidence of ability to mobilise at short notice: 15%

Expression of interest, including technical and financial proposals as well as the completed FCDO forms (Project Proposal Form for projects above £10,000 and Activity Based Budget) (a total of 4 different documents) should be emailed to BHC, addressed to Ms Pamela Victor at Pamela.Victor@fcdo.gov.uk by 4 August 2023 (23:59 Kuala Lumpur time).