# Terms of Reference: analysis to co-design research and innovation programme
Background
Three FCDO programmes are scheduled to conclude in March 2025, FCDO’s
Research and Evidence Directorate seeks to design a single successor programme, strengthening African, Indian and Southeast Asian research and innovation systems for development and diplomatic impact. FCDO seeks experts to conduct research and feed this research into Business Case design, ensuring the new programme is evidence-based.
The three FCDO programmes scheduled to conclude in March 2025 are:
- Strengthening Research Institutions in Africa (SRIA)
- Africa Technology and Innovation Partnerships (ATIP)
- Strengthening Africa’s Science Granting Councils, Phase II (SGCI2)
A fourth, related programme, the Africa Capacity Building Initiative (ACBI), concluded in 2022. Programme design will also consider lessons from ACBI,
including whether any initiative/project started through ACBI should be reprised.
FCDO wants to maximise its impact through the new research and innovation system strengthening programme. This means a programme design that:
- Rests on clear, evidence-based choices about how the programme will strengthen research and innovation in Africa, India and Southeast Asia, building on learning from SRIA, ATIP, SGCI, ACBI and other relevant programmes.1
- Sets out how the programme will expand its geographic scope to include India and South-east Asia, and why.
- Compliments other donor-funded research and innovation programming in these regions. This will require the experts to map (or access mapping of) other
research and innovation capacity strengthening initiatives.
- Matches its ambition to the likely size of budget and proposed scope, whilst maintaining the flexibility to scale up or down.
- Selects its delivery partners based on what the programme wants to achieve, and where.
# Objectives and scope of work
Objectives
Produce on-demand evidence synthesis and analysis to feed into programme design decisions. This will involve synthesising learning from existing FCDO programmes and research capacity strengthening and innovation programmes, and other funders’ programmes. It will also involve taking a critical look at the

1 See for example UK Collaborative for Development Research (2022) Research Capacity Strengthening: Lessons from UK-Funded Initiatives in Low- and Middle-Income Countries.
value for money of current programmes and whether similar support should continue or evolve.
- With FCDO colleagues, identify and propose options for the type of investments FCDO makes. Consider, among other things: geographical scope; system strengthening goals, such as poverty reduction, gender and social inclusion, climate change mitigation and adaptation; varied ecosystem maturity levels; existing partnerships; and presence of other development actors. Gather, synthesise and present evidence to support decision making.
- With FCDO colleagues, identify and propose options for the best delivery model to achieve the objectives, based on decisions taken about the overall geographic scope and approach (see previous bullet point.) Options here might include grants, challenge funds or longer-term investment in teams of facilitators who use a combination of catalytic grants, convening, technical assistance and advocacy to achieve transformative change in research and innovation systems.2 There is also scope to use different delivery models in different components of the programme.
- Set up and co-deliver design workshops with the FCDO design team.
- Contribute to early drafting of the programme Business Case. Specifically, we anticipate contributions to the Strategic, Appraisal and Commercial Cases. FCDO staff will lead the overall Business Case.

Proposed sequencing of research and design work
Programme design will be iterative. With so many variables and options, we will save time and feel more productive if our design decisions are well sequenced. The diagram below suggests a rough order in which key decisions are likely to be taken.

2

Geographic scope
FCDO, informed by expert analysis through this assignment, will need to decide
which countries and regions this programme will work in. For context, here are a few of the considerations likely to inform decisions:
- Wellcome Trust and FCDO co-fund DELTAS II; we plan similar programming in Southeast Asia. FCDO’s contribution would form a component of the new programme being designed here.
- There may be a trade-off between targeting the poorest places and targeting places with the most potential to grow their research and innovation systems. The experts will advise on the geographic scope that offers the best balance between pro-poor benefit and with R&I systems growth potential.
- It is tempting to focus on places where research and/or innovation systems are already quite strong, such as Nairobi. However, research and innovation systems in these places may need less support; they tend to attract more donor, private sector and domestic government funding than less-advanced research and
innovation systems. FCDO will consider where its investment adds the most value. This may require the experts to help us understand which national and subnational research and innovation systems have the greatest growth potential over the next 10-15 years, with donor support.
India has a strong track record of creating pro-poor innovations, many of which have the potential to benefit large numbers of poor women and men in Africa. Many Indian innovators are at an early stage of understanding African markets.
The programme may decide to play a role in providing Indian innovators with support to encourage their market entry in Africa. Programme designers will also need to decide the extent to which trilateral partnerships around scaling Indian
innovation in public sector digitalisation fits within the scope of this programme.
ATIP and SRIA have focused on a small number of countries, engaging with a wide range of research and innovation stakeholders within them. SGCI2, in contrast, partners mainly with a single type of stakeholder, across many countries. There are pros and cons of both approaches; intervening in many countries adds complexity but may offer economies of scale.
International Climate Finance
  - FCDO will need to decide whether to design the programme in a way that a significant proportion of it contributes to the UK’s International Climate
Finance commitments.3 Counting part of the budget as International Climate Finance has implications for programme design; programme-funded support would need to improve research and innovation systems in ways that demonstrably enhance climate change adaptation and mitigation.
# Methodology
  - We anticipate that most of the analysis will be desk-based.
  - Most design workshops with FCDO colleagues will be virtual.
  - Travel to/within Africa or India may be required to identify prospective partners among research institutions (including partners involved in existing FCDO programmes.) Travel may also be required for in-person workshops/deep dives, to translate findings from analysis into programme design decisions.
# Skills
Required:
Track record of delivering evidence-based analysis for programme design,
including learning and monitoring across a complex portfolio of programmes.
- Understanding of research and innovation ecosystems, and how they can deliver development impact, especially in Africa and India.
- Ability to diagnose what most constrains a research or innovation system from reaching its potential
- Understanding of how to measure the impact of ecosystem support initiatives
- Deep expertise in how development actors can effectively change systems, to benefit poor women and men.

3 FCDO will need to decide what percentage of the programme is eligible to count as International Climate Finance.
- Ability to take a view on programme design that is sufficiently independent from own commercial considerations.
- Demonstrated networks with key stakeholders in research and innovation systems in targeted geographies.
- Demonstrated ability to write and communicate clear, well-evidenced analysis. Desirable:
- Ability to write clear, well-evidenced FCDO Business Cases.
- A small team (e.g., 2 experts), as opposed to a large team. We believe that successful performance of this assignment will require immersion in the topic; a large team who each give a small set of inputs is likely to be less cost-effective.
- Substantial multi-country experience, for at least one of the experts, and that at least one expert resides in a developing country.

# Programme management arrangements
- The experts will be contracted through FCDO’s Evidence Fund. PwC, as the Evidence Fund manager, will arrange for this assignment to be tendered.
- The delivery partner will sign a contract with PwC, as Evidence Fund Manager. The delivery partner will submit invoices to PwC; PwC will subsequently seek payment from FCDO.
- FCDO will appoint one of its staff as Design Lead. This person will serve as the delivery partner’s main contact in FCDO for this assignment.
- Fortnightly, the delivery partner will meet the design lead, plus a group of their FCDO colleagues involved in programme design. Meetings will serve both to discuss the delivery partner’s analysis and to agree subsequent deliverables.
- The delivery partner will be contractually bound to share all information gained through their involvement in this assignment. FCDO will share information that could have a material benefit to anyone bidding for the programme being designed with all parties interested in bidding for the programme’s
implementation phase, to ensure a level playing field.
# Timeframe, deliverables and budget
Table: Timeline
Phase	Timing
ITT published	18 August 2023
Deadline for clarification questions	15 September 2023
Clarification responses	20 September 2023
Deadline for applications	4 October 2023
Anticipated award date	16 October 2023

Deliverables:
- Bespoke, rapid analysis to inform programme design. The number, length and format of analytical pieces will be agreed between FCDO and the successful bidder in a kick-off meeting and may evolve as the assignment progresses.
- Co-facilitation of meetings/online workshops to discuss findings from analysis and their implications for programme design.
- Inputs to final draft of the programme Business Case (co-created with FCDO).
The delivery partner is expected to make substantial contributions to drafting the Strategic, Appraisal and Commercial cases. FCDO staff will lead the overall Business Case.
Timeframe:
- All deliverables should be complete by 31st May 2024. Budget:
- The budget for this assignment is £98,000. The budget includes fees for expert time, travel, other eligible expenses.
- Bidders should budget for two ten-day trips to/within Africa or India. Bidders should also budget travel for travel to two in-person design workshops, lasting approximately two days each.

# Quality assurance mechanisms
FCDO staff involved in programme design will quality assure the delivery partner’s analysis and translation of that analysis into Business Case design.
There will be no external peer review process, however the draft business case is likely to be reviewed by FCDO’s internal Quality Assurance Unit.

# Eligibility, ethics and safeguarding
FCDO is unlikely to accept bids to carry out this assignment from organisations that play leading roles in FCDO’s current research capacity strengthening
programmes. Such organisations would face a conflict of interest and may therefore struggle to provide independent advice on the relative value of continuing with the same or similar programmatic approach and delivery model, compared with other approaches. The views of FCDO’s current delivery partners will feed into the design of the new programme through separate consultation exercises.
The delivery partner must under no circumstances withhold information from FCDO that might give them an advantage in bidding for a subsequent programme. FCDO wants to ensure a level playing field between prospective
bidders – key information gathered during programme design will be made public.
The Supplier Code of Conduct will be included in the Terms and Conditions of the Contract. New compliance checking mechanisms are now in place to review supplier documentation, their approaches to legal compliance and demonstration of good practice in meeting international principles on labour and ethical employment and to provide assurance that whistleblowing systems are accessible across delivery chains. FCDO will monitor risk and mitigation plans throughout the project cycle. The commitments made by all organisations in
receipt of FCDO funding need to provide spending teams with concrete assurance that the new enhanced safeguarding standards are being applied. The approach will help to promote the adoption of new standards for all organisations in the aid sector.