## Terms of Reference
## Programme of support for the UK-India Co-Operation on Pensions
INTRODUCTION
- The Foreign, Commonwealth & Development Office (Authority) is commissioning a supplier to support the development of the UK-India Co-operation on Pensions. The project is intended to span from August 2023 to March 2024. The key objective of the programme is to deepen knowledge-sharing on recent and planned regulatory reforms in UK and Indian pension sectors to promote economic development in both countries by facilitating greater pensions links.
- The Foreign, Commonwealth and Development Office (FCDO) leads the UK government’s work to end extreme poverty. FCDO’s strategic objectives are:
- strengthening global peace, security and governance
- strengthening resilience and response to crisis
- promoting global prosperity and economic development including finance
- tackling extreme poverty and helping the world’s most vulnerable
This programme which will help India to implement its proposed economic and finance reforms, climate and infrastructure development priorities, with a view to support its long-term growth objectives. It will provide expertise and support, primarily to Pension Fund Regulatory and Development Authority (PFRDA) and Ministry of Finance. The programme will engage in areas where the UK is well-placed to make the greatest strategic impact: (i) private finance and reforms to the business environment; (ii) tax revenue mobilisation and public finance; and (iii) high quality, low carbon and resilient infrastructure.

BACKGROUND
- Background of the programme- This programme is an extension of the pensions work that was planned under the Technical Assistance Programme for Financial Services in India (FS) which was established through a Memorandum of Understanding (MoU) signed between the UK Foreign and Commonwealth Office (now Foreign, Commonwealth and Development Office) and the Indian Ministry of Finance in January 2019.
- The FS Programme aimed at interventions that strengthen regulatory capacity in data analytics, risk-based supervision, product innovation, improving awareness and distribution, behavioural economics and fund management that would aim to enhance pension coverage; particularly among the economically weaker segments of the society and women. It focused on working with with the Pension Fund Regulatory and Development Authority (PFRDA) to build capacity on developing and regulating new pension products.
- Through this programme we will work closely with PFRDA to support strengthening of the pensions reforms in India learning from the UK’s experience in order to promote FCDO objectives of promoting economic development and reducing extreme poverty. The programme will provide support to the PFRDA in the sharing of best practices on policy development and closer co-operation on capacity building.
- The programme seeks to build on the announcement at the 12th UK-India Economic and Financial Dialogue, by the Chancellor of the Exchequer and the Hon’able Finance Minister of India on a new partnership between the UK and India on the insurance and pensions sectors. Both sides have agreed to develop a work plan on the collaboration which will include deepening knowledge-sharing on recent and planned regulatory reforms in our insurance and pension sectors.

- SCOPE OF SERVICES
- The Supplier will be expected to finalise this programme work after discussions with the relevant stakeholders in the Ministry of Finance and the Pension Fund Regulatory and Development Authority (PFRDA) within two weeks of commencing programme delivery. This will include finalizing of the logframe as in annex A below.
- Deliver a Project Commencement Report of not more than 5 pages, covering:
- Overview of the pensions sector in India for both public and private sectors in comparison to the UK, with focus on identifying key challenges and opportunities in deepening pensions penetration across India. The report should also include the demographic comparison between the UK and India.
- Early lessons from the UK’s pension sector (both private and public funds) for India, with a particular focus on areas such auto-enrolment, defined contribution schemes and annuity markets.
- On the basis of the research conducted in 1(a) and 1(b), set out the top three interventions to be delivered through the programme, along with a project plan and work plan for the same.
- Deliver at least (2) two policy papers for regulators covering key learnings from international markets such as the UK on supporting the growth of the pensions sector in India. The policy papers will aim to be presented and ratified by the Ministry of Finance and/or the PFRDA, with topics to be agreed with these stakeholders during the project commencement phase. Emerging themes to be explored include:
- Incorporation of ESG principles in pension funds business with an aim to scaling up the sustainable finance portfolio, incorporating climate change risk into existing risk management framework(s) and unlocking sustainable infrastructure investment opportunity.
- Recommendations on leveraging digital infrastructure to facilitate deeper pensions penetration in India.
- Learnings on customer protection and data privacy, and best practices on steps taken to address these issues.
3.7	Design and deliver a high level one day conference on pensions in India, which must include:
- Dissemination of the key recommendations of the policy papers finalised through the programme with key external stakeholders in Government and business.
- Experience sharing sessions by experts from the UK on implementing a reforms programme for pensions growth in India.
- Discussions on opportunity for collaboration between the UK and India on pension development, and the case for pension funds in both countries to increase participation in each other’s jurisdictions.
How India can scale up pension coverage quickly and the necessary policy mix between public and private pensions in the first phase of rollout.
        This event is expected to be held in in-person, in either New Delhi/Mumbai.
DETAILS OF REQUIREMENT (OBJECTIVES)
 4.1 The following will be the expected deliverables:
- To deliver the scope of work, the supplier needs to work with Foreign, Commonwealth & Development Office and establish relationships with the Ministry of Finance (Department of Economic Affairs and Department of Financial Services) and Pension Fund Regulatory and Development Authority (PFRDA).
- Two (2) policy papers on deepening pensions penetration in India basis emerging themes set out in the scope of services above.
- A high-level one day in-person conference on the pensions sector in India, leveraging learnings and inputs from UK experts.
- Periodic progress reports based on a mutually agreed format and frequency with FCDO.
- During this process, the supplier will undertake the entire management of the activities outlined in the scope of work and provide periodic progress updates over email and phone call with Foreign, Commonwealth & Development office.
- At the end of the programme supplier is expected to submit the Programme Report in the agreed format with FCDO.

EXPECTED OUTPUTS
5.1 Through this work we aim to achieve the following objectives:
- We aim to achieve deepening and expansion of the coverage of the pensions market in India
- Wider collaboration between UK and India on pensions reform learning best practice for public and private systems alike
- Identifying any obstacles to scaling up pensions in India and making recommendations to policy makers how to overcome them.
5.2 The supplier is required to deliver phased outputs against set timelines (subject to confirmation).

No	Deliverable	Anticipated Activities / (not limited to)	Milestone Date
1	Contract signed with chosen supplier and start the implementation	Proposed work plan for the whole programme	1st week November 2023
2.	Project Commencement Report	Detailed list of finalised activities for the programme	3rd week November 2023
3.	Delivery of initiatives	Implement of activities as agreed with stakeholders	November 2023 onwards
4	Submission of policy papers	Finalisation and submission of policy papers	Policy paper 1: December 2023 / Policy paper 2: January 2024
5	Conference on Pensions in India	One day in person, high level dialogue on the pensions sector in India	February 2024
7	Periodic Reports	Progress and Impact Assessment of the projects	Bi-monthly - Last working day of the second month
8	Draft Programme Report	Progress and impact of the whole progress	15 March 2024
9	Final Programme Report	Submission of final report and a summary presentation for UK and Indian stakeholders.	31 March 2024
9	Programme Completion Report	As agreed with FCDO highlighting the outcome and impact of the programme	pril 2024

6. REPORTING AND ACCOUNTABILITY OF DELIVERY
6.1 The Supplier will submit progress reports and update on calls to FCDO as per mutually agreed format and frequency. These will summarise progress made in agreed timelines against agreed Work Plans, including details of resources deployed.
6.2 A detailed Project Completion Report (PCR) in the FCDO format, a Project Report (in mutually agreed format) including post evaluation report to identify gaps and future opportunities in the pensions sector in India. The outputs outlined above are indicative and may be refined in discussion with FCDO as the assessment progresses.
6.3 The contractor will have to submit a Financial report (along with other reports) at the end of the project. Submission of final report (Project Report) and a summary presentation.
6.4 The Team Leader in the Economic and Finance Team will be first point of contact on the programme for FCDO. Within FCDO, a senior programme manager and senior advisor will be responsible for day-to-day co-ordination and delivery of the programme, reporting to the Team Leader.
7. Monitoring, Reporting, Evaluation and Learning (MREL)
7.1 A central monitoring, reporting, evaluation and learning system has been established to provide reporting on expenditure and outcomes achieved across the FCDO and delivery of tailored evaluations to determine of the quality and effectiveness of the Programmes.  These evaluations will be used to inform the FCDO about whether the operation of the Programme is meeting the required objectives (the "MREL System").
7.2The Service Delivery Partner shall:
- in a timely manner, fully co-operate and engage constructively with the MREL team to ensure the success of the MREL System.  Such co-operation and engagement shall include:
- complying with data quality assurance
- engaging with MREL team to identify the reporting and management information; and
- engaging with the MREL team during evaluations to ensure that it is conducted in a timely and effective manner in accordance with the evaluation methodology and plan;
- provide the reporting and management information to the MREL team in an agreed format and at an agreed frequency;
- provide any other information or reports required by the FCDO;
- provide data in accordance with GDPR.
- The Service Delivery Partner shall ensure that all Sub-Contractors comply with the obligations set out in Clause II.  The Service Delivery Partner shall aggregate all information provided by Sub-Contractors into the information provided by the Service Delivery Partner to provide a consolidated view across the supply chain.
- The Service Delivery Partner agrees that all information provided by the Service Delivery Partner (or any Sub-contractor) in accordance with Clause III and any evaluations generated by the FCDO as a result of that information shall not be deemed to be confidential information of the Service Delivery Partner.
CAPABILITIES AND OTHER INFORMATION
- The successful tenderer should be in a position to commence the implementation by 1st November 2023 and commit to front-loading project activity to ensure a 100% spend of budget by March 2024.
- Working independently: Whilst it is expected that the Contractor checks-in with the FCDO at identified key milestones and that visits and meetings may offer the opportunity for representatives FCDO to join the Contractor if appropriate;
- Tenderers should have a clear understanding of India and International including UK in the requested field, and have good contacts with government agencies, research institutions and business.
- At least 10 years of experience in working with the Government of India and/or financial sector regulators
- Experience of working in the pensions sector primarily in India, the UK and other emerging economies.
- Experience of working with Financial sector regulators in implementing reforms bases international best practices
- Consultancy engagements in the Pensions sector in India and the UK. Any experience of delivering Pensions projects with the Government of India and/or the PFRDA will be desirable.
- Experience of consultancy projects with financial sector regulators as beneficiaries.
- Tenderers must submit a fully-costed proposal with specific timelines.
CONTRACT MANAGEMENT
The service provider would need to follow the British High Commission – New Delhi requirement on invoicing and reporting, and provide information requested by the British High Commission – New Delhi for management and monitoring purposes.
CONFLICT OF INTEREST
- All bidders should demonstrate their ability to avoid conflict of interest between engagements by setting up ethical walls e.g. how they track personnel and the engagements they have worked on.
- In the event that the FCDO judges that these ethical walls are not sufficient, bidders may still be awarded the contract but on condition that they will be precluded from taking part in any competition for subsequent stages of any programme that they have been involved in through this contract.
- Please note that the final outcome of this scoping project and relevant information developed by the successful provider will be expected to be released to prospective bidders as part of the tender process for wider FCDO programmes.
BUDGET
- This is an ODA funded programme. The budget available for the service is in the range of £ 100,000 to £110,000 inclusive of all applicable taxes. The service provider should provide quotation for each component separately. Value for Money will be one of the key evaluation criteria.
- The service provider will propose the overall budget for this work which must be inclusive of all applicable taxes (detailed separately), overheads and travel costs for any field visits. Bidders are expected to show value for money.
- In line with FCDO’s policy, all journeys by rail or air will be budgeted by a class of travel that is no more than “standard economy” unless higher travel classes are representative of improved value for money or are required to adhere to specific legislation, for example the Equality Act 2010. Your FCDO representative will confirm if this is appropriate and no travel should be booked in a class higher than “standard economy” without express written permission. First class travel will not be permitted under any circumstances. Alcohol and tobacco are not allowable subsistence items. Travel and living expenses will be paid at a rate consistent with the HMRC’s schedule of rates.
- Actual expenses (Travel and accommodation of international speakers needs to be budgeted) that may occur for the delivery of the stakeholder engagement workshop, will be reimbursed based on actual expense. Service Delivery Partner should include the indicative costs of such expenses in the bid.
POINT OF DELIVERY
The project is to be delivered in Delhi and Mumbai.

PAYMENT SCHEDULE
Deliverable	Payment
Inception plan and methodology	10%
Policy Paper 1	20%
Policy Paper 2	20%
Conference	25%
End of Programme Report	25%

Annex A - Draft Results Framework for the Project / Programme
Purpose / Objective of the Project / Programme:
Outcome:
Outcome level Indicator(s)		Baseline	Target	Progress against the indicator		Data / information source (means of verification)

Intermediate Outcome level Indicator(s)		Baseline	Target (by project end)	Progress against the indicator (to be updated at the end of project)		Data / information source (means of verification)

Output 1:
Activities linked to Output 1	Output level Indicator(s)	Baseline	Target (by project end)	Milestones		Data / Information source (means of verification)
				1st Month – 3rd Month	4th Month – 6th Month

				<achieved>	<achieved>

				<achieved>	<achieved>

				<achieved>	<achieved>

				<achieved>	<achieved>

				<achieved>	<achieved>

Output 2:
Activities linked to Output 2	Output level Indicator(s)	Baseline	Target (by project end)	Milestones		Data / Information source (means of verification)
				1st Month – 3rd Month	4th Month – 6th Month