## About this tool
Tool Version 0.1
Capacity Analysis Tool for Housing and Regeneration
Purpose
This is a self-evaluation tool designed to help identify the skills and capacity within housing and regneration by undertaking a preliminary assessment of its current capability, and steps that can be taken to improve performance.
Note: This is for internal use and does not form part of any funding regime. Completion is not linked to any funding opportunities.
Benefits
Completing the Capacity Analysis Tool can offer several benefits:
Informed Decision-Making: Provides valuable insights into your organisation’s strength and weaknesses.
Resource Optimisation: Helps identify gaps and enables you to allocate resource more effectively.
Risk Mitigation: Enables users to anticipate potential challenges and enhance the likelihood of successful project delivery.
Enhanced Planning: Helps in setting realistic project timelines, milestones, and goal.
Accountability: Promotes accountability across organisation and encourages teams to takes ownership or their role in delivery.
Effective Communication: Can facilitate better communication across organisation, enabling teams to align their efforts and work cohesively towards project success.
Structure
The tool evaluates organisational capacity and capability for delivery aligned to the following two lenses:
Corporate: To identify and understand corporate maturity in terms of capability and capacity to support programme delivery.
Project: Understanding property-led opportunities and projects, and potential to achieve transformative regeneration.
Time
The expected time to complete this tool is 30 minutes.
How to use this tool:
If you are completing the tool as a team or group of people, you can save it to a shared drive and share a link to the tool with other participants
Multiple users can access this tool and populate it at the same time.
If you need to zoom in or out, use the slider in the bottom corner of the window.
1. Populate the green User Tabs, one tab per person or team
To complete the Input tab, follow the instructions at the top. If there are more than ten individuals, group together based on function or similar responsibilities and complete one tab as a team.
2. Review the Results
Once the input tabs have been completed:
A graph and tables are generated on the Results tab 1) Collective (Corporate and Project Lens) 2) Corporate Lens 3) Project Lens
3. Interpret your results
The "Interpreting your results" tab explains how to analyse your results effectively.
It sets out what a radar chart is, why you would use one, what to look for and how to use this important management information to best effect.
4. Guidance
On the "Tailored Guidance" tab a bespoke table is populated setting out the average user score for each theme.
On that same tab, relevant tangible actions are identified and online resources to help improve delivery readiness are signposted.
5. Save a copy of your completed spreadsheet
This is essential if you wish to compare scores over time using the Re-Analysis tab.
6. Compare your previous score via the Re-analysis Input tab
This tab enables users to track organisational improvement by comparing previous and latest outputs of this tool
Compare scores, by populating (copy and paste) the previous score column. The current score will automatically pull through.
Please note, you will have to have access to the saved version of your previous scores in order to populate this tab.

## User 1
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Step 1: You can insert your name in the box where indicated if you wish and by double clicking the tab name, otherwise, you can leave this blank.
Step 2: In "Theme" box select the first Theme from the drop-down list.
Step 3: Four levels of behaviours will appear in the box beneath, identify which of the four most accurately represents your organisation.
If you are between levels, select the lower level. If you are unsure select "Unknown"
Step 4: Enter the level number into the table using the drop down box.
Step 5: Use the dropdown box to work your way through each of the themes until you have a score for each one.
Step 6: Move to the Results tab
Name (optional):
Theme: | 1. Strategy & Vision
Levels: | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation.
1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Acountability | 4. Governance | 5. Project & Programme Management | 6. Performance Management | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development & Delivery Track Record | 17. Development through Partnerships | 18. Regeneration & Delivery & Track Record

## User 2
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Step 1: You can insert your name in the box where indicated if you wish and by double clicking the tab name, otherwise, you can leave this blank.
Step 2: In "Theme" box select the first Theme from the drop-down list.
Step 3: Four levels of behaviours will appear in the box beneath, identify which of the four most accurately represents your organisation.
If you are between levels, select the lower level. If you are unsure select "Unknown"
Step 4: Enter the level number into the table using the drop down box.
Step 5: Use the dropdown box to work your way through each of the themes until you have a score for each one.
Step 6: Move to the Results tab
Name (optional):
Theme: | 1. Strategy & Vision
Levels: | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation.
1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Acountability | 4. Governance | 5. Project & Programme Management | 6. Performance Management | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development & Delivery Track Record | 17. Development through Partnerships | 18. Regeneration & Delivery & Track Record

## User 3
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Step 1: You can insert your name in the box where indicated if you wish and by double clicking the tab name, otherwise, you can leave this blank.
Step 2: In "Theme" box select the first Theme from the drop-down list.
Step 3: Four levels of behaviours will appear in the box beneath, identify which of the four most accurately represents your organisation.
If you are between levels, select the lower level. If you are unsure select "Unknown"
Step 4: Enter the level number into the table using the drop down box.
Step 5: Use the dropdown box to work your way through each of the themes until you have a score for each one.
Step 6: Move to the Results tab
Name (optional):
Theme: | 1. Strategy & Vision
Levels: | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation.
1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Acountability | 4. Governance | 5. Project & Programme Management | 6. Performance Management | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development & Delivery Track Record | 17. Development through Partnerships | 18. Regeneration & Delivery & Track Record

## User 4
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Step 1: You can insert your name in the box where indicated if you wish and by double clicking the tab name, otherwise, you can leave this blank.
Step 2: In "Theme" box select the first Theme from the drop-down list.
Step 3: Four levels of behaviours will appear in the box beneath, identify which of the four most accurately represents your organisation.
If you are between levels, select the lower level. If you are unsure select "Unknown"
Step 4: Enter the level number into the table using the drop down box.
Step 5: Use the dropdown box to work your way through each of the themes until you have a score for each one.
Step 6: Move to the Results tab
Name (optional):
Theme: | 1. Strategy & Vision
Levels: | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation.
1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Acountability | 4. Governance | 5. Project & Programme Management | 6. Performance Management | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development & Delivery Track Record | 17. Development through Partnerships | 18. Regeneration & Delivery & Track Record

## User 5
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Step 1: You can insert your name in the box where indicated if you wish and by double clicking the tab name, otherwise, you can leave this blank.
Step 2: In "Theme" box select the first Theme from the drop-down list.
Step 3: Four levels of behaviours will appear in the box beneath, identify which of the four most accurately represents your organisation.
If you are between levels, select the lower level. If you are unsure select "Unknown"
Step 4: Enter the level number into the table using the drop down box.
Step 5: Use the dropdown box to work your way through each of the themes until you have a score for each one.
Step 6: Move to the Results tab
Name (optional):
Theme: | 1. Strategy & Vision
Levels: | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation.
1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Acountability | 4. Governance | 5. Project & Programme Management | 6. Performance Management | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development & Delivery Track Record | 17. Development through Partnerships | 18. Regeneration & Delivery & Track Record

## User 6
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Step 1: You can insert your name in the box where indicated if you wish and by double clicking the tab name, otherwise, you can leave this blank.
Step 2: In "Theme" box select the first Theme from the drop-down list.
Step 3: Four levels of behaviours will appear in the box beneath, identify which of the four most accurately represents your organisation.
If you are between levels, select the lower level. If you are unsure select "Unknown"
Step 4: Enter the level number into the table using the drop down box.
Step 5: Use the dropdown box to work your way through each of the themes until you have a score for each one.
Step 6: Move to the Results tab
Name (optional):
Theme: | 1. Strategy & Vision
Levels: | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation.
1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Acountability | 4. Governance | 5. Project & Programme Management | 6. Performance Management | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development & Delivery Track Record | 17. Development through Partnerships | 18. Regeneration & Delivery & Track Record

## User 7
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Step 1: You can insert your name in the box where indicated if you wish and by double clicking the tab name, otherwise, you can leave this blank.
Step 2: In "Theme" box select the first Theme from the drop-down list.
Step 3: Four levels of behaviours will appear in the box beneath, identify which of the four most accurately represents your organisation.
If you are between levels, select the lower level. If you are unsure select "Unknown"
Step 4: Enter the level number into the table using the drop down box.
Step 5: Use the dropdown box to work your way through each of the themes until you have a score for each one.
Step 6: Move to the Results tab
Name (optional):
Theme: | 1. Strategy & Vision
Levels: | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation.
1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Acountability | 4. Governance | 5. Project & Programme Management | 6. Performance Management | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development & Delivery Track Record | 17. Development through Partnerships | 18. Regeneration & Delivery & Track Record

## User 8
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Step 1: You can insert your name in the box where indicated if you wish and by double clicking the tab name, otherwise, you can leave this blank.
Step 2: In "Theme" box select the first Theme from the drop-down list.
Step 3: Four levels of behaviours will appear in the box beneath, identify which of the four most accurately represents your organisation.
If you are between levels, select the lower level. If you are unsure select "Unknown"
Step 4: Enter the level number into the table using the drop down box.
Step 5: Use the dropdown box to work your way through each of the themes until you have a score for each one.
Step 6: Move to the Results tab
Name (optional):
Theme: | 1. Strategy & Vision
Levels: | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation.
1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Acountability | 4. Governance | 5. Project & Programme Management | 6. Performance Management | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development & Delivery Track Record | 17. Development through Partnerships | 18. Regeneration & Delivery & Track Record

## User 9
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Step 1: You can insert your name in the box where indicated if you wish and by double clicking the tab name, otherwise, you can leave this blank.
Step 2: In "Theme" box select the first Theme from the drop-down list.
Step 3: Four levels of behaviours will appear in the box beneath, identify which of the four most accurately represents your organisation.
If you are between levels, select the lower level. If you are unsure select "Unknown"
Step 4: Enter the level number into the table using the drop down box.
Step 5: Use the dropdown box to work your way through each of the themes until you have a score for each one.
Step 6: Move to the Results tab
Name (optional):
Theme: | 1. Strategy & Vision
Levels: | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation.
1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Acountability | 4. Governance | 5. Project & Programme Management | 6. Performance Management | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development & Delivery Track Record | 17. Development through Partnerships | 18. Regeneration & Delivery & Track Record

## User 10
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Step 1: You can insert your name in the box where indicated if you wish and by double clicking the tab name, otherwise, you can leave this blank.
Step 2: In "Theme" box select the first Theme from the drop-down list.
Step 3: Four levels of behaviours will appear in the box beneath, identify which of the four most accurately represents your organisation.
If you are between levels, select the lower level. If you are unsure select "Unknown"
Step 4: Enter the level number into the table using the drop down box.
Step 5: Use the dropdown box to work your way through each of the themes until you have a score for each one.
Step 6: Move to the Results tab
Name (optional):
Theme: | 1. Strategy & Vision
Levels: | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation.
1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Acountability | 4. Governance | 5. Project & Programme Management | 6. Performance Management | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development & Delivery Track Record | 17. Development through Partnerships | 18. Regeneration & Delivery & Track Record

## Composite Table (hidden)
| 1. Strategy & Vision | 2. Organisation & Leadership | 3. Culture of Trust & Accountability | 4. Governance | 5. Project and Programme Management | 6. Performance Measurement | 7. Quality Management | 8. Risk and Issues Management | 9. Stakeholder Communications | 10. Finance | 11. Legal | 12. Procurement | 13. Town & Country Planning | 14. Sustainability & Net Zero Carbon | 15. Site Readiness & Pipeline | 16. Housing Development and Delivery Track Record | 17. Development through Partnerships | 18. Regeneration and Delivery and Track Record
User 1
User 2
User 3
User 4
User 5
User 6
User 7
User 8
User 9
User 10
High | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Low | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Average

## Results
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Please ensure you have read the first tab 'about this tool' before progressing.
Step 1: Your average (mean) score will automatically populate based on your inputs. Please ensure you have completed all the inputs or the graph will return error messages.
Step 2: You can view your score via the table on the "Tailored Guidance" tab.
Step 3: Review the Radar Chart below which compares the average score from all responses and sets them against the highest and lowest score. The bottom two tables set out everyone's specific responses.
Step 4: Move on to "Interpreting your results" Tab to understand how to use the graphs to best effect.
[6 empty] | Theme |  |  |  |  | High | Low | Average | Gap
[6 empty] | 1. Strategy & Vision |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 2. Organisation & Leadership |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 3. Culture of Trust & Accountability |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 4. Governance |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 5. Project and Programme Management |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 6. Performance Measurement |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 7. Quality Management |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 8. Risk and Issues Management |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 9. Stakeholder Communications |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 10. Finance |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 11. Legal |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 12. Procurement |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 13. Town & Country Planning |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 14. Sustainability & Net Zero Carbon |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 15. Site Readiness & Pipeline |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 16. Housing Development and Delivery Track Record |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 17. Development through Partnerships |  |  |  |  | 0 | 0 |  | 0
[6 empty] | 18. Regeneration and Delivery and Track Record |  |  |  |  | 0 | 0 |  | 0
| User 1 | User 2 | User 3 | User 4 | User 5 | User 6 | User 7 | User 8 | User 9 | User 10
Corporate lens
1. Strategy & Vision | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Organisation & Leadership | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Culture of Trust & Accountability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4. Governance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5. Project and Programme Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6. Performance Measurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7. Quality Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8. Risk and Issues Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9. Stakeholder Communications | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10. Finance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11. Legal | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12. Procurement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13. Town & Country Planning | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14. Sustainability & Net Zero Carbon | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project Lens
15. Site Readiness & Pipeline | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16. Housing Development and Delivery Track Record | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17. Development through Partnerships | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18. Regeneration and Delivery and Track Record | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Interpreting your results
Capacity Analysis Tool for Housing and Regeneration
Please ensure you have read the first tab 'about this tool' before progressing.
What is a Radar Chart?
A Radar chart allows you to compare data, in this case, you can see the highest scores, lowest scores and average scores on one chart.
Scores on each theme are automatically plotted around the chart, starting from the middle.
The scores for the themes for each person's responses are connected to form a “radar image” or “spider web” pattern.
When to Use the Radar Chart?
Decision-making: It can help direct management decisions as the chart depicts the range of responses in one place.
Re-analysis: By comparing historic charts, this can help you understand progress and improvement in an any given theme over time.
Worked Example
This chart below has been created using some mock data. It represents 5 people's responses. On the "Results" tab there is also a handy table giving the exact high, low and average score for each theme.
So what does this tell us?
1. We can tell at a glance that the responses by all 5 people are complete as there are no zero scores.
2. The scores closest to the centre are lower. Any Theme which is scored as a one indicates an area of little resource, capability or capacity (or a combination of all 3)
The highest scores are shown in green and the lowest are in red. The grey/blue shows the average score.
In this case there are low scores recorded in Governance, Stakeholder Communications, Finance, Legal, Housing Development and Delivery Track Record and Development through Partnerships.
There will be some guidance on first steps to make set out in the Top Tips on the "Tailored Guidance" tab.
3. You can see on the chart where there are large differences between the highest and lowest scores against each theme.
In this case the six themes with the lowest scores have a difference of more than 2 levels against the highest score.
These are very important early indicators of potential issues that should be looked into.
Take Legal, as an example - one person has given a 4, whilst at least one of the other four responses is a 1.
There are 4 main conclusions that can be drawn from this:
a) Potentially someone in the legal team has scored themselves highly, with perhaps an overly optimistic sense of capacity or capability
As there is also a single low score, there could also be an inter-personnel issue
b) that there is a barrier in the process of delivery
c) the legal team are working in silo to the project or programme
d) there is a gap in legal resource capacity or capability
There is a table on the "results" tab allow for a more detailed look at each persons response at more granular level.
This assists in identifying who might be needed to join a conversation in order to draw out the issues at hand.
It is important to recognise that there is no right or wrong score when using this tool.
The different levels are only a visual indication about your organisations readiness to deliver regeneration and development.
What do we do now?
1. If those completing the tool are comfortable, a private conversation could take place to understand the reason for an outlying high or low score.
2. If the scores for a theme are broadly aligned, review the tangible actions and top tips set out in the Dashboard tab.
3. Where there is an identified barrier to progress:
a) Improve the communication of the project or programmes vision and objectives
b) Encourage collaboration between teams
c) Create a multi-skilled cross department team
d) Use collaborative tools and a shared cloud-based electronic filing system
e) Provide training as required

## Tailored Guidance
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Please ensure you have read the first tab 'about this tool' before progressing.
Step 1: The average (mean) score of your organisation will automatically populate based on your inputs.
Step 2: You can view the average scores in the below table and on the Results tab. In addition below is a tailored list of tangible actions and top tips to support you to improve. Some high-level links are also provided from the Housing Information Hub.
Step 3: Save the completed tool so that the results can be compared whenever the tool is revisted in the future.
| Theme | Average Score | Tangible actions and Top Tips | Housing Information Hub - General Resources
Corporate Lens | 1. Strategy & Vision |  |  | https://www.gov.uk/government/collections/leading-homebuilding-and-regeneration#programme-and-project-management
| 2. Organisation & Leadership |  |  | https://www.gov.uk/government/collections/leading-homebuilding-and-regeneration#programme-and-project-management
| 3. Culture of Trust & Accountability |  |  | https://www.gov.uk/government/collections/leading-homebuilding-and-regeneration#governance
| 4. Governance |  |  | https://www.gov.uk/government/collections/leading-homebuilding-and-regeneration#governance
| 5. Project and Programme Management |  |  | https://www.gov.uk/government/collections/leading-homebuilding-and-regeneration#programme-and-project-management
| 6. Performance Measurement |  |  | https://www.gov.uk/government/collections/leading-homebuilding-and-regeneration#governance
| 7. Quality Management |  |  | https://www.gov.uk/government/collections/leading-homebuilding-and-regeneration
| 8. Risk and Issues Management |  |  | The risk management section of the hub should prove useful: https://www.gov.uk/government/collections/leading-homebuilding-and-regeneration#risk-management
| 9. Stakeholder Communications |  |  | https://www.gov.uk/government/collections/leading-homebuilding-and-regeneration#community-engagement
| 10. Finance |  |  | https://www.gov.uk/government/collections/financing-homebuilding-and-regeneration
| 11. Legal |  |  | https://www.gov.uk/government/collections/using-land-for-homebuilding-and-regeneration#due-diligence
| 12. Procurement |  |  | The procurement section of the Hub will prove helpful: https://www.gov.uk/government/collections/financing-homebuilding-and-regeneration#procurement
| 13. Town & Country Planning |  |  | The planning section of the Hub will be useful: https://www.gov.uk/government/collections/planning-for-homebuilding-and-regeneration
| 14. Sustainability & Net Zero Carbon |  |  | See the Environment and Sustainability section of the Hub: https://www.gov.uk/government/collections/planning-for-homebuilding-and-regeneration#environment-and-sustainability
Project Lens | 15. Site Readiness & Pipeline |  |  | https://www.gov.uk/government/collections/using-land-for-homebuilding-and-regeneration
| 16. Housing Development and Delivery Track Record |  |  | https://www.gov.uk/government/collections/using-land-for-homebuilding-and-regeneration
| 17. Development through Partnerships |  |  | https://www.gov.uk/government/collections/using-land-for-homebuilding-and-regeneration#partnership-working
| 18. Regeneration and Delivery and Track Record |  |  | The Masterplanniing and Estate Regeneration sections of the Hub will be helpful: https://www.gov.uk/government/collections/planning-for-homebuilding-and-regeneration

## Top Tips (hidden)
Themes | 1 | 2 | 3 | 4
1. Strategy & Vision | - Review the outputs of the Housing or Regeneration Strategy - Ensure a Project Initiation Document (PID) is in place to outline the Project in detail - Utilise a cloud based central file sharing software | - Review documentation to Ensure that the Housing or Regeneration Strategy is explicit about intended outcomes - Ensure a Project Initiation Document (PID) is in place to outline the Project in detail - Ensure the PID is a live dynamic working Document with an owner - Check that all component parts of the PID are fully set out - Utilise a cloud based central file sharing software | - Revisit the outcomes of the Housing or Regeneration Strategy to Ensure your Project or programme's alignment. - Ensure the PID is freely accessible for viewing by the Project/programme team. - Ensure that all component parts of the PID are fully set out, approved and updated. - Consider implementing a file naming protocol and rigorous filing structure. | - Review the Housing and Regeneration strategy documents to ensure they remain current and set up a regular review pattern. - Review each PID to ensure the outputs remain in alignment with the project brief. | 3
2. Organisation & Leadership | - Request that senior managers cease to resolve problems themselves. - Focus on culture of organisation and start to break down silos. - Set out in writing key processes and procedures. - Set out at high-level how programmes and projects are to be managed in your organisation. - Create energy around cross-functional teamwork. - Simple praise and encouragement for all. | - Encourage leaders to focus on role of raising performance of team. - Encourage senior managers to cease resolving problems themselves and look instead to unblock issues for others. - Break down silos by modelling teamwork and delivering cross functional workshops or team building. - Set out in writing key processes and procedures with agreed review pattern. - Roll out workshops to explain how programmes and project/programmes are to be managed. - Create energy around cross-functional teamwork. - Simple praise and encouragement for all. | - Ensure that leaders to focus on raising performance of team. - Explain to senior managers how they can help by focussing on unblocking issues and breaking down barriers to progress. - Continue delivering cross functional workshops with an emphasis on team building. - Review key processes and procedures, keep them current. - Author a corporate guide to how programmes and project/programmes are to be managed. - Praise and apply for awards for the team delivering new homes and/or regeneration. | - Seek out and upskill promising talent and sponsor through suitable training courses. - Ensure senior managers continue to unblock issues and remove unnecessary bureaucracy. - Ensure the Senior Responsible Officer (SRO) and other senior managers attend workshops to continue to drive enthusiasm and raise profile of projects and programmes. - Revisit processes and procedures with a view to implementing further policies and reducing unnecessary bureaucracy. - Author a corporate guide to how programmes and project/programmes are to be managed. - Praise and apply for awards for the team delivering new homes and/or regeneration. | 4
3. Culture of Trust & Accountability | - Identify team and individual objectives which are tied directly to programme/project plans. - Live the cultural values and display model behaviours (agree not to multi-task during meetings). - Attend regular team meetings to demonstrate commitment. - Celebrate success. | - Identify team and individual objectives which are tied directly to programme/project plans. - Live the cultural values and display model behaviours. - Ensure regular team sessions/standup meetings take place to build sense of commitment. - Celebrate success and ensure learning built into all assessments. | - Ensure team and individual objectives are tied directly to programme/project plans. - Live the cultural values and display model behaviours. - Ensure regular team sessions/standup meetings take place. Encourage people to speak out freely and to identify barriers to progress. - Continue to celebrate success and ensure learning built into all assessments. - Apply for external validation via accreditations and awards. | - Reward those Teams and individuals who deliver on their objectives as part of the programme/project plans. - Continue to underpin cultural values and display model behaviours. - Attend all regular team sessions/standup meetings or send a representative. Develop a safe space to encourage people to speak out freely and to identify barriers to progress. - Publicise and acknowledge successes, recognise teams and individuals. - Promote external validation via accreditations and awards. | 4
4. Governance | - Establish a governance structure and establish who has delegated authority. - Make sure a PID is in place and used to guide the programme. - Publicise a Programme Plan with milestones and gateways. - Agree who will create an auditable actions list following each meeting and share that list across the team. - Research other projects or programmes in your organisation and seek to find any lessons learned. | - Establish a governance structure with clear lines of accountability and delegations at all levels of the project/programme. - Make sure a PID is in place and used to guide the programme. - Publicise a Programme Plan with milestones and gateways. - Ensure meetings, decisions and actions are minuted and shared across the team. - Evidence improvement through learning from other projects or programmes in your organisation. | - Ensure those accountable are performing and delegations remain appropriate. - Check that the PID is current and up to date. - Observe the adherence to milestones and gateways, follow the variation process. - Ensure meetings, decisions and actions are minuted and shared promptly across the team. - Evidence continued improvement through learning from difficult decisions. | - Review and refine governance structure to ensure it is appropriately resourced and "lean". - Seek to understand where and why a project/programme has failed to meet planned milestones, and share lessons learned. - Ensure all outstanding actions are reviewed at the start of each meeting, prevent continual rolling on of incomplete tasks. - Be prepared to make difficult decisions and to share the experience to avoid a repeat in the future. | 3
5. Project and Programme Management | - Use an agreed project management methodology. - Collate and review all relevant key processes. - Establish who are experienced and/or qualified Project Managers. - Implement a Programme or Project Management Office (PMO). - Set some programme/project targets for each person in the team. - Identify and implement appropriate governance structure. | - Use an agreed project management methodology. - Document, agree and regularly review all key processes. - Develop a cohort of skilled Project Managers. - Implement a Programme or Project Management Office (PMO). - Develop project/programme-based scorecards. - Identify and commit to appropriate governance structure with agreed terms of reference. | - Continue to use the agreed project management methodology. - Regularly review all key processes. Identify any obvious process gaps and seek to have new documents prepared and agreed. - Develop a cohort of skilled Project Managers. - Review the suitability and resource within the Programme or Project Management Office (PMO). - Review project/programme-based scorecards. - Review the governance structure and terms of reference. | - Roll out an agreed project management methodology across all projects and programmes in your organisation. - Critique adherence to all key processes and seek to understand and reduce deviations. - Seek out and upskill promising talent and sponsor through suitable Project Management courses. - Review the suitability and resource within the Programme or Project Management Office (PMO). - Consider supporting actions to help ensure objectives and scorecards are met. - Support the agreed governance structure and delegate decisions as much as possible. | 4
6. Performance Measurement | - Identify (or create if not existing) a system and process for collecting financial data. - Identify and agree which performance data to report upon. - Agree a template reporting format. - Agree clear reporting periods and review times. - Agree and use a standard agenda in project/programme meetings. - Ensure clear lines of delegated authority are in place. | - Review both systems and processes for collecting financial and other data and amend as necessary. - Identify a suite of performance data to drive the project/programme. - Regularly use an agreed template reporting format. - Ensure that data is robust and timely and agree clear reporting periods and review times. - Structure project/programme meetings to review data and drive decisions. - Ensure clear lines of delegated authority are in place, allied with appropriate change control measures. | - Review and refine both systems and processes for collecting financial and other data. - Identify a suite of performance data to drive the project/programme and ensure all understand the purpose and importance. - Ensure use of template reports as standard. - Ensure that data is robust and timely and agree clear reporting periods and review times. - Ensure meetings are purposeful that review data and drive decisions. - Ensure change control measures are being adhered to. - Investigate systems that provide real time data and consider a business case for investment. | - Review systems and processes with a view to making them less bureaucratic and streamlined. - Review the appropriateness and relevance of performance data, seek to minimise unnecessary data gathering. - Roll out template reporting forms across the organisation, to become standard for all projects and programmes. - Ensure that data is robust and timely and agree clear reporting periods and review times. - Strive for consistent, fact-based decision making. - Review the continued relevancy of delegated authorities and that appropriate lessons learned from projects are shared widely. - Consider investment in systems that provide real time data. | 4
7. Quality Management | - Seek to identify and collate standard specifications for your organisation. - Set out and agree basic quality standards and how they will be monitored. - Review the quality standard measures in Project/programme team meetings. | - Seek to agree a set of Employers Requirements (ER's) approved in advance of project/programme start. - Establish that the ER's reflect on lessons learned. - Develop quality standards and prepare quality review documentation. - Review the progress of a project against the quality standard measures in Project/programme meetings. | - Agree a set of Employers Requirements (ER's) approved in advance of project/programme start. - Establish that the ER's reflect on time/cost/quality impacts of decisions as well as feedback from end users. - Review completed quality review documentation and investigate variances. - Review all quality indicators and incorporate into Project/programme team meetings (and update ER's as necessary). | - Review the continued relevancy of the Employers Requirements (ER's) including the adoption of changes based on lessons learned. - Review the Design Authority's handling of the ER control measures and its process of making adaptations based on lessons learned. - Review the continued relevancy of the agreed quality standards and make changes if necessary. - Revisit the relevancy and impact of agreed quality indicators as overly ambitious targets often lead to breaking of budget envelopes. | 4
8. Risk and Issues Management | - Identify who has delegated authority for your project/programme. - Create a risk register, have all members of the team contribute. - Utilise a risk register/ risk management spreadsheet from the start. - Identify and evaluate all potential risks, agree action plan, and take actions. | - Establish that delegated authority for decisions is in place. - Embed risk management in governance process, all identified risks have a risk owner. - Utilise risk management tools from start of project/programme, review the risks with regularity. - Identify and evaluate all potential risks, agree action plan, and take actions. | - Ensure that the appropriate delegated authority continues to make fact-based decisions. - Ensure that all risk owners have a suitable mitigation process in place, for each of their assigned risks. - Utilise an industry standard risk management tool. - Review RAID (risks, actions, issues, decisions) log regularly at Project/Programme Boards. | - Revisit the delegated authority process and financial delegations, to ensure they continue to be practical and appropriate. - Review the reasoning behind any major issues that arise which had not previously been identified as a risk. Feed back into lessons learned process. - Consider investment in an electronic risk management tool applicable across the organisation. - Review RAID (risks, actions, issues, decisions) log regularly at Project/Programme Boards. | 4
9. Stakeholder Communications | - Identify and understand how to deal with each of your stakeholders as early as possible. - Develop a Communications Plan and agree within project/programme team. - Regularly review stakeholder feedback. - Bring politicians and especially local ward councillors into proactive 2-way communications. | - Stakeholder mapping is often best achieved with all team members contributing. Stakeholders are both internal and external to your organisation. - Develop multi-media Communications Plan and agree within project/programme team. - Regularly review stakeholder feedback at team meetings. - Bring politicians and especially local ward councillors into proactive 2-way communications. | - Consider the current levels of engagement of each stakeholder and ensure that they all become supportive towards the project. - Consider if some projects or programmes may benefit from external expertise in resident, stakeholder, and general public communications. - Regularly review stakeholder feedback/interventions at team meetings and respond. - Bring local politicians into a regular cadence of bespoke briefings and communications. | - Critique the identified stakeholders. Politicians and senior staff will need managing appropriately. - Ensure there is suitable stakeholder management resource built integrally to the project/programme team, as managing those stakeholders is a critical step. - Carefully consider genuine negative feedback, recalcitrant stakeholders should be managed appropriately. - Pro-actively engage, update, and inform politicians and senior organisation staff of progress. | 4
10. Finance | - Identify a finance team member to be part of the project/programme team. - Agree which financial performance data to report. - Agree variation process. - Agree the required information for each gateway review. | - Identify a finance team member to be part of the project/programme team. - Ensure appropriate team members are competent in business planning. - Embed financial performance data in project and programme meetings. - Agree variation process. - Agree the required information for each gateway review. | - Identify finance team members and allocate project/programme team objectives to them. - Ensure appropriate team members are competent in business planning. - Monitor financial performance data in project and programme meetings. - Embed the agreed variation process as standard. - Ensure stage gate reviews reconsider business case. - Provide support and training to upskill non-financial staff. | - Identify finance team members and allocate project/programme team objectives to them. - Consider supporting actions to improve business planning across the organisation. - Roll out the variation process across the organisation. - Make tough decisions if a project or programme's business case is no longer viable. - Provide support and training to upskill non-financial staff. | 3
11. Legal | - Identify someone in Legal to support the project or programme. - Ensure accuracy of project/programme constraints by commissioning a title report. - Seek external legal support If legal team lack capacity. | - Identify legal team members and allocate project/programme team objectives to them. - Ensure accuracy of project/programme constraints by commissioning a title report. - If legal team lack capacity, procure external support in advance to undertake work at pressure points. | - Identify legal team members and allocate project/programme team objectives to them. - Feed the identified project constraints and ownership information through to the design team. - Arrange that external Legal advisers are procured on call off contracts or similar, for swift deployment. | - Ensure that the Legal team pro-actively support project goals. - Consider a case to support a project to have all organisationally owned property registered at the Land Registry. - Review the capacity of the Legal team and consider business case to increase the size of the team if appropriate. | 3
12. Procurement | - Ensure clarity on pre-agreed frameworks setting out each vendor and pricing. - Look to expand approved supplier list. - Agree a robust change control process. | - Ensure clarity on pre-agreed frameworks setting out each vendor and pricing. - Agree absolute caps or acceptable mitigation within contracts as labour and material costs can be volatile. - Diversify and expand approved supplier lists to reduce risk and increase bargaining power. - Instil a robust change control process across the whole programme/project. | - Agree absolute caps or acceptable mitigation within contracts as labour and material costs can be volatile. - Diversify and expand approved supplier lists to reduce risk and increase bargaining power. - Tighten change control decisions and ensure swift approval where necessary. | - Regularly review mechanisms for protecting project viability from price fluctuations. - Make tough decisions if a project or programme ceases to be viable. | 2
13. Town & Country Planning | - Identify someone in Planning to support the project or programme. - Discuss the process for installing a Design Review Panel. - Encourage sharing and discussion of creative ideas to resolve challenges. - A programme of projects will need an independent Planning Officer to process its own applications. To protect against a conflict of interest, processes must be in place to prevent sharing of confidential information. | - Ensure dedicated planning resource within the LPA and allocate project/programme team objectives to them. - Install and develop effective Design Review Panel process. - Encourage sharing and discussion of creative ideas to resolve challenges. - Identify a Planning Officer to act independently to process planning applications made by the Project Team. | - Empower the planning resource to act proactively and creatively to support the project or programmes objectives. - Utilise a Design Review Panel to provide impartial advice on your scheme's design matters. - Share creative ideas as regular part of project/programme workshops. - Ensure that the independent Planning Officer contributes through per-application advice only. | - Consider a case to expand planning resource. - Identify a Planning Officer to act independently to process planning applications made by the Project Team. | 1
14. Sustainability/ Net Zero Carbon | - Review your organisations sustainability aspirations, making allowances in cost considerations. - Embody a sustainability led approach into the Project Brief. - Only use contractors with a proven track record with regards to achieving sustainability targets. | - Review all relevant strategy documents to include sustainability aspirations and understand cost and other implications. - Embody sustainability approach into Project Brief, Employers Requirements and Key Performance Indicators. - Ensure procurement process identifies contractor suitability/track record. - Use customer focused guide on future use of new buildings. | - Review all relevant strategy documents to include sustainability aspirations and understand cost and other implications. - Embody sustainability approach into Project Brief, Employers Requirements and Key Performance Indicators. - Narrow the choice of contractors to those who have demonstrable track record of meeting sustainability targets to budget. - Develop customer focused guide to use of buildings. - Carry out reviews of customer experience and implement lessons learned. | - Revisit the relevancy and impact of sustainability and net zero targets, as overly ambitious targets often lead to breaking of budget envelopes. - Strive to ensure that sustainability sits at the heart of all decision making and strategy decisions. - Link sustainability targets as a core part of a project/programme scorecard. - Ensure that post-occupancy surveys of customer experience take place and implement any lessons learned. | 4
Site Readiness & Pipeline | - Use collective knowledge to identify all potential sites. - Visit all sites, ideally with a colleague. - Review site potential in terms of massing and height. - Share and gain support for proposed list. - Seek advice from colleagues about all potential funding sources. | - Use collective knowledge to identify all potential sites. - Visit sites with cross-departmental, multi-disciplinary team. - Review site potential, allied with any risks or issues, to create a prioritised list. - Share and gain support for pipeline list, especially with politicians and other key stakeholders. - Horizon scan existing and potentially new funding sources. | - Encourage all staff to help identify potential sites. - Embed a cross-departmental, multi-disciplinary team approach to all new sites under consideration. - Review site potential using a weighted matrix or similar tool to create a prioritised list. - Ensure non-progressing sites on the pipeline list are not stymied by their designation for development. Some could be progressed through to planning permission stage. - Continue to horizon scan funding sources. | - Ensure that the prioritised list of sites is kept current and reviewed at least annually, if not actively being progressed. - Have sites ready to go with planning permission, to take advantage of unexpected funding opportunities such as a new grant becoming available or underspend from another project or programme. - Pass any early intelligence about potential new funding sources to the relevant colleagues. | 3
Housing Development and Delivery Track Record | - Start to create a project or programme team with colleagues from relevant departments. - Set up governance tools and structure (where absent). - Identify potential pipeline. - Build outline business case for approval. - Ensure project forms part of the team members personal objectives. | - Develop a team with skilled key representatives from each relevant department. - Utilise appropriate governance tools and structure. - Identify potential pipeline. - Build outline business case for approval. - Ensure project forms part of the team members personal objectives. | - Have an operational development team, skilled, funded and resourced to take projects forward. - Continue to utilise appropriate governance tools and structure. - Maintain and update the potential pipeline. - Build outline business case for approval. - Ensure project forms part of the team members personal objectives. | - Seek out and upskill promising talent from each department. - Revisit governance tools and structure, with a view to ensure relevancy and practicality, and minimising excess bureaucracy. - Continue to keep potential pipeline site list current. | 3
Development through partnerships | - Identify a leader with great inter-personal skills and adaptability. - Research what partners internal blockages are. - Develop a shared clear vision, strategy and action plan. - Seek to agree a Partnering Agreement. - Hold an engagement event for potential partners. | - Identify great personal leadership who is both brave and adept at risk-taking. - Spend time identifying institutional blockages to partnering and put mitigation plans in place. - Develop a shared clear vision, strategy and action plan. - Agree and approve Partnering Agreement that sets out the principles of the partnership. - Facilitate an engagement event for potential partners to meet each other and to create new ideas and opportunities. - Install a mechanism for partners and/or groups of interested town centre stakeholders to meet as a group. | - Identify great personal leadership: brave, risk-taking people able to operate in ambiguous situations while remaining outcome focused. - Utilise mitigation plans to bypass partners organisational blockages. - Continue to maintain and update a shared clear vision, strategy and action plan. - Agree and approve Partnering Agreement that sets out the principles, values, mechanism for resolving conflicts, and expected behaviours to which all partners commit. - Continually engage and network with potential partners, sharing ideas. - Install a mechanism for partners and/or groups of interested town centre stakeholders to meet as a group. | - Utilise mitigation plans to bypass partners organisational blockages. - Maintain the agreed principles, values and behaviours. - Facilitate a regular networking event for existing and potential new partners. | 3
Regeneration Delivery and Track Record | - Identify the Project Champion. - Establish an evaluation methodology for reviewing proposals. - Identify market KPIs to be monitored. - Ensure routine data is collected. - Review concept & Town Centre regeneration strategies, look to align any discord between them and whole town strategy documents. - Seek to receive emerging plans as early as possible. - Focus on a smaller number of priority actions. - Carry out town centre health checks and monitor regularly. | - Ensure the Project Champion is empowered to make effective and coordinated decision making. - Develop critical evaluation and appraisal skills within the regeneration team. - Identify and provide guidance and training on the KPIs to be monitored. - Ensure routine data to be collected is timely and robust. - Review concept & Town Centre regeneration strategies, look for discord between them and whole town strategy documents. - Critique early plans and provide feedback promptly. - Focus on a smaller number of priority actions. - Carry out town centre health checks and monitor regularly for changes in market and sentiment. | - Ensure strong civic leadership and Project Champion to ensure effective and coordinated decision making. - Continue to develop critical evaluation and appraisal skills. - Provide guidance and training on the KPIs to be monitored. - Ensure routine data to be collected is timely, robust and shared with partners and stakeholders. - Ensure complex concept & Town Centre regeneration strategies are integrated and sitting within whole town strategies. - Critique early plans and provide feedback to promising projects on how to strengthen results chains. - Focus on a number of priority actions. | - Continue to support strong civic leaders and the Project Champion, with accurate management information. - Provide support and training to upskill staff in evaluation and appraisal skills. - Continue to collect routine data that is timely, robust and subsequently shared with partners and stakeholders. - Maintain concept & Town Centre regeneration strategies ensuring alignment with all other policies and strategies. | 2

## Re-Analysis Input
Capacity Analysis Tool for Housing and Regeneration
Instructions:
Please ensure you have read the first tab 'about this tool' before progressing.
Step 1: Open your previous version of this tool and copy across the previous average score into the 'previous average score' column below. Your current score will automatically populate.
Step 2: You can view how your organisation has improved via the table and the chart.
Collective Assessment
Corporate Lens | Themes | Previous Average Score | Current Score | Diff +/-
1. Strategy & Vision
2. Organisation & Leadership
3. Culture of Trust & Accountability
4. Governance
5. Project and Programme Management
6. Performance Measurement
7. Quality Management
8. Risk and Issues Management
9. Stakeholder Communications
10. Finance
11. Legal
12. Procurement
13. Town & Country Planning
14. Sustainability & Net Zero Carbon
Project Lens | 15. Site Readiness & Pipeline
16. Housing Development and Delivery Track Record
17. Development through Partnerships
18. Regeneration and Delivery and Track Record

## 5.Corporate Lens Descriptions (hidden)
Version 0.1
| Theme | Organisational Descriptions
CORPORATE LENS | 1. Strategy & Vision | Level 1: - A Housing or Regeneration Strategy does not exist, or if it does, it doesn't provide vision and clarity for the project/programme. Level 2: - Housing or Regeneration Strategy outlines programme objectives but does not feed directly into project/programme documentation. - Project or programme mandate is unclear. Level 3: - The Project Initiation Document flows from the objectives in the Housing or Regeneration Strategy. - Project Mandate, Scope and Brief are all aligned. Level 4: - Direct link between delivery of benefits and strategic objectives measured by post-completion reviews. - Lessons learned incorporated across all project/programmes in the organisation. | 1. Strat & Vision
| 2. Organisation & Leadership | Level 1: - Only a few organisational processes exist, they are rarely referred to and often out of date - Results that are achieved are driven by force of character of a key (or small number of) individuals - No effective delegation to an empowered and engaged team - Little sense of cross departmental working and team commitment. Level 2 - Leaders understand the need to update and embed processes and procedures but this has not been done - Leaders recognise the need for cultural change but may lack the skills or the time to deliver it - Culture of the management team is linked to a healthy organisational culture Level 3: - Leaders are consistently clear and focused on increasing effectiveness through better processes and governance - Leaders establish a state of readiness for the changes that delivering new homes or regeneration will create - Direct reports engaged and committed to the approach and deliver higher quality more efficient outputs - A decrease in unexpected issues arise Level 4 - Leaders facilitate high quality work, focus on unblocking issues and building skills, capacity and capability - Strong focus on delivering the project/programme benefits and consistent and proactive reaction to internal and external threats - Leaders give credit to the people doing the work and to their managers | 2. Org & L'ship
| 3. Culture of Trust & Accountability | Level 1: - No culture of trust established which means team members are unwilling to own decisions or propose creative ideas. - Staff feel undervalued, overworked and not free to make decisions. - Team expect conflict and finger pointing. Level 2: - Some individuals in the team are able and willing to be accountable. - Significant proportion stick to the ways things have always been done. - There is a divide between those who are, and are not, process oriented. Level 3: - Team understands their objectives and responsibilities, and celebrates success together. - RACI chart created and agreed. - Strong evidence of cross departmental teamwork. - Less effective members have moved on. - Team profile is getting noticed Level 4: - Staff consistently report satisfaction with their work. - Team recognised as high performing via robust Key Performance Indicator (KPI) methodology. - High performers want to become part of the team. - Stability and staff retention delivers improving capability. | 3. Culture of Trust & A'ability
| 4. Governance | Level 1: - Project/programmes run through single layer management team structure. - Governanace lacks approporiate structure and/or Terms of Reference. - Budget envelope ill-defined Level 2: - Some governance structure but irregular meetings and uncoordinated cadence of meetings of decision making boards/ Programme or project/programme managers in place but working in silos - leaning on colleagues for ad hoc support. - Senior Responsible Officer not fully authorised to make decisions. - Project/programme plan created but progress is not regularly reported against key milestones. Level 3: - Calendar for Board meetings set annually. - Strategic, Programme/Project board, and a Design Authority in place. - Meeting minutes, decisions and actions recorded, assigned and followed up. - Project Initiation Document establishes clear framework for delivery. - Industry standard RIBA stages and gateway reviews are used. - Decision making based on real and timely data. - Change control protocol established. Level 4: - Information of the appropriate level of detail flows between Boards. - Difficult decisions are made for projects that are unviable, delayed or unlikely to deliver the expected benefits. - Lessons learned are studied and process changes made. | 4. G'nance
| 5. Project and Programme Management | Level 1: - Project/programme Manager(s) lack formal skills and the capacity to run the programme effectively. - Project/programme control is limited, typically only by line manager or Head of Service. - Lack of core Cross-functional team awareness. Level 2: - Project/programme Manager has the necessary skills and experience. - Key processes are documented but less than 100% adherence. - Sporadic governance meetings and inadequate clarity of decision making processes. - Cross functional team in place. Level 3: - All processes are configured around established project management methodology held in a central accessible location. - Project/Programme Management Office (PMO) established to: track and report progress, control information management, lead financial accounting, track risks and issues, ensure quality controls and change management processes are embedded. Level 4: - All processes managed with measures of both quality and quantity. - Continuous improvement through lessons learned and peer reviews, and applied consistently across the organisation. - Appropriate authority vested in expert Project/programme managers. | 5. Proj and Prog M'ment
| 6. Performance Measurement | Level 1: - Reporting is inaccurate, untrusted, and irregular. - Reports not sufficiently detailed and/or delayed and not used to drive decisions. - Individuals entrusted with a large capital budget with limited/no control. - No KPI's in place. Level 2: - Basic financial measures are available at close of reporting period, but not all costs fully accounted for. - Incomplete data leads to erroneous decisions. - Communication on performance between project/programme managers and finance staff in place. - Occasional disagreement with regards to actual financial position. - Some measurements on Time/Cost/Quality are collected/reported but not all. Level 3: - Appropriate suite of KPIs is used to manage and measure the performance of the project/programme. - Business case sets out the expected benefits and outcomes and how they will be measured. - Analysis of stakeholder satisfaction is a key factor when planning new project/programmes. Level 4: - KPIs linked directly to the success of the whole organisation. - Post-project evaluations take place with stakeholders, occupants, residents and team members, actions taken and lessons learned embedded into future project/programmes. | 6. Perf M'ment
| 7. Quality Management | Level 1: - Quality standards are an ambition, no real checks made. - No consistency or learning from experience. Level 2: - A set of Employers Requirements (ER's) may exist but with limited focus on impact of time, cost, quality. - Changes made unilaterally by project/programme managers to meet budgetary constraints. - Compliance with ER's is unenforced or monitored. - Little or no change control in practice. Level 3: - Individuals responsible follow procedures and processes are clearly understood. - Quality standards are prepared but limited checks made. - Project reviews held but lessons learned not implemented fully. Level 4: - All members of project/programme team including elected members take shared responsibility to ensure quality of deliverables. - Quality Standards table is prepared and all have a required minimum standard. - Quality checks are carried out to ensure every deliverable is fit for purpose, meets requirements and realises the benefits. | 7. Qual M'ment
| 8. Risk and Issues Management | Level 1: - Risk management, if carried out, is a superficial exercise and rarely reviewed. - Project/programme managers avoid discussing risks and issues, lack of clarity around authority to approve mitigation plans. - Risks & issues dealt with reactively Level 2: - Approved protocol of delegated authority in place. - Some active risk management in place but not carried out by the whole team. - Lack of clarity over risk ownership. - Identified risks are usually project/programme level risks and not strategic risks. Level 3: - Risk management embedded in the project/programme using appropriate tools. - Centrally held Risk and Issues Register is regularly reviewed at each board meeting and continually updated. - All risks have an allocated owner. Level 4: - All risks have an allocated owner and a mitigation strategy. - Risks constantly monitored, appropriately communicated and appropriate timely action taken. - Informed decisions based on accurate data and appropriate controls are in place. | 8. Risk and Issues M'ment
| 9. Stakeholder Communications | Level 1: - Sporadic and reactive consultation, often prompted by negative media or political interest. - Stakeholder plan non-existent or not fit for purpose. - Little or no thought to identifying all stakeholders. - Limited communication results in low market confidence to invest or develop. Level 2: - Stakeholder plan in place but only superficial consultation planned. - Some resident engagement, but no iterative process as designs progress. - No wider communications plan to advertise Local Authority's strategy and progress. - Limited use of website and hoardings to provide updates. - Limited dialogue with investors and developers. Level 3: - All stakeholders identified and a consultation and management strategy approved. - Communications Plan agreed with appropriate use of social media. - Effective political engagement in place. - Consultation over a wider area than just the immediate development site. - Some limited iterative consultation with residents. - Community Review Panel engaged and involved. Level 4: - All stakeholders identified and a consultation and management strategy approved. - Communications Plan agreed with appropriate use of social media. - Effective political engagement in place. - Consultation over a wider area than just the immediate development site. - Some limited iterative consultation with residents. -Community Review Panel engaged and involved | 9. S'holder Comms
| 10. Finance | Level 1: - Little connection between finance and project/programme teams. - Limited capacity in finance team to support project/programme. - Limited ownership of financial performance. - Little connection between project/programme plans and the Medium Term Financial Plan (MTFP) and capital strategy. - Limited or no investment appraisal tools used Level 2: - Some dedicated finance resource allocated to the project/programme. - Finance team make limited links between project and corporate financing. - Financial performance and Value for Money considerations are not integrated in overall project/programme reporting. - Non-finance staff have limited understanding of business case and financial indicators. - Business planning is not suitably mature to support effective decision making. - Limited cost control even when actual/forecast project spend is over budget. Level 3: - Financial team member is available and integral to the project/programme team. - Visible connection between project/programme plans and MTFP, and any other financial plans. - Financial data used to manage and monitor performance proactively. - Finance colleagues report to boards alongside project/programme managers. - Business Case is reviewed at each gateway. Level 4: - Robust controls and variation process embedded across all project/programmes. - Each project/programme has its own scorecard. - Project/programme is embedded in finance team members' personal objectives. - Sophisticated strategy for using Local Authority financing for long-term housing and regeneration projects. | 10. Finance
| 11. Legal | Level 1: - Capacity or capability or both to undertake housing and regeneration related legal work is lacking. - Sporadic use of external suppliers. - Limited use of legal frameworks. - Legal costs escalate rapidly. Level 2: - Some experience in-house, although may not always be available when needed. - External legal support not readily available to supplement internal team. Level 3: - Legal department resourced to deliver support at key stages. - External legal support available as required. - Lack of support available for strategic matters e.g. CPO/site assembly. Level 4: - High level of understanding of relevant legal matters within the project/programme team. - Support from legal team (internal or external) requested and received as required. | 11. Legal
| 12. Procurement | Level 1: - Capacity or capability or both to undertake built-environment related procurement is lacking. - Project requirements are not well defined. - Contract provides limited control and/or penalties for cost, quality or time overruns. - Reporting methodology not fit for purpose. - Work commences on site with no contract in place leading to unexpected costs incurred. - Unapproved vendors instructed. Level 2: - Some procurement expertise exists but may not always be available. - Limited knowledge of the procurement of construction contracts. - Procurement process is generally being followed in line with the programme plan. - Some cost analysis performed however negotiations with contractors are limited and robust challenge is avoided. - Over/under utilisation of procurement frameworks. - Contingency sums are accepted but aren't sense checked and/or appropriate Level 3: - Procurement colleagues are able to resource at appropriate time. - Use of appropriate public procurement processes and frameworks. - Contracts negotiated to include relevant KPI's. - Timing for procurement decisions is aligned with overall plan, but sometimes not delivered in practice. - Consideration given to new technologies, methods and opportunities (such as Modern Methods of Construction). Level 4: - Full knowledge and utilisation of appropriate routes to market. - Procurement risk is considered and managed effectively. - Suppliers are monitored and poor performers are managed carefully and/or replaced. - Key stakeholders are fully aware of roles and responsibilities for the procurement process chosen. | 12. P'ment
| 13. Town & Country Planning | Level 1: - Dedicated planning resource is not allocated to the project or programme. - Input from a Planning Officer is sporadic. - Limited and mainly reactive advice given. - Limited effort to link housing and regeneration ambitions with local planning strategy. - Limited consideration of design quality. Level 2: - Planning resource identified but still largely reactive. - Not involved from inception and/or site identification stages. - Planning feedback unduly unimaginative and/or pessimistic. - Inconsistent approach to design input and advice across one or more projects. Level 3: - Dedicated resource to the project/programme and released in part from other work. - Fed back planning policy into early feasibility studies and concept designs. - Separate planning officer resource ring-fenced to ensure impartiality in role as Local Planning Authority. - Use of Pre-Application discussions for all schemes and Planning Performance Agreements for larger schemes. - Design Guides and expertise used with regularity. Level 4: - Capacity and timings of planning committee meetings carefully considered to allow for new schemes as well as business as usual. - Applications dealt with within statutory timetable. - Independent Design Review Panel set up, resourced and inputting at appropriate stages. - Clear relationship between Strategic Plan and Local Plan. | 13. T & C Planning
| 14. Sustainability & Net Zero Carbon | Level 1: - Little practical application to address Climate Emergency. - Inconsistent application of sustainability measures through built environment policies. - Short-term financial pressures reduce investment in sustainability. Level 2: - Some reference within strategic documents. - Renewable heating and electricity utilised. - Awareness and limited introduction of SUDS (Sustainable Underground Drainage Systems). Level 3: - Whole life cost approach used. - All relevant strategies lead to practical measures to address climate change. - Low carbon, high quality urban design at forefront. Level 4: - High quality design aligns with best practice sustainability measures. - Sustainability extends beyond built assets to include infrastructure, circular economy and biodiversity. - Organisation commits to both science-based decarbonisation pathways and purchasing carbon offsets. | 14. S'ability & Net Zero Carbon
| 15. Site Readiness & Pipeline | Level 1: - No centrally agreed and resourced site list. - Sites identified on ad hoc basis. - HELAA (Housing and economic land availability assessment) not regularly maintained and updated. - Little or no technical or legal due diligence carried out. Level 2: - Single list of potential sites exists. - Basic information held, mostly viewed using online mapping tools. - Sites being progressed without empirical assessment of priority. - Some leaseholders and freeholders identified. - Limited due diligence carried out. Level 3: - Sites reviewed by cross-departmental team, all sites visited, photographed and brief summary reports prepared. - Tools used to analyse and compare each site to prioritise the pipeline list. - Legal and technical due diligence carried out on preferred sites (including some contingency sites). - All affected occupiers and owners correctly identified. Level 4: - Prioritised schedule of sites approved. - Feasibility and/or massing studies concluded. - Where relevant secure cabinet approval to the principle of progressing CPOs. - Pre-application discussions held and supportive reports received. - Site assembly progressed to maximise potential opportunities in a timely manner. - Budget approved to purchase unexpected sites that become available. | 15. Site R'ness & Pipeline
| 16. Housing Development and Delivery Track Record | Level 1: - Some small scale developments developed in an ad hoc way and without a multi skilled team. - Lack of clarity about client role and skillset. - Total build cost per square metre (excluding abnormal costs) vary considerably from one project to another. Level 2: - Some new build schemes have been completed or are underway. - The team is under resourced. - Project Managers have the required skillset but lead too many projects. - Costs have a tendency to overrun. Level 3: - The team has a track record and a pipeline of projects. - Staff are experienced in project, programme and client management, although issues over pace and cost still occur. Level 4: - Progress and quality standards are monitored regularly and carefully. - Effective change and cost control in place. - Confident team looking for opportunities to maximise impact. - Organisation is well regarded as a leader in their locality. | 16. Ho. D'ment and Deliv Track Record
| 17. Development through Partnerships | Level 1: - Limited knowledge of the benefits and process of partnering by members and officers. - Little or no governance in place for the partnership. - Lack of trust and conflicts of interest between partners leading to limited transparency. - Power imbalance skews focus of projects away from original aims. - Business partners remain too focussed on short-term-financial gain. Level 2: - Recognition that delivering projects and programmes requires coordination with partners but limited clarity on roles and responsibilities. - Only tentative links have been made between seemingly disparate projects/areas. - Partnership Agreement not concluded. - Partners start to look long-term and recognise the benefits of aligning their interests. Level 3: - Leadership by those with most relevant skills and experience rather than the largest partner. - Resources are often committed over timescales that are too short to deliver realistic and lasting change. - Civic leaders/project champions prioritise partnership outcomes and create confidence in vision, strategy and delivery of the action plan. - Project, Management and Advisory Boards are set up as appropriate and regular communications delivered to all partners. - Appropriate partnering agreements and legally binding contracts are agreed and in force. Level 4: - Organisation is identified by senior level commitment, a partnering mindset and skill set. - Ongoing collaborative relationship among partners who are all sufficiently experienced and empowered within their respective roles. - Different stakeholders have aligned interests around a common vision and share resources, competencies and risk. - Projects seek to maximise value creation and deliver benefits to all partners. - A spirit of curiosity, tolerance for mistakes and collective problem-solving. | 17. D'ment through P'ships
| 18. Regeneration and Delivery and Track Record | Level 1: - Lack of strategic plan and limited co-ordinated delivery. - Individual sites progress in isolation from rest of locality. - Limited understanding of the varying professional disciplines required. - Limited consideration of relationship between physical interventions and economic and social benefits. - Limited investment in development enabling activities. f) No appreciation of complex land assembly processes. Level 2: - Strategic plan exists but only loosely defined, with no monitoring, scale or context to surrounding area. - Where plans exist, often conceived on basis of deductive reasoning and not observational facts. - Limited or no infrastructure planning. - Timing disconnect between varying inter-related projects (especially infrastructure). - Small-scale targeted investment made in enabling works/actions. Level 3: - Recognition at a senior level that regeneration is a long-term aspiration requiring co-ordinated delivery of the varying parts of the plan. - Place making, planning and regeneration policies recognise trends. - Regeneration plans align development priorities with business/community needs and resources. - Developers begin to engage with communities, businesses and services. - Business case emphasises wider benefits of regeneration. Level 4: - Integrated approach to regeneration agreed across local authority functions, businesses and communities. - Regeneration focuses on people, place, environment and economy. - Transport connectivity and infrastructure planning delivered in line with programme plan. - Active involvement with local businesses, communities and stakeholders. - Results chains linking activities and inputs with anticipated outcomes are well established. | 18. R'tion and Deliv and Track Record

## 6.Project Lens Descriptions (hidden)
| Theme | Organisational Descriptions
PROJECT LENS | 15. Site Readiness & Pipeline | Level 1: - No centrally agreed and resourced site list. - Sites identified on ad hoc basis. - HELAA (Housing and economic land availability assessment) not regularly maintained and updated. - Little or no technical or legal due diligence carried out. Level 2: - Single list of potential sites exists. - Basic information held, mostly viewed using online mapping tools. - Sites being progressed without empirical assessment of priority. - Some leaseholders and freeholders identified. - Limited due diligence carried out. Level 3: - Sites reviewed by cross-departmental team, all sites visited, photographed and brief summary reports prepared. - Tools used to analyse and compare each site to prioritise the pipeline list. - Legal and technical due diligence carried out on preferred sites (including some contingency sites). - All affected occupiers and owners correctly identified. Level 4: - Prioritised schedule of sites approved. - Feasibility and/or massing studies concluded. - Where relevant secure cabinet approval to the principle of progressing CPOs. - Pre-application discussions held and supportive reports received. - Site assembly progressed to maximise potential opportunities in a timely manner. - Budget approved to purchase unexpected sites that become available.
| 16. Housing Development and Delivery Track Record | Level 1: - Some small scale developments developed in an ad hoc way and without a multi skilled team. - Lack of clarity about client role and skillset. - Total build cost per square metre (excluding abnormal costs) vary considerably from one project to another. Level 2: - Some new build schemes have been completed or are underway. - The team is under resourced. - Project Managers have the required skillset but lead too many projects. - Costs have a tendency to overrun. Level 3: - The team has a track record and a pipeline of projects. - Staff are experienced in project, programme and client management, although issues over pace and cost still occur. Level 4: - Progress and quality standards are monitored regularly and carefully. - Effective change and cost control in place. - Confident team looking for opportunities to maximise impact. - Organisation is well regarded as a leader in their locality.
| 17. Development through Partnerships | Level 1: - Limited knowledge of the benefits and process of partnering by members and officers. - Little or no governance in place for the partnership. - Lack of trust and conflicts of interest between partners leading to limited transparency. - Power imbalance skews focus of projects away from original aims. - Business partners remain too focussed on short-term-financial gain. Level 2: - Recognition that delivering projects and programmes requires coordination with partners but limited clarity on roles and responsibilities. - Only tentative links have been made between seemingly disparate projects/areas. - Partnership Agreement not concluded. - Partners start to look long-term and recognise the benefits of aligning their interests. Level 3: - Leadership by those with most relevant skills and experience rather than the largest partner. - Resources are often committed over timescales that are too short to deliver realistic and lasting change. - Civic leaders/project champions prioritise partnership outcomes and create confidence in vision, strategy and delivery of the action plan. - Project, Management and Advisory Boards are set up as appropriate and regular communications delivered to all partners. - Appropriate partnering agreements and legally binding contracts are agreed and in force. Level 4: - Organisation is identified by senior level commitment, a partnering mindset and skill set. - Ongoing collaborative relationship among partners who are all sufficiently experienced and empowered within their respective roles. - Different stakeholders have aligned interests around a common vision and share resources, competencies and risk. - Projects seek to maximise value creation and deliver benefits to all partners. - A spirit of curiosity, tolerance for mistakes and collective problem-solving.
| 18. Regeneration and Delivery and Track Record | Level 1: - Lack of strategic plan and limited co-ordinated delivery. - Individual sites progress in isolation from rest of locality. - Limited understanding of the varying professional disciplines required. - Limited consideration of relationship between physical interventions and economic and social benefits. - Limited investment in development enabling activities. f) No appreciation of complex land assembly processes. Level 2: - Strategic plan exists but only loosely defined, with no monitoring, scale or context to surrounding area. - Where plans exist, often conceived on basis of deductive reasoning and not observational facts. - Limited or no infrastructure planning. - Timing disconnect between varying inter-related projects (especially infrastructure). - Small-scale targeted investment made in enabling works/actions. Level 3: - Recognition at a senior level that regeneration is a long-term aspiration requiring co-ordinated delivery of the varying parts of the plan. - Place making, planning and regeneration policies recognise trends. - Regeneration plans align development priorities with business/community needs and resources. - Developers begin to engage with communities, businesses and services. - Business case emphasises wider benefits of regeneration. Level 4: - Integrated approach to regeneration agreed across local authority functions, businesses and communities. - Regeneration focuses on people, place, environment and economy. - Transport connectivity and infrastructure planning delivered in line with programme plan. - Active involvement with local businesses, communities and stakeholders. - Results chains linking activities and inputs with anticipated outcomes are well established.