## External Plan Format
Magnox Limited Procurement Plan as at end of September 2023 | [13 empty] | #N/A
1
UNIQUE EXTERNAL REF | DIRECTORATE OR CATEGORY TEAM | SITE | CONTRACT DESCRIPTION (Values in brackets represent anticipated duration) | CATEGORY | CONTACT | PROCUREMENT ROUTE | BANDING | PIN or PRE QUAL ADVERT PUBLISH DATE | ITT ISSUE (a) Actual (f) Forecast |  | CONTRACT AWARD DATE (a) Actual (f) Forecast |  | CONTRACTOR / SUPPLIER Tend: Tenderers or Contractor(s) if awarded | STATUS
C10498 | Decommissioning | Trawsfynydd | Rolling Programme of Decommissioning - Laser Trials Trawsfynydd | Design services/support | claire.scott@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2023-05-11 | (a) | 2023-11-07 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C11007 | Decommissioning | Trawsfynydd | Rolling Prog of Decom (RPD) - Scheme Design - Integration Support | Design services/support | claire.scott@magnoxsites.com | DPS Call-Off | £1m to £5m | n/a | 2023-02-10 | (a) | 2023-08-09 | (a) | Atkins Limited | 12. Contract in place
C11008 | Decommissioning | Trawsfynydd | Rolling Programme of Deccommissioning (RPD) - Scheme Design - Bioshield Break In | Design services/support | claire.scott@magnoxsites.com | DPS Call-Off | £1m to £5m | n/a | 2023-05-11 | (a) | 2023-09-08 | (a) | Nuvia Limited | 11. Contract awarded
C12811 | Decommissioning | Chapelcross | Chapelcross Ponds Decommissioning - Enabling Works | Plant & Equipment & Materials | Shelley.Lawrence@magnoxsites.com | FTS Open | £1m to £5m | n/a | 2023-03-12 | (a) | 2023-11-07 | (f) | Tend: More than 10 | 10. Identification of preferred bidder
C12970 | Decommissioning | Enablers/Not Location Specific | Rolling Programme of Decommissioning (RPD) Strategic Enablers Graphite Treatment | Design services/support | claire.scott@magnoxsites.com | Other - No Competition | <£100K | n/a | 2023-02-10 | (a) | 2023-10-08 | (f) | Tend: Manchester University | 10. Identification of preferred bidder
C13251 | Decommissioning | Trawsfynydd | Rolling Programme of Decommissioning (RPD) - Enablers Graphite Sample Analysis | Design services/support | claire.scott@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2023-02-10 | (a) | 2023-08-09 | (a) | GAU (University of Southampton) | 12. Contract in place
C14325 | Decommissioning | Wylfa | Wylfa Air Gap Formation Of The Circulating Water Intake and Outlet System | Design services/support | lindsay.gibson@magnoxsites.com | Other - No Competition | <£100K | n/a | 2023-05-11 | (a) | 2023-10-08 | (f) | Tend: Kaymac Marine & Civil Engineering Ltd | 10. Identification of preferred bidder
C14412 | Decommissioning | Wylfa | BATS 059 300323 LG AW | Design services/support | lindsay.gibson@magnoxsites.com | DPS Call-Off | <£100K | n/a | 2023-05-11 | (a) | 2023-10-08 | (f) | Tend: More than 10 | 10. Identification of preferred bidder
C14691 | Decommissioning | Harwell | Building at Harwell Demolition | Decommissioning, Demolition & Deplant | david.m.sanderson@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2023-11-07 | (f) | 2024-03-06 | (f) | Not yet confirmed | 07. ITT in preparation
C14894 | Decommissioning | Harwell | Pre-fabricated Building(s) | Construction | Shelley.Lawrence@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2023-07-10 | (a) | 2023-12-07 | (f) | Tend: Kier McAvoy,Actiform Limited,Pickerings Hire Limited,Rollalong Limited,Deborah Services (Holding Limited) t/a Actavo,Wernick Buildings Limited,Portakabin Limited,Integra Buildings Limited,Module-AR Limited t/a M-AR Off-site,Elite Systems (GB) Limited,ESS ISG Consortium (EIC) | 10. Identification of preferred bidder
C14945 | Decommissioning | Sizewell | Sizewell Ponds Cutting Rig - modifications | Decommissioning, Demolition & Deplant | sarah.j.deeble@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2023-06-10 | (a) | 2023-08-09 | (a) | N-ERGISE Ltd | 12. Contract in place
C15220 | Decommissioning | Oldbury | Oldbury Turbine Hall - Data Quality Objective | Design services/support | paul.phillips@magnoxsites.com | Other - No Competition | <£100K | n/a | 2023-07-10 | (a) | 2024-02-05 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C15588 | Decommissioning | Hinkley | HPA produce Waste Management Plan (WMP) and Site Wide Enviro Safety Case | Design services/support | kim.cook@magnoxsites.com | Other - No Competition | <£100K | n/a | 2023-08-09 | (a) | 2023-08-09 | (a) | Galson Sciences Limited. | 12. Contract in place
C15687 | Decommissioning | Trawsfynydd | Reactor Retrievals Enablers - Transport Feasibility Study | Transport of materials | claire.scott@magnoxsites.com | Other - No Competition | <£100K | n/a | 2023-08-09 | (a) | 2023-09-08 | (a) | International Nuclear Services Ltd | 11. Contract awarded
C15711 | Decommissioning | Trawsfynydd | Reactor Retrievals Enablers - 4M Box Calculation | Design services/support | claire.scott@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2023-08-09 | (a) | 2023-09-08 | (a) | International Nuclear Services Ltd | 11. Contract awarded
C15918 | Decommissioning | Trawsfynydd | Trawsfynydd - Reactor Retrievals SD4 Main Retrievals & Processing Facilities | Design services/support | claire.scott@magnoxsites.com | FTS Restricted | £1m to £5m | 2023-12-13 | 2024-02-05 | (f) | 2024-06-04 | (f) | Not yet confirmed | 02. Strategy being developed
C16013 | Decommissioning | Hinkley | Hinkley R1 & R2 Pipe Bridges | Decommissioning, Demolition & Deplant | sarah.j.deeble@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2024-01-06 | (f) | 2024-08-03 | (f) | Not yet confirmed | 01. On the horizon
C16104 | Decommissioning | Trawsfynydd | BATS 063 250523 RC AW - Provision of Engineering Design Management | Design services/support | ruth.cox@magnoxsites.com | DPS Call-Off | £500k to £1m | n/a | 2023-10-27 | (f) | 2023-11-04 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0121 | Decommissioning | Harwell; Hinkley; Oldbury; Sizewell; Wylfa | Consultancy support: Guidance on requirements for release of nuclear sites from rad substances regulation | Manpower | rachel.thompson@magnoxsites.com | DPS Call-Off | £500k to £1m | n/a | 2023-10-08 | (f) | 2023-12-07 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0140 | Decommissioning | Sizewell | Deplant Crane Grab | Engineering | sarah.j.deeble@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2024-04-05 | (f) | 2024-06-04 | (f) | Not yet confirmed | 01. On the horizon
DEC 0418 | Decommissioning | Dungeness | DNA Boilers - Turbine Hall Infill | Construction | richard.sadd@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2023-02-10 | (a) | 2023-10-08 | (f) | Tend: Erith Contractors Ltd,Gallagher Limited,Jackson Civil Engineering Group Limited,Walker Construction (UK) Ltd,I D Corcoran Building Contractors Ltd,Trant Engineering Ltd | 10. Identification of preferred bidder
DEC 0439 | Decommissioning | Oldbury | Oldbury Turbine Hall Demolition | Decommissioning, Demolition & Deplant | paul.phillips@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2024-03-06 | (f) | 2025-03-11 | (f) | Not yet confirmed | 01. On the horizon
DEC 0492 | Decommissioning | Wylfa | Control and Instrumentation (C&I) Overlay System | Engineering | claire.scott@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2024-02-05 | (f) | 2024-08-03 | (f) | Not yet confirmed | 01. On the horizon
DEC 0529 | Decommissioning | Chapelcross | Chapelcross Ponds Decommissioning-Divers | Engineering | Shelley.Lawrence@magnoxsites.com | FTS Open | £1m to £5m | n/a | 2024-03-06 | (f) | 2024-09-02 | (f) | Not yet confirmed | 01. On the horizon
DEC 0538 | Decommissioning | Sizewell | AB/CD Boiler Houses Asbestos Removal | Hazardous materials removal | sarah.j.deeble@magnoxsites.com | Mini Competition F/W | £25m to £50m | n/a | 2024-10-02 | (f) | 2025-11-06 | (f) | Not yet confirmed
DEC 0597 | Decommissioning | Trawsfynydd | Reactor Buildings Height Reduction (EXECUTION phase) | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | FTS Comp Proc with Negotiation | £50m to £100m | 2022-12-06 | 2023-12-07 | (f) | 2024-09-01 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0601 | Decommissioning | Harwell | Project Demolition (phase 4) | Engineering | Shelley.Lawrence@magnoxsites.com | FTS Open | £10m to £25m | n/a | 2024-06-04 | (f) | 2024-12-01 | (f) | Not yet confirmed
DEC 0699 | Decommissioning | Harwell | Project Enabling Works - Char Execution (phase 3) | Engineering | Shelley.Lawrence@magnoxsites.com | Non-FTS Competition | £500k to £1m | n/a | 2024-01-06 | (f) | 2024-07-04 | (f) | Not yet confirmed | 01. On the horizon
DEC 0701 | Decommissioning | Dungeness | DNA Boilers - New Stores Building | Construction | richard.sadd@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2023-02-10 | (a) | 2023-07-10 | (a) | Walker Construction (UK) Ltd | 12. Contract in place
DEC 0708 | Decommissioning | Dungeness | Dismantle A Frame Crane & Remove Skip Mast | Decommissioning, Demolition & Deplant | david.m.sanderson@magnoxsites.com | FTS Open | <£100K | n/a | 2024-03-06 | (f) | 2024-06-04 | (f) | Not yet confirmed | 01. On the horizon
DEC 0720 | Decommissioning | Trawsfynydd | Ponds Complex Demolition - Execution | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | FTS Comp Proc with Negotiation | £5m to £10m | n/a | 2024-02-05 | (f) | 2025-06-09 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0738 | Decommissioning | Winfrith | Winfrith Sea Pipeline - Marine Engineering (civil) Consultant | Engineering | janet.smith@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2024-10-02 | (f) | 2025-02-09 | (f) | Not yet confirmed
DEC 0764 | Decommissioning | Harwell | Project Enabling Works Electrical Overlay (line 6) (PHASE TBC) | Engineering | Shelley.Lawrence@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2024-02-05 | (f) | 2024-08-03 | (f) | Not yet confirmed | 01. On the horizon
DEC 0773 | Decommissioning | Winfrith | EIA Support for Winfrith Sea Pipeline (Terrestrial Section) removal | Design services/support | janet.smith@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2024-01-06 | (f) | 2023-10-08 | (f) | Not yet confirmed | 01. On the horizon
DEC 0785 | Decommissioning | Dungeness | DNA Boilers - Waste Clearance Facility - fit-out | Construction | david.m.sanderson@magnoxsites.com | Other - No Competition | <£100K | n/a | 2024-05-05 | (f) | 2024-07-04 | (f) | Not yet confirmed | 01. On the horizon
DEC 0790 | Decommissioning | Harwell | Characterisation Execution and Asbestos R&D Survey | Engineering | Shelley.Lawrence@magnoxsites.com | FTS Restricted | £5m to £10m | 2023-04-26 | 2023-08-09 | (a) | 2023-12-07 | (f) | Not yet confirmed | 09. Tenders being assessed
DEC 0805 | Decommissioning | Trawsfynydd | Rolling Prog of Decom (RPD) - Scheme Design - Out of Core Comp'nt & In Core Furn | Design services/support | claire.scott@magnoxsites.com | FTS Restricted | £1m to £5m | n/a | 2023-07-10 | (a) | 2023-11-07 | (f) | Not yet confirmed | 09. Tenders being assessed
DEC 0807 | Decommissioning | Trawsfynydd | Rolling Prog of Decom (RPD) - Scheme Design - Building Modifications | Design services/support | claire.scott@magnoxsites.com | FTS Restricted | £500k to £1m | n/a | 2023-12-07 | (f) | 2024-03-06 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0841 | Decommissioning | Winfrith | SGHWR Manufacture and Oversee the Installation of a Can Compactor | Engineering | Liz.Gilbert@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2023-10-08 | (f) | 2024-01-06 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0842 | Decommissioning | Winfrith | Winfrith Cross Site Transportation - Procurement of a Tug | Transport of materials | Liz.Gilbert@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2023-01-01 | (a) | 2023-09-08 | (a) | Kallmar | 11. Contract awarded
FRM 0093 | Decommissioning | Enablers/Not Location Specific | DAR: Decommissioning & Asbestos Removal | Construction | nicola.j.smith-lee@magnoxsites.com | FTS Restricted | £250m plus | n/a | 2022-04-06 | (a) | 2023-07-10 | (a) | Altrad Support Services Limited, KAEFER LIMITED, KDC Contractors Limited, NSG Environmental Ltd, Nuvia Limited, KELTBRAY LIMITED, Costain Limited, Celadon Alliance | 12. Contract in place
FRM 0171 | Decommissioning | Dungeness | Package 1: Demolition & Boiler and ancillary equipment removal (Dungeness) | Decommissioning, Demolition & Deplant | nicola.j.smith-lee@magnoxsites.com | FTS Competitive Dialogue | £50m to £100m | 2023-02-07 | 2023-06-10 | (a) | 2025-05-10 | (f) | Not yet confirmed | 10. Identification of preferred bidder
ASM 0859 | Ops & Enablers | Enablers/Not Location Specific | LC28 Inspections 2023/24+ for All Sites | Support Services | steven.j.lock@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2022-12-02 | (a) | 2023-07-10 | (a) | Mott MacDonald Ltd, Mott MacDonald Ltd | 12. Contract in place
C10070 | Ops & Enablers | Enablers/Not Location Specific | Occupational Health (inc DNA Testing) 26+ | Support Services | Amy.Vale@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2024-03-06 | (f) | 2024-09-02 | (f) | Not yet confirmed | 01. On the horizon
C12719 | Ops & Enablers | Enablers/Not Location Specific | Pension administration - ESPS | Support Services | alwena.owen@magnoxsites.com | Other - No Competition | £1m to £5m | n/a | 2023-07-10 | (a) | 2023-07-10 | (a) | Railpen Limited | 12. Contract in place
C12780 | Ops & Enablers | Enablers/Not Location Specific | Public Affairs Agency | Manpower | michelle.a.edwards@magnoxsites.com | DPS Call-Off | £100k to £500k | n/a | 2023-04-11 | (a) | 2023-07-10 | (a) | Pagefield Communications Ltd | 12. Contract in place
C12802 | Ops & Enablers | Enablers/Not Location Specific | Maggas tool | IT hardware/software | debbie.collin@magnoxsites.com | Sole Source - No Choice | <£100K | n/a | 2023-09-08 | (a) | 2023-10-08 | (f) | Tend: Jacobs UK Ltd | 08. ITT issued
C14078 | Ops & Enablers | Enablers/Not Location Specific | ERP, FP&A and Talent Management | IT hardware/software | jayne.chalmers@magnoxsites.com | G-Cloud F/W Call off | £5m to £10m | n/a | 2023-11-07 | (f) | 2023-12-07 | (f) | Not yet confirmed | 02. Strategy being developed
C14079 | Ops & Enablers | Enablers/Not Location Specific | BATS 061 110423 AO AW_Human Factors Intelligent Customer / Practitioner | Design services/support | alwena.owen@magnoxsites.com | DPS Call-Off | £100k to £500k | n/a | 2023-08-09 | (a) | 2023-11-07 | (f) | Not yet confirmed | 09. Tenders being assessed
C14457 | Ops & Enablers | Enablers/Not Location Specific | 2023/24 Pension Fund - Investment Advice | Support Services | alwena.owen@magnoxsites.com | Sole Source - No Choice | £1m to £5m | n/a | 2023-06-10 | (a) | 2023-07-10 | (a) | Aon Insurance Managers (Guernsey) Limited | 12. Contract in place
C14511 | Ops & Enablers | Enablers/Not Location Specific | BATS 066 250723 AV AW Apprenticeship Recruitment | Support Services | holly.griffith@magnoxsites.com | DPS Call-Off | £100k to £500k | n/a | 2023-08-09 | (a) | 2023-10-08 | (f) | Not yet confirmed | 08. ITT issued
C14737 | Ops & Enablers | Dungeness | RPD Strategic Enablers Dungeness Knowledge and Information Management Phase 1 | Manpower | claire.scott@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2023-06-10 | (a) | 2023-07-10 | (a) | Ove Arup and Partners Limited | 12. Contract in place
C15003 | Ops & Enablers | Enablers/Not Location Specific | BATS 065 100723 AO AW_Provision of Management System and Independent Assessment | Design services/support | alwena.owen@magnoxsites.com | DPS Call-Off | £100k to £500k | n/a | 2023-08-09 | (a) | 2023-09-08 | (a) | Managing for Quality Ltd | 11. Contract awarded
C15014 | Ops & Enablers | Enablers/Not Location Specific | BATS 062 140623 ME AW | Manpower | michelle.a.edwards@magnoxsites.com | DPS Call-Off | £100k to £500k | n/a | 2023-07-10 | (a) | 2023-09-08 | (a) | increased access 2 psychological support (ia2ps) | 11. Contract awarded
C15086 | Ops & Enablers | Enablers/Not Location Specific | Burges Salmon Legal Support Services RM6179 | Support Services | gissela.m.hughes@magnoxsites.com | Other - No Competition | <£100K | n/a | 2023-04-11 | (a) | 2023-07-10 | (a) | Burges Salmon LLP | 12. Contract in place
C15161 | Ops & Enablers | Enablers/Not Location Specific | Supply of Electronic Personal Dosimeters | Engineering | caroline.j.milner@magnoxsites.com | Sole Source - No Choice | £1m to £5m | n/a | 2023-10-08 | (f) | 2023-12-07 | (f) | Not yet confirmed | 07. ITT in preparation
C15381 | Ops & Enablers | Enablers/Not Location Specific | Access & Insulation Services 2024-2028 | Construction | steven.j.lock@magnoxsites.com | FTS Restricted | £50m to £100m | n/a | 2024-01-06 | (f) | 2024-10-02 | (f) | Not yet confirmed | 02. Strategy being developed
C15759 | Ops & Enablers | Enablers/Not Location Specific | Development of 10 year strategy | Manpower | holly.griffith@magnoxsites.com | DPS Call-Off | <£100K | n/a | 2023-09-08 | (a) | 2023-09-08 | (a) | Inflowing Ltd | 11. Contract awarded
C16075 | Ops & Enablers | Bradwell | BATS 064 110923 GHAW Security Independent Assurance for Bradwell Remote Working | Design services/support | gissela.m.hughes@magnoxsites.com | DPS Call-Off | <£100K | n/a | 2023-09-08 | (a) | 2023-10-08 | (f) | Not yet confirmed | 08. ITT issued
C16171 | Ops & Enablers | Enablers/Not Location Specific | Project Manager & Business Analyst and Technical Design Architecture 2023 | IT hardware/software | jonathan.harris@magnoxsites.com | CCS F/W Call off | £5m to £10m | n/a | 2023-09-08 | (a) | 2023-12-07 | (f) | Not yet confirmed | 08. ITT issued
C8976 | Ops & Enablers | Enablers/Not Location Specific | COSHH Management Database and Advisory Service 2024 | IT hardware/software | debbie.collin@magnoxsites.com | FTS Open | £100k to £500k | n/a | 2023-06-10 | (a) | 2023-10-08 | (f) | Tend: One NDA,Sopra Steria Ltd,Ricardo AEA Ltd,Arctec Data Ltd,Infosys Limited.,Anya Consultancy Services Limited,Specialist Computer Centres PLC | 10. Identification of preferred bidder
FRM 0100 | Ops & Enablers | Enablers/Not Location Specific | Dosimetry 2022+ | Engineering | caroline.j.milner@magnoxsites.com | FTS Open | £5m to £10m | n/a | 2022-09-03 | (a) | 2023-07-10 | (a) | Cavendish Nuclear, Nuvia Limited | 12. Contract in place
FRM 0129 | Ops & Enablers | Enablers/Not Location Specific | Site Security Maintenance Systems 2023+ | Maintenance | sion.apglyn@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2023-05-11 | (a) | 2023-11-07 | (f) | Not yet confirmed | 10. Identification of preferred bidder
FRM 0159 | Ops & Enablers | Enablers/Not Location Specific | Tools and Consumables (2023 - 2027) | Consumables | james.hiller@magnoxsites.com | CCS F/W Call off | £25m to £50m | n/a | 2023-04-11 | (a) | 2023-11-07 | (f) | Tend: Huws Gray Ltd,THOMAS GRAHAM & SONS LTD | 10. Identification of preferred bidder
FRM 0168 | Ops & Enablers | Enablers/Not Location Specific | Legal Services 2022+ | Support Services | gissela.m.hughes@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2023-11-07 | (f) | 2024-02-05 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0182 | Ops & Enablers | Enablers/Not Location Specific | Land Quality Services 2024+ | Remediation & Environmental Services | Kwadwo.Awuku@magnoxsites.com | FTS Open | £10m to £25m | n/a | 2023-06-10 | (a) | 2024-04-05 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C11317 | Waste | Oldbury | Oldbury FED Waste Retrieval Facilty Scheme Design | Design services/support | danielle.staples@magnoxsites.com | DPS Call-Off | £500k to £1m | n/a | 2023-05-11 | (a) | 2023-10-08 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C11318 | Waste | Sizewell | Sizewell FED Waste Retrieval Facility Scheme Design | Design services/support | danielle.staples@magnoxsites.com | DPS Call-Off | £100k to £500k | n/a | 2023-05-11 | (a) | 2023-10-08 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C12468 | Waste | Harwell | Californium Source | Consumables | Liz.Gilbert@magnoxsites.com | Sole Source - No Choice | £100k to £500k | n/a | 2023-10-08 | (f) | 2024-02-05 | (f) | Tend: High Technology Sources Ltd | 02. Strategy being developed
C12530 | Waste | Wylfa | Wylfa HAW LAW Facility Building | Waste management, disposal & storage | fiona.pearse@magnoxsites.com | FTS Restricted | £10m to £25m | 2024-04-16 | 2024-06-04 | (f) | 2024-10-02 | (f) | Not yet confirmed
C12757 | Waste | Enablers/Not Location Specific | Multi-site Project Support - Engineering & Project Management | Design services/support | karen.maguire@magnoxsites.com | CCS F/W Call off | £10m to £25m | n/a | 2023-07-10 | (a) | 2023-10-08 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C12758 | Waste | Enablers/Not Location Specific | Waste Projects - Engineering Design Management | Design services/support | karen.maguire@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2023-07-10 | (a) | 2023-09-08 | (a) | Jacobs U.K. Limited | 11. Contract awarded
C12763 | Waste | Hunterston | Supply of 3m Boxes | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | DPS Call-Off | £1m to £5m | n/a | 2023-03-12 | (a) | 2023-10-08 | (f) | Tend: More than 10 | 10. Identification of preferred bidder
C14201 | Waste | Enablers/Not Location Specific | Project Green Oak - Feasibility Phase | Design services/support | pauline.z.mackemsley@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2023-05-11 | (a) | 2023-07-10 | (a) | Jacobs U.K. Limited | 12. Contract in place
C14790 | Waste | Hinkley | Decabling of Ponds buildings (HPA) | Construction | karen.maguire@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2023-07-10 | (a) | 2023-10-08 | (f) | Tend: MMES 2012 LTD,AMALGAMATED CONSTRUCTION LTD | 09. Tenders being assessed
C14792 | Waste | Oldbury | PFP building penetrations - Oldbury site | Construction | karen.maguire@magnoxsites.com | Other - No Competition | <£100K | n/a | 2023-07-10 | (a) | 2023-09-08 | (a) | Core Cut Ltd | 12. Contract in place
C14832 | Waste | Harwell | Harwell POCO Project Support | Design services/support | danielle.staples@magnoxsites.com | DPS Call-Off | £1m to £5m | n/a | 2023-07-10 | (a) | 2023-12-07 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C15065 | Waste | Hinkley | Lance Nozzle & Stools | Engineering | suzanne.macmillan@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2023-07-10 | (a) | 2023-07-10 | (a) | Lyndhurst Precision Engineering | 12. Contract in place
C15303 | Waste | Enablers/Not Location Specific | Hinkley Waste Projects Support - Engineering & Project Management | Design services/support | karen.maguire@magnoxsites.com | CCS F/W Call off | £10m to £25m | n/a | 2023-07-10 | (a) | 2023-10-08 | (f) | Not yet confirmed | 09. Tenders being assessed
WAS 0237 | Waste | Hinkley | FED HNK - Dry & Wet Vaults Retr & MOSAIK Load facil. Detail design and exec | Waste management, disposal & storage | karen.maguire@magnoxsites.com | Mini Competition F/W | £50m to £100m | n/a | 2021-07-10 | (a) | 2023-08-09 | (a) | Tend: Jacobs Clean Energy Cavendish Nuclear | 12. Contract in place
WAS 0544 | Waste | Enablers/Not Location Specific | AVDS Service and Maint | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | FTS Restricted | £1m to £5m | 2024-02-05 | 2024-04-05 | (f) | 2024-08-03 | (f) | Not yet confirmed | 01. On the horizon
WAS 0589 | Waste | Hinkley | Compact Heavy Lift Truck - with boom attachement | Plant & Equipment & Materials | danielle.staples@magnoxsites.com | FTS Open | £100k to £500k | n/a | 2024-06-04 | (f) | 2024-10-02 | (f) | Not yet confirmed | 07. ITT in preparation
WAS 0624 | Waste | Enablers/Not Location Specific | Mortuary Tube Structure - Furniture and grouting procurement | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2023-05-11 | (a) | 2023-09-08 | (a) | Stainless Metalcraft (Chatteris) Ltd | 11. Contract awarded
WAS 0646 | Waste | Wylfa | Wylfa DCIC Storage (ISF) Building Detailed Design and Construction | Construction | llyr.williams@magnoxsites.com | Non-FTS Competition | £1m to £5m | n/a | 2024-04-05 | (f) | 2024-10-02 | (f) | Not yet confirmed
WAS 0685 | Waste | Hinkley | HAI Phase 1b - Retrieval - Detailed Design, Manufacture and Installation | Waste management, disposal & storage | karen.maguire@magnoxsites.com | FTS Restricted | £1m to £5m | 2023-11-28 | 2024-02-05 | (f) | 2024-06-04 | (f) | Not yet confirmed
WAS 0755 | Waste | Harwell | Mezzanine Floor and Goods Lift | Construction | danielle.staples@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2023-10-08 | (f) | 2023-12-07 | (f) | Not yet confirmed | 07. ITT in preparation