## Procurement_Plan
		Nuclear Restoration Services Limited (Dounreay) - Procurement Plan August 2024
For further information contact Dounreay at commercial.services@dounreay.com

☆ Record Ref	Business Unit	Sourcing to Contract: Record Name	☆ Published Description	Procurement Route (If Known)	Contract Type	Commercial Strategy	Desired Contract Start Date	Desired Contract End Date	Value Range	Previous Contract Ref	Ops Project Manager	Contract Owner
C21291	Balance of Site	Non Active Drain Effluent Treatment Plant Detail Design	Non Active Drain Effluent Treatment Plant Detail Design	Framework - Direct Award	Services		19/08/2024	22/08/2025	< £100k		Steve Efemey	Dawn Sewell
C20653	Balance of Site	LINC Opportunity 21- Silo Waste Object Recovery Device Concept Deployment Trials	LINC Opportunity 21- Silo Waste Object Recovery Device Concept Deployment Trials	Below Threshold - Competitive Tender	Services		19/08/2024	25/10/2024	≥ £100k to <£500k		Grant Coghill	Lauren J Mackay
C19577	FCA	Safety Case Consultant to provide safety case support to D1203 and D2001	A Safety Case Consultant to provide safety case support to D1203 and D2001 decommissioning, and provide inventory support to the Irradiated Fuels Programme.	Framework - Further Competition	Services	Re-procurement (same scope)	26/08/2024	27/07/2026	≥ £100k to <£500k	3300032871	Ewen Boyd	Alex Wood
C20778	People	Provision of Doctor's Services for Occupational Health Support	Provision of Doctor's Services for Occupational Health Support: health surveillance and case management with option for adhoc support.	Direct Award - Below Threshold	Services		26/08/2024	31/12/2025	< £100k		Kirsty McIntosh	Lauren J Mackay
C21237	Capability	LINC Opportunity 24- Network Cabling	Provision of upgrade to 40 network cabinets	Below Threshold - Competitive Tender	Works		30/08/2024	28/02/2025	≥ £100k to <£500k		Rob Bohee	Ilona Unger-Russell
C20745	Portfolio & Support	Nuclear Restoration Services Limited (Dounreay) Excellence Plan	Nuclear Restoration Services Limited (Dounreay) Excellence Plan	Framework - Further Competition	Services		30/08/2024	29/11/2024	≥ £100k to <£500k		Fredric Stalin	Ilona Unger-Russell
C17690	Portfolio & Support	Ongoing Support to SPOT Robot	Ongoing Support Contract for SPOT Robot System	Direct Award - Below Threshold	Services		30/08/2024	29/08/2025	< £100k		Heather Fairweather	Robert McDonald
C17717	FCA	Supply of Stainless Steel Boxes	Supply of Stainless Steel Boxes	Below Threshold - 3 Quotes	Supplies		31/08/2024	30/11/2024	< £100k		Robert McKiddie	Erica Innes
C13963	EHSSQ	Fuel Cycle Area North Perimeter Fence Razor Wire Repair	Fuel Cycle Area North Perimeter Fence Razor Wire Repair	Below Threshold - Competitive Tender	Works		31/08/2024	31/10/2024	≥ £100k to <£500k		Richard Berry	Hannah Budge
C19906	Balance of Site	D1208 East Fire Escape Removal & Installation	Removal of the current and installation of a new D1208 Fire Escape Staircase	Below Threshold - Competitive Tender	Works		31/08/2024	20/12/2024	≥ £100k to <£500k		Michael Gray	Heidi Warner
C17940	Site Services	D1208 In-cell Inspections	D1208 In-cell Inspections	Framework - Further Competition	Services	Re-procurement (same scope)	01/09/2024	01/09/2027	< £100k	3300021440	Andrew Cormack	Hannah Budge
C19853	Reactors	Breeder Fuel Test Rig	Rental and Ad-Hoc Support to the Breeder Fuel Trials Rig	Direct Award - PCR Single Source (Reg 32)	Services	Re-procurement (same scope)	01/09/2024	30/06/2028	≥ £1m to <£5m	3300019316	Chris Wratten	Robert McDonald
C20599	FCA	Laboratory Analysis of Natural Depleted Uranium	Laboratory Analysis of Natural Depleted Uranium to Identify the Type of Uranic Material	Framework - Direct Award	Services		01/09/2024	30/09/2024	< £100k		Robert McKiddie	Robert McDonald
C21297	Balance of Site	Completion of Mechanical & Electrical installation - DCP Stores Extension	Nuclear Restoration Services Limited (Dounreay) intends to procure a contractor to complete the remaining mechanical and electrical (M&E) works for the Dounreay Cementation Plant Store Extension project at the Dounreay Nuclear site in Caithness, Scotland.	Below Threshold - Competitive Tender	Works	Re-procurement (same scope)	01/09/2024	31/05/2025	≥ £500k to <£1m	3300004730	Fiona Forbes	Sonja Sinclair
C20812	Balance of Site	Electrical Control and Instrumentation Services	Electrical Control and Instrumentation Services	Framework - Further Competition	Services		01/09/2024	31/08/2025	≥ £100k to <£500k		Michael Gray	Sonja Sinclair
C20809	Balance of Site	Mechanical Design Services	Mechanical Design Services	Framework - Further Competition	Services		01/09/2024	31/08/2025	≥ £500k to <£1m		Michael Gray	Sonja Sinclair
C9875	Balance of Site	Area 600 - Internal Cement Powders Line and Caustic Line installation	Area 600 - Internal Cement Powders Line installation, internal and external Caustic Line installation and Phase 1 internal ventilation installation	Below Threshold - Competitive Tender	Works		01/09/2024	14/11/2024	≥ £100k to <£500k		Michael Gray	Sonja Sinclair
C20957	FCA	D1201 Modification Package of Works - Phase 1	This is for Phase 1 and includes: / • Fuel Cycle Area Tea Bar upgrades / • New D1201 Meeting Room, Storage Area and Hot Desk Space / • New Health Physics Office / • New Health Physics Supervisor’s Office / • Lead Technician Area (Goldfish Bowl) upgrades	Below Threshold - Competitive Tender	Services		02/09/2024	05/09/2025	≥ £100k to <£500k		Jason Simpson	Dawn Sewell
C20370	FCA	Provision of Safety Case Advisor	Provision of Safety Case Advisor	Framework - Further Competition	Services		02/09/2024	31/08/2025	< £100k		Ewen Boyd	Erica Innes
C20364	FCA	Provision of Breathing Air Panel	Provision of Breathing Air Panel	Direct Award - Below Threshold	Supplies		02/09/2024	30/04/2025	< £100k		Michael L Tait	Erica Innes
C21302	Reactors	DN026/029 Upgrades Detailed Design	Detailed design for the upgrades of DN026/029	Direct Award - Below Threshold	Services		02/09/2024	31/10/2024	< £100k		Andy MacInnes	Jade Plowman
C16884	Reactors	Refit of IPM9 Monitor	Supply, Installation, Commissioning and Site Acceptance Testing of an IPM Rebuild Kit	Direct Award - Below Threshold	Works		02/09/2024	30/09/2024	< £100k		Chris Wratten	Jade Plowman
C17219	Capability	Programmatic Change Work	Information Technology (IT) Transformation Project Work	Framework - Further Competition	Services		02/09/2024	31/03/2025	≥ £500k to <£1m		Calum Mackay	Lynsey Will
C19908	Capability	Data Warehouse for Dounreay Site	Creation of a cohesive data ecosystem to eliminate fragmentation of information across Dounreay.	Framework - Further Competition	Services		02/09/2024	01/08/2025	≥ £100k to <£500k		Rob Bohee	Lynsey Will
C20555	Balance of Site	Shaft Head Removal - Facility Hire & Design / Construction of Mock Up Trials Rig	NRS looks to engage a contractor via Open Procedure on an Option A and Option E basis, to provide the hire of a facility, and the construction of a trials rig for the Shaft Head Removal Trials	Open Procedure	Services		02/09/2024	02/06/2025	≥ £500k to <£1m		Willie Ross	Samantha Davidson
C21535	FCA	Reserved - D1217 Grouting North and South Cells & Transfer Cell Block Pour	Reserved - D1217 Grouting North and South Cells & Transfer Cell Block Pour	Below Threshold - Competitive Tender	Works		09/09/2024	24/10/2024	≥ £100k to <£500k		Leslie D M Mackay	Erica Innes
C20732	FCA	D1217 Grouting North and South Cells & Transfer Cell Block Pour	D1217 Grouting North and South Cells & Transfer Cell Block Pour	Below Threshold - Competitive Tender	Works		09/09/2024	24/10/2024	≥ £100k to <£500k		Leslie D M Mackay	Erica Innes
C21303	Reactors	Demolition of Existing DN026 Structure	Demolition of the existing DN026 structure	Direct Award - Below Threshold	Works		09/09/2024	31/10/2024	≥ £100k to <£500k		Andy MacInnes	Jade Plowman
C16201	Site Services	Purchase of 2 x new Tipper / Gritter Lorries	Purchase of 2 x new Tipper / Gritter Lorries	Open Procedure	Supplies		16/09/2024	31/07/2025	≥ £100k to <£500k		Ian Mackay	Fraser Bruce
C1129	FCA	D1217 Cell Floor Equipment Manufacture, Concrete and Steel and Hire of Facility	D1217 Cell Floor Equipment Manufacture, Concrete and Steel and Hire of Facility for Testing	Below Threshold - Competitive Tender	Works		19/09/2024	30/03/2025	≥ £100k to <£500k		Leslie D M Mackay	Alex Wood
C21104	Balance of Site	Safety Case Support to Balance of Site	Nuclear Restoration Services Limited is required to produce and validate Safety Cases for the design, construction, installation, operation, and eventual decommissioning of plant on the Dounreay Site in accordance with Licence Condition (LC) 14.	Framework - Further Competition	Services		25/09/2024	24/09/2027	≥ £100k to <£500k		Jared Fraser	Samantha Davidson
C14046	Site Services	D1208 Peer Review	D1208 Peer Review	Framework - Further Competition	Services		30/09/2024	28/02/2026	< £100k		Andrew Cormack	Hannah Budge
C1254	Site Services	D1215 Instrument Lab - Inductively Coupled Plasma - Mass Spectrometer	D1215 Instrument Lab - Inductively Coupled Plasma - Mass Spectrometer	Direct Award - Below Threshold	Supplies		30/09/2024	28/02/2025	≥ £100k to <£500k		Jeremy Andrew	Hannah Budge
C17227	Capability	Internet Resilience Project for the Dounreay Site	Wide Area Network connectivity/ Internet Feeding requirement	Framework - Direct Award	Services		30/09/2024	20/01/2025	≥ £100k to <£500k		Rob Bohee	Ilona Unger-Russell
C20150	Capability	Private 5G Wireless Upgrade	Private 5G Wireless Upgrade	Direct Award - PCR Single Source (Reg 32)	Services		30/09/2024	31/07/2025	≥ £100k to <£500k		Rob Bohee	Ilona Unger-Russell
C20152	Capability	Checkpoint Firewall Replacement	Checkpoint Firewall Replacement	Framework - Further Competition	Services		30/09/2024	30/09/2025	≥ £100k to <£500k		Rob Bohee	Lynsey Will
C21282	Balance of Site	Procurement of new X-Ray Equipment	NRS is seeking a SQEP Contractor to undertake the design, manufacture, installation and commissioning of X-Ray equipment to enhance their capability Gamma Radiation Protection Instruments (RPI) at high dose rates.	Open Procedure	Services		30/09/2024	23/12/2024	≥ £100k to <£500k		Bernie Jones	Samantha Davidson
C1177	FCA	Design for Active Filter Change Replacement Robot Implementation	Design for Active Filter Change Replacement Robot Implementation	Framework - Further Competition	Services		01/10/2024	02/11/2025	< £100k		Graham Carle	Alex Wood
C20369	FCA	Provision of Environmental Advisor	Provision of Environmental Advisor	Framework - Further Competition	Services		01/10/2024	30/09/2025	< £100k		Bill Lambie	Erica Innes
C20538	Reactors	Breeder Fast Reactor Senior Design Engineer Support	Breeder Fast Reactor Senior Design Engineer Support	Framework - Further Competition	Services		01/10/2024	30/09/2027	≥ £100k to <£500k		Magnus O'Brien	Erica Innes
C10632	Balance of Site	Replacement of the Whole Body Monitor and Supporting Equipment	This procurement is to supply a replacement Whole Body Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Open Procedure	Services		01/10/2024	28/02/2025	≥ £100k to <£500k		Avril Fell	Fraser Bruce
C9673	Site Services	Telehandler	Telehandler	Below Threshold - Competitive Tender	Supplies		01/10/2024	31/01/2025	< £100k		Stephen Mackie	Janet Rosie
C16823	FCA	Procurement of a Non-Destructive Assay System (NDA 34 Replacement)	Procurement of a Non-Destructive Assay System	Open Procedure	Supplies		07/10/2024	06/10/2028	≥ £100k to <£500k		Ewen Boyd	Erica Innes
C16984	Balance of Site	Replacement of Wound Monitor and Supporting Equipment	This procurement is to supply a replacement Wound Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Below Threshold - Competitive Tender	Supplies		07/10/2024	31/01/2025	< £100k		Avril Fell	Fraser Bruce
C20976	Reactors	Prototype Fast Reactor Trade Personnel Requirement	Trade personnel requirement for Prototype Fast Reactor	Direct Award - Below Threshold	Services		07/10/2024	07/04/2025	< £100k		Stephen Farquhar	Jade Plowman
C1113	Site Services	Voidage and Container Assessments	Voidage and Container Assessments	Framework - Further Competition	Services		07/10/2024	31/08/2025	≥ £100k to <£500k		Stephen Mackie	Janet Rosie
C20857	Site Services	LINC Opportunity 22 - Maintenance Workflow Management Review	Dounreay is looking to improve the efficiency of how they execute maintenance activities. This opportunity is to carry out a comprehensive work management and execution assessment to get a full understanding of current maintenance performance.	Below Threshold - Competitive Tender	Services		07/10/2024	15/11/2024	< £100k		Laurence Campbell	Kerrie Mackay
C20530	Balance of Site	Provision of Environmental Support	The purpose of this Contract is to provide embedded Environmental Support to NRS Dounreay.	Framework - Further Competition	Services		07/10/2024	06/10/2025	≥ £100k to <£500k		Elizabeth Irwin	Samantha Davidson
C20273	People	Leadership Development Programme	Leadership Development Programme	Open Procedure	Services		14/10/2024	09/10/2026	≥ £100k to <£500k		Joanna Boyd	Lauren J Mackay
C1114	Site Services	Low Level Waste Metals Diversion Projects	Low Level Waste Metals Diversion Projects	Framework - Further Competition	Services		16/10/2024	31/03/2025	≥ £100k to <£500k		Kerryn Sievewright	Hannah Budge
C18811	Site Services	D1310 Total Organic Carbon backup	D1310 Total Organic Carbon backup	Below Threshold - 3 Quotes	Supplies		16/10/2024	31/01/2025	< £100k		Jeremy Andrew	Hannah Budge
C18791	Site Services	NDA40 equipment and Software	NDA40 equipment and Software	Direct Award - Below Threshold	Supplies		16/10/2024	31/01/2025	< £100k		Jeremy Andrew	Hannah Budge
C18805	Site Services	Shielded High Resolution Gamma Spectrometry System and Collimator	Shielded High Resolution Gamma Spectrometry System and Collimator	Direct Award - Below Threshold	Supplies		16/10/2024	31/01/2025	≥ £100k to <£500k		Jeremy Andrew	Hannah Budge
C1128	FCA	D1217 - Cell Floor Block Lifting Bags	D1217 - Cell Floor Block Lifting Bags	Below Threshold - Competitive Tender	Supplies		28/10/2024	31/12/2024	< £100k		Leslie D M Mackay	Alex Wood
C1096	Balance of Site	Non Active Drain Effluent Treatment Plant Works	Non Active Drain Effluent Treatment Plant Works	Below Threshold - Competitive Tender	Works		31/10/2024	24/06/2025	≥ £1m to <£5m		Adreain Gill	Dawn Sewell
C20153	Capability	Dounreay Electronic Document and Records Management System (EDMRS) Support	Dounreay Electronic Document and Records Management System (EDMRS) Support	Framework - Further Competition	Services		31/10/2024	31/10/2025	≥ £100k to <£500k		Rob Bohee	Lynsey Will
C19981	Site Services	Lynx II Digital Signal Analyser and Gamma Spec interfaces	Lynx II Digital Signal Analyser and Gamma Spec interfaces	Direct Award - Below Threshold	Supplies		01/11/2024	03/03/2025	< £100k		Ian Swainson	Immi Smith
C21304	Reactors	Erection and Outfitting of DN026 Building	Erection and Outfitting of new DN026 Building including Services Racking & Access Platforms	Below Threshold - Competitive Tender	Works		01/11/2024	31/03/2025	≥ £1m to <£5m		Andy MacInnes	Jade Plowman
C17177	Portfolio & Support	Legionella Risk Assessment	Legionella Risk Assessment	Direct Award - Below Threshold	Works		01/11/2024	31/03/2025	< £100k		Matthew Hitchin	Kelsey Bain
C1168	Portfolio & Support	Waste Optimisation - Waste Optimisation Improvements	Waste Optimisation - Waste Optimisation Improvements	Framework - Further Competition	Services		04/11/2024	31/08/2025	< £100k		Alan Mowat	Janet Rosie
C20938	Balance of Site	Faecal Lab Upgrade	Faecal Lab Upgrade	Below Threshold - Competitive Tender	Works		11/11/2024	31/03/2025	≥ £100k to <£500k		Gary Armstrong	Hannah Budge
C16843	Site Services	Low Level Waste Effluent Treatment Plant Accommodation Electrical Design	Low Level Waste Effluent Treatment Plant Accommodation Electrical Design	Framework - Further Competition	Services		18/11/2024	31/01/2025	< £100k		Morris Macleod	Lee Parnell
C1122	Site Services	D3000 Switchboard	D3000 Switchboard	Open Procedure	Supplies		18/11/2024	27/06/2025	≥ £100k to <£500k		Morris Macleod	Lee Parnell
C9877	Balance of Site	Area 300 Main Immobilisation Line installation	Area 300 Main Immobilisation Line installation	Below Threshold - Competitive Tender	Works		18/11/2024	09/06/2026	≥ £100k to <£500k		Michael Gray	Sonja Sinclair
C17121	Balance of Site	D1215 Dampers Manufacturing and Delivery	D1215 Dampers Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		25/11/2024	25/04/2025	< £100k		Robert Spence	Lee Parnell
C18809	Site Services	Supply of Cryocooler for D1310	Supply of Cryocooler for D1310	Direct Award - Below Threshold	Supplies		30/11/2024	01/03/2025	< £100k		Jeremy Andrew	Hannah Budge
C1172	Site Services	Repair of Steelwork	Repair of Steelwork	Below Threshold - Competitive Tender	Works		30/11/2024	30/11/2025	≥ £100k to <£500k		Jason Park	Heidi Warner
C1173	Site Services	Design of Steelwork Repair	Design of Steelwork Repair	Framework - Further Competition	Services		30/11/2024	14/03/2025	≥ £100k to <£500k		Jason Park	Heidi Warner
C19455	Site Services	Provision of Grounds Maintenance on the Dounreay Estate	Provision of Grounds Maintenance on the Dounreay Estate	Open Procedure	Services	Re-procurement (same scope)	01/12/2024	30/11/2034	≥ £1m to <£5m	3300008447	Peter Swanson	Kelsey Bain
C13987	Site Services	D3000 Generator	D3000 Generator	Below Threshold - Competitive Tender	Supplies		02/12/2024	09/05/2025	< £100k		Morris Macleod	Lee Parnell
C13986	Site Services	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Below Threshold - Competitive Tender	Services		02/12/2024	30/05/2025	≥ £100k to <£500k		Morris Macleod	Lee Parnell
C12886	Balance of Site	D1215 / D1218 Ventilation System Electrical, Control and Instrumentation	D1215 / D1218 Ventilation System Electrical, Control and Instrumentation	Below Threshold - Competitive Tender	Services		02/12/2024	28/06/2025	< £100k		To be confirmed	Lee Parnell
C12887	Balance of Site	D1215 Glove box Manufacturing and Delivery	D1215 Glove box Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		02/12/2024	27/06/2025	≥ £100k to <£500k		To be confirmed	Lee Parnell
C12893	Balance of Site	D1215 Fit-out and Commissioning of Glovebox and Extract Systems	Electrical, Control and Instrumentation Fit-out and Commissioning of Glovebox and Extract Systems	Open Procedure	Services		02/12/2024	12/12/2025	≥ £100k to <£500k		To be confirmed	Lee Parnell
C12623	EHSSQ	Firefighter and Officer Related Training	Firefighter and Officer Related Training	Open Procedure	Services		02/12/2024	30/11/2029	≥ £500k to <£1m		Richard Berry	Lauren J Mackay
C8637	Balance of Site	Dounreay Cementation Plant Licence Condition 15 and Engineering Substantiation	Dounreay Cementation Plant Licence Condition 15 and Engineering Substantiation	Framework - Further Competition	Services		02/12/2024	19/12/2025	≥ £500k to <£1m		Frank Simmons	Samantha Davidson
C8624	Site Services	Low Level Waste Effluent Treatment Plant Ventilation System Upgrade	Low Level Waste Effluent Treatment Plan Ventilation System Upgrade	Below Threshold - Competitive Tender	Works		09/12/2024	02/05/2025	< £100k		Morris Macleod	Lee Parnell
C12892	Balance of Site	D1215 Panel Build & Factory Acceptance Testing of Panels for Red Extract System	D1215 Panel Build and Factory Acceptance Testing of Panels for Red Extract System	Below Threshold - Competitive Tender	Services		09/12/2024	27/06/2025	< £100k		To be confirmed	Lee Parnell
C12889	Balance of Site	Manufacturing and Delivery of the D1215 Red Extract System Filter Housings	Manufacturing and Delivery of the D1215 Red Extract System Filter Housings	Open Procedure	Services		09/12/2024	01/08/2025	≥ £100k to <£500k		To be confirmed	Lee Parnell
C1246	Balance of Site	The supply of Cameras, Camera Encoders & Server Upgrade & supporting maintenance	- The supply and delivery of Cameras, Camera Encoders and Server Upgrade. / - Maintenance of Titan Vision Control Equipment.	Direct Award - PCR Single Source (Reg 32)	Supplies		01/01/2025	31/12/2029	≥ £1m to <£5m		Douglas Mackenzie	Kelsey Bain
C20502	Site Services	Maintenance of Air Compressors	Maintenance of Air Compressors	Open Procedure	Services	Re-procurement (same scope)	01/01/2025	31/12/2034	≥ £100k to <£500k	3300024069	Laurence Campbell	Kerrie Mackay
C19935	Reactors	Prototype Fast Reactor Water Vapour Nitrogen System and Effluent Pump	A requirement has been identified requiring a Water Vapour Nitrogen injection point to be installed within the Prototype Fast Reactor reactor vessel as an addition to the current installation	Below Threshold - Competitive Tender	Supplies		06/01/2025	28/03/2025	< £100k		James Campbell	Dawn Sewell
C15173	Balance of Site	Reserved Procurement - Air Handling Unit Design	Reserved Procurement - Air Handling Unit Design	Below Threshold - Competitive Tender	Services		13/01/2025	28/03/2025	< £100k		Gary Armstrong	Lee Parnell
C12890	Balance of Site	D1215 Ductwork Manufacturing and Delivery	D1215 Ductwork Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		13/01/2025	30/05/2025	≥ £100k to <£500k		To be confirmed	Lee Parnell
C12897	Balance of Site	D1215 Mechanical Fit-out and Commissioning of Glovebox and extract systems	D1215 Mechanical Fit-out and Commissioning of Glovebox and extract systems	Open Procedure	Services		13/01/2025	19/12/2025	≥ £100k to <£500k		To be confirmed	Lee Parnell
C18787	Site Services	Gamma Spectroscopy Detector	Gamma Spectroscopy Detector	Direct Award - Below Threshold	Supplies		13/01/2025	30/04/2025	≥ £100k to <£500k		Jeremy Andrew	Hannah Budge
C15329	Balance of Site	Shaft & Silo Waste Retrieval System	Procurement of a Silo Retrieval System for the Shaft & Silo programme - Detail Design, Manufacture, Installation & Commissioning,.	Restricted Procedure	Works		15/01/2025	15/01/2031	≥ £10m to <£25m		Grant Coghill	Lee Parnell
C1157	Site Services	Maintenance of Air Compressors	Maintenance of Air Compressors	Open Procedure	Services	Re-procurement (same scope)	01/02/2025	31/01/2029	≥ £100k to <£500k	3300024069	Laurence Campbell	Corrinda Pearson
C20047	Site Services	Maintenance of Air Compressors	Maintenance of Air Compressors	Open Procedure	Services	Re-procurement (same scope)	01/02/2025	31/01/2035	≥ £100k to <£500k	3300032756	Laurence Campbell	Kerrie Mackay
C1222	Reactors	Prototype Fast Reactor Transformers	Prototype Fast Reactor Transformers	Below Threshold - Competitive Tender	Supplies		02/02/2025	31/12/2025	≥ £100k to <£500k		Laurence Campbell	Fraser Bruce
C12385	Balance of Site	Dounreay Cementation Plant Peer Review	Dounreay Cementation Plant Peer Review	Framework - Further Competition	Services		03/02/2025	30/01/2026	< £100k		Frank Simmons	Lesley-Ann Crombie
C20641	EHSSQ	Call-off contract for ambulance training and Learning in Practice days	Call-off contract for ambulance training and Learning in Practice days	Direct Award - Below Threshold	Services		10/02/2025	07/08/2026	< £100k		John Dunnet	Lauren J Mackay
C21099	Reactors	Panel Upgrades	Prototype Fast Reactor Irradiated Fuel Cave Panel Upgrades	Below Threshold - Competitive Tender	Works		18/02/2025	01/09/2025	≥ £100k to <£500k		Hamish Boyd	Robert McDonald
C16547	Site Services	Low Level Waste Pits - Provision of Cover Building	Low Level Waste Pits - Provision of Cover Building	Below Threshold - Competitive Tender	Supplies		03/03/2025	27/06/2025	< £100k		Morris Macleod	Lee Parnell
C15305	Site Services	Low Level Waste Pits - Resurfacing	Low Level Waste Pits - Resurfacing	Below Threshold - Competitive Tender	Works		03/03/2025	30/05/2025	≥ £100k to <£500k		Morris Macleod	Lee Parnell
C21109	Reactors	Painting Accessible Areas of the Sphere	Painting Accessible Areas of the Dounreay Fast Reactor Sphere	Below Threshold - 3 Quotes	Services		11/03/2025	31/07/2025	≥ £100k to <£500k		Chris Wratten	Robert McDonald
C21098	Reactors	Upgrades Prior to Fuel Repackaging	Prototype Fast Reactor Irradiated Fuel Cave Upgrades Prior to Fuel Repackaging (Electrical, Control & Instrumentation Upgrades)	Below Threshold - Competitive Tender	Works		25/03/2025	30/09/2025	≥ £100k to <£500k		Hamish Boyd	Robert McDonald
C14394	Portfolio & Support	Provision of Criticality Software MONK & Visual Workshop	Provision of Criticality Software MONK & Visual Workshop	Direct Award - PCR Single Source (Reg 32)	Services	Re-procurement (same scope)	01/04/2025	31/03/2030	≥ £100k to <£500k	3300031908	Mike Potts	Kelsey Bain
C1150	Site Services	Development of Individual Component Environmental Safety Cases	Development of Individual Component Environmental Safety Cases	Framework - Further Competition	Services		01/04/2025	31/12/2025	< £100k		Adreain Gill	Kelsey Bain
C1149	Site Services	Site Closure and Environmental Restoration - Peer Review	Site Closure and Environmental Restoration - Peer Review	Framework - Further Competition	Services		01/04/2025	31/12/2025	< £100k		Adreain Gill	Kelsey Bain
C1151	Site Services	Low Level Waste Pits - Review and development of the Environmental Safety Case	Low Level Waste Pits - Review and development of the Environmental Safety Case	Framework - Further Competition	Services		01/04/2025	31/03/2026	< £100k		Adreain Gill	Kelsey Bain
C15129	EHSSQ	Supply of Electronic Personal Dosimeters 400no. + 400no.	Supply of Electronic Personal Dosimeters 400no. + 400no.	Direct Award - PCR Single Source (Reg 32)	Supplies		07/04/2025	31/03/2026	≥ £100k to <£500k		Anthony Ridgley	Fraser Bruce
C20814	Capability	Electric Vehicle Charging Off-Site (Design and Installation)	Electric Vehicle Charging Off-Site (Design and Installation)	Below Threshold - Competitive Tender	Works		07/04/2025	03/04/2026	≥ £100k to <£500k		Christopher Simpson	Lauren J Mackay
C20817	Capability	Programme Carbon Consultancy Lifecycle Carbon Assessment	Programme Carbon Consultancy Lifecycle Carbon Assessment	Framework - Further Competition	Services		07/04/2025	02/04/2027	≥ £100k to <£500k		Christopher Simpson	Lauren J Mackay
C20815	Capability	Water Meter Option Study	Water Meter Option Study	Framework - Further Competition	Services		07/04/2025	31/10/2025	< £100k		Emily Kearl	Lauren J Mackay
C1155	Site Services	Supply of Heavy Weight Towing Vehicle	Supply of Heavy Weight Towing Vehicle	Open Procedure	Supplies	Re-procurement (same scope)	01/05/2025	01/04/2026	≥ £100k to <£500k	3300028934	Stephen Mackie	Janet Rosie
C18928	Portfolio & Support	Provision of Lifting Services	Provision of Lifting Services	Framework Agreement – Set up of a new Framework	Services	Re-procurement (same scope)	01/05/2025	30/04/2029	≥ £500k to <£1m	CFA/21/0011	Laurence Campbell	Janet Rosie
C1072	Balance of Site	Shaft and Silo Process Cell and Waste Transfer System	Shaft and Silo Process Cell and Waste Transfer System	Framework - Further Competition	Services		01/05/2025	29/09/2030	≥ £10m to <£25m		Iain Lyall	Kirstin Polson
C17834	People	Provision of Opticians Services	Provision of Opticians Services	Below Threshold - Competitive Tender	Services		01/05/2025	30/04/2030	< £100k		Kirsty McIntosh	Lauren J Mackay
C15131	Portfolio & Support	Framework Agreement for Provision of Design Services (Minor)	Framework Agreement for Provision of Design Services (Minor)	Framework Agreement – Set up of a new Framework	Services	Re-procurement (same scope)	01/05/2025	30/04/2029	≥ £1m to <£5m	CFA/21/0002-0010	Mike Potts	Lesley-Ann Crombie
C19966	People	Outward Bound Experience	Outward Bound Experience	Framework - Further Competition	Services		02/06/2025	20/10/2025	< £100k		Rhona Gill	Lauren J Mackay
C21101	Reactors	Pre Asbestos Clean Up	Prototype Fast Reactor Intermediate Level Waste Size Reduction Facility Pre Asbestos Clean Up	Open Procedure	Services		25/06/2025	30/06/2026	≥ £500k to <£1m		Chris Wratten	Robert McDonald
C18813	Site Services	Dionex Ion Chromatography System (Effluent Lab)	Dionex Ion Chromatography System (Effluent Lab)	Direct Award - Below Threshold	Supplies		30/06/2025	01/09/2025	< £100k		Jeremy Andrew	Hannah Budge
C18812	Site Services	Portable X-Ray Radiography System	Portable X-Ray Radiography System	Below Threshold - Competitive Tender	Supplies		30/06/2025	01/08/2025	< £100k		Jeremy Andrew	Hannah Budge
C1211	Site Services	D1310 - Gas Chromatography - Mass Spectrometer	D1310 - Gas Chromatography - Mass Spectrometer	Below Threshold - Competitive Tender	Supplies		30/06/2025	17/11/2025	≥ £100k to <£500k		Jeremy Andrew	Hannah Budge
C18814	Site Services	Supply of Easycount System for D2176	Supply of Easycount System for D2176	Direct Award - Below Threshold	Supplies		30/06/2025	01/10/2025	≥ £100k to <£500k		Jeremy Andrew	Hannah Budge
C1120	Site Services	Supply of Half Height ISO Low Level Waste Containers Framework Agreement	Framework Agreement for the Supply of Half Height ISO Low Level Waste Containers	Framework Agreement – Set up of a new Framework	Supplies	Re-procurement (same scope)	01/07/2025	30/06/2029	≥ £10m to <£25m	CFA/12/0048 - CFA/12/0049	Alistair Ross	Janet Rosie
C20891	Capability	Maintenance of the Dounreay Data Management System	Maintenance of the Dounreay Data Management System	Framework - Further Competition	Services	Re-procurement (same scope)	01/07/2025	30/06/2029	≥ £1m to <£5m	3300015868	Tracy Alexander	Lesley-Ann Crombie
C11262	Capability	U4BW Software as a Service	Unit4 Business World (U4BW) Software as a Service (SaaS).	Framework - Direct Award	Services	Re-procurement (same scope)	01/07/2025	30/06/2028	≥ £500k to <£1m	3300026361	Amanda Petrie	Lynsey Will
C13988	Site Services	Gravity Receipt Tank Ladder Replacement	Gravity Receipt Tank Ladder Replacement	Below Threshold - Competitive Tender	Works		08/07/2025	08/01/2026	< £100k		Morris Macleod	Lee Parnell
C1142	Balance of Site	Manufacture and Design Ammonium Diuranate Floc Transport Stillage Lifting Beam	Manufacture and Design of Ammonium Diuranate Floc Transport Stillage Lifting Beam	Below Threshold - Competitive Tender	Services		18/07/2025	07/01/2026	≥ £100k to <£500k		Michael Gray	Sonja Sinclair
C1108	FCA	Thorium Nitrate Manufacture, Integrated Works Testing, Installation	Thorium Nitrate Manufacture, Integrated Works Testing, Installation and Commissioning	Framework - Further Competition	Works		01/08/2025	31/05/2026	≥ £500k to <£1m		Ewen Boyd	Dawn Sewell
C1073	FCA	Thorium Nitrate Drums Final Letter of Compliance	Thorium Nitrate Drums Final Letter of Compliance	Framework - Further Competition	Services		01/08/2025	01/05/2026	< £100k		Robert McKiddie	Dawn Sewell
C1252	Finance	Programme Controls Support	Programme Controls Support	Direct Award - PCR Single Source (Reg 32)	Services	Re-procurement (same scope)	11/08/2025	11/08/2028	≥ £500k to <£1m	3300027789	Neil Cook	Ilona Unger-Russell
C1100	FCA	D2001 Irradiated Fuels Containers Manufacture	D2001 Irradiated Fuels Containers Manufacture	Open Procedure	Services		01/09/2025	30/01/2028	≥ £1m to <£5m		Andrew Hamilton	Erica Innes
C9903	Balance of Site	Electrical Control and Instrumentation Services	Electrical Control and Instrumentation Services	Open Procedure	Services		01/09/2025	31/03/2028	≥ £500k to <£1m		Michael Gray	Sonja Sinclair
C9905	Balance of Site	Mechanical Design Services	Mechanical Design Services	Open Procedure	Services		01/09/2025	31/03/2028	≥ £1m to <£5m		Michael Gray	Sonja Sinclair
C13989	Site Services	Break Tank Improvements	Break Tank Improvements	Below Threshold - Competitive Tender	Works		02/09/2025	02/03/2026	< £100k		Morris Macleod	Lee Parnell
C9890	Balance of Site	Stillage Transfer System- Gantry Crane & Frame	Works on the Stillage Transfer System- the Gantry Crane and Frame only	Below Threshold - Competitive Tender	Works		05/09/2025	16/03/2026	≥ £100k to <£500k		Michael Gray	Sonja Sinclair
C9887	Balance of Site	Area 400 Internal Ventilation	To be coordinated with the installation of Area 300 and Area 400 Fan and Filter Rooms	Direct Award - Below Threshold	Works		02/10/2025	10/12/2025	< £100k		Michael Gray	Sonja Sinclair
C9919	Balance of Site	Stillage Transfer System - Changing Room	Stillage Transfer System - Changing Room	Below Threshold - Competitive Tender	Works		06/01/2026	06/04/2026	< £100k		Michael Gray	Sonja Sinclair
C9897	Balance of Site	Stillage Transfer System - Control System Modifications	Control system Modifications design and implementation	Below Threshold - Competitive Tender	Works		15/01/2026	18/03/2026	< £100k		Michael Gray	Sonja Sinclair
C12555	EHSSQ	Purchase of Ambulance	Purchase of Ambulance	Below Threshold - Competitive Tender	Supplies		01/04/2026	31/03/2027	≥ £100k to <£500k		Richard Berry	Debbie Weir
C19142	EHSSQ	Provision of Internal and Criticality Accident Dosimetry Service	Provision of Internal and Criticality Accident Dosimetry Service	Open Procedure	Services	Re-procurement (different scope)	01/04/2026	31/03/2030	≥ £1m to <£5m	3300008206	Anthony Ridgley	Fraser Bruce
C18815	Site Services	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Direct Award - PCR Single Source (Reg 32)	Supplies		01/04/2026	01/08/2026	≥ £100k to <£500k		Jeremy Andrew	Hannah Budge
C19644	Portfolio & Support	Provision of Decommissioning Operatives	Provision of Decommissioning Operatives	Framework Agreement – Set up of a new Framework	Services	Re-procurement (same scope)	01/04/2026	31/03/2031	≥ £25m to <£50m	3300031138	Graeme Dunnett	Robert McDonald
C1239	Balance of Site	65 tonne Bogie Modifications Package	65 tonne Bogie Modifications Package	Below Threshold - Competitive Tender	Works		23/04/2026	25/08/2026	≥ £100k to <£500k		Michael Gray	Sonja Sinclair
C1238	Balance of Site	Lid Lifting Frame and Bedplate Frame Package	Lid Lifting Frame and Bedplate Frame Package	Below Threshold - Competitive Tender	Works		21/05/2026	11/08/2026	< £100k		Michael Gray	Sonja Sinclair