## Cover
Building Safety Remediation Data Release, England: 31 October 2023
Back to Contents
Background
This publication provides data on 1) the remediation progress across DLUHC’s Building Safety Remediation portfolio, covering buildings in the ACM programme, Building Safety Fund, Cladding Safety Scheme, developer remediation contract and reported by registered providers of social housing, 2) Progress with remediation of high-rise (18 metres and over in height) residential buildings (including student accommodation and hotels) and publicly owned buildings with ACM cladding systems unlikely to meet Building Regulations in the ACM programme, 3) the progress of the Waking Watch Relief Fund and Waking Watch Replacement Fund, 4) progress with remediation of high-rise residential buildings with non-ACM cladding systems assessed as eligible for funding from the Building Safety Fund , 5) Progress with the applications for and remediation of medium-rise (11 – 18 metres in height) residential buildings in England and high-rise residential buildings outside of London with non-ACM cladding systems in the Cladding Safety Scheme, 6) progress of remediation of residential buildings 11 metres and over in height with life-safety defects under the developer remediation contract, 7) progress of remediation of residential buildings 11 metres and over in height with life-safety cladding defects reported by registered providers of social housing, 8) enforcement action taken by local authorities against high-rise residential buildings with cladding defects under the Housing Act 2004.
Tables on the ACM programme, BSF, CSS, developer remediation contract and social housing surveys inlcude buildings which can be in multiple schemes so counting across tables can result in double counting. Tab Combined_2 provides an overall summary of all remediation progress.
Publication dates
The data tables in this spreadsheet were originally published on 16 November 2023.
The next publication is scheduled for 21 December 2023.
Useful Information
Further information on the data collection, data quality and definitions is available in the Technical Note published alongside these statistics.
Technical Note
Contact details
BuildingSafetyData2@levellingup.gov.uk
NewsDesk@levellingup.gov.uk
Date published: 16 November 2023

## Table_of_Contents
Building Safety Remediation Data Release Contents
Worksheet Name	Worksheet Title
Cover	Background information about the statistics.
Notes	Notes found in the tables.
ACM_1	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 October 2023
ACM_2	Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 October 2023
ACM_3	Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 October 2023
ACM_4	ACM remediation progress by local authority, England, 31 October 2023
ACM_5	ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 October 2023
ACM_6	ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 October 2023
ACM_7	Number of dwellings in buildings identified with unsafe ACM cladding by remediation status
ACM_8	ACM remediation progress by sources of funding, England, 31 October 2023
ACM_9	Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 October 2023
ACM_10	Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 October 2023
WWRF_1	Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 October 2023
WWRF_2	Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 October 2023
WWRF_3	Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 October 2023
BSF_1	Remediation status of buildings within BSF by tenure, England, 31 October 2023
BSF_2	BSF remediation progress by region, England, 31 October 2023
BSF_3	BSF number of buildings by tenure and funding allocation type, England, 31 October 2023
BSF_4	BSF funding approved and expenditure by tenure, England, 31 October 2023
Combined_1	Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 October 2023
Combined_2	Remediation progress for buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 October 2023
CSS_1	Application status of buildings within the CSS, England, 31 October 2023
CSS_2	CSS remediation progress by region, England, 31 October 2023
CSS_3	CSS remediation progress by height, England, 31 October 2023
CSS_4	CSS remediation progress by tenure, England, 31 October 2023
Social_1	Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 31 October 2023
Developer_1	Remediation status of buildings covered by the developer remediation contracts by height group, England, 31 October 2023
Developer_2	Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 October 2023
Developer_3	Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 October 2023
Developer_4	Developer by developer breakdown of buildings covered by the developer remediation contract, by assessment status, England, 31 October 2023
Developer_5	Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 October 2023
Developer_6	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 October 2023
Developer_7	Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation, by engagement and remediation status, England, 31 October 2023
Enforcement_1	Enforcement action taken by local authorities against high-rise buildings under the Housing Act (2004) by remediation programme status, England, 31 October 2023
Enforcement_2	Building inspections conducted by local authorities, England, 31 October 2023
Enforcement_3	Statutory notices served by local authorities under the Housing Act (2004), England, 31 October 2023
Enforcement_4	Number of building inspections by local authorities supported by the Joint Inspection Team, England, 31 October 2023
JIT_1	Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 October 2023

## Notes
Notes
Back to Contents
Note	Note Explanation	Note Location
[note 1]	Vacant buildings detailed in this table are included in table ACM_1 and ACM_2.	ACM_3
[note 2]	This table excludes local authorities with fewer than 10 high-rise residential buildings, regardless of whether they have unsafe cladding, and groups local authority figures into bands. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	ACM_4, Enforcement_1, Enforcement_2, Enforcement_3, Enforcement_4
[note 3]	Yet to complete remediation includes all dwellings in buildings that are yet to fully complete remediation works, including those that have completed works but are awaiting sign-off from building control where necessary.	ACM_7
[note 4]	Social Sector Fund: Payments are made as cash grants, and will be payable in two tranches. The government will pay 80% of eligible costs at stage one. Once building owners confirm that they have tendered for the removal and replacement of cladding systems and work has started on site, we will make the first payment. Then we will pay the remaining 20% of eligible costs once building owners have submitted further evidence and confirmed final costs.	ACM_8
[note 5]	Private Sector Fund: The majority of private sector buildings receiving government funding for ACM remediation are funded through the Private Sector Cladding Remediation Fund. Payments from the Private Sector Cladding Remediation Fund will be made as cash grants and will be made on the basis of monthly valuations of work carried out on site, with an appropriate degree of due diligence, mirroring industry standard practice. Following Practical Completion the government will withhold a final payment which will be made on completion of the defects liability period.	ACM_8
[note 6]	The approved figure for the Private and Social Sector ACM Cladding Remediation Funds incorporates tendering support for applicants and approved project cost overrun. This figure reflects funding for the costs of remediation of unsafe ACM cladding only.	ACM_10
[note 7]	The Private Sector ACM Cladding Remediation Fund approved funding figure does not yet include any funds that will be reimbursed by developers who have signed the Pledge in relation to buildings they had a role in developing or refurbishing which have received government funding. All eligible applications to the Private Sector ACM Cladding Remediation Fund will be funded.	ACM_10
[note 8]	Expenditure for the Private and Social Sector ACM Cladding Remediation Funds is based on grant payments made by Delivery Partners to the applicant.	ACM_10
[note 9]	Private Sector ACM Cladding Remediation Fund (PSCRF) expenditure includes spend for non-ACM remediation works on buildings with unsafe ACM cladding funded through the PSCRF and therefore can exceed the amount approved which reflects unsafe ACM cladding remediation costs only.	ACM_10
[note 10]	Total figures may not sum due to rounding.	WWRF_1, WWRF_2, WWRF_3, BSF_3, BSF_4, Combined_1
[note 11]	Remediation complete figures in this table include buildings that have completed remediation but are still awaiting building control sign off.	BSF_2
[note 12]	Number of private sector buildings with full applications approved is a subset of those buildings with pre-tender support allocations therefore these numbers cannot be added together to give a total.	BSF_3
[note 13]	This table includes allocation figures for buildings which have only non-ACM cladding and buildings which have both non-ACM and ACM cladding.	BSF_4
[note 14]	For buildings with both ACM and non-ACM cladding in this table, 'Remediation not Started' is assigned for buildings that have not started works on either type of cladding. 'Remediation Started' is assigned for buildings where work has started on remediating at least one type of cladding. 'Remediation complete: awaiting building control sign off' is assigned for buildings that have completed remediation but sign off is required for work on remediating at least one type of cladding. 'Remediation complete' is assigned for buildings that have completed, and received sign off, on works for the remediation of both types of cladding.	Combined_1, Combined_2
[note 15]	Enforcement action is where an inspection under the Housing Act 2004's Housing Health and Safety Rating System has been organised/undertaken, and includes where a statutory notice has also then been served.	Enforcement_1
[note 16]	The Housing Health and Safety Rating System (HHSRS) is a risk-based assessment evaluation tool to help local authorities identify and protect against potential risks and hazards to health and safety from any deficiencies identified in residential premises. Each hazard has a weighting which will help determine whether the building is rated as having risks which are either category 1 or category 2. Where a risk is deemed to be category 1, a local authority has a duty to take enforcement action; where a risk is deemed to be category 2, an authority has the power to take action.	Enforcement_2
[note 17]	The Government-funded Joint inspection Team, hosted by the Local Government Association, provides expert advice to local authorities on enforcement on buildings with unsafe cladding.	Enforcement_4
[note 18]	The number of training sessions for Wandsworth and Richmond are combined as Merton, Wandsworth and Richmond operate a joint service where Merton officers attend training on behalf of Richmond and Wandsworth.	JIT_1
[note 19]	340 buildings confirmed by delivery partners to be transferred to developers have been withdrawn from the Building Safety Fund, this has led to a decrease in the number of eligible buildings in the Fund. The number is expected to increase as more confirmed and transferred out of the fund.	BSF_1, BSF_2
[note 20]	The Building Safety Fund first opened to registrations from June to July 2020. DLUHC received registrations from 3,488 buildings. In July 2022 the Building Safety Fund reopened to new applications.	BSF_1, BSF_2, BSF_3, BSF_4
[note 21]	Some buildings have an unknown remediation status reported by the developer. These have been interpreted as ‘Remediation not started – no plans in place’.	Developer_1
[note 22]	A building is defined as requiring works under the developer remediation contract if it is either self-reported by the developer as requiring works; is an eligible building in the BSF or ACM and the developer has agreed to re-imburse the funds; has had money paid out by the BSF or ACM; or has a self-reported work status of either: works completed, works started, or works not started but plans in place.	Developer_1
[note 23]	51 developers have signed the contract, but only 49 were required to submit a return at 31 October 2023. Estimates are based on the data returns submitted by these 49 developers. Of the 49 developers who were required to submit a return, estimates are based on 40 data returns at 31 October 2023 and 9 data returns at 31 July 2023. These developers have an astrix (*) next to their name in the data table to represent the July data.	Developer_3, Developer_4, Developer_5, Developer_6, Developer_7
[note 24]	This table covers only buildings which have been self-reported by the developer as requiring works under the data return field Does this building require works?.	Developer_3
[note 25]	The row 'Other (combined total for all developers with 5 or fewer buildings each' summarises information of 11 developers with five or fewer buildings, this includes: Allison Homes, Bloor, CG Fry, Courdace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata and William Davis. This data has been supressed due to the number of buildings and is represented in the data with a dash and two asterisks (-**) in the data.	Developer_3, Developer_4, Developer_5, Developer_6, Developer_7
[note 26]	A building is interpreted as having an assessment if one or more of the following fields show as 'Yes' in the developer data return: Have you carried out an assessment of whether External Wall System (EWS) works are required on this building?; Have you carried out an assessment of whether non-EWS (other fire safety defects) works are required on this building?; Does the Building have an FSA?; Does the Building have an FRAEW?; and Does this building require works?	Developer_4
[note 27]	One developer is not required to report assessments in this section.	Developer_3
[note 28]	The data here is comprised of 'Don't know' and blanks in response to the field 'Does this building require works?'	Developer_3
[note 29]	The total estimated cost of remediation is based on the actual or estimated cost reported by developers, and an assumed average where a cost has not been reported (averages are based on the developer-reported costs, by height).	Developer_2
[note 30]	Data is taken from The Fire Safety Remediation Survey (FRS) for 11 metre plus buildings, which opened to all landlords on 23 August 2023 and closed on 15 September 2023. / Where landlords are the responsible entity, they were asked to provide information on any life critical fire safety (LCFS) defects, which the survey defined as defects, shrinkages, faults or other failings in a building that give rise to fire safety risks. These are identified by: / 1) a Fire Risk Appraisal of External Wall construction (FRAEW) undertaken in accordance with PAS 9980 that assesses the external wall construction or cladding as not “medium - tolerable” (or better); or / 2) a fire risk assessment (FRA) that assesses the relevant parts of the building as high risk or medium risk or equivalent according to industry standards.	Social_1

## ACM_1
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Tenure	Number of buildings this month	Number of buildings last month	Monthly change
Social sector residential	161	161	0
Private sector residential	237	234	3
Student accommodation	58	58	0
Hotels	31	31	0
Publicly-owned buildings	8	8	0
Total buildings	495	492	3

## ACM_2
Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Completed Remediation	123	76%	165	70%	50	86%	24	77%	7	88%	369	75%
Works complete awaiting building control signoff	18	11%	29	12%	3	5%	3	10%	0	0%	53	11%
Remediation started - cladding removed	19	12%	15	6%	2	3%	2	6%	0	0%	38	8%
Remediation started	1	1%	10	4%	0	0%	1	3%	1	13%	13	3%
Remediation plans in place	0	0%	14	6%	1	2%	0	0%	0	0%	15	3%
Reported an intent to remediate	0	0%	0	0%	2	3%	1	3%	0	0%	3	1%
Remediation plan unclear	0	0%	4	2%	0	0%	0	0%	0	0%	4	1%
Total buildings	161	100%	237	100%	58	100%	31	100%	8	100%	495	100%

## ACM_3
Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 October 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff - Vacant	0	3	1	0	0
Remediation started - cladding removed - Vacant	0	1	0	0	0
Remediation started - Vacant	0	0	0	0	0
Remediation plans in place - Vacant	0	1	0	0	0
Reported an intent to remediate - Vacant	0	0	0	1	0
Remediation plan unclear - Vacant	0	0	0	0	0
Total vacant buildings	0	5	1	1	0

Remediation Category for occupied buildings	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff	18	26	2	3	0
Remediation started - cladding removed	19	14	2	2	0
Remediation started	1	10	0	1	1
Remediation plans in place	0	13	1	0	0
Reported an intent to remediate	0	0	2	0	0
Remediation plan unclear	0	4	0	0	0
Total occupied buildings	38	67	7	6	1

## ACM_4
ACM remediation progress by local authority, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_2]	Number of buildings identified with ACM cladding systems (unlikely to meet Building Regulations)	Number of buildings with ACM cladding systems (unlikely to meet Building Regulations) yet to be remediated	Percentage of buildings with ACM cladding systems completed remediation	Percentage of buildings with ACM cladding systems started or completed remediation
Barking and Dagenham	1 to 5	1 to 5	Between 50% and 99%	100%
Barnet	6 to 10	1 to 5	Less than 50%	Between 50% and 99%
Bedford	1 to 5	None	100%	100%
Birmingham	6 to 10	1 to 5	Between 50% and 99%	100%
Bournemouth, Christchurch and Poole	1 to 5	1 to 5	Less than 50%	100%
Bradford	1 to 5	None	100%	100%
Brent	11 to 20	11 to 20	Less than 50%	Between 50% and 99%
Brighton and Hove	1 to 5	None	100%	100%
Bristol, City of	6 to 10	None	100%	100%
Bromley	1 to 5	1 to 5	Less than 50%	100%
Calderdale	1 to 5	None	100%	100%
Camden	6 to 10	6 to 10	Less than 50%	Between 50% and 99%
City of London	1 to 5	None	100%	100%
Croydon	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Dacorum	1 to 5	None	100%	100%
Doncaster	1 to 5	None	100%	100%
Ealing	1 to 5	1 to 5	Between 50% and 99%	100%
Elmbridge	1 to 5	None	100%	100%
Gateshead	1 to 5	None	100%	100%
Greenwich	Over 20	1 to 5	Between 50% and 99%	100%
Hackney	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Hammersmith and Fulham	6 to 10	1 to 5	Between 50% and 99%	100%
Haringey	6 to 10	1 to 5	Between 50% and 99%	100%
Harrow	1 to 5	1 to 5	Between 50% and 99%	100%
Havering	1 to 5	None	100%	100%
Hillingdon	1 to 5	None	100%	100%
Hounslow	1 to 5	None	100%	100%
Islington	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Kensington and Chelsea	1 to 5	None	100%	100%
Kingston upon Thames	1 to 5	None	100%	100%
Kirklees	1 to 5	1 to 5	Less than 50%	100%
Lambeth	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Leeds	6 to 10	None	100%	100%
Leicester	1 to 5	None	100%	100%
Lewisham	1 to 5	1 to 5	Between 50% and 99%	100%
Lincoln	1 to 5	None	100%	100%
Liverpool	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Luton	1 to 5	1 to 5	Less than 50%	100%
Manchester	Over 20	6 to 10	Between 50% and 99%	100%
Medway	1 to 5	None	100%	100%
Merton	1 to 5	None	100%	100%
Milton Keynes	1 to 5	1 to 5	Less than 50%	100%
Newcastle upon Tyne	6 to 10	None	100%	100%
Newham	Over 20	1 to 5	Between 50% and 99%	100%
Norwich	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Nottingham	6 to 10	1 to 5	Between 50% and 99%	100%
Oldham	1 to 5	None	100%	100%
Plymouth	1 to 5	None	100%	100%
Portsmouth	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Reading	1 to 5	1 to 5	Between 50% and 99%	100%
Redbridge	1 to 5	None	100%	100%
Salford	Over 20	11 to 20	Between 50% and 99%	100%
Sandwell	1 to 5	None	100%	100%
Sefton	1 to 5	None	100%	100%
Sheffield	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Slough	1 to 5	1 to 5	Between 50% and 99%	100%
Southwark	11 to 20	6 to 10	Between 50% and 99%	Between 50% and 99%
Stockton-on-Tees	1 to 5	None	100%	100%
Sunderland	1 to 5	None	100%	100%
Sutton	1 to 5	1 to 5	Between 50% and 99%	100%
Tower Hamlets	Over 20	11 to 20	Between 50% and 99%	Between 50% and 99%
Trafford	1 to 5	1 to 5	Less than 50%	100%
Waltham Forest	1 to 5	None	100%	100%
Wandsworth	11 to 20	1 to 5	Between 50% and 99%	100%
Westminster	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Windsor and Maidenhead	1 to 5	None	100%	100%
Wolverhampton	1 to 5	None	100%	100%

## ACM_5
ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 October 2023
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Greater Manchester	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	33	70%	7	39%	5	100%	1	50%	0	0%	46	64%
Works complete awaiting building control signoff	5	11%	6	33%	0	0%	0	0%	0	0%	11	15%
Remediation started - cladding removed	9	19%	3	17%	0	0%	1	50%	0	0%	13	18%
Remediation started	0	0%	2	11%	0	0%	0	0%	0	0%	2	3%
Plans in place	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	47	100%	18	100%	5	100%	2	100%	0	0%	72	100%

London	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	58	71%	122	74%	9	69%	11	73%	0	0%	200	72%
Works complete awaiting building control signoff	13	16%	10	6%	2	15%	2	13%	0	0%	27	10%
Remediation started - cladding removed	10	12%	10	6%	1	8%	1	7%	0	0%	22	8%
Remediation started	1	1%	8	5%	0	0%	1	7%	1	100%	11	4%
Plans in place	0	0%	11	7%	1	8%	0	0%	0	0%	12	4%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	4	2%	0	0%	0	0%	0	0%	4	1%
Total buildings	82	100%	165	100%	13	100%	15	100%	1	100%	276	100%

Rest of England	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	32	100%	36	67%	36	90%	12	86%	7	100%	123	84%
Works complete awaiting building control signoff	0	0%	13	24%	1	3%	1	7%	0	0%	15	10%
Remediation started - cladding removed	0	0%	2	4%	1	3%	0	0%	0	0%	3	2%
Remediation started	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Plans in place	0	0%	3	6%	0	0%	0	0%	0	0%	3	2%
Responded with intent	0	0%	0	0%	2	5%	1	7%	0	0%	3	2%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	32	100%	54	100%	40	100%	14	100%	7	100%	147	100%

## ACM_6
ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 October 2023
Back to Contents
This worksheet contains four tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Identified by 31 December 2019	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	118	77%	147	79%	49	94%	22	81%	7	88%	343	80%
Works complete awaiting building control signoff	17	11%	22	12%	2	4%	2	7%	0	0%	43	10%
Remediation started - cladding removed	19	12%	9	5%	1	2%	2	7%	0	0%	31	7%
Remediation started	0	0%	6	3%	0	0%	0	0%	1	13%	7	2%
Plans in place	0	0%	3	2%	0	0%	0	0%	0	0%	3	1%
Responded with intent	0	0%	0	0%	0	0%	1	4%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	154	100%	187	100%	52	100%	27	100%	8	100%	428	100%

Identified by 31 December 2020	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	119	76%	161	76%	50	93%	23	79%	7	88%	360	78%
Works complete awaiting building control signoff	18	12%	25	12%	3	6%	3	10%	0	0%	49	11%
Remediation started - cladding removed	19	12%	12	6%	1	2%	2	7%	0	0%	34	7%
Remediation started	0	0%	9	4%	0	0%	0	0%	1	13%	10	2%
Plans in place	0	0%	5	2%	0	0%	0	0%	0	0%	5	1%
Responded with intent	0	0%	0	0%	0	0%	1	3%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	156	100%	212	100%	54	100%	29	100%	8	100%	459	100%

Identified by 31 December 2021	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	122	76%	163	72%	50	89%	24	77%	7	88%	366	76%
Works complete awaiting building control signoff	18	11%	27	12%	3	5%	3	10%	0	0%	51	11%
Remediation started - cladding removed	19	12%	14	6%	2	4%	2	6%	0	0%	37	8%
Remediation started	1	1%	10	4%	0	0%	1	3%	1	13%	13	3%
Plans in place	0	0%	12	5%	1	2%	0	0%	0	0%	13	3%
Responded with intent	0	0%	0	0%	0	0%	1	3%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	160	100%	226	100%	56	100%	31	100%	8	100%	481	100%

All buildings identified	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	123	76%	165	70%	50	86%	24	77%	7	88%	369	75%
Works complete awaiting building control signoff	18	11%	29	12%	3	5%	3	10%	0	0%	53	11%
Remediation started - cladding removed	19	12%	15	6%	2	3%	2	6%	0	0%	38	8%
Remediation started	1	1%	10	4%	0	0%	1	3%	1	13%	13	3%
Plans in place	0	0%	14	6%	1	2%	0	0%	0	0%	15	3%
Responded with intent	0	0%	0	0%	2	3%	1	3%	0	0%	3	1%
Remediation plan unclear	0	0%	4	2%	0	0%	0	0%	0	0%	4	1%
Total buildings	161	100%	237	100%	58	100%	31	100%	8	100%	495	100%

## ACM_7
Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, 31 October 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed	9,100	12,900	15,400	22,000	24,500
Yet to complete remediation [note_3]	2,700	6,400	7,400	9,100	10,100
Occupied and yet to complete remediation	2,700	6,300	7,200	9,000	9,900

Leasehold dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed	2,600	12,900	15,400	15,500	18,000
Yet to complete remediation [note_3]	700	6,400	7,400	7,100	8,100
Occupied and yet to complete remediation	700	6,300	7,200	7,000	7,900

## ACM_8
ACM remediation progress by sources of funding, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	In social fund / [note_4]	Not in social fund	Private: government funded / [note_5]	Private: not government funded
Remediation completed	116	7	65	100
Works complete awaiting building control signoff	18	0	18	11
Remediation started - cladding removed	9	10	12	3
Remediation started	1	0	9	1
Plans in place	0	0	11	3
Responded with intent	0	0	0	0
Remediation plan unclear	0	0	0	4
Total	144	17	115	122

## ACM_9
Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Category	Number of buildings inside London	Number of buildings outside London
No contact with delivery partners	0	0
Preparing application	0	0
Eligibility application submitted	0	0
Eligibility approved	3	0
Applications approved: for pre-contract support	3	1
Full cost application submitted	0	0
Applications approved: for full costs	65	39
Total	71	40

## ACM_10
Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Funding	Social Sector / (£ million)	Private Sector / (£ million)
Approved [note_6, note_7]	292	230
Expenditure [note_8, note_9]	270	261

## WWRF_1
Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 October 2023
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Tranche	Applications	Buildings	Approved Applications	Approved Buildings	Leasehold dwellings in approved buildings	Approved Funding / (£ million)	Mean Waking Watch cost per month per dwelling in approved buildings / (£)	Median Waking Watch cost per month per dwelling in approved buildings / (£)	Buildings with alarm installation complete
Waking Watch Relief Fund	329	468	212	320	24,700	27.3	169	104	289
Waking Watch Replacement Fund	38	67	25	47	2,200	2.4	216	210	41
Total [note_10]	367	535	237	367	26,900	29.7	172	106	330

## WWRF_2
Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 October 2023
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Buildings	Approved Buildings	Approved Funding / (£ million)
Birmingham	9	8	1	0	0	9	8	1.6
Bristol	3	2	1	0	0	3	2	0.1
Greater London Authority	110	65	29	16	0	171	111	8.3
Greater Manchester Combined Authority	25	20	5	0	0	38	33	2.5
Leeds	10	9	0	1	0	12	11	1.8
Liverpool	18	17	1	0	0	19	18	1.7
Newcastle	3	3	0	0	0	3	3	0.4
Sheffield	6	5	0	1	0	7	6	0.5
DLUHC (1st tranche)	35	21	14	0	0	55	39	2.7
DLUHC (2nd tranche)	60	27	32	1	0	70	34	3.8
DLUHC (3rd tranche)	50	35	14	1	0	81	55	3.9
Total [note_10]	329	212	97	20	0	468	320	27.3

## WWRF_3
Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 October 2023
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Buildings	Approved Buildings	Approved Funding (£m)
Birmingham	2	2	0	0	0	4	4	0.4
DLUHC	25	21	1	3	0	46	40	1.8
Greater Manchester Combined Authority	11	2	9	0	0	17	3	0.2
Leeds	0	0	0	0	0	0	0	0
Liverpool	0	0	0	0	0	0	0	0
Sheffield	0	0	0	0	0	0	0	0
Total [note_10]	38	25	10	3	0	67	47	2.4

## BSF_1
Remediation status of buildings within BSF by tenure, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 20].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note 19]	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)
Remediation complete	22	13%	102	13%
Remediation complete: awaiting building control sign-off	11	7%	64	8%
Remediation started	66	40%	194	24%
Remediation not yet started	64	39%	453	56%
Total buildings	163	100%	813	100%

## BSF_2
BSF remediation progress by region, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 20].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note 19]	Eligible Buildings in the BSF / Number	Not Started Remediation / Number	Started Remediation / Number	Completed Remediation [note_11] / Number	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible BSF buildings that have started or completed remediation / Percentage (%)
North West	139	63	45	31	22%	55%
London	581	333	146	102	18%	43%
East of England	28	14	7	7	25%	50%
East Midlands	29	18	7	4	14%	38%
North East	14	11	1	2	14%	21%
South East	72	25	20	27	38%	65%
South West	33	22	7	4	12%	33%
West Midlands	21	11	7	3	14%	48%
Yorkshire and The Humber	59	20	20	19	32%	66%
Total	976	517	260	199	20%	47%

## BSF_3
BSF number of buildings by tenure and funding allocation type, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 20].
Some cells in this table are empty because data was not available for these variables.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Funding Allocation [note_10, note_12]	Private Sector Residential / Number	Social Sector Residential / Number
Full Applications Approved	424
Pre-Tender Support Allocations	671
Total		101

## BSF_4
BSF funding approved and expenditure by tenure, England, 31 October 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are GBP £ million.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 20].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Some cells in this table are empty because data was not available for these variables.
Table BSF_4a: Amount of funding allocated by funding type and tenure for buildings eligible for the BSF.
Funding Allocations [note_10, note_13]	Private Sector Residential / (£ millions)	Social Sector Residential / (£ millions)	Total / (£ millions)
Full Applications Approved	1,712		1,712
Pre-Tender Support Allocations	253		253
Total	2,092	205	2,297

Table BSF_4b: Amount of expenditure from the BSF by tenure.
Expenditure [note_10]	Private Sector Residential / (£ millions)	Social Sector Residential / (£ millions)	Total / (£ millions)
	1,112	147	1,259

## Combined_1
Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_14]	ACM cladding only / Number	ACM cladding only / Percentage (%)	Non-ACM cladding only in the BSF / Number	Non-ACM cladding only in the BSF / Percentage (%)	Both ACM and non-ACM cladding in the BSF / Number	Both ACM and non-ACM cladding in the BSF / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation completed	314	79%	95	11%	27	28%	436	32%
Works complete awaiting building control signoff	45	11%	67	8%	10	10%	122	9%
Remediation started	29	7%	235	27%	51	52%	315	23%
Remediation not started	9	2%	481	55%	10	10%	500	36%
Total	397	100%	878	100%	98	100%	1,373	100%

## Combined_2
Remediation progress for buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_14]	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	703	19%
Remediation underway	809	21%
In programme	2,285	60%
Total	3,797	100%

## CSS_1
Application status of buildings within the CSS, England, 31 October 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Application category for pre-eligible buildings	Number	Percentage (%)
Pre - application	429	46%
Initial Application	395	42%
FRAEW	46	5%
Eligibility in review	68	7%
Total pre-eligible buildings	938	100%

Application category for eligible buildings	Number	Percentage (%)
GFA	42	88%
Pre - works package	1	2%
Works package	5	10%
Works started	0	0%
Works completed	0	0%
Total eligible buildings	48	100%

## CSS_2
CSS remediation progress by region, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region	Eligible Buildings in the CSS / Number	Not Started Remediation / Number	Started Remediation / Number	Completed Remediation / Number	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible CSS buildings that have started or completed remediation / Percentage (%)
North West	6	6	0	0	0%	0%
London	18	18	0	0	0%	0%
East of England	8	8	0	0	0%	0%
East Midlands	3	3	0	0	0%	0%
North East	0	0	0	0	0%	0%
South East	5	5	0	0	0%	0%
South West	4	4	0	0	0%	0%
West Midlands	0	0	0	0	0%	0%
Yorkshire and The Humber	4	4	0	0	0%	0%
Total	48	48	0	0	0%	0%

## CSS_3
CSS remediation progress by height, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)
Remediation complete	0	0%	0	0%
Remediation started	0	0%	0	0%
In programme	43	100%	5	100%
Total buildings	43	100%	5	100%

## CSS_4
CSS remediation progress by tenure, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)
Remediation complete	0	0%	0	0%
Remediation started	0	0%	0	0%
In programme	6	100%	42	100%
Total buildings	6	100%	42	100%

## Developer_1
Remediation status of buildings requiring works under the developer remediation contract by height group, England, 31 October 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - All Defect Types [Note_21, Note_22]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	96	18%	166	21%	262	20%
Remediation started	62	11%	149	19%	211	16%
Remediation not Started - Plans in Place	241	44%	265	33%	506	38%
Remediation not Started - No Plans in Place	145	27%	218	27%	363	27%
Total buildings	544	100%	798	100%	1342	100%

Remediation Category - Cladding Defects [Note_21, Note_22]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	80	16%	164	21%	244	19%
Remediation started	54	11%	146	19%	200	16%
Remediation not Started - Plans in Place	224	46%	253	33%	477	38%
Remediation not Started - No Plans in Place	134	27%	215	28%	349	27%
Total buildings	492	100%	778	100%	1270	100%

## Developer_2
Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for estimated cost of buildings identified as requiring works under the Developer Remediation Contract in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Cost Category [Note_29]	11-18m / (£ millions)	18m+ / (£ millions)	Total / (£ millions)
Total estimated cost of works	588	2,151	2,739

## Developer_3
Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_23] [Note_25]	Number of buildings for which the developer has accepted responsibility under the contract	Number of buildings assessed and found to require remediation [Note_24]	Number of buildings assessed and found to require remediation, and which will be remediated by the developer directly (rather than being remediated through a government fund, with cost re-imbursed by developer)	Number of buildings where it is not known whether remediation is required [Note 28]
Allison Homes Group Limited	- **	- **	- **	- **
Viva Midco Limited (Avant Homes)	53	0	0	53
Ballymore Limited	85	32	17	1
Barratt Developments PLC	708	128	116	-
Bellway PLC	502	195	170	245
The Berkeley Holdings Group PLC	815	68	57	-
Bewley Group Limited	9	2	0	-
Bloor Investments Limited	- **	-**	-**	-**
The British Land Company PLC*	16	2	2	-
Cala Group (Holdings) Limited	26	1	1	3
Canary Wharf Group PLC	13	0	0	9
C.G. Fry and Son Limited*	-	-	-	-
Churchill Retirement PLC	8	0	0	8
Crest Nicholson Holdings PLC	282	116	110	152
Croudace Homes Group Limited	-**	-**	-**	-**
Dandara Living Holdings Limited	24	19	13	-
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-**	-**	-**	-**
Fairview Holdings Limited	136	53	50	8
Frasers Property (UK) Ltd*	23	0	0	-
Galliard Group Limited	96	16	16	65
MJ Gleeson PLC	17	8	7	9
Grosvenor Group Limited	17	2	2	1
Hill Holdings Limited*	87	3	3	2
Hopkins Home Group Limited*	-**	-**	-**	-**
Jelson Holdings Limited	7	3	3	4
Keepmoat Limited	- **	-**	-**	-**
Land Securities Group PLC	43	4	3	23
Lendlease Europe Holdings Limited	94	15	14	46
Lifestory Holdings Limited (also covers Anthology Group)	18	1	1	-
London Square Development (Holdings) Limited	43	0	0	-
McCarthy & Stone Limited	61	12	12	15
Miller Homes Limited	36	17	17	19
Morgan Sindall Group PLC (parent company for Lovell and Muse)	119	13	13	9
Morris Homes Group Limited	6	2	2	-
Persimmon Public Limited Company	64	42	35	5
Redrow PLC	120	43	29	77
Regal Holdco Limited (parent company for Regal London)	15	1	1	-
Rowland Group Limited*	- **	-**	-**	-**
Rydon Group Holdings Limited	25	14	11	-
Sorbon Group Limited (parent company for Shanly Homes)*	25	5	5	12
St Modwen Group Holdings Company Limited*	13	3	0	-
Story Homes Limited	-**	-**	-**	-**
Strata Homes Group Limited	-**	-**	-**	-**
Taylor Wimpey PLC	384	171	164	3
Telford Homes Limited	148	61	50	81
Tilia Homes Limited*	8	5	5	3
Vistry Group PLC	288	85	80	27
Weston Group PLC	88	21	21	10
Broadthorpe Limited (parent company for William Davis Homes)	-**	-**	-**	-**
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	18	3 [Note_27]	2 [Note_27]	5 [Note_27]
Total	4,540	1,166	1,032	895

## Developer_4
Developer by developer breakdown of buildings covered by the developer remediation contract, by assessment status, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_23] [Note_25]	Progress with assessments
	Buildings that…
	…have had an Assessment [Note 26]		…have not had an assessment [Note 26]		…have been assessed and confirmed to require remediation
Allison Homes Group Limited	-**	-**	-**	-**	-**	-**
Viva Midco Limited (Avant Homes)	9	17%	44	83%	0	-
Ballymore Limited	72	85%	13	15%	32	38%
Barratt Developments PLC	457	65%	251	35%	128	18%
Bellway PLC	274	55%	228	45%	195	39%
The Berkeley Holdings Group PLC	755	93%	60	7%	68	8%
Bewley Group Limited	9	100%	0	0%	2	22%
Bloor Investments Limited	-**	-**	-**	-**	-**	-**
The British Land Company PLC*	16	100%	0	0%	2	13%
Cala Group (Holdings) Limited	8	31%	18	69%	1	4%
Canary Wharf Group PLC	13	100%	0	0%	0	-
C.G. Fry and Son Limited*	-**	-**	-**	-**	-**	-**
Churchill Retirement PLC	8	100%	0	0%	0	-
Crest Nicholson Holdings PLC	140	50%	142	50%	116	41%
Croudace Homes Group Limited	-**	-**	-**	-**	-**	-**
Dandara Living Holdings Limited	21	88%	3	13%	19	79%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-**	-**	-**	-**	-**	-**
Fairview Holdings Limited	136	100%	0	0%	53	39%
Frasers Property (UK) Ltd*	10	43%	13	57%	0	-
Galliard Group Limited	75	78%	21	22%	16	17%
MJ Gleeson PLC	14	82%	3	18%	8	47%
Grosvenor Group Limited	9	53%	8	47%	2	12%
Hill Holdings Limited*	75	86%	12	14%	3	3%
Hopkins Home Group Limited*	-**	-**	-**	-**	-**	-**
Jelson Holdings Limited	7	100%	0	0%	3	43%
Keepmoat Limited	-**	-**	-**	-**	-**	-**
Land Securities Group PLC	17	40%	26	60%	4	9%
Lendlease Eurpoe Holdings Limited	72	77%	22	23%	15	16%
Lifestory Holdings Limited (also covers Anthology Group)	18	100%	0	0%	1	6%
London Square Development (Holdings) Limited	43	100%	0	0%	0	-
McCarthy & Stone Limited	61	100%	0	0%	12	20%
Miller Homes Limited	33	92%	3	8%	17	47%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	112	94%	7	6%	13	11%
Morris Homes Group Limited	6	100%	0	0%	2	33%
Persimmon Public Limited Company	61	95%	3	5%	42	66%
Redrow PLC	120	100%	0	0%	43	36%
Regal Holdco Limited (parent company for Regal London)	15	100%	0	0%	1	7%
Rowland Group Limited*	-**	-**	-**	-**	-**	-**
Rydon Group Holdings Limited	25	100%	0	0%	14	56%
Sorbon Group Limited (parent company for Shanly Homes)*	16	64%	9	36%	5	20%
St Modwen Group Holdings Company Limited*	8	62%	5	38%	3	23%
Story Homes Limited	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-
Taylor Wimpey PLC	257	67%	127	33%	171	45%
Telford Homes Limited	75	51%	73	49%	61	41%
Tilia Homes Limited*	6	75%	2	25%	5	63%
Vistry Group PLC	119	41%	169	59%	85	30%
Weston Group PLC	78	89%	10	11%	21	24%
Broadthorpe Limited (parent company for William Davis Homes)	-**	-**	-**	-**	-**	-**
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	13	100%	4	24%	3	100%
Total	3,263	72%	1,277	28%	1,166	26%

## Developer_5
Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_23] [Note_25]	Remediation Status
	Proportion of buildings being remediated by the developer directly where remediation is...
	…not yet started		…started		…complete
Allison Homes Group Limited	-**	-**	-**	-**	-**	-**
Viva Midco Limited (Avant Homes)	-	-	-	-	-	-
Ballymore Limited	8	47%	2	12%	7	41%
Barratt Developments PLC	74	64%	21	18%	21	18%
Bellway PLC	122	72%	37	22%	11	6%
The Berkeley Holdings Group PLC	15	26%	8	14%	34	60%
Bewley Group Limited	-	-	-	-	-	-
Bloor Investments Limited	-**	-**	-**	-**	-**	-**
The British Land Company PLC*	2	100%	0	0%	0	0%
Cala Group (Holdings) Limited	1	100%	0	0%	0	0%
Canary Wharf Group PLC	-	-	-	-	-	-
C.G. Fry and Son Limited*	-**	-**	-**	-**	-**	-**
Churchill Retirement PLC	-	-	-	-	-	-
Crest Nicholson Holdings PLC	99	90%	7	6%	4	4%
Croudace Homes Group Limited	-**	-**	-**	-**	-**	-**
Dandara Living Holdings Limited	0	0%	13	100%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-**	-**	-**	-**	-**	-**
Fairview Holdings Limited	28	56%	9	18%	13	26%
Frasers Property (UK) Ltd*	-	-	-	-	-	-
Galliard Group Limited	4	25%	1	6%	11	69%
MJ Gleeson PLC	7	100%	0	0%	0	0%
Grosvenor Group Limited	1	50%	1	50%	0	0%
Hill Holdings Limited*	2	67%	1	33%	0	0%
Hopkins Home Group Limited*	-**	-**	-**	-**	-**	-**
Jelson Holdings Limited	3	100%	0	0%	0	0%
Keepmoat Limited	-**	-**	-**	-**	-**	-**
Land Securities Group PLC	3	100%	0	0%	0	0%
Lendlease Eurpoe Holdings Limited	12	86%	2	14%	0	0%
Lifestory Holdings Limited (also covers Anthology Group)	1	100%	0	0%	0	0%
London Square Development (Holdings) Limited	-	-	-	-	-	-
McCarthy & Stone Limited	9	75%	1	8%	2	17%
Miller Homes Limited	12	71%	0	0%	5	29%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	10	77%	2	15%	1	8%
Morris Homes Group Limited	0	0%	2	100%	0	0%
Persimmon Public Limited Company	33	94%	2	6%	0	0%
Redrow PLC	22	76%	5	17%	2	7%
Regal Holdco Limited (parent company for Regal London)	0	0%	0	0%	1	100%
Rowland Group Limited*	-**	-**	-**	-**	-**	-**
Rydon Group Holdings Limited	2	18%	7	64%	2	18%
Sorbon Group Limited (parent company for Shanly Homes)*	5	100%	0	0%	0	0%
St Modwen Group Holdings Company Limited*	-	-	-	-	-	-
Story Homes Limited	-**	-**	-**	-**	-**	-**
Strata Homes Group Limited	-**	-**	-**	-**	-**	-**
Taylor Wimpey PLC	114	70%	11	7%	39	24%
Telford Homes Limited	50	100%	0	0%	0	0%
Tilia Homes Limited*	5	100%	0	0%	0	0%
Vistry Group PLC	77	96%	3	4%	0	0%
Weston Group PLC	15	71%	6	29%	0	0%
Broadthorpe Limited (parent company for William Davis Homes)	-**	-**	-**	-**	-**	-**
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	1	50%	1	50%	0	0%
Total	737	71%	142	14%	153	15%

## Developer_6
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_23] [Note_25]	Buildings that require remediation by the developer which have not yet started, with a start date…

	...at all		…within the next 12 months
Allison Homes Group Limited	-**	-**	-**	-**
Viva Midco Limited (Avant Homes)	-	-	-	-
Ballymore Limited	2	25%	2	25%
Barratt Developments PLC	73	99%	44	59%
Bellway PLC	88	72%	23	19%
The Berkeley Holdings Group PLC	14	93%	14	93%
Bewley Group Limited	-	-	-	-
Bloor Investments Limited	-**	-**	-**	-**
The British Land Company PLC*	2	100%	1	50%
Cala Group (Holdings) Limited	0	0%	0	0%
Canary Wharf Group PLC	-	-	-	-
C.G. Fry and Son Limited*	-**	-**	-**	-**
Churchill Retirement PLC	-	-	-	-
Crest Nicholson Holdings PLC	95	96%	84	85%
Croudace Homes Group Limited	-**	-**	-**	-**
Dandara Living Holdings Limited	-	-	-	-
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-**	-**	-**	-**
Fairview Holdings Limited	23	82%	18	64%
Frasers Property (UK) Ltd*	-	-	-	-
Galliard Group Limited	4	100%	4	100%
MJ Gleeson PLC	4	57%	4	57%
Grosvenor Group Limited	0	0%	0	0%
Hill Holdings Limited*	0	0%	0	0%
Hopkins Home Group Limited*	-**	-**	-**	-**
Jelson Holdings Limited	0	0%	0	0%
Keepmoat Limited	-**	-**	-**	-**
Land Securities Group PLC	0	0%	0	0%
Lendlease Europe Holdings Limited	7	58%	3	25%
Lifestory Holdings Limited (also covers Anthology Group)	1	100%	1	100%
London Square Development (Holdings) Limited	-	-	-	-
McCarthy & Stone Limited	1	11%	0	0%
Miller Homes Limited	11	92%	6	50%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	7	70%	7	70%
Morris Homes Group Limited	-	-	-	-
Persimmon Public Limited Company	32	97%	29	88%
Redrow PLC	22	100%	15	68%
Regal Holdco Limited (parent company for Regal London)	-	-	-	-
Rowland Group Limited*	-**	-**	-**	-**
Rydon Group Holdings Limited	0	0%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)*	2	40%	0	0%
St Modwen Group Holdings Company Limited*	-	-	-	-
Story Homes Limited	-**	-**	-**	-**
Strata Homes Group Limited	-**	-**	-**	-**
Taylor Wimpey PLC	102	89%	95	83%
Telford Homes Limited	18	36%	7	14%
Tilia Homes Limited*	5	100%	0	0%
Vistry Group PLC	60	78%	39	51%
Weston Group PLC	15	100%	5	33%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	0	0%	0	0%
Total	588	80%	401	54%

## Developer_7
Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation, by engagement and remediation status, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_23] [Note_25]	where the developer or ‘responsible entity’ has engaged with the leaseholders, freeholders, residents, occupiers or other users regarding works for…
	…buildings requiring works, including those that have completed remediation	…buildings requiring works, excluding those that have completed remediation
Allison Homes Group Limited	-**	-**
Viva Midco Limited (Avant Homes)	-	-
Ballymore Limited	65%	40%
Barratt Developments PLC	89%	96%
Bellway PLC	95%	96%
The Berkeley Holdings Group PLC	100%	100%
Bewley Group Limited	-	-
Bloor Investments Limited	-**	-**
The British Land Company PLC*	100%	100%
Cala Group (Holdings) Limited	0%	-
Canary Wharf Group PLC	-	-
C.G. Fry and Son Limited*	-**	-**
Churchill Retirement PLC	-	-
Crest Nicholson Holdings PLC	100%	100%
Croudace Homes Group Limited	-**	-**
Dandara Living Holdings Limited	100%	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-**	-**
Fairview Holdings Limited	100%	100%
Frasers Property (UK) Ltd*	-	-
Galliard Group Limited	31%	100%
MJ Gleeson PLC	100%	100%
Grosvenor Group Limited	100%	100%
Hill Holdings Limited*	100%	100%
Hopkins Home Group Limited*	-**	-**
Jelson Holdings Limited	100%	100%
Keepmoat Limited	-**	-**
Land Securities Group PLC	0%	-
Lendlease Europe Holdings Limited	79%	79%
Lifestory Holdings Limited (also covers Anthology Group)	100%	100%
London Square Development (Holdings) Limited	-	-
McCarthy & Stone Limited	100%	100%
Miller Homes Limited	94%	92%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	100%	100%
Morris Homes Group Limited	100%	100%
Persimmon Public Limited Company	100%	100%
Redrow PLC	100%	100%
Regal Holdco Limited (parent company for Regal London)	0%	-
Rowland Group Limited*	-	-
Rydon Group Holdings Limited	82%	78%
Sorbon Group Limited (parent company for Shanly Homes)*	100%	100%
St Modwen Group Holdings Company Limited*	-	-
Story Homes Limited	-**	-**
Strata Homes Group Limited	-**	-**
Taylor Wimpey PLC	100%	100%
Telford Homes Limited	98%	98%
Tilia Homes Limited*	100%	100%
Vistry Group PLC	93%	93%
Weston Group PLC	100%	100%
Broadthorpe Limited (parent company for William Davis Homes)	-**	-**
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	100%	100%
Total	96%	96%

## Social_1
Remediation status of buildings with cladding defects reported by Registered Providers of social housing, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [Note 30]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	47	5%	59	8%	106	7%
Remediation started	212	23%	182	26%	394	25%
Remediation works planned	320	35%	271	39%	591	37%
Remediation plans unclear from survey	327	36%	183	26%	510	32%
Work is not required – planned for demolition	3	0.3%	4	0.6%	7	0.4%
Total buildings	909	100%	699	100%	1608	100%

## Enforcement_1
Enforcement action taken by local authorities against high-rise buildings under the Housing Act (2004) by remediation programme status, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for the number of enforcement actions by local authority and by the type of remediation programme each building is in [note_15].
Local Authority [note_2]	BSF only (non-ACM cladding only) / Number	ACM cladding only / Number	BSF (non-ACM) and ACM cladding / Number	Not in any remediation fund (non-ACM cladding only) / Number	Total / Number
Barking and Dagenham	0	0	0	0	0
Barnet	1	3	1	2	7
Birmingham	2	0	0	0	2
Bournemouth, Christchurch and Poole	2	2	0	1	5
Bradford	0	1	0	0	1
Brent	0	2	0	0	2
Brighton and Hove	0	0	0	0	0
Bristol, City of	0	1	0	0	1
Bromley	0	0	0	0	0
Calderdale	0	0	0	0	0
Camden	15	1	0	18	34
City of London	1	0	0	0	1
Croydon	2	0	1	0	3
Dacorum	0	0	0	0	0
Ealing	2	1	1	0	4
Gateshead	0	0	0	0	0
Greenwich	4	0	0	1	5
Hackney	3	4	0	2	9
Hammersmith and Fulham	1	0	0	5	6
Haringey	0	0	0	0	0
Harrow	0	0	0	0	0
Hillingdon	3	0	0	1	4
Hounslow	0	0	0	1	1
Ipswich	0	0	0	0	0
Islington	0	0	0	0	0
Kensington and Chelsea	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0
Kirklees	0	0	0	0	0
Lambeth	2	2	0	0	4
Leeds	0	0	0	0	0
Leicester	0	0	0	0	0
Lewisham	0	0	0	0	0
Liverpool	2	3	2	1	8
Maidstone	0	0	0	0	0
Manchester	0	0	0	0	0
Medway	0	1	0	0	1
Merton	0	0	0	0	0
Milton Keynes	0	0	0	0	0
Newcastle upon Tyne	7	0	0	3	10
Newham	8	1	1	5	15
North Somerset	0	0	0	0	0
Norwich	0	0	0	0	0
Nottingham	1	1	0	1	4
Plymouth	1	0	0	0	1
Portsmouth	0	1	0	1	2
Reading	0	0	0	0	0
Redbridge	2	0	0	0	2
Salford	1	0	0	0	1
Sheffield	0	0	0	0	0
Slough	0	0	0	0	0
Southampton	3	0	0	0	3
Southwark	13	4	2	7	26
Sunderland	0	0	0	0	0
Sutton	0	0	1	0	1
Thanet	0	0	0	0	0
Tower Hamlets	9	1	4	5	19
Trafford	0	0	0	0	0
Waltham Forest	1	0	0	0	1
Wandsworth	1	2	1	0	4
Westminster	31	5	5	3	44
Windsor and Maidenhead	0	0	0	0	0
Others	13	0	2	12	26
Total	131	36	21	69	257

## Enforcement_2
Building inspections conducted by local authorities, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for the number of inspections by type of rating outcome.
Local Authority [note_2]	Inspections with the building rated Category 1 [note_16] / Number	Inspections with the building rated Category 2 [note_16] / Number	Rating outcome to be confirmed / Number	Total / Number
Barking and Dagenham	0	0	0	0
Barnet	4	3	0	7
Birmingham	0	1	1	2
Bournemouth, Christchurch and Poole	5	0	0	5
Bradford	0	1	0	1
Brent	1	1	0	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	1	0	1
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	0	34	0	34
City of London	0	0	1	1
Croydon	1	1	1	3
Dacorum	0	0	0	0
Ealing	1	3	0	4
Gateshead	0	0	0	0
Greenwich	2	0	3	5
Hackney	5	2	2	9
Hammersmith and Fulham	0	6	0	6
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	0	4	0	4
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	0	0	0
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	3	4	1	8
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	0	9	1	10
Newham	6	4	5	15
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	1	3	0	4
Plymouth	1	0	0	1
Portsmouth	0	1	1	2
Reading	0	0	0	0
Redbridge	0	1	1	2
Salford	0	1	0	1
Sheffield	0	0	0	0
Slough	0	0	0	0
Southampton	0	0	3	3
Southwark	10	15	1	26
Sunderland	0	0	0	0
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	0	9	10	19
Trafford	0	0	0	0
Waltham Forest	0	1	0	1
Wandsworth	1	3	0	4
Westminster	5	39	0	44
Windsor and Maidenhead	0	0	0	0
Others	11	13	2	26
Total	62	162	33	257

## Enforcement_3
Statutory notices served by local authorities under the Housing Act (2004), England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of statutory notices served, broken down by type of notice, for each Local Authority.
Local Authority [note_2]	Improvement notices / Number	Hazard awareness notices / Number	Prohibition orders / Number	Total / Number
Barking and Dagenham	0	0	0	0
Barnet	6	0	0	6
Birmingham	0	0	0	0
Bournemouth, Christchurch and Poole	3	0	0	3
Bradford	1	0	0	1
Brent	0	0	0	0
Brighton and Hove	0	0	0	0
Bristol, City of	0	0	0	0
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	8	2	0	10
City of London	0	0	0	0
Croydon	0	0	0	0
Dacorum	0	0	0	0
Ealing	2	0	0	2
Gateshead	0	0	0	0
Greenwich	1	0	0	1
Hackney	5	0	0	5
Hammersmith and Fulham	0	2	0	2
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	2	1	0	3
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	0	0	0
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	4	0	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	5	0	0	5
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	2	3	0	5
Newham	7	0	0	7
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	2	0	0	2
Plymouth	1	0	0	1
Portsmouth	1	0	0	1
Reading	0	0	0	0
Redbridge	0	0	0	0
Salford	0	0	0	0
Sheffield	0	0	0	0
Slough	0	0	0	0
Southampton	0	0	0	0
Southwark	8	0	0	8
Sunderland	0	0	0	0
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	4	2	0	6
Trafford	0	0	0	0
Waltham Forest	0	0	0	0
Wandsworth	1	0	0	1
Westminster	1	14	1	16
Windsor and Maidenhead	0	0	0	0
Others	14	0	0	14
Total	81	24	1	106

## Enforcement_4
Number of building inspections by local authorities supported by the Joint Inspection Team, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for the number of inspections supported by the Joint Inspection Team.
Local Authority [note_2]	Inspections supported by the Joint Inspection Team [note_17] / Number
Barking and Dagenham	0
Barnet	4
Birmingham	2
Bournemouth, Christchurch and Poole	2
Bradford	0
Brent	2
Brighton and Hove	0
Bristol, City of	0
Bromley	0
Calderdale	0
Camden	4
City of London	0
Croydon	3
Dacorum	0
Ealing	4
Gateshead	0
Greenwich	5
Hackney	8
Hammersmith and Fulham	1
Haringey	0
Harrow	0
Hillingdon	2
Hounslow	1
Ipswich	0
Islington	0
Kensington and Chelsea	0
Kingston upon Thames	0
Kirklees	0
Lambeth	2
Leeds	0
Leicester	0
Lewisham	0
Liverpool	6
Maidstone	0
Manchester	0
Medway	0
Merton	0
Milton Keynes	0
Newcastle upon Tyne	1
Newham	15
North Somerset	0
Norwich	0
Nottingham	2
Plymouth	1
Portsmouth	2
Reading	1
Redbridge	1
Salford	1
Sheffield	0
Slough	0
Southampton	3
Southwark	4
Sunderland	0
Sutton	1
Thanet	0
Tower Hamlets	7
Trafford	0
Waltham Forest	1
Wandsworth	4
Westminster	2
Windsor and Maidenhead	0
Others	8
Total	100

## JIT_1
Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for the number of Joint Inspection Team training sessions attended by local authority officers.
Local Authority [note_18]	Intro to Fire Safety (Level 1) Number	Intermediate Fire Safety: Theoretical HHSRS assessments (Level 2 Part 1) Number	Intermediate Fire Safety: Practical HHSRS assessments (Level 2 Part 2) Number
Barking and Dagenham	0	0	0
Barnet	4	3	3
Birmingham	10	2	3
Bournemouth, Christchurch and Poole	10	4	1
Bradford	24	4	1
Brent	1	4	0
Brighton and Hove	0	0	0
Bristol, City of	10	4	2
Bromley	3	0	0
Calderdale	3	1	0
Camden	16	12	5
City of London	8	4	1
Croydon	26	3	4
Dacorum	4	2	1
Ealing	10	3	2
Gateshead	6	3	0
Greenwich	2	4	5
Hackney	18	3	4
Hammersmith and Fulham	20	3	9
Haringey	4	2	0
Harrow	1	0	0
Hillingdon	3	1	0
Hounslow	4	3	0
Ipswich	0	0	0
Islington	11	6	1
Kensington and Chelsea	0	0	1
Kingston upon Thames	3	0	0
Kirklees	2	1	0
Lambeth	16	3	7
Leeds	6	1	1
Leicester	0	0	0
Lewisham	5	2	1
Liverpool	32	12	3
Maidstone	0	0	0
Manchester	7	4	1
Merton	6	2	0
Medway	12	5	0
Milton Keynes	6	4	3
Newcastle upon Tyne	6	3	2
Newham	10	5	0
North Somerset	8	3	2
Norwich	11	7	0
Nottingham	34	5	3
Plymouth	3	2	1
Portsmouth	2	5	0
Richmond and Wandsworth	8	5	4
Reading	15	3	1
Redbridge	4	1	1
Salford	8	7	0
Sheffield	0	0	0
Slough	5	7	0
Southampton	1	0	0
Southwark	7	0	0
Sunderland	3	3	2
Sutton	2	0	0
Thanet	2	1	0
Tower Hamlets	9	9	1
Trafford	6	3	0
Waltham Forest	6	2	3
Westminster	17	5	1
Windsor and Maidenhead	8	4	0
Others	401	110	45
Total	869	295	125