## 2020 Tracker
SNS ACTIVITY TRACKER
[15 empty] | MARCH | [30 empty] | APRIL | [29 empty] | MAY | [30 empty] | JUNE | [29 empty] | JULY | [30 empty] | AUGUST | [30 empty] | SEPTEMBER
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | DATE OPERATIONS COMPLETED | DURATION IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 31 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
SA/1290 - GS/1074 | Submitted |  | OPRED | 3D Seismic Survey | Ion Geophysical Corporation | Blocks 35-38 and 41-44 |  | 2020-04-01 | 2020-10-22 |  | 165 | 3D Seismic | 13265 | 4240 cu. in.
Source Option 2 - 3x 2 sub arrays; 3070 cu. in.
Source Option 3 - 2x 1 sub arrays; 8000 cu. in.
CL/1095 | Submitted |  | OPRED | Tolmount Conductor Piling Operations | Premier Oil | 42/28d | WGS84 54, 2, 27.31 N, 0, 26, 28.57 E | 2020-05-01 | 2020-10-31 |  | 18 (2) | Conductor Piling | bar: MAY 1; MAY 4 to MAY 8; MAY 11 to MAY 15; MAY 18 to MAY 22; MAY 25 to MAY 29; JUNE 1 to JUNE 5; JUNE 8 to JUNE 12; JUNE 15 to JUNE 19; JUNE 22 to JUNE 26; JUNE 29 to JULY 3; JULY 6 to JULY 10; JULY 13 to JULY 17; JULY 20 to JULY 24; JULY 27 to JULY 31; AUGUST 3 to AUGUST 7; AUGUST 10 to AUGUST 14; AUGUST 17 to AUGUST 21; AUGUST 24 to AUGUST 28; AUGUST 31 to SEPTEMBER 4; SEPTEMBER 7 to SEPTEMBER 11; SEPTEMBER 14 to SEPTEMBER 18; SEPTEMBER 21 to SEPTEMBER 25; SEPTEMBER 28 to SEPTEMBER 30
| Proposed |  | OPRED | Pipeline Survey | BBL Company |  | WGS84: Start 52.8925N 4.5999E End 52.8640N 1.4856E |  |  |  |  | Pipeline Survey
GS/1068 | Approved |  | OPRED | Pegasus Pipeline Survey | Spirit Energy | 43/13, 43/18, 43/19 & 43/24 |  | 2020-04-01 |  |  |  | Pipeline Survey | bar: APRIL 1
DCO/2013/00014 | Approved | 2013 | MMO | Triton Knoll offshore wind farm | innogy | SW edge of SNS SAC summer area (piling outside limits but max piling with 26km impact would impact just inside SAC) |  | 2020-02-16 | 2020-06-13 |  | 23 | Piling | bar: MAY 12 to MAY 15; MAY 18 to MAY 19; MAY 28 to MAY 31; JUNE 2 to JUNE 5; JUNE 7 to JUNE 9; JUNE 12 to JUNE 13; JUNE 22 to JUNE 25
DCO/2016/00007 | Approved | 2016 | MMO | Hornsea 2 offshore wind farm | Orsted | See https://marinelicensing.marinemanagement.org.uk/mmofox5/fox/live/?thread_id=8ph18jjgvhu1ro9p20l1amoj547ncreun9kja78j7ue9dsaqvd36rv652m8c39d37dkgfa8eqe8u0lr6qpgjvk92s0ocs2778t1d&resume=1 |  | 2020-09-01 | 2021-12-31 |  |  | Piling | bar: SEPTEMBER 1 to SEPTEMBER 30
L/2019/00266 | Approved | 2019 | MMO | Hornsea 2 UXO campaign | Orsted | See https://marinelicensing.marinemanagement.org.uk/mmofox5/fox/live/?thread_id=8ph18jjgvhu1ro9p20l1amoj547ncreun9kja78j7ue9dsaqvd36rv652m8c39d37dkgfa8eqe8u0lr6qpgjvk92s0ocs2778t1d&resume=1 |  | 2020-04-01 | 2020-09-30 |  |  | UXO detonation | bar: APRIL 1 to SEPTEMBER 30

## 2021 Tracker
SNS ACTIVITY TRACKER
[15 empty] | MARCH | [30 empty] | APRIL | [29 empty] | MAY | [30 empty] | JUNE | [29 empty] | JULY | [30 empty] | AUGUST | [30 empty] | SEPTEMBER
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | DATE OPERATIONS COMPLETED | DURATION IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 31 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
GS/1070 | Completed |  | OPRED | Ossian Rig Site Survey | Spirit Energy | 42/3 |  | 2020-04-12 | 2021-04-01 |  | 6 | Rig Site Survey | 39 | 160cu
| Completed |  | OPRED | Grove NE Site Survey and Pipeline Route Survey | Spirit Energy | 49/10 |  | 2020-06-01 | 2021-05-31 |  | 1 | Site Survey and Pipeline Route Survey (SBP) | 13.6
DCO/2016/00007 | Approved | 2016 | MMO | Hornsea 2 offshore wind farm | Orsted | Search Public Register:https://marinelicensing.marinemanagement.org.uk/mmofox5/fox/live/?thread_id=lottn0d1b1pp1jdko35qqsish58p7993ovu18v2cquia83b2qqfdl6gjsrvv4u6vsu6rpffgv5f9u9mr0hgq32rp1hskocr73cpn&resume=1 |  | 2020-09-01 | 2021-12-31 |  |  | Piling | 2874 | bar: SEPTEMBER 1 to SEPTEMBER 30
GS/1164 | Approved |  | OPRED | Debris clearance survey at 2021 well abandonment subsea locations | Chrysaor Production (U.K.) Limited | 49/11, 49/12, 4917, 49/22 and 44/22 | Various around subsea well locations | 2021-01-15 | 2021-07-31 |  | 5 | Innomar SES-2000 pinger | 254 | SEL 214, SPL 233 db/ 1 micropascal
WIA/1154 ML654 | Approved | 2021 | OPRED | Alexandra subsea well abandonment - explosives environmental cap | Chrysaor Production (U.K.) Limited | 49/11a-6 |  | 2021-03-01 | 2021-09-30 |  | 38 | Explosive TCP gun to perforate and set environmental cap approx 200m in well |  | 3.6kg 2 planned, 2 contingency
WIA/1057 ML/655 | Submitted | 2021 | OPRED | Victor JM subsea well abandonment - explosives environmental cap | Chrysaor Production (U.K.) Limited | 49/17-11(K1) |  | 2021-03-01 | 2021-09-30 |  | 46 | Explosive TCP gun to perforate and set environmental cap approx 200m in well |  | 1.01kg 2 planned 2 contingency
WIA/1155 ML/656 | Approved | 2021 | OPRED | Boulton BM subsea well abandonment - explosives environmental cap | Chrysaor Production (U.K.) Limited | 44/22b | Latitude: 54° 11’ 18.71’’N; Longitude: 02° 12’ 33.79’’E | 2021-03-01 | 2021-09-30 |  |  | Explosive TCP gun to perforate and set environmental cap approx 200m in well |  | xxxx kg 2 planned 2 contingency
SA/1375 GS/1172 | Completed | 2021 | OPRED | Pipeline survey 150m from shore to Viking AR of TGT pipelines PL0027/PL0161 Innomar SES-2000 pinger | Chrysaor Production (U.K.) Limited | 47/17,18,19,20 48/16,17,18,19,20 49/16,11,12 | Latitude: 53° 21’ 31.89’’N; Longitude: 00° 15’ 33.35’’E to Latitude: 53° 32’ 00.35’’N; Longitude: 02° 15’ 16.39’’E | 2021-02-25 | 2021-03-17 |  | 3 | Innomar SES-2000 pinger |  | SEL 218, SPL 236 db/ 1 micropascal frequency 100KHz
SA/1375 GS/1174 | Completed | 2021 | OPRED | Pipeline survey LOGGS to Viking Bravo pipelines PL2643/PL2644 | Chrysaor Production (U.K.) Limited | 49/16,17 | Latitude: 53° 26’ 50.17’’N; Longitude: 02° 19’ 51.97’’E to Latitude: 53° 23’ 24.59’’N; Longitude: 02° 00’ 07.82’’E | 2021-02-25 | 2021-03-17 |  | 2 | Innomar SES-2000 pinger |  | SEL 218, SPL 236 db/ 1 micropascal frequency 100KHz
SA/1375 GS/1175 | Completed | 2021 | OPRED | Vulcan UR and RD safety zone determination stub depths | Chrysaor Production (U.K.) Limited | 49/16, 48/25 | 500m HSE safety zones | 2021-02-25 | 2021-03-17 |  | 2 | Innomar SES-2000 pinger |  | SEL 218, SPL 236 db/ 1 micropascal frequency 100KHz
SA/1385 GS/1184 | Completed | 2021 | OPRED | Survey 14 former platforms determine remediation, SBP 5m above seabed on ROV | CHrysaor Production (U.K.) Limited | 44/23, 49/12,16,17,22 | 500m HSE safety zones and 100m extension some locations on pipeline | 2021-03-12 | 2021-04-30 |  | 10 | DW-106 Chirp SBP |  | SEL 182, SPL 194 db/ 1 micropascal frequency 100KHz
SA/1280 GS/1199 | Completed | 2021 | OPRED | MCG21001 - Regional Deep Imaging 2D Survey 2021 | MULTICLIENT GEOPHYSICAL, FILIAL AV GEOEX LTD | 19/9,13,18,24,30. 20/9, 24, 30. 21/11. 22/8, 13, 16, 21, 26. 26/5, 15, 25, 28. 27/1, 5. 28/1, 6, 25. 29/1, 21, 26. 30/1, 6, 11, 26. 31/21, 26. 34/2, 25, 30. 35/3, 9, 15, 17. 36/1, 6, 22,28. 37/1,14,17. 38/1. 39/1, 6, 11. 41/10, 15. 42/1, 10. 43/1, 6. 21/16, 23 | Various - see application | 2021-06-10 | 2021-09-30 |  | 120 | 2D, Magnetic & Gravity survey | 1705 | 6270 cu in | bar: JUNE 1 to SEPTEMBER 30
SA/1365 GS/1163 | Submitted | 2021 | OPRED | 3D towed streamer seismic survey | ION (GX Technology) | Q35-38; 41/15, 18-20; 42/1-20; 43/1-15 and 44/1-9 | Various - see application | 2021-04-01 | 2021-10-31 |  | 165 | 3D seismic | 700 | 3390 cu in | bar: APRIL 1 to SEPTEMBER 30
ML/652 | Approved | 2021 | OPRED | PL83 Pipeline Section Cutting and Mattress Removal |  | 52/5 |  | 2021-02-05 | 2021-07-31 |  | 20 | Disturbance of seabed and removal of articles from seabed
ML/659 | Approved | 2021 | OPRED | PL84 cutting operation |  | 48/29 |  | 2021-03-18 | 2021-08-31 |  | 5 | Disturbance of seabed and removal of articles from seabed
ML/664 | Approved | 2021 | OPRED | PL1325 Cutting |  | 48/30 |  | 2021-03-24 | 2021-08-31 |  | 5 | Disturbance of seabed and removal of articles from seabed
ML/663 | Approved | 2021 | OPRED | PL1177/ PL135B Pipeline Cutting & Mattress Removal |  | 40/30 |  | 2021-03-24 | 2021-08-31 |  | 10 | Disturbance of seabed and removal of articles from seabed
PR/2093/0 | Completed | 2021 | OPRED | Southwark Platform |  |  |  | 2021-05-12 | 2021-07-03 |  | 4 | Disturbance of seabed
ML/690 | Approved | 2021 | OPRED | PL24 salvage operations | Perenco UK Ltd | 53/1 | Various - see application | 2021-05-28 | 2021-09-30 |  | 55 | Disturbance of seabed, temporary and permanent deposits
GS/1207 | Approved | 2021 | OPRED | MBES and SBP in Endurance Store Area | BP Exploration Operating Company Limited | 42/23-25, 42/27-28, 47/2, 47/6-7, 47/11, 40/15, 41/11-14, 41/19-20, 42/16-18, 42/23-25 | Various - see application | 2021-05-25 | 2021-07-31 |  | 3.9 | Various - see application | 40 | SEL 211.8 dB
WIA/1152, ML/722 | Approved | 2021 | OPRED | 48/30- 14 Deborah Well P&A | ENI HEWETT LIMITED | 48/30-14 | Latitude 53 Minute 05 Second 10.42 North Longitude Degree 1 Minute 51 Second 0.99 East | 2021-06-22 | 2021-09-30 |  | 30 | Well P&A explosive use downhole for punching casing and tubing
GS/1252 | Submitted | 2021 | OPRED | MBES and SBP in Endurance Store Area | BP Exploration Operating Company Limited | 42/23-25, 42/27-28, 47/2, 47/6-7, 47/11, 40/15, 41/11-14, 41/19-20, 42/16-18, 42/23-25 | Various - see application | 2021-06-24 | 2021-09-24 |  | 70 (1.5 in SAC) | Various - see application | 40 | SEL 211.8 dB
GS/1263 | Submitted | 2021 | OPRED | MBES and SBP at Saturn, Mimas and Tethys platforms in the SNS | Chrysaor Production (U.K.) Limited | 48/10, 49/11 & 44/23 | Within 500m of platforms and rig anchor locations | 2021-07-17 | 2021-08-31 |  | 3 | Reviewing seabed and debris for rig location | 3 | SEL 207dB, SPL 245dB, Peak freq 288Hz
WIA/1195 ML/733 | Submitted | 2021 | OPRED | Mimas well abandonment, deep set and shallow set barrier using explosives | Chrysaor Production (U.K.) Limited | 48/09 | 500m safety zone platform | 2021-07-28 | 2022-01-31 |  | 37 | Disturbance from explosives 500ft in well likely half day | 0.5
MLA/2020/00581 | Approved | 2021 | MMO | Dogger Bank A UXO campaign | Doggerbank Project 1 Bizco Limited | Search Public Register:https://marinelicensing.marinemanagement.org.uk/mmofox5/fox/live/?thread_id=lottn0d1b1pp1jdko35qqsish58p7993ovu18v2cquia83b2qqfdl6gjsrvv4u6vsu6rpffgv5f9u9mr0hgq32rp1hskocr73cpn&resume=1 |  | 2021-06-03 | 2021-12-31 | 2021-07-15 | 9 | UXO detonation - high order is worst case scenario | 2124
MLA/2018/00503 | Approved | 2020 | MMO | Hornsea 2 offshore wind farm | Orsted | Search Public Register:https://marinelicensing.marinemanagement.org.uk/mmofox5/fox/live/?thread_id=lottn0d1b1pp1jdko35qqsish58p7993ovu18v2cquia83b2qqfdl6gjsrvv4u6vsu6rpffgv5f9u9mr0hgq32rp1hskocr73cpn&resume=1 |  | 2019-07-11 | 2022-03-31 |  |  | UXO detonation - will not be doing UXO the same time as piling set out in line 3 therefore the worst case is Line 3 and this is only required to be taken into account.
PLA/838 PL/2121 | Approved | 2021 | OPRED | Thames pipeline PL370 modification | ODE Asset Management Ltd | 48/29 |  | 2021-07-27 | 2021-09-30
SA/1495, GS/1287 | Submitted | 2021 | OPRED | Notification of a marine survey (MBES, SSS, visual etc) | TULLOW OIL SK LIMITED | 49/28, 49/29, 49/30, 50/26, 53/3 and 53/4 | See application | 2021-08-05 | 2021-08-31 |  | 1 | Survey notification | 17.4

## 2022 Tracker
| SNS ACTIVITY TRACKER | [16 empty] | Season | Area | Days
[18 empty] | summer | 27028 | 183
[18 empty] | winter | 12696 | 182
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | ACTUAL ACTIVITIES START DATE | ACTUAL ACTIVITIES END DATE | DATE OPERATIONS COMPLETED | DURATION OF ACTIVITY IN DAYS | DURATION OF ACTIVITY IMPACTING SAC IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | LINK TO DECISION | DAILY THRESHOLD (summer) | SEASONAL THRESHOLD (summer)
| Proposed is included to highlight the potential activities but should not be used to in AA | [6 empty] | Initial start date within the Application - remains the same for Audit | Initial end date within the Application - remains the same for Audit | Refined start date of activities - updated once the final programme has been | Refined end date of activities - updated once the final programme has been | Update from notification of completion | The number of days the activity will take place | The number of days the activity will impact the SAC | Be clear on the impact to the SAC and any information that could assist in completing AA | Still in discussion on if it is within the SAC or average WCS | SEL, dB, cu, kg - depending on activity - put as much information as possible | Which season is impacted? | Only take into account the none greyed out figures | Only take into account the none greyed out figures
MLA/2018/00503/2 | Completed |  | MMO | Hornsea 2 offshore wind farm UXO Clearance - low order but with high order reserve - THIS ROW IS HIGH ORDER **see row 23 for LOW ORDER data | Orsted | N/A | https://marinelicensing.marinemanagement.org.uk/mmofox5/fox/live/MMO_PUBLIC_REGISTER/search?area=3 | 2022-01-01 | 2022-09-30 |  |  |  | 40 | 40 | Scheduling of activities in Summer 2022. HOW02 will commit to undertaking Low order UXO clearance activities only when piling works at Dogger bank A &B and BP seismic survery is underway. If High Order is required it will be undertaken when at least one of Dogger Bank A&B piling and the BP survey activities are not active and in a 24 hour period when Sofia is not planning High order UXO. Applicant will also use Bubble curtain for UXO > 50kg where possible and ADD and scare charges. | 2303 |  | Summer | 8.5208 | 1.8625
GS/1332 | Approved |  | OPRED | Greater NEP 3D Towed-streamer (Endurance & BC39) Seismic Survey | BP Exploration Operating Company Limited | 42/19-20, 42/23-25,42/29-30, 43/17-19, 43/21-30, 44/21-22, 44/26-27, 48/5, 49/1 | Various - see application | 2022-04-01 | 2022-08-15 |  |  |  | 64 | 64 | 3D Seismic | 2190 | SEL 220.6 dB |  | 8.1027 | 2.8337
MLA/2020/00489 | Completed |  | MMO | Sofia OWF UXO Clearance - Low order | RWE LTD | N/A | https://marinelicensing.marinemanagement.org.uk/mmofox5/fox/live/MMO_PUBLIC_REGISTER/search?area=3 | 01/04/2022 | 30/09/2022 |  |  |  | 25 | 25 | UXO Clearance campaign - I have put both the high order and low order information in for reference. | 157.08 |  |  | 0.58118 | 0.079396
MLA/2020/00489 | Completed |  | MMO | Sofia OWF UXO Clearance - High order | RWE LTD | N/A | https://marinelicensing.marinemanagement.org.uk/mmofox5/fox/live/MMO_PUBLIC_REGISTER/search?area=3 | 2022-04-01 | 2022-09-30 |  |  |  | 25 | 25 |  | 3782 |  |  | 13.9929 | 1.9116
DCO/2013/00010 | Approved |  | MMO | Dogger Bank A Piling | DOGGERBANK OFFSHORE WIND FARM PROJECT 1 PROJCO LIMITED | N/A | https://marinelicensing.marinemanagement.org.uk/mmofox5/fox/live/MMO_PUBLIC_REGISTER/search?area=3 | 2022-06-01 | 2023-03-31 |  |  |  | 110 | 108 | Piling | 2227.68 |  |  | 8.2421 | 4.8642
ML/766 | Approved | 2022 | OPRED | Leman 27 C P & A | Perenco UK Limited | 49/27c | various - see application | 2022-01-06 | 2022-03-31 | [5 empty] | Downhole explosives |  | Below PTS and TTS |  | 0 | 0
MLA/2021/00552 | Submitted |  | MMO | Doggerbank Array Area A and B UXO - Low Order | DOGGERBANK OFFSHORE WIND FARM PROJECT 1 PROJCO LIMITED | N/A |  | 2022-05-01 | 2022-12-31 |  |  |  | 6 | 6 | UXO Clearance campaign - I have put both the high order and low order information in for reference. | 79 |  |  | 0.29229 | 0.0095833
MLA/2021/00552 | Submitted |  | MMO | Doggerbank Array Area A and B UXO - High Order | DOGGERBANK OFFSHORE WIND FARM PROJECT 1 PROJCO LIMITED | N/A |  | 2022-05-01 | 2022-12-31 |  |  |  | 6 | 6 |  | 2124 |  |  | 7.8585 | 0.25766
MLA/2021/00524 | Cancelled |  | MMO | CIRCE North 2 UXO Clearance | ZAYO GROUP UK LTD | N/A | [12 empty] | 0 | 0
GS/1342/1 | Approved |  | OPRED | Theddlethorpe Gas Terminal to Murdoch MD PL929/PL930 Pipeline Route Survey - SBP Pinger, SSS, MBES | CHRYSAOR PRODUCTION (U.K.) LIMITED | Various (begins 150 m from shore) |  | 2022-02-10 | 2022-04-07 |  |  |  | 11 | 11 | Sub-bottom profiler (pinger) along sections of pipeline, side scan sonar and multi-beam echo sounder along entire length (181 km route) using Unmanned Survey Vessel |  | SEL 218, SPL 236 |  | 0 | 0
GS/1343/1 | Approved |  | OPRED | Murdoch MD to Caister CM PL935/PL936 Pipeline Route Survey - SBP Pinger, SSS, MBES | CHRYSAOR PRODUCTION (U.K.) LIMITED | 44/22 and 44/23 |  | 2022-02-01 | 2022-03-31 |  |  |  | 1 | 1 | Sub-bottom profiler (pinger), side scan sonar and multi-beam echo sounder along entire length of pipeline (11 km route) using Unmanned Survey Vessel |  | SEL 218, SPL 236 |  | 0 | 0
GS/1327/0 | Approved | 11/03/22 | OPRED | Goddard | IOG NORTH SEA LIMITED | 48/11 and 48/12 |  | 2022-03-07 | 2022-07-31 | 2022-03-07 | 18/03/2022 (Seismic completion) |  | 7 | 7 | 2D seismic, SBP (chirper/boomer). Following the initial geophysical survey, a geotechnical and environmental survey at a site identified as suitable for drilling. Survey instruments not requiring consent are: Side scan sonar Multi beam echo sounder Cone penetrometer Box core or van Veen grab Drop camera Magnetometer |  | Seismic - 160 cu SEL 233; SPL 235 SBP SEL 205 SPL 182 | Seismic completed in winter season by end of March | 0 | 0
GS/1328 | Approved | 11/03/2022 | OPRED | Kelham Block 53/1b | IOG NORTH SEA LIMITED | 53/1b |  | 2022-03-07 | 2022-07-31 | 2022-03-07 | 31/03/2022 (Seismic completion) |  | 7 | 7 | 2D seismic, SBP (chirper/boomer). Following the initial geophysical survey, a geotechnical and environmental survey at a site identified as suitable for drilling. Survey instruments not requiring consent are: Side scan sonar Multi beam echo sounder Cone penetrometer Box core or van Veen grab Drop camera Magnetometer |  | Seismic - 160 cu SEL 233; SPL 235 SBP SEL 205 SPL 183 | Seismic completed in winter season by end of March | 0 | 0
MLA/2019/00488 | Approved | 11/03/2022 | MMO | NEUCONNECT BRITAIN LTD | NEUCONNECT BRITAIN LTD |  | See applicaton |  | 2037-03-08 | [5 empty] | *REMOVED FROM 2022- confimed by developer that no works are to be undertaken in the SAC in 2022. Original data: Geophysical Surveys for 93 days with 314km2 Activity size. Geophysical Surveys: Sub Bottom Profiler- Conditioned that it cannot be carried out in the SNS SAC during the wintering period between the months of 1 October to 31 March inclusive. |  |  |  | 0 | 0
GS/1373 | Approved | 14/04/2022 | OPRED | Tolmount East Geophysical Survey | Premier Oil UK Limited | 42/28 | [12 empty] | 0 | 0
GS/1374 | Approved | 14/04/2022 | OPRED | Hunter HK-1 Site Survey | Premier Oil UK Limited | 44/23a | [12 empty] | 0 | 0
GS/1368 | Approved | 22/04/2022 | OPRED | NW Bell ZX, Victor JM and Kelvin TM site survey | CHRYSAOR PRODUCTION (U.K.) LIMITED | 49/22, 49/17, 44/18 |  | 2022-04-25 | 2022-08-31 |  |  |  | 6 | 4 | Sub-bottom profiler (one of pinger/boomer/sparker) at each of three sites (2 are located within SNS SAC), plus echo-sounder, multi-beam and side scan sonar |  | SEL 192, SPL 226 |  | 0 | 0
MLA/2018/00503/2 | Completed |  | MMO | Hornsea Project Two Offshore Wind Farm - Offshore UXO Inspection and Clearance - 80% Low order 20% High order. **this is the low order data for Hornsea 2 UXO- See Row 5 for high order data. | OPRED | N/A | See applicaton | 2022-01-01 | 2022-09-30 |  |  |  | 40 | 40 | UXO Clearance campaign - this is low order for the Hornsea 2 UXO- I have put both the high order and low order information in for reference. | 393 |  |  | 1.454 | 0.31782
ML/828 | Submitted |  | OPRED | A2D P & A | Petrodec UK Limited | 47/14A | 53" 37' 24", 0" 47' 26"E | 2022-05-29 | 2022-09-16 | [5 empty] | explosives below mudline for perforations |  |  |  | 0 | 0
GS/1413 | Submitted |  | OPRED | NEP Nearshore Ground Investigations - Humber Landfall | BP Exploration Operating Company Limited | Block 40 | Various - see application | 2022-08-01 | 2022-10-28 | [5 empty] | The sub-surface imaging comprises: − Sub-bottom profiling (SBP), used for imaging marine sediment; − Ultra-short line base (USBL) acoustic positioning; and − Ultra-high resolution seismic (UHRS), used for rockhead and rock mass imaging. The seabed imaging includes the following: ─ Marine Multi-beam Echo Sounding Survey (MBES), used for bathymetric data; ─ Side Scan Sonar Survey (SSS), to identify obstacles (contacts) on the seabed; ─ Marine Magnetometer Survey, to identify ferrous objects and potential for UXO (on the seabed and up to 3m depth penetration). | 0.89 | Seismic 100 cu, SPL - 226 |  | 0.0032929 | 0
GS/1416 | Submitted |  | OPRED | NEP Nearshore Ground Investigations - Teesside Landfall | BP Exploration Operating Company Limited | Block 47 | Various - see application | 2022-08-01 | 2023-05-31 | [5 empty] | The sub-surface imaging comprises: − Sub-bottom profiling (SBP), used for imaging marine sediment; − Ultra-short line base (USBL) acoustic positioning; and − Ultra-high resolution seismic (UHRS), used for rockhead and rock mass imaging. The seabed imaging includes the following: ─ Marine Multi-beam Echo Sounding Survey (MBES), used for bathymetric data; ─ Side Scan Sonar (SSS) Survey, to identify obstacles on the seabed; ─ Marine Magnetometer Survey, to identify ferrous objects and potential UXO (on the surface and up to 3m depth penetration). | 0.89 | Seismic 100 cu, SPL - 226 |  | 0.0032929 | 0
GS/1441 | Approved | 29/07/2022 | OPRED | Clipper 2022 Geophysical and Environmental Survey | Shell U.K. Limited | 48/19a | Various - see application | 2022-09-01 | 2022-11-30 |  |  |  | 3 | 3 | Notification only - SSS, SBES, MBES, visual and grab samples | 1 | N/A |  | 0.0036999 | 6.0654e-05
GS/1448 | Approved | 04/08/2022 | OPRED | Garrow pre-decommissioning survey | Alpha Petroleum | 42/25 | Various - see application | 2022-08-25 | 2022-08-31 |  |  |  | 1 | 1 | Notification only - grab samples, videos and stills | 2 | N/A |  | 0.0073997 | 4.0436e-05
GS/1449 | Approved | 04/08/2022 | OPRED | TORS GI survey | Alpha Petroleum | 42/25, 43/21, 43/22, 43/23 and 43/24 | Various - see application | 2022-08-25 | 2022-08-31 |  |  |  | 1 | 1 | Notification only - pipeline route survey | 100m x 45m | N/A |  | #VALUE! | #VALUE!
GS/1452 | Submitted |  | OPRED | NEP Geotechnical Borehole survey | BP Exploration Operating Company Limited | 40/15, 42/25 and 43/21 | Various - see application | 2022-09-05 | 2022-11-30 |  |  |  | 7 | 7 | Borehole, shallow drilling and core penetrometer tests | 1.5e-05 | N/A |  | 5.5498e-08 | 2.1229e-09
ML/860 | Approved | 09/09/2022 | OPRED | Anglia A decommissioning wells | Ithaca Energy UK Limited | 48/19b | Various - see application | 2022-08-15 | 2022-12-15 | [5 empty] | wellhead severance using explosoves |  |  |  | 0 | 0
DL/53, ML/875 | Submitted |  | OPRED | Breagh Decommissioning Wells | Ineos SNS Uk Limited | 42/13 | Various - see application | 2022-09-18 | 2022-10-31 |  |  |  | 12 | 12 | wellhead severance using explosoves |  |  |  | 0 | 0
GS/1456 | Approved | 23/09/2022 | OPRED | Katy/Munro/Boulton/Tethys Site Surveys | CHRYSAOR PRODUCTION (U.K.) LIMITED | 44/17, 44/19, 44/21, 49/11 | Various - see application | 2022-09-23 | 2022-12-31 |  |  |  | 5 | 5 | Sub-bottom profiler (pinger) at each site, plus echo-sounder, multi-beam, side-scan sonar and passive magnetometer | 1 | SPL 250, SEL 232 |  | 0.0036999 | 0.00010109
GS/1483 | Approved | 2/12/2022 | OPRED | Crosgan field geopphysical site survey | One Dyas Uk Ltd | 42/15 (survey), GWA 42/9, 42,10, 42/14 | Various - see application | 2022-12-08 | 2023-01-31 |  |  |  | 2 | 2 | 2DHR seismic survey and Sub-bottom profiler (pinger) | 1 | SPL 245, SEL 221 |  | 0.0036999 | 4.0436e-05
MLA/2022/00287 | Submitted |  | MMO | Project Rissa A | Dong Energy- Hornsea Project Three | N/A | Various - see application | 2022-10-01 | 2023-02-01 |  |  |  | 3 | 3 | Piling | 1 | 224.4dB |  | 0.0036999 | 6.0654e-05
MLA/2022/00333 | Submitted |  | MMO | Project Rissa B | Dong Energy- Hornsea Project Three | N/A | Various - see application | 2022-11-01 | 2023-03-01 |  |  |  | 3 | 3 | Piling | 1 | 224.4dB |  | 0.0036999 | 6.0654e-05
[19 empty] | 0 | 0
[19 empty] | 0 | 0

## 2023 Tracker
| SNS ACTIVITY TRACKER | [16 empty] | Season | Area | Days
[18 empty] | summer | 27028 | 183
[18 empty] | winter | 12696 | 182
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | ACTUAL ACTIVITIES START DATE | ACTUAL ACTIVITIES END DATE | DATE OPERATIONS COMPLETED | DURATION OF ACTIVITY IN DAYS | DURATION OF ACTIVITY IMPACTING SAC IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | LINK TO DECISION | DAILY THRESHOLD (summer) | SEASONAL THRESHOLD (summer)
| Proposed is included to highlight the potential activities but should not be used to in AA | [6 empty] | Initial start date within the Application - remains the same for Audit | Initial end date within the Application - remains the same for Audit | Refined start date of activities - updated once the final programme has been | Refined end date of activities - updated once the final programme has been | Update from notification of completion | The number of days the activity will take place | The number of days the activity will impact the SAC | Be clear on the impact to the SAC and any information that could assist in completing AA | Still in discussion on if it is within the SAC or average WCS | SEL, dB, cu, kg - depending on activity - put as much information as possible | Which season is impacted? | Only take into account the none greyed out figures | Only take into account the none greyed out figures
DCO/2016/00024 | Cancelled |  | MMO | Dogger Bank B Piling | DOGGERBANK OFFSHORE WIND FARM PROJECT 1 PROJCO LIMITED | N/A | https://marinelicensing.marinemanagement.org.uk/mmofox5/fox/live/MMO_PUBLIC_REGISTER/search?area=3 | [5 empty] | 138 | 52 | Piling. Moved to 2024 | 2124 |  |  | 7.8585 | 2.233
DCO/2013/00010 | Completed |  | MMO | Dogger Bank A Piling | DOGGERBANK OFFSHORE WIND FARM PROJECT 1 PROJCO LIMITED | N/A | See applicaton | 2023-04-01 | 2023-08-09 | 2023-04-04 | 2023-10-10 |  | 130 | 53 | Piling | 2124 |  |  | 7.8585 | 2.276
MLA/2019/00488 | Completed | 11/03/2022 | MMO | NEUCONNECT BRITAIN LTD | NEUCONNECT BRITAIN LTD | N/A | See applicaton | 2023-05-08 | 2023-05-28 | 2023-05-08 | 2023-05-28 |  | 7 | 7 | Original data: Geophysical Surveys for 93 days with 314km2 Activity size. Dates TBC. Geophysical Surveys: Sub Bottom Profiler- Conditioned that it cannot be carried out in the SNS SAC during the wintering period between the months of 1 October to 31 March inclusive. | 314 |  |  | 1.1618 | 0.044439
MLA/2022/00287 | Completed |  | MMO | Project Rissa A | Dong Energy- Hornsea Project Three | N/A | Various - see application | 2022-10-01 | 2023-02-01 | 2023-02-04 | 2023-03-31 |  | 3 | 3 | Piling | 1 | 224.4dB | Summer | 0.0036999 | 6.0654e-05
MLA/2022/00333 | Completed |  | MMO | Project Rissa B | Dong Energy- Hornsea Project Three | N/A | Various - see application | 2022-11-01 | 2023-03-01 | 2023-02-04 | 2023-03-31 |  | 3 | 3 | Piling | 1 | 224.4dB | Summer | 0.0036999 | 6.0654e-05
MLA/2021/00552 | Completed |  | MMO | Doggerbank Array Area A and B UXO - High Order | DOGGERBANK OFFSHORE WIND FARM PROJECT 1 PROJCO LIMITED | N/A | See applicaton | 2023-02-01 | 2023-03-31 | 2023-02-14 | 2023-03-03 |  | 6 | 6 | UXO | 0 | up to 795kg | Summer | 0 | 0
EXE/2023/00009 | Completed |  | MMO | Sofia Offshore Wind Farm Limited | Sofia OWF- geophysical and seismic survey (array) |  |  | 2023-02-20 | 31/04/2023 |  |  |  | 34 | 34 | Geophysical Surveys |  |  |  | 0 | 0
EXE/2023/00009 | Completed |  | MMO | Sofia Offshore Wind Farm Limited | Sofia OWF- geophysical and seismic survey (array) |  |  | 2023-06-01 | 2023-07-31 |  |  |  | 60 | 20 | Geophysical Surveys |  |  |  | 0 | 0
EXE/2023/00009 | Completed |  | MMO | Sofia Offshore Wind Farm Limited | Sofia OWF- geophysical and seismic survey (array) |  |  | 2023-07-01 | 2023-12-31 |  |  |  | 75 | 25 | Geophysical Surveys |  |  |  | 0 | 0
GS/1499 | Completed |  | OPRED | Crosgan well VSP operations | One Dyas Uk Ltd | 42/15a | 54" 39' 41.094", 0" 47' 7.64"E | 2023-02-01 | 2023-12-31 |  |  |  | 1 | 1 | Vertical Seismic Profiling | 0.79 | SPL 245, SEL 221 |  | 0.0029229 | 1.5972e-05
DR/2345 | Completed |  | OPRED | Crosgan well piling operations | One Dyas Uk Ltd | 42/15a | 54" 39' 41.094", 0" 47' 7.64"E | 2023-03-23 | 2023-03-31 |  | 2023-03-31 |  | 1 | 1 | 30" piling of conductor (winter season only). Operations to be completed by end March 23. | 706.86 |  |  | 2.6153 | 0.014291
GS/1519 | Completed |  | OPRED | Hewett Field Bathymetric and Seismic Survey and OBN (Dependent upon approval of CCS Licence) | Eni UK Ltd | 48/29, 48/30, |  | 2023-06-20 | 2023-10-31 |  |  |  | 80 | 80 | Geophysical Surveys | 663 | 400 cu | Summer & Winter | 2.453 | 1.0724
GS/1503 | Completed |  | OPRED | Murdoch KM and Nw Bell ZX Survey | Chrysaor (harbour energy) | 49/22, 49/23 (NW Bell ZX) 44/22, 44/23 (Murdoch KM) | See application | 2023-03-09 | 2023-05-30 |  |  |  | 2 | 2 | Geophysical Surveys : Sub-bottom Profiling (SBP), Multibeam Echosounder (MBES), Side Scan Sonar (SSS), Echo-sounder Survey and passive magnetometer | 3.6 | 192dB | summer | 0.01332 | 0.00014557
GS/1508 | Completed |  | OPRED | Johnston site survey | Premier Oil (harbour energy) | 43/27 (GWA also slightly transects 43/26 and 48/2) | See application | 2023-03-15 | 2023-05-30 |  |  |  | 2 | 2 | Geophysical Surveys: 2D Ultra High Resolution Seismic (UHRS) Survey, Sub-bottom Profiling (SBP), Multibeam Echo Sounder (MBES), Side Scan Sonar (SSS) and Echo Sounder Survey. | 1.3 | 203dB | summer | 0.0048098 | 5.2566e-05
GS/1500 | Completed |  | OPRED | Bunter Outcrop Survey | BP Exploration Operating Company Limited | 43/27 and 43/28 | See application | 2023-03-23 | 2023-05-31 |  | 2023-04-05 |  | 20 | 6 | 3D high resolution seismic survey | 188 | 213dB | Summer | 0.69557 | 0.022806
GS/1520 | Cancelled |  | OPRED | Q43 Lodestone West 2023- multi-client regional survey | CGG Services (UK) Limited | 41/11, 16, 21, 42/6 to 25, 43/6 to 25, 44/6, 11,16, 21 | See application- to be clarified | 2023-06-01 | 2023-12-31 |  |  |  | 114 | 114 | 3D high resolution seismic survey- some details to be clarified |  | 3390 (cu in); SEL 233 dB; SPL 254 dB | Summer & Winter | 0 | 0
ML/941 | Completed |  | OPRED | Platypus Well Abandonment |  |  | See application | 2023-03-01 | 2023-06-30 |  |  |  | 10 | 10 | Downhole explosives used during well abandonment |  |  |  | 0 | 0
GS/1538 | Completed | 22-03-23 | OPRED | Annual Leman And NUI pipeline inspection | Shell U.K. Limited | 48/29, 48/30, 49/19, 49/20, 49/23, 49/24, 49/26, 49/27, 52/3, 52/4 and 52/5 | See application | 2023-04-01 | 2023-07-01 |  |  |  | 21 | 21 | Side scan sonar and Multi Beam Echo Sounder |  |  |  | 0 | 0
GS/1530 | Completed |  | OPRED | Anning and Somerville site survey | Hartshead Resources | 49/17 | See application- to be clarified | 2023-04-10 | 2023-05-31 |  |  |  | 10 | 10 | 2D High Resolution (2DHR) seismic, sub bottom profiler, multi beam, echo-sounder, sidescan sonar | 108 | 160 cu in | Summer | 0.39959 | 0.021835
GS/1533 | Completed |  | OPRED | Viking & LOGGs Fields | Chrysaor (harbour energy) | 49/12, 49/16, 49/17. 49/21, 49/22 | See application | 2023-04-15 | 2023-05-31 |  |  |  | 20 | 20 | Sub-bottom profiler pinger survey, multi-beam survey, side scan sonar survey, visual survey. | 52.9 | SEL 218 dB, SPL 236 dB | Summer | 0.19572 | 0.02139
MLA/2020/00489 | Completed |  | MMO | Sofia OWF UXO Sidescan sonar, multibeam echo sounder and magnetometer equipment | RWE LTD | N/A |  | 2023-06-02 | 2028-05-31 | [5 empty] | Geophysical surveys |  |  |  | 0 | 0
GS/1570 | Completed | 22/06/2023 | OPRED | Earn - 1 exploration well VSP | Dana Petroleum | 42/27 | See application | 2023-06-22 | 2023-12-31 |  | 2023-09-13 | 2023-09-13 | 2 | 2 | VSP of main bored and of sidetrack. | 0.0008 | SEL 219 dB, SPL 236 dB | Summer & Winter | 2.9599e-06 | 3.2349e-08
EXE/2023/00032 | Approved | 23/02/2023 | MMO | Dogger Bank South Geotech 23 Shallow Boreholes, Vibrocores and CPTs | RWE LTD |  |  | 2023-04-03 | 2023-09-30 |  |  |  | 20 | 20 |  |  |  |  | 0 | 0
GS/1596/0 | Completed | 2023-07-21 | OPRED | Selene seismic survey | Shell U.K. Limited | 48/8b | Epicentre 53d46m33.516S (N) , 1d30m57.737s(E) - 1km suvey area, 21km greater survey area | 2023-08-01 | 2023-10-31 |  |  |  | 7 | 7 | Geophysical and environmental site survey - 2D seismic, SBP, Magnetic, ES, MBES, SSS, Visual, Grab Samples | 717 | SEL 218dB, SPL 249dB | Summer and Winter | 2.6528 | 0.10147
GS/1604/0 | Submitted |  | OPRED | Viking Cabon Storage SBP survey | Chrysaor (harbour energy) | 48/20, 49/16, 49/17, 49/22 and 49/23 | See application | 2023-08-01 | 2023-12-31 | 2023-09-11 | 2023-09-18 | 2023-09-18 | 8 | 8 | Sub-bottom profiler (sparker or pinger) survey | 14km2 (Viking survey and Tee 1 area) | SEL 228 SPL(rms) 243 | summer | coming soon | #VALUE!
GS/1605 | Cancelled |  | OPRED | NEP Expansion Survey | BP EXPLORATION OPERATING COMPANY LIMITED | 44/21, 22, 26 and 27; 43/, 24, 25, 29 and 30 |  | 2023-09-01 | 2023-11-30 |  |  |  | 40 | 40 | 2D seismic (160 cu inch); SBP and SSS. | 655 | SEL 214dB SPL 245dB | Summer & Winter | 2.4234 | 0.52971
GS/1636 | Completed | 31/08/23 | OPRED | Sommerville and Anning Pipeline Route survey SBP | Hartshead REsources Ltd | 49/9, 49/10, 49/12, 49/14, 49/17, 49/18, 49/22, 49/26 & 49/27 | See application | 2023-09-02 | 2023-10-31 | 1900-01-16 |  |  | 25 | 14 | SBP | 14 | SEL 170dB SPL 223dB | summer and winter | 0.051798 | 0.0039627
GS/1635 | Submitted | 06/09/2023 | OPRED | Interconnector survey | Interconnector Ltd | 52/3 | see app | 2023-09-15 | 2023-10-31 | 2023-09-21 | 2023-10-11 | 2023-10-11 | 14 | 3 | SBP |  | SEL 241dB SPL 225dB | winter | 0 | 0
GS/1642 | Submitted |  | OPRED | Multi Site Survey - Baker Project | Petrogas North Sea Limited |  | See application | 2023-09-18 | 2023-11-30 |  |  |  | 3 |  | 2D seismic (160 cu inch); SBP | 0.33 | SEL 170dB SPL 223dB | Summer & Winter
GS/1643 | Submitted |  | OPRED | Multi Site Survey - Birgitta Project | Petrogas North Sea Limited |  | See application | 2023-09-18 | 2023-11-30 |  |  |  | 3 |  | 2D seismic (160 cu inch); SBP | 0.33 | SEL 170dB SPL 223dB | Summer & Winter

## 2024 Tracker
SNS ACTIVITY TRACKER | [17 empty] | Season | Area | Days
[18 empty] | summer | 27028 | 183
[18 empty] | winter | 12696 | 182
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | ACTUAL ACTIVITIES START DATE | ACTUAL ACTIVITIES END DATE | DATE OPERATIONS COMPLETED | DURATION OF ACTIVITY IN DAYS | DURATION OF ACTIVITY IMPACTING SAC IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | LINK TO DECISION | DAILY THRESHOLD (summer) | SEASONAL THRESHOLD (summer)
| Proposed is included to highlight the potential activities but should not be used to in AA | [6 empty] | Initial start date within the Application - remains the same for Audit | Initial end date within the Application - remains the same for Audit | Refined start date of activities - updated once the final programme has been | Refined end date of activities - updated once the final programme has been | Update from notification of completion | The number of days the activity will take place | The number of days the activity will impact the SAC | Be clear on the impact to the SAC and any information that could assist in completing AA | Still in discussion on if it is within the SAC or average WCS | SEL, dB, cu, kg - depending on activity - put as much information as possible | Which season is impacted? | Only take into account the none greyed out figures | Only take into account the none greyed out figures
MLA/2019/00488 | Completed | 11/03/2022 | MMO | NEUCONNECT BRITAIN LTD | NEUCONNECT BRITAIN LTD | N/A | See applicaton | 2023-05-08 | 2023-05-28 |  |  |  | 0 | 7 | No Geophysical surveys planned in 2024. | 314 |  |  | 1.1618 | 0.044439
DCO/2013/00011 | Approved |  | MMO | Sofia Offshore Wind Farm Piling | Sofia Offshore Wind Farm Limited |  |  | 2024-01-01 | 2024-12-31 |  |  |  | 365 | 100 | Piling. Combined with DBB piling = daily maximum 16.39% | 1995.83 |  | Summer | 7.3843 | 1.54
DCO/2013/00011 | Approved |  | MMO | Sofia OWF Piling - Offshore Converter Platform (OCP) pin-pile installation | Sofia Offshore Wind Farm Limited |  |  | 2024-04-01 | 2024-09-30 |  |  |  | 8 | 8 | Piling | 133 |  | Summer | 0.49208 | 0.021512
EXE/2023/00009 | Completed |  | MMO | Sofia OWF - geophysical survey (export cable) | Sofia Offshore Wind Farm Limited |  |  | 2023-05-01 | 2023-07-31 |  |  |  | 80 | 20 | Geophysical Surveys |  |  |  | 0 | 0
EXE/2023/00009 | Completed |  | MMO | Sofia - geophysical survey (array) | Sofia Offshore Wind Farm Limited |  |  | 2023-07-01 | 2023-12-31 |  |  |  | 0 | 0 | Geophysical Surveys |  |  |  | 0 | 0
MLA/2020/00489 | Completed |  | MMO | Sofia OWF UXO Sidescan sonar, multibeam echo sounder and magnetometer equipment | RWE LTD | N/A |  | 2023-06-02 | 2028-05-31 | [5 empty] | Geophysical Surveys |  |  |  | 0 | 0
MLA/2023/00209 | Submitted |  | MMO | East Anglia THREE - UXO Investigation and Clearance - High Order | Scottish Power |  | See applicaton | 2024-04-01 | 2024-09-30 |  |  |  |  | 3 | High Order UXO | 2124 |  | Both | 7.8585 | 0.12883
MLA/2023/00209 | Submitted |  | MMO | East Anglia THREE - UXO Investigation and Clearance - Low Order | Scottish Power |  |  | 2024-04-01 | 2024-10-31 | [5 empty] | Low Order UXO | 79 |  | Both | 0.29229 | 0
DCO/2016/00024 | Approved |  | MMO | Dogger Bank B | SSE |  |  | 2024-03-01 | 2024-08-31 |  |  |  | 214 | 95 | Piling. Combined with Sofia piling = daily maximum 16.39% | 2123.7 |  | Summer | 7.8574 | 4.079
| Proposed |  | MMO | Hornsea Three Landfall HDD UXO Inspection and Removal | ORSTED |  |  | 2024-08-01 | 2024-12-31 |  |  |  | 153 | 100 | UXOs |  |  | Summer | 0 | 0
MLA/2023/00373 | Submitted |  | MMO | NEUCONNECT BRITAIN LTD UXOs | NEUCONNECT BRITAIN LTD |  |  | 2024-04-01 | 2024-09-30 |  |  |  | 183 |  | UXOs |  |  |  | 0 | 0
GS/1605 | Approved |  | OPRED | NEP Expansion Survey | BP EXPLORATION OPERATING COMPANY LIMITED | 44/21, 22, 26 and 27; 43/, 24, 25, 29 and 30 |  | 2024-04-01 | 2024-06-30 |  |  |  | 40 | 40 | 2D seismic (160 cu inch); SBP and SSS. | 655 | SEL 214dB SPL 245dB | Summer | 2.4234 | 0.234
TBC | Cancelled | Resubmitting spring 2024 | OPRED | Q43 Lodestone West 2023- multi-client regional survey | CGG Services (UK) Limited | 41/11, 16, 21, 42/6 to 25, 43/6 to 25, 44/6, 11,16, 21 | See application- to be clarified | 01/09/2024 maybe october | 1905-07-17 |  |  |  | 114 | 114 | 3D high resolution seismic survey- some details to be clarified |  | 3390 (cu in); SEL 233 dB; SPL 254 dB | Summer & Winter | 0 | 0
GS/1680 | Cancelled |  | OPRED | UK SNS Transformation 3D | WesternGeco | 23/17 - 21; 23,25 and 29. 44/21-30 |  | 2024-03-25 | 2024-10-24 |  |  |  | 178 | not stated | Towed Streamer 3D Marine Seismic Survey in an area just south of the Dogger Bank shallows area in the UK Southern North Sea. The maximum survey area size is approximately 5,100sqkm. | 4.76 | 1090cu in |  | 0.017611 | #VALUE!
GS/1642 | Submitted |  | OPRED | Baker Survey - 2D seismic & Sub-bottom profiler. (Winter area only) | PETROGAS NORTH SEA LIMITED | 47/3 | see application - winter | 2023-09-18 | 2024-07-31 |  |  |  | 4 | 4 | 2D seismic (160 cu inch) and SBP. |  | 160 cu inch | winter | 0 | 0
GS/1692 | Submitted |  | OPRED | NEP Expansion Survey: Phase 2 - 2D seismic | BP EXPLORATION OPERATING COMPANY LIMITED | 43/17, 43/21, 43/22 | See application | 2024-04-15 | 2024-07-15 |  |  |  | 5 | 5 | 2D seismic |  |  |  | 0 | 0
GS/1682 | Submitted |  | OPRED | Katy KT, NW Bell ZX & Murdoch KM | Chrysaor Production (U.K) Limited | 44/19, 44/22, 49/22 | See applicaton | 2023-02-01 | 2023-08-31 |  |  |  | 3 | 1 | Sub-bottom profilling and other survey methods (echo-sounder, sidescan sonar, multibeam sonar) | 0.25 | SEL 232 dB SPL 250 dB | Both | 0.00092497 | 5.0545e-06
GS/1683 | Submitted |  | OPRED | Hunter Wells Survey | Premier Oil | 44/23 | See applicaton | 2024-02-01 | 2024-08-31 |  |  |  | 3 | 3 | Geophysical survey using a passive magnetometer, MBES, SSS and SBP. | 0.75 | SEL 232 dB SPL 250 dB | Both | 0.0027749 | 4.549e-05
GS/1689 | Approved |  | OPRED | Crosgan 2D seismic | One Dyas UK Limited | 42/14 | See applicaton | 2024-03-01 | 2024-09-30 |  |  |  | 4 | 4 | 2D seismic (160 cu inch) and SBP. | 1 | 160 cu inch |  | 0.0036999 | 8.0871e-05
DR/2469 | Approved | 04/04/2024 | OPRED | Hewett Injectivity Testing | ENI UK Limited |  |  | 2024-04-05 | 2024-04-30 |  |  |  | 1 | 1 | Downhole perforation using explosives 3500ft below seabed. |  |  | Summer | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0
[19 empty] | 0 | 0