FCDO
Programme Operating Framework

Foreword from PUS

1. Introduction

2. PrOF Principles

3. PrOF Ruleset

4. PrOF Roles and Responsibilities

5. PrOF Lifecycle

6. PrOF Governance

Foreword from 2PUS
The FCDO delivers many of its strategic objectives through programmes and projects. It does this on some of the most complex international policy issues in the world and in some of the most complex and fragile environments. It takes world class project delivery to deliver on commitments in the Integrated Review Refresh and the International Development Strategy, and to help those in most need around the world. Our aim is to ensure that there is policy coherence and that themes and geographies are joined up.

 The FCDO Programme Operating Framework (PrOF) was first published in 2021 as the structure within which programme teams throughout the network will operate for ODA and non-ODA. In 2022 the PrOF was reviewed by the Independent Commission for Aid Impact (ICAI), who endorsed the PrOF, and made recommendations for its improvement. Their findings have been integrated in this version, updated for 2023. The PrOF continues to ensure that we deliver excellent programmes and address the FCDO’s priorities through a blend of diplomacy and development programming, spending Official Development Assistance (ODA) and non-ODA funds, and ensuring that we comply with cross-HMG standards on project delivery.

Alongside the updated mandatory PrOF rules, the programming principles set out the ways of working which you are encouraged to use to shape how you work – ensuring that the FCDO reflects the values of respect, expertise, resilience, and kindness to empower all of us to deliver effectively and to continue to make the FCDO the best department it can be.

The PrOF sets out the expectations of teams involved in the FCDO’s policy programme delivery. In return, teams can expect to be supported and enabled at all stages and levels by their FCDO senior managers in utilising the FCDO capability and profession offer, structured around the associated competence framework, which includes the opportunity to become accredited professionals in programme management.

This principles-based approach reflects the vision for programme delivery in the FCDO; flexible, agile and adaptive - and ready to pioneer methods in places where there is no tried and tested approach.

As Accounting Officer for the FCDO’s ODA spending, I take our responsibilities in oversight of the PrOF’s operation seriously – ensuring appropriate controls are in place, and monitoring performance and compliance in programmes through MI reported to the Management Board. I expect you and your teams to work within this framework and to continue to embed this approach in the way the FCDO delivers our work.

1. Introduction

This chapter introduces the PrOF and where it applies. This section is most useful to those who have never used the PrOF before or who are unfamiliar with the FCDO approach to programme delivery – for example new Portfolio SROs or new programme managers.

1.1 What is the programme operating framework

Excellent programme delivery is crucial for FCDO to deliver its UK government objectives and is expected by Cabinet Office. Whether the work is on National Security Council (NSC) priorities, the UK’s foreign policy priorities or eradicating poverty in a complex and fragile world, delivering results and addressing the underlying causes of poverty and conflict requires programmes that are flexible and designed to respond to and influence the local context.

FCDO needs to maintain high standards of programme delivery and risk management in a wide range of difficult operating environments. We must make risk- and evidence-based decisions, apply professional judgement, act proportionately, learn and share lessons, ensure a clear audit trail of our decisions and be properly accountable to UK taxpayers in everything we do. Our approaches are drawn from best practice, building on established project and programme management approaches and realising our obligations for alignment with The Orange Book: Management of Risk – Principles and Concepts, Managing Public Money and HM Treasury guidance on business case approvals.
FCDO works closely with the Infrastructure and Project Authority (IPA), to ensure that the PrOF sets a high standard for delivery in FCDO and is in strong alignment with central government expectations for international programming. The IPA is the government’s centre of expertise for infrastructure and major projects. It leads the government project delivery function and sits at the heart of government, reporting to the Cabinet Office and HM Treasury. The IPA is responsible for system level improvements across the project delivery landscape and will set the framework for government project delivery, project assurance and support arrangements for government projects which departments are required to follow.

The PrOF specifies the rules which must be applied in delivering all FCDO’s policy programmes. It is nested within FCDO’s corporate operating framework – which provides all of the wider organisation-wide set of rules that each member of staff must follow.

The PrOF applies to the breadth of project and programme delivery in pursuing FCDO’s policy objectives – this includes development, diplomacy, and our financial transactions (such as guarantees). The PrOF does not cover FCDO operational expenditure (overseen by the Operations Committee), such as the delivery of FCDO’s infrastructure, IT systems etc.

The PrOF aims to:

- Be a “one-stop framework” for programme delivery, giving clarity on what is mandatory, setting the parameters within which all teams must work.
- Give clear accountabilities and responsibilities and roles for delivery – enabling empowered accountability​ with support from the centre.
- Provide a framework which builds on the successes and the lessons of programme delivery approaches (in FCDO and elsewhere)
- Take a principles-based approach to achieving high quality, contextualised programme delivery, embodying and complementing the FCDO’s values
- Guide FCDO programme teams in responsive programme delivery in complex, volatile and ambiguous environments
- Enable programmes and projects in FCDO to contribute in a coherent way to higher level objectives at Portfolio and Department level​.

The PrOF includes:

Principles to guide staff in designing and delivering high-quality programmes and presenting to external implementers how the FCDO is committed to delivering internationally. The programme delivery principles of the PrOF are designed to complement the FCDO How we Work Statement. Rather than expanding on the statement, the principles work to contextualise the culture of the new department tangibly in the way we deliver programmes.

Roles and responsibilities to inform teams what is expected of different members of FCDO programme teams.

Mandatory rules, clearly explained with an expanded rationale to assist teams in taking a proportional approach to their programmes and providing a sense of empowered accountability to teams.

Governance, risk and assurance arrangements to facilitate effective oversight of programme delivery and implementation of the PrOF by programme teams.

Links to good practice guides that draw on experience and expertise from across FCDO and beyond. These documents contain no additional rules or mandatory procedures. They are designed to illustrate what can be done within our operating framework and to deepen learning.

The PrOF is governed by the Programme Cycle Panel (PCP), consisting of Deputy Directors representing the breadth of FCDO, and chaired by the Centre for Delivery. This panel is providing oversight and governance of the PrOF, carefully considering any proposals for new rules or changes to rules and protecting against more rules being added unless absolutely necessary. Anyone in the Department can propose changes to the framework and its ruleset. Proposed changes should be emailed to the Centre for Delivery. You may be invited to attend the PCP to talk about the proposal to help the PCP reach a decision about the change.

DEFINITIONS

- A portfolio comprises part or all of an organisation’s investment required to achieve its objectives. Governed through its portfolio (or business) plan, a portfolio comprises of programmes, projects, and other related work.
- A programme is a thematic set of inter-related projects and activities designed to bring about outcomes that support higher level strategic objectives.
- A project is a set of discrete, time bound interventions usually designed to produce a set of outputs. Projects may be managed in-house but will more often be implemented by external partners under a funding arrangement.
- Activities are everything making up a programme that are not projects. This may include FCDO staff salaries and costs funded from the programme, or discrete activities undertaken by others in support of the programme – for example specific pieces of monitoring or operational research, or audits.
- Programme lifecycle - The design, delivery and assessment of programmes and projects follows a common process or "lifecycle", consisting of definition, mobilisation, delivery, and closure.

1.2 Who is the PrOF for?
The PrOF is for everyone in FCDO because programmes are an integral part of policy-making and delivery: that includes senior decision-makers such as Heads of Mission, Directors, Development Directors, Heads of Department - as well as members of programme teams (such as Programme Managers, Advisers, Senior Responsible Owners, Programme Responsible Owners), corporate teams, our partners, and other external stakeholders.

FCDO programme teams are expected to make proportionate judgements on how to apply the rules for their intervention and context informed by a good understanding of the risks they are accepting through their approach. Risks must be managed well, with resources prioritised to reducing risks which exceed our risk appetite. FCDO Teams are:

- Empowered to create better policy and programme outcomes through increased innovation, taking well-­judged risks and managing them appropriately, responding to assurance findings and having the flexibility to adapt to realities on the ground.
- Accountable for effective delivery, through clarity of roles and responsibilities to consider choices and make good decisions, seeking early approval (and re-approval, where appropriate), and utilising good quality information and evidence.

1.3 Applying the PrOF across the diverse FCDO portfolio

The PrOF applies to all programmes led and delivered through the FCDO (i.e. on the FCDO baseline – so not just those that are funded by the FCDO, but also CSSF). This includes the full spectrum from smaller projects through to the large value multilateral contributions and subscriptions, but excludes corporate programmes, as set out above. This ensures the strategic direction and risk parameters of all programmes are considered holistically and within the context of FCDO’s broader policy priorities and activity.

We recognise that programmes are not all the same. The PrOF Rules apply to all Projects and Programmes although the rules may apply in different ways, depending on the type (and size) of project/programme. For example, smaller projects (under £250K) may have streamlined approvals and reviews, including when grouped into a programme under £2m (such as in the case of many International Programme projects). Another example is the cross-government CSSF projects/programmes. These projects/programmes are managed on the FCDO baseline – and are subject to the PrOF (the PrOF takes precedence over the CSSF Operating Framework, managed by the Joint Funds Unit). The PrOF also applies differently where we are making core contributions to multilateral organisations, where a Concept Note is not typically required in the approval process.

1.4 FCDO Portfolio Management

The IPA defines a portfolio as the programmes, projects, and related work (which may be in the form of policy development) required to meet common objectives. In a portfolio there are choices to be made about the activities undertaken in pursuit of the portfolio objectives - unlike in a programme, where all the activities need to be delivered to achieve the outcome. In FCDO, business and country plans describe some of our portfolios. A portfolio focus drives better ways of working - integrating project and non-project activities to more effectively manage and deliver our objectives.

1.5 Management Systems and Reporting Processes: Maintaining an Evidence Base

Reliable monitoring and reporting processes allow us to ensure our delivery methods are evidence based, accountable and stand up to scrutiny, in line with the guiding principles of FCDO delivery. The Centre for Delivery is generating management information and reporting on programme performance – drawing on data in the programme management platform (AMP). This reporting is made available to the organisation and formally reported to the Investment and Delivery Committee and the Management Board to ensure that programme activities are meeting expectations, following rules, achieving impact, and delivering value for money. Aggregating programme data also supports strengthened portfolio management allowing us to understand the make-up of individual programmes and portfolios to ensure they remain aligned with overall strategic objectives.

2. Programme Operating Framework Principles

2.1 The FCDO How we Work Statement highlights that culture underpins delivery. The programme principles reflect in more detail what that means for programme delivery, illustrating how values drive programme excellence.

The programme principles should form a common vocabulary, a basis from which all projects and programmes throughout the portfolio can build upon and refer to. They complement and expand upon FCDO-wide principles and embody empowered accountability. They provide teams with the language for engagements with partners, stakeholders and assurers about what and why decisions were taken throughout the delivery cycle.

2.2 The principles have been mapped to the rules which follow – so when thinking about what the rule says, also think about how to follow the rule by reflecting on the associated principles.
How we lead and behave towards each other: We put respect and kindness first. We are inclusive, we get to know each other, and value our diversity and the contribution we each bring. We are fair, act with integrity, and tackle inequality and unacceptable behaviour. We work together and take responsibility to solve problems. Therefore, in our programmes we are:

Collaborative
We work and learn together to help and support each other across the organisation and build capability. We build strong working relationships with partners in order to deliver results, including formal collaborations on knowledge sharing as a risk mitigation strategy. Teams evolve in make-up as necessary and collaboration with delivery partners remains a consideration through the project lifecycle. We ensure diversity of expertise in all collaborations so that our ideas are scrutinised from a range of perspectives.
Honest
We speak truth to power. We foster an open and honest culture, encouraging challenge and the flagging of risks. We escalate risks and issues which exceed programme appetite, and ensure we have a listening culture to hear all concerns. FCDO programme teams are empowered to challenge colleagues and senior leaders at all stages of the programme cycle.

How we make decisions: We draw on the expertise, insight and diverse perspectives of people across the FCDO, HMG, and beyond. We use the best available data and evidence. We are open to challenge and take a long-term approach. We are transparent about the rationale for decisions and smart about taking and managing risks. Therefore, in our programmes we are:

Professional
We aim to deliver maximum impact and value for taxpayers’ money, we follow the Civil Service Code and HM Treasury’s guidance on Managing Public Money and we get the basics right. We are knowledgeable, experienced and commercially astute - and our delivery teams hold our partners to account. FCDO sets the standards for international diplomacy and development best practice.

Ambitious
Drawing on our knowledge, skills and experience, we are bold in proposing transformational programmes in challenging and high-risk environments, and we openly discuss the risks with ministers and colleagues.
Transparent
British taxpayers, beneficiaries, and constituents in the countries where we operate have a right to know what we’re doing, why and how we’re doing it, how much it will cost and what it will achieve. Where total transparency is not possible due to heightened sensitivity, FCDO will be clear and able to justify our rationale for this decision.

How we get the job done: We are responsive and alert to emerging opportunities. We encourage learning, innovation and use of data and digital. We are all clear on what we are expected to deliver and support each other in doing so. We look to reduce duplication and unnecessary process. We are committed to transforming both the FCDO and the way HMG delivers international policy. Therefore, in our programmes we are:

Innovative and Agile
We deal proactively with uncertainty and complexity, identifying where it exists and building in ways to respond to and manage it. We are ready to adapt existing and pioneer new design and delivery methods where the context allows and there are no tried and tested approaches. We are outcome focused and prepared to flex based on evidence. We encourage and reward innovative, creative, agile and value for money approaches to achieve impact. We are alert and prepared to respond to emerging opportunities and volatile or changing environments.
Responsible and Accountable
We are responsible for delivering against ministerial and HMG priorities, with a clear understanding of our role and the role of others in pursuing government policy. We are accountable for rigorous programme design, managing programme risk and performance effectively, maximising benefits and avoiding doing harm. Programme Teams will ensure the information used in our programmes is from trusted sources and consider the risks of dis-and-misinformation. As the people closest to the detail, beneficiaries, programme constituents, and FCDO programme teams are empowered to take decisions within their projects once all core rules are complied with.
Context-specific
By drawing on available evidence and listening to the views and experiences of the breadth of our stakeholders (especially beneficiaries and programme constituents), we understand the strategic, social, political, economic and operational environments within which we work, influencing the political context and HMG’s international policy priorities. We take a risk-based approach to gaps in our understanding and ensure our programmes are well integrated to the context.
Evidence-based
We plan rigorously using evidence to create a strong foundation on which to base change. We are constantly reviewing and where evidence gaps exist, we take steps to fill them, testing new approaches and applying our learning as we go. We identify errors and opportunities; we learn from and share lessons readily. We monitor, record and report progress through the appropriate channels including ministers, as necessary. If success no longer seems achievable, we are prepared to flex or initiate closure, taking stock of what we have learnt to inform future endeavours.

Proportionate and Balanced
We make proposals and take decisions that are proportionate to the situation, the information available and level of urgency and escalate where appropriate. We work in planned, manageable stages, pausing to assess delivery and ensure continuing viability at each stage of the project.

Value for Money

Value for money (VfM) is a key consideration throughout the PrOF and the supporting relevant principles. This is important as we are spending taxpayers’ money and need to be able to explain and defend out decisions. VFM enables FCDO to maximise the impact and cost-effectiveness of each pound spent through consideration given to the following:

- economy - buying of inputs of appropriate quality at the right price
- efficiency - how well inputs converting to outputs
- effectiveness - how well are outputs produced by an intervention having the intended effect e.g., children less susceptible to childhood diseases, and
- equity - ensuring interventions reach marginalized or hard to reach populations.

VFM means that we should aim for the best feasible programme to achieve maximum impact. For example, this would mean a speedy response in the case of humanitarian crises work, where time is of the essence. A speedy response in cases like this is essential where the interventions impact outweighs cost savings which may have been secured with slower paced procurement. VFM should be assessed through drawing on evidence to appraise delivery options at the design stage of a programme. It is not about opting simply for the cheapest option or easiest things to measure. It is more about understanding the drivers of costs to ensure we get the desired quality at the lowest feasible price. VFM should be considered throughout the life of a programme to ensure it drives decisions and is considered in programme and project evaluations.

3. Programme Operating Framework Ruleset

3.1 This section sets out the mandatory rules for FCDO programme delivery. Each core rule (listed below) has an associated 1-pager, which provides the information which teams are required to understand:

- Why FCDO has this rule - the rationale, logic and purpose of this rule for FCDO
- Who is responsible and accountable for the actions in implementing the rule. There is more information on implementing this in practice in the Roles & Responsibilities section
- How you need to go about implementing the rule

In providing this expanded information for each rule, the intention is that teams will have a better understanding of the mandatory structure within which they need to operate. They will also have a fuller appreciation of their empowerment to use their judgement and a clear understanding of their accountability. Given the diverse nature of the FCDO portfolio, the intent is to ensure that each team can take a proportionate approach that is appropriate for their programme.

3.2 Teams should use their judgement, in line with the principles outlined above, in applying the rules proportionately to their programme or project. This will help to ensure that unnecessary duplication is avoided whilst ensuring that the team is effectively accountable, in accordance with the rules, for the delivery of work managed on the FCDO baseline.

3.3 Within each rule 1-pager there are associated pop-out boxes. These contain examples of how the principles should be applied in implementing the rule, disaggregation of the rule for application to multilaterals and sign-posting to further guidance (such as ProF Guides).
Working with multilaterals
Where it is useful or necessary to disaggregate the rules for application to multilateral programmes this is included as a pop out box.

Principles in practice:
Principles in practice boxes are included throughout the Framework. Each rule is linked to one or more of the core FCDO Delivery principles. The in practice boxes will allow you to contextualise the principles within each rule. The guiding principles provide teams with a common vocabulary with which to communicate and justify decisions taken throughout the programme cycle.

Further guidance and learning: Sources of further information and guidance and learning on implementing the rule. Guidance documents (PrOF Guides) will not be fully updated for 1st April – this will be an ongoing activity.

3.4 Programme Rules and One-pagers

Operating Framework and Strategic Alignment Rules

1. Portfolios, programmes, and the projects within them, must comply with all relevant UK law and follow guidance including regulatory requirements. International law including human rights and humanitarian law and reputational risks to HMG must also be considered. (1-pager)
2. All transactions reported as Official Development Assistance (ODA) must meet the agreed OECD definition of aid, principally that the main objective must be to promote the economic development and welfare of an ODA eligible country. (1-pager)
3. All programmes and projects must align with FCDO and HMG policy priorities and business objectives. (1-pager)
4. All programmes must have a named Senior Responsible Owner (SRO) and Programme Responsible Owner (PRO). (1-pager).
5. All programmes must align with the Paris Agreement – an international treaty on climate change and assess climate and environmental impacts and risks, taking steps to ensure that no environmental harm is done. Any International Climate Finance (ICF) programmes must identify and record ICF spend and results. (1-pager)
6. Programmatic and project decisions (including payments and commitments) must only be taken within delegated budget and approved levels of individual authority and in line with the agreed risk appetite. Decisions going beyond these limits and risks which exceed appetite must be escalated to the appropriate level. (1-pager)
7. All FCDO programmes and projects must be as transparent as possible with taxpayers, our partners, host countries and programme constituents (beneficiaries). Programme documents and decisions must be saved correctly for publication. Sensitive information must be treated appropriately. (1-pager)
Programme Design and Approval Rules

1. At an early stage of design, an outline of the programme's intended outcomes, operating context, activities, budget and high-level risks must be set out and approved at the appropriate level, using the Concept Note template. All Concept Notes over £5m must be approved by a Minister (FS if Minister decides to escalate). (1-pager)
2. All programmes must be appropriately designed and have a suitably approved Business Case (BC) in place prior to the start date (and for the full duration), using the BC template. Material changes and extensions to this design must be formalised and approved in a BC addendum. Prior HMT approval (via a concept note) is required for any announcements involving spend if related to a business case or a package of business cases, yet to be developed, totalling £100m or over across the lifetime of the spend period. Only crisis programming should include Internal Risk Facilities/contingency funds, and these should be limited to a maximum value of 10% of a programme’s proposed lifetime value. (1-pager)
3. All programmes (and policies) must consider and provide evidence on how their interventions will impact on gender equality, disability inclusion and other equality considerations. (1-pager)
4. For any programmes which may involve novel and contentious financial arrangements, teams must engage with the Management Accounts Group and Financial Accounting at concept note stage. And any programmes carrying significant diplomatic, financial, or reputational risk must consider whether FS should approve (to be escalated through relevant Minister). (1-pager)

1. All programmes must follow FCDO's branding guidance, and appropriately document their approach to external communications. (1-pager).
2. Digital elements of programmes or projects (e.g. text messaging, cash transfers with a digital angle, websites and databases) must be reviewed at the earliest possible stage in the process by FCDO's Portfolio Assurance and Controls Team, and most also require assurance from the internal Portfolio Assurance Forum (PAF). (1-pager)
Mobilisation and Procurement Rules
1. FCDO can only pay for costs that are incurred after signature and between the start and end date stated in a funding agreement or contract. The duration and value of all funding arrangements must be fully covered by an approved budget (e.g., business case or project proposal) and must use the latest funding arrangement templates or frameworks. (1-pager)
2. The tender and awarding of new contracts and amendments must comply with the Public Contract Regulations 2015 or Defence and Security Public Contract Regulations 2011. An approved budget must cover the full period of any contract and amendments. Relevant approvals must be in place as detailed in associated guidance. All contracts must have a designated, appropriately accredited Contract Manager and comply with Cabinet Office transparency requirements. Contracts must be effectively managed proportionate to their complexity, risk, value, and opportunity throughout the life of the programme. (1-pager)
3. For each funding arrangement FCDO must have a suitable, proportionate and documented assessment of any partner who is intended to be the direct recipient of FCDO funding, to determine if they have the capacity and capability to manage programme funds and deliver the programme or project objectives. (1-pager)
4. Staff must declare any conflicts of interest, or offers of gifts, advantages or hospitality, as soon as they arise. (1-pager)
Programme Management and Delivery Rules

Risk throughout the life of a programme or project must be managed in line with the agreed risk appetite using appropriate controls. (1-pager)

Any suspicions and/or credible allegations of fraud, terrorist financing, money laundering, bribery, corruption, sexual exploitation and abuse and sexual harassment (SEAH), by any person or any partner (including downstream delivery partners) connected to a FCDO programme or project, must be promptly reported to the FCDO Fraud and Safeguarding Investigation Team in Internal Audit and Investigations Directorate. (1-pager)

All projects, programmes and portfolios must have sufficient monitoring in place to provide performance and financial oversight, manage risks and support decision-making at appropriate levels. (1-pager)

All programmes must undergo a formal review of progress and effectiveness at regular intervals (annually, as a minimum, and after completion) using an agreed results framework or logframe and the appropriate tools and templates. (1-pager)

Any programme or project that demonstrates sustained underperformance must be subject to formal improvement measures, before a decision is taken at the appropriate level to continue, to restructure or to close it. (1-pager)
Financial Management Rules

Budgets must be accurately profiled and forecast, regularly reviewed, and updated as necessary. (1-pager)

Funds must only be paid to the intended recipient and only be used for the purposes formally agreed. (1-pager)

No payment can be made in advance of need, i.e., before the funding is required to enable activities to proceed. (1-pager)

Any ODA programme foreign currency commitments above £50,000 must be agreed in advance by the Head of Financial Accounting & Policy. ODA programme foreign currency commitments below £50,000 must be agreed by the Director or Head of Mission. (1-pager)

FCDO staff roles charged to a Programme or Project budget (except for CSSF/ISF) must be essential for the delivery of a programme, approved in line with PrOF Rule 9, and offer better value for money than an outsourced alternative. Details must be notified to Centre for Delivery and Strategic Finance as soon as a project-funded role is being considered. (1-paper)

A complete, accurate and up-to-date inventory must be maintained for all programme assets owned by FCDO. These assets must be disposed of in a way that represents best value for money, with a clear record of decision making and appropriate approval of transfer. (1-pager)

The write-off of costs related to losses or fruitless payments, including assets lost, stolen or damaged, must be approved at the appropriate level. (1-pager)

Programme Closure Rule

All programmes and projects must be closed effectively and responsibly, even when closing early. Outstanding project payments must be made, liabilities extinguished, and underspend returned to FCDO within eighteen months of the programme’s end date. All required audited accounts and financial statements covering the full duration of every project withing the programme must have been received before the programme can then be closed and archived. (1-pager)

GLOSSARY

Smaller Projects/Programmes
The definition of a Smaller Project is a single funding arrangement with a single implementer (where implemented by an external organisation) with a defined output or set of outputs and not exceeding £250,000 in value. Smaller Projects are usually clustered in a “Programme” for approval, performance reporting and accountability purposes (these are not strictly programmes as defined by the PrOF, because they may contribute to multiple Outcomes, but can be treated as a programme provided the total budget does not exceed £2 million).
The PrOF applies lighter touch processes for approval and performance measurement of portfolios of smaller projects. This means a single stage of programme approval, through a light touch Business Case (there is no need to do a separate Concept Note) and a lighter touch process and template for annual reviews of progress and performance. All other PrOF Rules apply to these projects and programmes but should be applied in a proportionate way.

Core Multilateral / International Subscriptions
Multilateral institutions are key delivery partners that mobilise significant resource and expertise to deliver key outcomes in UK priority areas. Working through multilaterals expands our global reach and influence and enables us to work effectively with other international partners. Our multilateral investments must be clearly justified and are annually assessed to ensure they deliver results, remain cost effective and value for money.
International Subscriptions are legally binding payments to organisations where we are a member. The FCDO pays subscriptions to the Commonwealth, Council of Europe, United Nations Office of the High Commission for Human Rights (OHCHR), Organisation for Economic Cooperation and Development, North Atlantic Treaty Organisation (NATO), Organisation for Security and Co-operation in Europe (OSCE), United Nations.
The PrOF applies to all multilateral programmes and international subscriptions, but there are some rules that don’t apply or are applied differently, for example where FCDO is making core contributions to multilaterals or paying international subscriptions. These areas are made clear in the detail of the programme operating framework rules.
UK Integrated Security Fund (CSSF)
The CSSF was created in 2015 to “prevent conflicts and tackle threats to UK interests that arise from instability overseas”. The CSSF plays a key part in driving the Government’s fully integrated response to conflict and instability, guided by UK National Security and UK Development priorities. Its programmes help uphold the rules based international system and drive forward the UK’s ambitions to meet the Sustainable Development Goals (SDG), particularly SDG 16 – to promote just, peaceful, and inclusive societies. The UK Integrated Security Fund (UKISF) will replace the CSSF.

UK ISF/CSSF projects/programmes which are managed on the FCDO baseline are subject to the PrOF, but also to the Joint Funds Unit’s UK ISF/CSSF operating framework. The requirements of these two frameworks have been harmonised as far as possible. Some PrOF Rules are applied in a different way to UK ISF/CSSF Programmes - specified in the relevant Rule one-pagers. Concept Notes are not required for UK ISF/CSSF Programmes under £5 million in value. As a cross-government fund, UK ISF/CSSF also has different rules governing when the cost of FCDO staff can be charged to a project or programme, so PrOF Rule 27 is applied differently.
CDEL
Capital DEL (CDEL) is a budget limit of total capital expenditure permitted in year, e.g., infrastructure spending or spend by multilateral development banks where FCDO is a shareholder. It also includes programme expenditure where our funding creates or acquires an asset and research and development spend which meets the FCDO research definition as approved by the Chief Scientific Adviser. Research and Evidence Directorate leads on FCDO’s research expenditure and is responsible for reporting to HMG and internationally. Teams should ensure that CDEL spend recorded as research is applied in consultation with Research and Evidence Directorate and meets this definition. If teams are unsure whether a programme meets the definition of CDEL research, they should contact the Research and Evidence Directorate.
Non-Fiscal Capital DEL (also known as Development Capital/Financial Transaction spend) – this is a subset of FCDO’s Capital DEL. The main difference is that FCDO is creating an asset on its own balance sheet. Creating this asset will mean that FCDO has a legal right to reclaim any returns on its investment (principal, interest, and dividends) and/or direct how those returns are to be used.

Rule 1: Portfolios, programmes, and the projects within them, must comply with all relevant UK law and follow guidance including regulatory requirements. international law including human rights and humanitarian law and reputational risks to HMG must also be considered.
Principles in Practice
Responsible and Accountable: HMG must comply with applicable UK and international legal obligations. Our programmes must uphold HMG’s reputation as a defender and promoter of human rights and democracy. Programmes which do not comply with applicable legal obligations pose a reputational risk to the government and undermine the programme’s and wider FCDO objectives.

Why? HMG must comply with all relevant UK law and guidance. All programme interventions must also be consistent with FCDO policy and objectives.

Who? Heads of Mission (post) and Directors (HQ) must provide evidence of their portfolio’s compliance with relevant UK law in the annual Management Assurance Process. Programme Responsible Owners are responsible for identifying security and justice sector interventions requiring specific assessment and approval. Legal Directorate are available for advice. Questions of local law should ordinarily be directed to Honorary Legal Advisors or local lawyers at post.

How? The Head of Mission/Director must ensure that their portfolio complies with all relevant UK law and guidance, in particular (but not exhaustive):
Development and humanitarian assistance under the International Development Act and Official Development Assistance (see Rule 2) are subject to different tests, Aid spending should meet both tests.

- International Development Act 2002 which, following amendment by the International Development (Gender Equality) Act 2014, includes the gender equality duty.
- Human Rights Act 1998
- Terrorist Act 2000 (TACT)
- International Development (Reporting and Transparency) Act 2006 for all aid spend (ODA and non-ODA).
- Export Control Order 2008
- Equality Act 2010 (which includes the Public Sector Equality Duty – see rule 10)
- Human Medicines Regulations 2012 Human Medicines Regulations 2012
- Public Contracts Regulations 2015 and Defence and Security Public Contracts Regulations 2011 and relevant Procurement Policy Notes (PPNs), for example, PPN 02/23 - Tackling Modern Slavery in Government Supply Chains - Guidance
- Sanctions and Anti-Money Laundering Act 2018 and regulations made under it, such as the Russia (Sanctions) (EU Exit) Regulations 2019 and the Sanctions (Humanitarian Exception) (Amendment) Regulations 2023
- Data Protection Act 2018 (and the UK General Data Protection Regulations)
- Environment Act 2021, including the Environmental Principles Policy Statement Duty, which came into force on 1 November 2023 and applies to policy making including Business and Country Plans and portfolio strategies
- Subsidy Control Act 2022 (and the UK subsidy control statutory guidance)
- British Sign Language Act 2022 (A BSL Advisory Board will issue guidance to departments on the promotion and facilitation of BSL)
- The Procurement Act 2023, its main provisions are expected to come into force in October 2024.

Interventions in the Security and Justice Sector must be assessed and approved in line with Overseas Security and Justice Assistance (OSJA) guidance before a programme or project is approved, and before a Grant Agreement, MoU or Contract is signed. OSJA’s consider the human rights (HR) and international humanitarian law (IHL) risks of programmatic activity which might support HR or IHL violations in the host country. Any funding to these types of activities, while meeting HMG’s national security priorities, must also be consistent with UK values, defending and promoting human rights and democracy. OSJAs must be updated regularly and at all stages of the programme cycle, including concept note, business case, annual reviews, and extensions, and where a substantial change in circumstances has significantly altered the risk.

Working with multilaterals
International financial institutions and other multilaterals operate in accordance with international law, rather than the laws of each of their shareholders.

Rule 2: All transactions reported as Official Development Assistance (ODA) must meet the agreed OECD definition of aid, principally that the main objective must be to promote the economic development and welfare of an ODA eligible country.
Principles in practice:
Accountability: ODA spend must be compliant with the OECD’s definition and the statutory power in the International Development Act 2002 (IDA). ODA spend can be challenged by Parliament and ICAI. Any perceived lack of consistency or robustness in our application of the rules risks significant reputational damage.

Why? In 2013 HMG committed to spend 0.7% of UK Gross National Income (GNI) on aid. For 2021 this was reduced to 0.5% because of the economic impact of COVID-19 on the UK but it is expected to return to 0.7% when fiscal conditions allow.
'Official development assistance' or ODA is the internationally agreed definition of what counts as aid. HMG reports to the OECD annually and as part of its national statistics. If FCDO spend is incorrectly or misleadingly classified as ODA, it may be rejected by the OECD impacting on the UK's ability to meet its ODA commitment, forcing a reclassification to non-ODA causing significant difficulties with budgetary planning in HMG’s ODA and non-ODA budgets. NB FCDO non-ODA programme spend is typically either for activity to deliver FCDO objectives in non-ODA countries or for activities in ODA countries which falls outside the OECD definition and domestic legislation on ODA (all non-ODA spend should be based on separate spending powers – if in doubt check with legal and/or finance business partner). Some programmes may combine ODA and non-ODA spend e.g. co-efficients for multilateral activity. This means non-ODA programmes support a broad range of activities: key requirements are that the work is programmed in accordance with the PrOF rules/principles and that it will contribute to the specific policy goal for which the money was allocated. Non-ODA cannot be used to fund ODA eligible activities (See also Rule 3).

Who? Heads of Mission/Directors, and Development Directors where present, are accountable for ensuring their ODA portfolios are compliant with these requirements. Programme Responsible Owners are responsible for carrying out all relevant compliance checks on programmes.

How? ODA can only be spent on activities which have the economic development and welfare of an eligible country as the main objective. Secondary benefits to non-ODA eligible countries, including the UK, are acceptable only if the activity primarily benefits developing countries. There are more specific and detailed rules on ODA such as administrative costs, debt relief, social and cultural programmes, student costs, refugees, research, and peace and security activities, including counterterrorism and countering violent extremism. If you are proposing ODA spend in these areas or are unsure about the rules you should consult with the ODA eligibility team (details below).

In addition to the OECD DAC ODA rules and the International Development Act 2002, and taking into account internal policies, UK ODA must not be used to fund or procure the following:

- Activities which are not aligned with the Paris Agreement on climate change (see Rule 4).
- Exploitation of adult workers or employment of children.
- Luxury goods (incl. alcohol, tobacco, fur skins, pearls and precious and semi-precious stones).
- Drugs not on the World Health Organization Essential Drugs List (with limited exceptions).
- Pesticides, unless agreed by a Climate and Environment Adviser. The UK is a signatory to the Stockholm Convention that seeks to eliminate 12 persistent organic pollutants.
- Chlorofluorocarbons (CFCs). The UK is a party to the Montreal Protocol and the substances currently controlled by the Protocol may not be supplied under the aid programme.
- Tobacco. For any purpose that identifiably supports the tobacco sector, including the agricultural production and processing. General agricultural inputs, such as fertilisers can still be funded if the tobacco sector is not an identifiable consumer.
Any relationship, financial, programmatic or bilateral with Breast Milk Substitute manufacturers that violate the International Code of Marketing of Breast Milk Substitutes. FCDO may on a case-by-case basis engage with these companies in multilateral or multi-donor funded programmes or initiatives, if approved by the relevant Director General.
Settlement or Confidentiality Agreements (also known as non-disclosure agreements or NDAs) which could be used to prevent staff or downstream partners from raising allegations of wrong doing, including SEAH, bullying, general harassment or discrimination.

Rule 3: All programmes and projects must align with FCDO/HMG policy priorities and business objectives.
Principles in practice:
Responsible and Accountable: Clear strategic alignment with organisational priorities. Accountable for delivering against ministerial and HMG priorities, with a clear understanding of our role and the role of others in pursuing government policy.

Transparent: being open about what we are doing, why and how

Evidence based: learning from previous experience facilitating organisational learning.

Context-specific: Understanding the political, economic and operational environments that we work in will help programmes deliver effective outcomes and impact.

Why? Strategic alignment of programmes and clear communication of this allows us to maximise our impact and value for money and recognise the synergies between various programmes in a portfolio. Through this process we reduce the likelihood of duplication, accidental gaps in delivery or outcomes and avoid programmes running at cross-purposes.
Examples of strategic misalignment and failure to communicate effectively can result in centrally managed programmes and bilateral programmes failing to work together; humanitarian and development programmes in the same space undermining each other; lack of co-ordination (or contradictory priorities) across numerous activities with multilateral partners; disjointed or contradictory communications to our stakeholders, etc. This can result in missed opportunities or inconsistent engagement with programme constituents and beneficiaries. It can leave delivery partners unclear on FCDOs aims and core priorities, negatively affecting external engagement, and putting delivery needs at risk.

Who? Directors/Heads of Mission are accountable for setting portfolio objectives in a Directorate/Country Business Plan. Heads of Department/Heads of Mission are accountable for delivery of the objectives in the Business Plan. SROs are accountable for a programme’s contribution to portfolio-level outcomes – including outcomes in other parts of FCDO - and should be empowered to make changes to programmes (within their delegated authority) that enhance a programme’s contribution to those outcomes.
Working with Multilaterals
Providing core funding to multilaterals should be assessed for high-level strategic alignment with FCDO priorities, rather than at the individual project level.
For programmes that work bilaterally through multilateral organisations, teams should be prepared to provide information and views on our partner’s performance allowing UK institutional leads (SROs, HoDs, UK Representatives to successfully manage the UK’s relationship exercising scrutiny and challenge). This will help avoid policy incoherence, achieve strategic alignment and synergies.

How? The Director/Head of Mission must set out in a Directorate/ Country Business Plan statements of intent, campaign goals and outcomes for their area of responsibility. Applying a Delivery Framework at the planning process of a programme, policy, or portfolio of work, can enable the strategic mapping out of the logical sequence of activities to bring about an impact or outcome.
Country Boards, chaired by the HoM, are responsible for alignment of all activity and spend to the Country Plan. The HoM/Director (as Portfolio SRO) may, in addition, convene and chair a Post/ Directorate Programme Implementation Board to oversee management of all programmatic and non-programmatic initiatives and activity through their Post or Department. Experience suggests these Boards are more effective when they focus on portfolio-level coherence and contribution to FCDO and/or HMG policy priorities, rather than taking a role in day-to-day decision-making on programmes, which are the role of the SRO and PRO.
The Director/HoM does not need to be a programme or project management expert. But they need to understand the key concepts and be able to provide strategic leadership, ensuring programme spend is integrated fully into policy work at Post and helps deliver clearly identified policy objectives in support of wider cross-government country plans/NSC strategies. Directors/HoMs have formal financial delegated accountability for the programmes they manage.

Rule 4: All programmes must have a named Senior Responsible Owner (SRO) and Programme Responsible Owner (PRO).
Principles in practice:
Responsible and Accountable: Programme delivery requires leadership and clear lines of accountability.

Context-specific, Innovative and Agile: In many areas of FCDO programming, evidence shows that we get better outcomes if people close to the programme are able to apply their judgement to operational decisions. The SRO and PRO roles are empowered to provide this devolved leadership.

Proportionate. The SRO and PRO roles should be allocated in a way that does not create unnecessary layers of hierarchy or slow down operational decision-making. Where it makes sense for both roles to be played by the same person, this is encouraged.

Why? Cross-HMG programme delivery standards state that “Strong leadership with clear accountability are key elements of successful project delivery”. The programme SRO and PRO roles, modelled on role definitions of SRO and Project Director used across government, provide clarity on who is accountable for projects and programmes.
The programme SRO role is accountable for a programme or project meeting its objectives, delivering the required outcomes and making the expected contribution to the higher-level objectives (in Delivery Frameworks, Country and Thematic Plans, and FCDO as a whole).
The PRO role is accountable to the SRO for driving, on a day to day basis, the delivery of programme outcomes within agreed time, cost and quality constraints. This includes effective management of risk, compliance with the Rules, objectivity about performance and design and adaptation of programmes to uncertain or changing contexts.
Although they are distinct roles, the programme SRO and PRO roles may be played by the same person, particularly where the programme is less complex and the person has the right experience. A person may be SRO or PRO for more than one programme.

Who? Heads of Mission (post) and Directors (HQ) are accountable for the coherence and delivery of the objectives in a Country/Directorate Business Plan. As part of their role as Portfolio SRO, the HoM (for in-country) and the Director (HQ) are responsible for assigning the roles of SRO and PRO for individual programmes, to the individual(s) who are best placed to carry out the responsibilities of that role, based on the complexity of the project or programme, and the personnel available. This responsibility may be delegated – e.g. to Heads of Department – and should be delegated to a Development Director (where present) for teams managing significant amounts of ODA (>£1m p.a.). For other programmes spending ODA in posts where they are present, Development Directors must identify (with the HoM) who is best placed to play SRO and PRO roles for programmes using ODA, and must help to define expectations of the role. The expectations of the role should be set out in a formal appointment letter. If one person is fulfilling more than one role for a programme, they are accountable to the next person up the accountability chain.

How? The programme SRO and PRO roles should be assigned to the person or people in the post or department who are best placed to perform the role(s). They are not attached to a particular position or grade. The HoM/Director or Development Director may decide to retain the SRO role for programmes themselves. In small posts where there are no other suitable people available, the HoM or Development Director may also retain the PRO role.
For less complex programmes, the expectation is that the SRO and PRO roles can usually be performed by the same person. For more complex programmes, particularly programmes that are expected to contribute to the objectives of more than one portfolio, it will be more appropriate to assign the two roles to different people, with the SRO role assigned at a more senior level, with enough of an overview of the programme to play a constructive challenge role, and the PRO role closer to day-to-day implementation. The SRO role must be fulfilled by a member of FCDO staff.

Where a programme contains large or complex projects within it, the SRO for the programme may also consider designating someone in the programme team as a named Project Lead for that project. For programmes on the Aid Management Platform, the names of the SRO and PRO must be recorded in the Teams tab.
Rule 5: All programmes must align with the Paris Agreement – an international treaty on climate change – and assess climate and environmental impacts and risks, taking steps to ensure that no environmental harm is done (see the four requirements below). Any International Climate Finance (ICF) programmes must identify and record ICF spend and results.
Principles in practice:
Ambitious: Programmes must consider how climate change and biodiversity loss will be impacted by delivery, mitigating this risk and supporting the climate and environment. We must be prepared to pioneer new design and delivery methods.
Responsible and Accountable: Failure to implement sufficient safeguards and consider the environmental impact of our work threatens our ‘do no harm’ principle, putting communities at risk of environmental damage.
Transparent: Accurately identifying ICF spend is important as we are obliged to publish all ICF spend.

Why? The UK Government made a public commitment in the May 2022 International Development Strategy to “ensure that all new bilateral UK Official Development Assistance (ODA) aligns with the Paris Agreement in 2023” and “build in the 2030 Strategic Framework for International Climate and Nature Action on our 2021 commitment to ensure all new UK bilateral aid spending does no harm to nature by taking steps to ensure UK bilateral ODA becomes ‘nature positive’, aligned with “Kunming Montreal Global Biodiversity Framework”.

The UK remains committed to spending £11.6bn ICF on programmes supporting developing countries to reduce poverty and respond to the causes and impacts of climate change and environmental degradation. In order to meet our commitments and demonstrate the impact that our ICR is having, we require accurate reporting of ICF spend and results.

Who? Programme Responsible Owners are responsible for ensuring climate and environment risks and opportunities are considered throughout the programme. Directors/Heads of Mission are responsible for minimising the risk that the overall portfolio does harm, and wherever possible, ensuring it provides an overall benefit for climate and the environment.
Working with Multilaterals: All of these elements should be considered in multilateral contributions. Further guidance on how to work with multilateral organisations is laid out in the PrOF guide.

How? Full guidance is available in the Climate and Environment ProF Guide, including:
- Paris alignment and Environmental Protection: All programme design documents must include a summary of how the programme will meet the Green Finance Strategy criteria of Paris alignment: 1) ensuring it does not go against a partner country’s climate plans; 2) abiding by the fossil fuel policy; 3) taking a proportional approach to carbon pricing analysis; and 4) climate and environment risks, impacts and opportunities and steps taken to mitigate any harm.
  Exceptions to this rule
  Programmes that address rapid onset humanitarian crises. In these cases, ICF reporting remains a requirement, but can be done retrospectively.
- International Climate Finance (ICF) ODA programmes across all development sectors can score as ICF if, in part or, they seek to address the impacts or causes of climate change. ICF programmes must report against all relevant ICF Key Performance Indicators through the annual ICF results commission. Programme log-frames should include indicators that align with relevant ICF KPIs. Programmes must use the Rio Marker for climate change adaptation and/or climate change mitigation on AMP, including a % split, and, if relevant, Rio Markers for biodiversity and/or desertification. Programmes not on AMP must contact the ICF Analyst in the Energy, Climate and Environment Division to discuss how they will report.

Rule 6: Programmatic and project decisions (including payments and commitments) must only be taken within delegated budget and approved levels of individual authority and in line with the agreed risk appetite. Decisions going beyond these limits and risks which exceed appetite must be escalated to the appropriate level.
Principles in practice:
Professional: delivering maximum impact and value for taxpayers’ money, following the Civil Service Code, HM Treasury’s guidance on Managing Public Money and The Orange Book.
Proportionate: Using common sense and judgement to present reasoned, value for money, evidence and risk-based proposals at all times. We need to meet minimum standards of compliance, even in a crisis when we need to move fast. Being proportionate and balanced is key.

Why? HMT’s Managing Public Money guidance requires Treasury consent for all spend and commitments. In practice, HMT has delegated authority to departments to make commitments and disburse funding, up to certain limits, without HMT prior approval. Management Accounts Group should be consulted to ensure that appropriate approval is sought for any planned activity going beyond predefined imits – whether due to its value, risk profile (i.e. novel and contentious – see Rule 11) or duration of the commitment.

Who? All staff are responsible for understanding their own personal sphere of delegated authority, decision-making power and risk management and assurance responsibilities. SROs also have a responsibility to be clear about any delegated responsibilities, both financial and risk management.

How? Formal delegated authority levels are set for Ministers and FCDO officials which provides the Foreign Secretary, HMT and Parliament with assurance that our programme decisions are being taken with an appropriate level of oversight (including from technical experts), that balances accountability and scrutiny with the practical demands of day-to-day delivery. Delegated authority in FCDO is set at departmental/organisational, directorate/post and individual level. It is important these that levels of authority are observed.

HMT can impose stricter limits on future spend, slowing delivery and reducing impact if FCDO oversteps its delegated authority. If staff make decisions outside of their delegated authority, senior leaders and Ministers are not appropriately informed of issues or engaged in decisions. Erosion of Ministerial trust in civil servants, leading to further reductions in delegated authority is a likely outcome. If we take decisions which push us substantially beyond the agreed programme risk appetite and risks materialise, Ministers are unprepared for these and cannot take responsibility. If we fail to control and oversee risks adequately in line with risk appetite, programme constituents (beneficiaries) are likely to be impacted. Poor controls management can also lead to qualified accounts, PAC hearings and significant reputational damage. Risk appetite should be dynamic and can be changed, in consultation with the HoM/Director.
Risk appetite is set for each of FCDO’s risk categories, which are:
- Strategy & Context – risk arising from pursuing diplomatic and development objectives which are undermined by a changing context, a lack of clarity or a weak evidence base. These risks undermine our delivery and impact.
- Policy & Programme Delivery – risk arising from implementation of our core business of diplomacy and development, due to weaknesses in influence and engagement, programme delivery, commercial management, resourcing and/or operational support. These risks undermine our impact and influence.
- Public Service Delivery & Operations - risk arising from weaknesses in the delivery of consular services or the delivery of internal operations which support our core business and wider HMG, including security, legal, technology and information and property risks, impacting delivery, our people and British citizens.
- People - risk arising from weaknesses in leadership and engagement, culture and behaviours and/or workforce capacity and capability, impacting on performance.
- Safeguarding - risk arising from failure to establish and maintain strong safeguards to prevent harm to beneficiaries of our programmes, staff and those implementing our programmes, the communities where we work, or the environment, resulting in ethical violations and reputational damage.
- Financial & Fiduciary – risk arising from our funds being used for unintended purposes or not managed in accordance with requirements and constraints, or poor management of assets/liabilities, resulting in weak value for money, compliance and delivery failures and reputational damage.
Reputational – risk arising from political or adverse events, including delivery failures and ethical violations, damaging FCDO’s and/or the UK’s reputation.

Early-stage programme documentation should set out specific approvals processes and risk mitigation/management decision making e.g. Concept Note, Business Case, Business Case Approval.

Rule 7: All FCDO programmes and projects must be as transparent as possible with taxpayers, our partners, host countries and programme constituents (beneficiaries). Programme documents and decisions must be saved correctly for publication. Sensitive information must be treated appropriately.
Principles in practice:
Transparency, Honesty: being open and honest with taxpayers, partners and those we are working with about what we are doing, why and how. Where full transparency isn’t possible due to security issues, we will be clear and justify this.
Responsible and Accountable:
Demonstrates how our programmes deliver against HMG priorities, provide value for money, do no harm (for ODA) and are open to legitimate scrutiny.
Professional: We will deliver our commitments on transparency while considering our rights and obligations under the GDPR, Data Protection and Freedom of Information Acts, handling personal data correctly and considering the implications of data release. E.g. for safety and security of staff and partners.

Why? The UK is a global leader in transparency, supporting other countries to be more transparent with their citizens, and we must continue to lead by example. HMT’s ‘Managing Public Money’ highlights transparency as a standard expected of all public services. The UK Government requires transparency from all Government departments. Transparency helps us to be more accountable, efficient and effective by:
- supporting evidence-based decision-making by feeding into FCDO management information
- improving engagement with programme constituents (beneficiaries), enabling empowerment of choice and control in programmes
- providing better oversight and coordination of spend
- reducing duplication by sharing information with others.
- delivers comprehensive, relevant and accessible aid information to the public domain via DevTracker and gov.uk.
- it enables sharing of information with countries where ODA spend supports better outcomes
- it helps us track funds to downstream partners and helps address corruption
- we are measured on transparency in the International Aid Transparency Initiative, and the global Aid Transparency Index, and there is reputational damage for FCDO if transparency commitments are not upheld.
This must be balanced with consideration of the implications of the release of sensitive data, in particular our legal rights and obligations to protect personal data and to protect our staff and partners.

Who? Programme Responsible Owners must identify where publication of programme information could put staff or partners at risk. The SRO must agree what data in the programme is sensitive and how it will be handled. Aside from excluded data, the SRO is accountable for ensuring transparency commitments are met.

How? All programmes must consider transparency at the early design stage, drafting documents with public release in mind, and considering how to engage partners and programme constituents (beneficiaries).
- Programme documents, data and decisions must be saved correctly for our records, and in a format that allows them to be published to DevTracker or for Freedom of Information purposes
- All Gold and Silver classified contracts must select 3 KPIs to publish quarterly through the Commercial Department.
- Where sensitive data is contained in documents staff must follow existing exclusions guidance and legal obligations. For example: in general, do not publish sensitive or personal information that might fall under the Freedom of Information Act or GDPR including email addresses, signatures, bank account details, or individual names instead exclude this information.
For programmes on the Aid Management Platform (AMP):
- Ensure all sections in AMP are up to date so that MI and Devtracker are accurate.
- Save all project documents (annual reviews, business cases, MOU/AG/contracts, logframes, evaluations) correctly to Records Management Systems. You can check it is public on the AMP Transparency tab or on DevTracker.
- Be aware that data on AMP is published automatically, so any exclusion request must be sent promptly, following the process set out in the Transparency PrOF Guide.

Rule 8: At an early stage of design, an outline of the programme's intended outcomes, operating context, activities, budget and high-level risks must be set out and approved at the appropriate level, using the Concept Note (CN) template. All CNs over £5m must be approved by a Minister (FS if Minister decides to escalate).
Principles in practice:
Ambitious: when proposing transformational programmes in difficult high-risk environments engage Ministers early before investing significant time in design. Early engagement also allows for ministerial buy-in of approaches that haven’t been previously tried and tested.
Context-specific: programmes should suit and influence the political context and meet HMG’s international policy priorities.
Evidence-based: Programmes must draw on any pre-existing evidence base, including evaluations. Experience sharing should be at the forefront of early stage design. Evidence gaps must be highlighted, with indicative plans for how they will be managed/mitigated through design and implementation.
Collaborative: take a systemic collaborative approach from the earliest stages of programme design to draw in diversity of expertise and a range of perspectives.

Why? Programmes must be strategically aligned with HMG priorities and FCDO objectives in host countries. The CN is the main point of ministerial approval of programmes ensuring fit with the organisational objectives and business plans, and legitimising the design process. Ministers will provide this for programmes over £5m and HoM (as Country Board chair)/Director for programmes under £5m. Approval confirms that the programme aligns with the wider portfolio, fits with the strategy in the Country/Business Plan and the recommended way forward for programme design. Engaging Ministers early in design gives them scope to influence shape and direction. Failure to engage them at this stage of programme design may lead to wasted time and resources by developing a business case that they are not content to approve.

Who? PROs are responsible for following process correctly, engaging key stakeholders, getting the right people involved in design and documenting approvals. SROs are responsible for providing constructive challenge on feasibility and how the programme will contribute to outcomes at the portfolio level (Country/Business Plan). HoMs (as Country Board chair)/Directors are responsible for taking a final decision on whether to escalate CNs below £5m to Ministers.

How? HoMs or Directors will approve all programmes below £5m and Ministers approve all programmes above £5m at the CN stage. The relevant Country Board, or HQ Regional Board (where present) should advise the HoM or Director, respectively. The Geographic Director (where present) should endorse the CN before it is submitted to the relevant Minister via the submissions process.

Exceptions: Any smaller projects or programme with a value of £2m or less do not require a concept note.

CSSF programmes expected to deliver <£5m of activity on the FCDO baseline over their lifetime will be approved using Programme Document by Country Board (HoM)/Director and those >£5m will follow the FCDO CN approvals process.

The Minister may decide to escalate any CN and those that are considered very high risk, novel and contentious to the FS. The Minister will endorse any CN in the first instance before escalating to the FS (the SRO must consider if the programme is very high risk, novel or contentious and clearly flag using the options on the Concept Note to ensure the FS’s ODA Adviser (where relevant), SpADs and PADs are aware).

For programmes not designed at post (e.g. Centrally managed programmes or multilateral programmes), CNs should be seen by the Development Director or equivalent at Post and cleared by the appropriate thematic or HQ Regional Board. Where there is no Board (e.g. Research), CNs should be cleared by the Geographic Director to confirm alignment with regional/thematic business plan.

Teams must articulate the rationale for and intended approach of the programme within the CN template, following the appropriate approvals route and processes in the Governance section.
- Teams with access to AMP must generate their concept note on the system, and use automated workflows to obtain approval.
- Ministers are likely to focus attention at strategic level of the FCDO portfolio while officials focus on implementation detail – this clarity is the focus of the new approvals process.
- High-level risks must be discussed in full as early as possible (risk appetite and mitigation).

To note that where you plan to deliver elements of your programme inhouse through project funded roles then please refer to rule 27 for further information on what is needed.
Working with Multilaterals: Multilateral Core Spending Teams can decide whether or not to use a Concept Note, beyond the minimal threshold of generating a blank CN when creating a new programme entry on the Aid Management Platform (AMP). Judgement on the appropriate, proportionate level of detail provided in that template is at HoD discretion.
Concept notes can be useful to get approval in principle early on in a replenishment, or for a potential capital increase, and to allow the work needed to flesh this into a firm proposal. However, Ministers will typically be consulted throughout the development of multilateral core contributions, and teams can use their records of these conversations and formal Ministerial approval in place of the CN, by noting the document record number(s) in the CN text field on AMP.

International Subscriptions: International Subscription teams managing non voluntary payments to the Commonwealth, Council of Europe, United Nations Office of the High Commission for Human Rights (OHCHR), Organisation for Economic Cooperation and Development, North Atlantic Treaty Organisation (NATO), Organisation for Security and Co-operation in Europe (OSCE), United Nations where we have a legal obligation as a member are exempt from this rule. This exemption does not apply to other subscriptions which we pay on a voluntary basis including where we provide additional funding to the organisation noted here on a voluntary basis which is over and above our legally binding obligation.

To note that a business case is still needed for both multilateral core funding and international subscriptions where we have a legal obligation to pay (see rule 9).

Rule 9: All programmes must be appropriately designed and have a suitably approved Business Case (BC) in place prior to the start date (and for the full duration), using the BC template. Material changes and extensions to this design must be formalised and approved in a BC addendum. Prior HMT approval (via a concept note) is required for any announcements involving spend if related to a business case or a package of business cases, yet to be developed, totally £100m or over across the lifetime of the spend period. Only crisis programming should include Internal Risk Facilities/contingency funds, and these should be limited to a maximum value of 10% of a programme’s proposed lifetime value.
Principles in Practice:
Professional: programmes must be designed for implementation, not just approval.
Responsible and Accountable: Robust design is essential to ensure we identify and manage potential risks and unintended consequences of our programmes, to meet our responsibility to do no harm.
Collaborative: designing a programme is a task for a multi-disciplinary team. Wide engagement early on with a range of people will ensure the right inputs and balance of perspectives.
Evidence-based: Design decisions should be guided by evidence. Where evidence is weak, the implications must be acknowledged and actively built into programme design.
Proportionate: Business Cases, particularly for Smaller Projects programmes, do not need to be lengthy documents.

Why? HMT Managing Public Money requires a BC to be in place for all spend. BCs should demonstrate how the programme will be delivered within the scope of the Country/Business plan and is consistent with the approved CN. BC approval confirms that the approver is satisfied that the programme meets a strategic need, is convinced the programme has been well designed, will deliver impact, represents good value for money (VfM), will reach beneficiaries equitably and has robust management and risk arrangements in place. All BCs £40M and above, must be reviewed by the Quality Assurance Unit.

The BC demonstrates how design choices, and the choice of delivery options represent best VfM in delivering intended outcomes, drawing on evidence on what, why and how to deliver them. Well-designed programmes ensure FCDO is investing in implementable and cost-effective programmes. When programmes need to evolve, for example in response to changes in context, or emerging lessons, this may challenge the Theory of Change. Therefore, BCs should build in a degree of flexibility commensurate with the strength of evidence, the risks that the programme may need to respond to, and the team’s overall confidence that the intervention can be delivered along the lines proposed within the budget and time allocated.

Who? PROs are responsible for following process correctly, convening the right stakeholders to design the programme, and documenting approvals. SROs are responsible for providing constructive challenge on feasibility and how the programme will contribute to portfolio-level outcomes. HoM/Director is responsible for ensuring the whole portfolio is compliant with this rule, taking a final decision on whether to escalate BCs that fall below the threshold for formal ministerial approval. For new programmes spending ODA, a Development Director (where present) or an equivalent senior development expert (in HQ departments) provides endorsement of BC as part of the scrutiny process. Approval advice is provided to HoM/Director by Country Board/HQ equivalent. Approval advice is provided to Ministers by the Investment and Delivery Committee, dependent on approval threshold. The SRO will prepare and present the BC Covernote 2-pager for Investment and Delivery Committee review for programmes £40m and above.
Exceptions: In cases of humanitarian emergency, Ministerial approval of a submission will allow teams to commit and disburse funds ahead of BC approval (which must be written as soon as possible). Release of funding before BC approval is potentially politically contentious, and so must be approved by the FS or Minister, even if below the usual Ministerial approval threshold.

After Concept Note (CN) approval, HoM/Dir can approve proportionate release of appraisal and design funds to support programme design. These funds are drawn from the approved CN budget.

How? Programmes should be designed robustly, but proportionately, based on an understanding of the context, a clearly identified problem, what the intervention is seeking to achieve and option(s) for delivery. A Delivery Framework approach and setting out a theory of change can help to articulate this understanding, and the assumptions behind it. Where the evidence base for the theory of change is weak, this may point to adaptive approaches that test and iterate. The design process must include realistic assessment of risks, opportunities and management requirements, including consideration of monitoring and evaluation requirements and programme resourcing. All programmes must include adequate resourcing for effective safeguarding against SEAH.
Smaller Projects:
Business cases for smaller projects/programmes, can be short, and need not specify and appraise interventions or delivery options in detail; but may simply set out processes and criteria for selecting and approving individual projects and delivery options – in a way that ensures VFM.

Recognising and exploring options, trade-offs and pros/cons are key to good design and appraisal of options should explore all facets of value for money, including the value for money of different delivery options. Delivery by FCDO staff (insourced roles) is an option to consider where this offers better value for money than an outsourced alternative. There should also be early consideration of the exit strategy – focusing on sustainable and responsible closure and including early closure scenarios. Programmes proposing insourced roles should take advice from HR and/or Heads of Profession on the likely demand for expertise after the programme ends, and take this into account in the VfM case.

The Quality Assurance Unit (QAU) provides an independent and robust evidence-based review and quality assurance of the VfM of FCDO’s major investments, i.e. business cases over £40m and those that are novel or contentious (with exception of financial transaction business cases which will be reviewed by Financial Transactions Steering Board). Reviews assess evidence for the cost-effectiveness of proposed spending and are agreed with the Chief or Deputy Chief Economist.

The BC template captures the output of programme design, presenting the culmination of the evidence-based process. On completion of the BC template, the correct approval thresholds and processes must be followed – including on scrutiny and re-approvals (see Governance sections 6.7 - 6.10 and Rule 11 Novel & Contentious programming). This ensures that, where necessary, BCs, extensions and announcements are also approved by HM Treasury. Approval is only confirmed once the final approval is given by someone with appropriate delegated authority e.g. £200m and above HM Treasury approval will mark the final approval point.

Once full approval is given then the programmes on the Aid Management Platform must be put through the workflow as soon as possible to avoid unnecessary gaps between final programme approval and the formal start date of the programme shown on the system.

For all programmes:
Business cases must cover the full duration of all related funding agreements and postings for staff in insourced roles, and costs incurred.
All programmes/ managed at Post must consider what role, if any, the Partnership Principles will play in the management, monitoring and evaluation of that programme, with a proportionate statement included in the strategic case.

HM Treasury approvals:
HM Treasury approval (via Management Accounts Group, using the HMT 1-pager template) is required in the following instances:
- Business cases (and cost extensions) where the value exceeds the FCDO delegated authority limit (£200m).
- Announcements involving spend related to a business case or a package of business cases, yet to be developed, £100m or more across the lifetime of the spend period. A concept note, Ministerial approval of the concept note and the HMT one page cover note will be required when seeking approval for an announcement. It is best practice to ensure the business case is in place within 3 months of the announcement being made.
- Where a business case, with a value of £100m or more, has been approved, FCDO must inform HMT of the announcement but does not require HMT approval in order to proceed.
- Internal Risk Facilities (IRF)/Contingency funds (see Business Case PrOF Guide) which would take a programme over FCDO’s £200m delegated authority limit (IRF should be included in the aggregate figure), including within existing programmes.
- The current DAL letter states that HMT should be notified of all multilateral replenishments but does not specifically state they need to approve them. Therefore, it is important that teams engage HMT (via Management Accounts Group) at the earliest possible point, and factor this into planning any multilateral replenishments, so HMT can advise whether they anticipate a need to do a full approval.

Note: HMT turnaround target is 28 working days. It is a target, and they cannot always meet this, but will endeavour to do their best. Whilst HMT is awaiting responses to queries, the countdown period is suspended.

For further guidance on where HMT approval is needed see the HMT one pager.

Development programmes:
The Development Minister must be copied into all submissions on development programmes requiring HM Treasury approval and/or those that are novel, contentious, high risk or affect our development reputation.

CSSF programmes to be delivered on the FCDO baseline will be approved using a CSSF Programme Document.

Rule 10: All programmes (and policies) must consider and provide evidence, on how their interventions will impact on gender equality, disability inclusion and other equality considerations.
Principles in practice:
Accountable (avoiding harm): without careful consideration of the risks to and impacts on different groups, programmes could exploit or exacerbate existing inequalities and vulnerabilities resulting in harm to communities and individuals.
Responsible and Accountable: we are publicly committed to the OECD DAC gender and disability policy markers. They are used to report on the total UK spend on gender equality and disability inclusion.
Context-specific (and participatory): analysing the potential impact on a broad range of groups and adapting our design accordingly improves programming and the value of our investments. This includes through participation - promoting and listening to diverse voices and ensuring meaningful engagement of women and excluded groups. Programmes are an integrated part of HMG’s country strategies, and understanding local views and the wider context supports successful delivery.
Evidence-based: Disaggregation of data and analysis by sex, age, disability, geography and other characteristics builds the evidence base for inclusive programme design and results.

Why? This is essential for compliance with our public law obligations and public commitments, including the SDGs and pledge to Leave No One Behind, and (for ODA) the International Development Act 2002 (as amended by the International Development Gender Equality Act 2014).
The International Women and Girls strategy, sets out that the whole of the FCDO will use its political, policy and programmatic levers to advance progress. This is also true for our broader equalities’ objectives, such as protecting the rights of LGBT+ people and people with disabilities, and tackling income inequality and vulnerability to crisis, especially for those most at risk of being left behind.
Ministers have committed to ensure that at least 80% of FCDO’s bilateral aid programmes have a focus on gender equality by 2030. This reflects how we are prioritising gender equality in our work and investment moving forward. The FCDO Disability Inclusion and Rights Strategy 2022 to 2030, reaffirms the UK’s commitment to act as a global leader on disability inclusion.
The Public Sector Equality Duty (PSED) in the Equality Act 2010 requires public authorities to have (and show evidence of) due regard to equality considerations when exercising their functions, namely, the need to:
- Eliminate discrimination, harassment, victimisation and any other conduct prohibited under the Equality Act 2010;
- Advance equality of opportunity between people who share relevant protected characteristic and people who do not; and
- Foster good relations between those who share a relevant protected characteristic and those who do not.
The relevant protected characteristics are: sex, age, disability, sexual orientation, race, religion/belief, pregnancy/maternity, and gender reassignment.
An approach that integrates equality and inclusion improves the value for money of programmes, through increased equity and cost effectiveness. It improves programmes’ social impact, the focus on poverty reduction, and reduces the risk of unintended consequences. It can help us to better design, deliver and target our interventions and explain who is benefitting from our activities and funding.
Who? The Programme Responsible Owner (PRO) is responsible for demonstrating that their programme has considered the potential impact on gender equality and the other equality considerations throughout the programme cycle, and has captured relevant information using markers and disaggregated data. Heads of Department/Mission are responsible for ensuring evidence of application of the PSED under the Management Assurance Process (MAP). All staff are responsible for considering the risk of harm caused by discrimination and exclusion towards local communities, partners and individuals and work towards reducing it. FCDO also has a zero-tolerance policy for action on bullying, harassment and discrimination, including Sexual Exploitation, Abuse and Sexual Harassment (SEAH).

How? The following are required:
- consideration of how to deliver in a way which reduces gender inequality (in the case of development assistance) and/or takes account of gender-related differences (in the case of humanitarian assistance);
- all bilateral ODA programme spend must use the gender equality and disability policy markers (on Aid Management Platform (AMP) where relevant) to accurately indicate the degree of focus on these issues. It excludes general budget support, core contribution to multilateral organisations, imputed student costs, debt relief and administrative costs.
- for all programmes, a proportionate statement summarising the impact assessment undertaken on gender equality and equality considerations under the PSED must be included in the business case or project proposal;
- all programmes and business units (ODA and non-ODA), to provide annual reporting on PSED as part of the Management Assurance Process (MAP);
- for all programme annual reviews, where relevant, provide updates on areas requiring particular assurance, including gender equality and Public Sector Equality Duty.
- For all VfM analysis to include assessment and measurement of the 4th E Equity.
- FCDO has signed up to the Inclusive Data Charter to improve quality and quality of inclusive data. Programmes with defined beneficiaries must disaggregate their data by sex, age, disability, geography and other relevant characteristics where possible (e.g. race, ethnicity, income, migratory status). Teams can take a proportionate approach.

Rule 11: For any programmes which may involve novel and contentious financial arrangements, teams must engage with the Management Accounts Group and Financial Accounting at concept note stage. And any programmes carrying significant diplomatic, financial or reputational risk must consider whether FS should approve (to be escalated through the relevant Minister).
Principles in Practice:
Innovative and Agile: doing things differently. Adapting our approach to deliver better Foreign Policy and Development outcomes and learn lessons.
Professional and Ambitious: deliver maximum impact and value for taxpayers’ money, following the Civil Service Code and HM Treasury’s guidance on Managing Public Money.
Proportion and Balance: Using common sense and judgement to present reasoned evidence and risk-based proposals that are proportionate to the situation, the context and level of urgency.

Why? Novel or contentious programming can expose FCDO to greater risks (diplomatic, financial and reputational) and must be closely monitored, and may require specific expertise to manage. HMT has not delegated authority to FCDO officials or ministers to approve programmes involving novel or contentious financial arrangements, and therefore require formal HMT approval which is co-ordinated and managed through Finance Directorate.  Contentious programmes or transactions might give rise to criticism by the public or the media or could be perceived as inconsistent with wider government policy or aims.  They could also hold the potential for dispute.
Novel and contentious financial arrangements include those that create a financial asset (either owned by FCDO or by a third party through FCDO funding), or include liabilities, guarantees, letters of comfort, indemnities, returnable investments, income-generating projects, or any different from the norm financial arrangements, must be approved in advance of spend by Finance Directorate and by HMT if appropriate (using HMT 1-pager).
All FCDO programmes should be strategically important. Programmes making a significant contribution to one of the Foreign Secretary’s top priorities, FCDO priority outcomes, a manifesto commitment, or an NSC strategy should be brought to the attention of Foreign Secretary after seeking advice from Private Office/SpAds.

The relevant Minister will be responsible for ensuring any programme that carries significant diplomatic, financial and reputational risk is escalated to the Foreign Secretary (the SRO must consider if the programme is very high risk, novel or contentious and clearly flag using the options on the Concept Note to ensure the Foreign Secretary’s ODA Adviser (where relevant), SpAds and PADs are aware – this could be because it includes: activity which is notably strategically important or carries significant diplomatic or financial risk; where the organisation has limited experience or evidence of what will work and is outside the range of FCDO’s normal business activity and there is no precedent for this type of activity or spend; that might give rise to criticism by the public or the media; that could hold the potential for dispute; that is inconsistent with wider government policy or aims).
Who? The SRO is responsible for identifying elements of a programme design that could be novel or contentious, and ensuring appropriate advice is taken and the appropriate approval route used. The PRO is responsible for consulting Management Accounts Group and Financial Accounting at CN stage on any transactions or instruments that could be novel or contentious, which might require escalation to HMT for approval. SROs and PROs should always err on the side of caution and consult with Finance Directorate where there is any doubt. The Head of Mission (post) or Director (HQ) must satisfy themselves when reviewing Concept Notes and Business Cases that there are no financial or reputational risks that may require approval by FS (to be escalated through the relevant Minister).
How? Financial arrangements must be approved in advance of spend in accordance with programme governance arrangements and in line with FCDO’s Finance Directorate and HMT policy. Finance Directorate must review all spend that falls into the novel and contentious category, in order to assess whether it should be escalated to HMT for approval and should be brought to Finance Directorate’s attention at the beginning of the design process to allow sufficient time for necessary approvals. This process allows us to take managed risks with programmes. HMT can impose stricter limits on future spend (slowing delivery and reducing impact) should FCDO overstep its delegated authority.
All centrally managed programmes (CMPs) need explicit Ministerial approval to work in the Occupied Palestinian Territories (OPTs) to help manage the reputational and terrorism risks of working there. Further guidance can be found in the Business Case PrOF Guide or contact the OPTs team to discuss if relevant. In addition, Programme Teams must consult geographical desks if in doubt when spending in countries where there may be sensitive political considerations e.g. China.

HMT approval of novel and contentious spend must be sought via Financial Accounting, by completing the HMT 1-pager template and sending it to Management Accounts Group.
The Foreign Secretary’s approval may be required for novel programmes which are also strategically important and carry a heightened diplomatic, financial or reputational risk, regardless of value. The relevant Minister will decide whether such cases should be escalated to the Foreign Secretary for approval, but SROs must consider if the programme falls into any of these categories and ensure SpAds and PADs are made aware. Wider reputational implications to consider include high Parliamentary or scrutiny body interest, or where it relates to issues that are likely to attract significant public or media attention. High financial risk where there is a significant risk of misappropriation/misuse of funds or value for money case is contested; where a non-standard financial model is being used including expenditure which might set a precedent, or which might have wider cost implications.

Rule 12: All programmes must follow FCDO's branding guidance, and appropriately document their approach to external communications.
Principles in practice:
Transparent: Clear branding means stakeholders and beneficiaries know where funding has originated from. It allows for appropriate connections to be made and harmonisation of complementary activities.
Accountable: Clear branding also supports accountability making it easier to report complaints or concerns.

For ODA programmes – SRO’s should ensure that the programme continues to follow the Branding guidance for ODA funded programmes and ensure the UK International Development logo is included on written materials and through use of the UK aid logo on programme assets as well as verbal acknowledgement, as appropriate. The UK aid logo is now purely for use on humanitarian programmes and responses to rapid onset disasters as outlined in the brand guidance.

For non-ODA programmes - SRO’s should ensure that appropriate branding is used. This means using the UK Government logo or the relevant mission crest for the Embassy or High Commission on written materials and on programme assets, or verbal acknowledgement, where appropriate. You can find more information in the FCDO brand guidance. For external communication activities, non-development programmes must be familiar with the Professional Communications Assurance guidance and approval process.

Why? Effective branding helps build the UK’s reputation and recognises the role that the UK plays internationally. Branding and communication can be a key part of a programme’s ability to maximise the impact of our investments and build our capability to deliver in future. Insensitive or poorly thought-through communications or use of logos can undermine a programme, derail a critical relationship, or lead to a reputational risk for FCDO.
Branding also promotes transparency and accountability by communicating quickly and easily how a programme has been funded, and who is ultimately responsible for the resources, personnel and equipment used. This is particularly important when access to information may be limited. Careful consideration must also be given to any security sensitivities which might affect the information that can be made publicly available about a programme. (Also See Rule 7 Transparency).

Who? PROs are responsible for documenting their approach to external communications, in line with the brand guidance, ensuring that communications consider the security and dignity of beneficiaries and staff.

We know that for both ODA and non-ODA programmes there are circumstances when it is not appropriate to use UK branding including; security concerns, reputational risk or political sensitivities, If you are concerned about branding your programme please contact the branding team and we can provide advice and alternative options.

PROs are responsible for identifying any exemptions (including security) and agreeing these with their partners and submitting these to their Head of Mission or Director (or delegate, e.g. the Programme SRO) for approval.

How?
- Be familiar with the FCDO Branding Guidance.
- Be familiar with the Branding guidance for ODA funded programmes.
- All non-ODA funded programmes/projects consisting advertising, communication and marketing costs must go through the Professional Communications Assurance prior to issuing the contracts/agreements to the implementers.
- For ODA programmes make sure a partner visibility statement is completed as a formal part of all relevant funding arrangements (it will be included in the template). This sets out the mandatory requirements for partners, and the criteria for exemptions. The statement helps ensure that implementing partners are clear on their branding responsibilities from the outset.
- In deciding where and how UK funding is recognised, priority must always be given to the safety, security and dignity of beneficiaries and staff. There are many circumstances in which the standard approach to branding would not be appropriate, and partners should be encouraged to flag any risks they perceive. Communication approaches should be kept under review throughout the lifetime of the programme or project, with changes formalised in the visibility statement as necessary.

Working with multilaterals:
Specific branding arrangements have been agreed with multilateral agencies. SROs should ensure they are familiar with these arrangements and apply this guidance as appropriate. This includes completing a visibility statement wherever possible.
It is rarely practical to apply UK International Development branding to core funding, because the UK’s contribution is not identifiable from that of other donors, and to recognise UK development assistance alone would misrepresent the UK government’s involvement. However, core funding teams should actively consider where if opportunities to acknowledge funding are available and appropriate.
International subscriptions: For those international subscriptions where we have a legal obligation and FCDO funding is impossible to disaggregate then branding should not be pursued, However, where membership subscriptions are voluntary then teams are advised to pursue branding opportunities where possible.

Rule 13: Digital elements of programmes or projects (e.g. text messaging, cash transfers with a digital angle (including mobile-cash transfers), websites and databases) must be reviewed at the earliest possible stage in the process by FCDO's Portfolio Assurance and Controls Team, and most also require assurance from the internal Portfolio Assurance Forum (PAF).
Principles:
Innovative and ambitious: Most programme teams lack specialist digital knowledge. Technical support and quality assurance from the Digital Service Team allows us to take managed risks in the digital space, investing in innovative new technologies and maximising the impact of our funding.

Why? The Central Digital and Data Office (CDDO), on behalf of Cabinet Office, monitors all digital spend across government. FCDO is required to report all spend and show that what we have approved meets with government standards including the Technology Code of Practice and Service Standard.

Digital is driving real transformation. It is making a difference to millions of people through new partnerships, better technology, creative design, smarter research and transformative solutions, such as engaging with beneficiaries. However, there is a risk that digital spend proposed by partners to address user needs, may be disproportionate, offer poor VfM, misaligned with FCDO's digital strategy and standards, or replicates something already being used in FCDO.
Working with multilaterals
Pooled funding, core and non-core funding to multilateral organisations is exempt from this rule.

Therefore, digital elements which use pooled and multilateral funding arrangements (i.e. contributions involving mixture of ODA and other donor funding sources) is not subject to digital spend approval.

Who? Technology spend of £1m or Digital spending of £100,000 or over will require spend approval by Central Digital and Data Office (CDDO) using the Digital and Technology Controls Pipeline process. Please email the Portfolio Assurance and Controls team with a FCDO Controls Pipeline Assessment Document  to seek advice, support and Cabinet Office spend control approval. Please note the spend controls process is complementary to other approvals and does not remove the need for more formal investment appraisal and approval. For example, all digital, data and technology spend over £1m should be approved by the Programme and Management Board (PMB).

The Portfolio Assurance and Controls Team are part of the Information and Digital Directorate portfolio assurance function and are responsible for CDDO assurance and securing spend control approval.
Advisory Service
If your project does not require official spend approval, you have already received approval, or you just want some help from technical experts we are still able to provide you with advice and help that can be used to manage risk and add an additional layer of assurance for your programme. This includes things such as questions, reviewing TORs (Terms of References) or helping to score bids for technical work.
The Portfolio Assurance and Controls Team will provide expert advice to make sure:
- you’ve considered the needs of the people who’ll use the service.
- you plan your spending and get the best value.
- you only spend on programmes and projects that meet government digital and technology strategies including the Technology code of Practice and the Service Standard.
- private businesses and members of the public can see how government makes decisions about spending money on digital projects or technology.
- you discover and solve any problems with your service before you spend money.
- you develop services using agile methods and best practices.
- be transparent about what you’re spending money on.
- get early support on issues you might need help with.
How? ‘Digital’ in this context is defined as any external-facing service or software provided to citizens, businesses, civil society or non-government organisations. It can range from text messaging to enable mobile cash transfers, satellite mapping to identify the spread of deforestation or disease, databases of beneficiaries and their feedback, knowledge portals to share programme research, websites and mobile apps.
Exemption: In case of rapid onset humanitarian emergencies, the Digital Service Team can fast-track approval and/or advice for digital developments. Contact the Digital Spend Team for more information.
In FCDO, this applies to any spend on web-based or mobile information services, websites, knowledge or open data portals, transactional services such as cash transfers, web applications and mobile phone apps.
The following elements fall within the scope for digital spend approval:
- websites and knowledge hubs (the digital elements include user research, design, build, hosting, licences, maintenance and support)
- transactional services (including interfaces for applying online for services such as grants)
- open data platforms, collection tools, monitoring, analytics
- mapping tools – mapping, geocoding
- mobile delivery systems – SMS, mobile money, cash transfers
- mobile apps
- online databases and management information systems, if they are external facing
- external facing e-learning tools or resources.
Key considerations when designing your website or digital presence:
- Understand and define the problem that you are trying to solve. Carrying out a discovery phase is recommended and will help you do this. This is part of the CDDO (Central Digital and Data Office) Service Standard.
- Carry out user research before you start so that you design a solution around user needs. Seek feedback at regular intervals throughout the lifetime of the digital tool or service to keep it relevant and ensure you continue to meet user needs
- Information management and website security – it’s essential that the web channels you manage and the personal information you capture is protected, managed and always kept secure.
- The FCDO formally endorse the Principles for Digital Development– a globally agreed set of guidelines on the design of digital aspects of development programmes, supported by organisations including USAID, UNICEF, WFP, UNHCR, Gates, SIDA and the World Bank. PROs of development programmes must check that partners planning digital spend are aware of and can explain how they follow these.

Rule 14:  FCDO can only pay for costs that are incurred after signature and between the start and end date stated in a funding arrangement or contract. The duration and value of all funding arrangements must be fully covered by an approved budget (e.g. business case or project proposal) and must use the latest funding arrangement templates or frameworks.
Principles in practice
Professional: The Cabinet Office Government Functional Standard for Grants requires that grant funding arrangements should (a) be justified and based on the content of the business case, and (b) contain a minimum set of requirements.
Accountable: appropriately approving spend ensures Ministers, HMT and senior officials can scrutinise proposals and accept responsibility for the activity.

Why? Approving funding arrangements before funds are committed to partners is a requirement in HMT’s Managing Public Money. Any commitment via funding arrangements in advance of the appropriate approval process critically undermines the role of Ministers, HMT and senior officials in scrutinising BCs, and creates a liability risk that FCDO may not be willing or able to accept responsibility for.
Backdating arrangements or allowing spend on activities undertaken outside of the start and end dates of an agreement, is a breach of HMT rules. Any breaches could result in FCDO accounts being qualified by National Audit Office and the Permanent Under Secretary (PUS) being called to Parliament to explain.
Who? Funding arrangements for all programmes and projects must be signed by an individual within FCDO that has the appropriate level of delegated authority to make such a commitment. The signatory must satisfy themselves that there is an approved business case or project proposal in place prior to signing the arrangement, and that the funding arrangement is the appropriate one for the organisation being funded.

The funding arrangement must be signed at an appropriate level by both parties prior to any commitment being made.

How?  FCDO provides funding through various modalities, including contracts, Memoranda of Understanding (MoU) or administrative arrangements, Grants or Delegated Cooperation Agreements. The section on Delivery Options (Section 5.4 in the PrOF) sets out the circumstances in which we use different types of funding arrangement. This funding arrangement decision tree helps identify the most appropriate non-contract funding type.

For all agreements
- the start date marks the first point at which FCDO can pay for any costs. On signature, our partners confirm that they will manage our money in accordance with the terms of the agreement. Before that point, we cannot hold them accountable for money already spent and activities undertaken.
- The end date marks the final moment when no further reimbursable costs can be incurred. Activities should not slip beyond the agreement end date. Payments can only be made after the end of an agreement if the activities took place beforehand.

Upholding the integrity of the agreement duration keeps programmes and projects on track to deliver against their approved timeframe. Formal extensions must be granted for costs incurred beyond the end date, allowing FCDO to keep track of how many programmes are completed on time. If costs have been incurred outside of a funding arrangement, approval from Financial Accounting for a special payment must be sought prior to payment.
To note: Any underspend must be returned to FCDO central contingency funds unless other elements of the programme are on-going in which case the underspend can be used to help meet the programmes outcome(s) as set out in the business case.

Rule 15: The tender and awarding of new contracts and amendments must comply with the Public Contract Regulations 2015 or Defence and Security Public Contract Regulations 2011. An approved budget must cover the full period of any contract and amendments. Relevant approvals much be in place as detailed in associated guides.
Principles in practice:
Professional: Conducting commercial activity in line with HMG Procurement Policy ensures FCDO follows best practice, delivering value for money of contracts.
Responsible and Accountable: non-discrimination and equal treatment are key principles of HMG procurement policy.
Transparent: Fair and transparent procurement and contract management processes, including the publication of tender documents and contracts, reporting on key-performance indicators, support the engagement and performance of the best suppliers, driving value for money.
All contracts must have a designated, appropriately accredited Contract Manager and comply with Cabinet Office transparency requirements. Contracts must be effectively managed proportionate to their complexity, risk, value and opportunity throughout the life of the programme.

Why? To comply with international and national obligations, develop a more competitive supply market, achieve best value for money, maximise programme outcomes and manage risks.
Exceptions:
In exceptional circumstances, authorities may need to procure with extreme urgency and without competition. See Cabinet Office guidance PPN 01/21 for further information. Use of this option is exceptional and must be agreed with the Commercial Lead. Exceptions to transparency may be utilised under the Freedom of Information Act or the public contract regulations, in consultation with Commercial.

Who? The PRO is responsible for ensuring appropriate commercial processes are followed, and necessary appropriate approvals are obtained, taking advice from commercial leads. The PRO or SRO is responsible for ensuring an individual is designated as a Contract Manager. The Contract Manager will be responsible for adhering to contract management processes and reporting on key performance indicators.

How? All Programme spend must follow the governance requirements as outlined the procurement governance slides. All new FCDO programme spend, contract amendments and contract management must follow the commercial guidance in the section ( Further Guidance below).
PROs must ensure compliance with the following key commercial controls.
1. All Procurements above £115K require early engagement with the Commercial Lead.
2. Ministerial approval is required for all supplier contracts £40m and over, including contract amendments and call-down contracts from framework agreements with a value of £40m and above. Cabinet Office approval is also required for contracts and amendments £20m and over.
3. All contracts and contract amendments (CA) for programme funded contracts must have an approved Business Case that covers the full period of the contract.
4. Procurements below the delegated threshold of £115k must be undertaken by a trained Delegated Procurement Officer and must be in line with the principles of non-discrimination, equal treatment and transparency. See Procurement Contracts below £115k. Increased levels of delegated authority for DPO’s using FCDO Frameworks are detailed along with information on requirements and commercial contact points in Procurement Frameworks.

Rule 16: For each funding arrangement FCDO must have a suitable, proportionate and documented assessment of any partner who is intended to be the direct recipient of FCDO funding, to determine if they have the capacity and capability to manage programme funds and deliver the programme or project objectives.
Principles in Practice:
Responsible and Accountable: effective risk-based due diligence provides assurance that public funds are being spent to maximise impact and value for money. It can help improve performance by identifying and appropriately responding to risks.
Context-specific: it is important to understand the capacity and capability of the partner to deliver in the context that they are operating in.
Evidence-based: Due diligence critically analyses a range of evidence including policies, processes, controls and financial information to inform decisions on each partner and provides an opportunity to identify and share lessons and good practice internally and externally.
Proportionate and balanced: assessment scope and depth depends on a range of criteria, including risk appetite, programme size and complexity programme, value, inherent risks, availability of evidence, programme objectives, timeline (urgency) and any history with the partner.
Transparent and collaborative: Due diligence helps us fully understand what we are investing in. This can help in being transparent with the public. Due diligence also helps assess whether partners have the capacity and capability to be transparent too. Due diligence should be done collaboratively working closely with the partner, which will assist in helping to foster positive ongoing relationships.

Why? To ensure that:

- The FCDO knows who it is engaging with and respond to any fiduciary, safeguarding or reputational risks from funding the partner.
- The partner has the technical capability and capacity to deliver the programme objectives effectively, efficiently and in a way that provides value for money.
- The partner has the financial stability to deliver the arrangement.
- The partner has adequate processes for managing fiduciary risks or risk that the intervention may result in harm.

It can also be used as a basis to develop a partner’s capacity and capability beyond the immediate funding arrangement and provide insights into our partners.

Who? The Programme SRO is accountable for ensuring due diligence is completed and for signing off due diligence reports conducted for Accountable Grants and MOUs . The PRO is responsible for conducting or delegating the completion of appropriate and proportionate assessments to give FCDO sufficient assurance over the partner’s capacity and capability to deliver the programme. The PRO is also responsible for ensuring that risks, actions and recommendations identified are followed through over the programme cycle and progress is documented. The PRO can delegate the task of completing due diligence or fiduciary risk assessments to other members of the programme team, or to experts brought in for the purpose, but should remain closely engaged in the scoping and quality assurance of the assessment, and judgements on the implications of the evidence gathered for the programme.

For commercial contracts established by the central Commercial team as per Rule 15 thresholds, due diligence is carried out by central Commercial team. For commercial contracts where the contract is established by the Delegated Procurement Officer (DPO) as per Rule 15 thresholds, the DPO and programme team carry out the due diligence.

How? A programme specific DDA is a mandatory process for all types of FCDO programme spend and must be completed before an agreement is signed and funding is disbursed. The depth and focus of assessment will vary depending on a range of criteria including: budget, risks faced, risk appetite and pre-existing assessments. The type of assessment to be used is dependent on the type of implementing partner and funding arrangement used but at its core, it should:
Exceptions: For rapid onset humanitarian emergencies (a different process applies for other humanitarian work) a formal DDA can be completed after an agreement is signed and first funds disbursed, but the PRO for the programme must have satisfied themselves that any risks identified are proportionate in relation to the expected programme outcomes and within the programme risk appetite.

There are other exceptions to the due diligence process which can be found at section 5 of the Due Diligence Guide.

- Identify and verify the identity of the partner entering into the funding arrangement and people significant association.
- Understand whether the partner is subject to either and investigation or litigation; or has been subject to an adverse funding from proceedings, which may call into questions the ethical integrity of the organisation or its ability to deliver the project satisfactorily.
- Assess fiduciary and safeguarding risk management practices.
- Assess the financial stability of the organisation.
- Assess the partner’s ability to deliver the project (including managing other partners where applicable).

Delivery chain mapping (DCM) is a process that identifies and captures, in visual form, the names of all partners involved in delivering a specific good, service or change, ideally down to the end beneficiary (see also rule 24). A dedicated ProF Guide provides more detailed guidance, and information on exemptions. A DCM should be in place for all funding modalities and reviewed as part of the due diligence process and updated throughout the programme cycle, with the exception of core funded arrangements with multilateral organisations (which are subject to CAAs).

Rule 17: Staff must declare any conflicts of interest, or offers of gifts, advantages or hospitality, as soon as they arise.
Principles in practice:
Transparent: being open and honest with taxpayers, partners and those we are working with about what we are doing, why and how.
Professional: deliver maximum impact and value for taxpayers’ money by following the Civil Service Code and HM Treasury’s guidance on Managing Public Money.

Why? The Civil Service Code, and the Diplomatic Service Regulations, highlight Conflicts of Interest, Gifts, Advantages and Hospitality are areas where staff integrity or personal judgment can be (or be perceived to be) compromised.

To maintain public confidence and protect the integrity of both FCDO and its staff, it is important that all staff follow central processes and policies to declare conflicts of interest, gifts and hospitality. This will drive transparency within the organisation.

If you fail to declare a Conflict of Interest (actual, potential or perceived) or the offer of a Gift, Advantage or Hospitality (accepted or declined), appropriate action will be taken in line with FCDO's Disciplinary Policy. This could result in dismissal. Any criminal conduct will also be referred to the relevant authorities.

Who? Relevant to all staff. Directors/ Heads of Mission must ensure all staff record conflict of interest, gifts and hospitality in line with central HR guidance.

How? Under this obligation to confirm compliance via the Management Assurance Process, Directors/Heads of Mission must remind staff every six months of the requirement to register any conflicts of interest, gifts and hospitality. Directors/Heads of Mission should perform a quarterly check of the registers to ensure relevant records are maintained. All staff should be reminded every six months.

Rule 18: Risk throughout the life of a programme or project must be managed in line with the agreed risk appetite using appropriate controls.
Principles in Practice
Professional: Our risk management framework is based on the principles set out in The Orange Book: Management of Risk – Principles and Concepts.

Ambitious: managing risk effectively to maximise the impact of our work and value for money, while keeping our staff and assets safe.

Innovative: trying new things in new places, knowing we have systems and processes in place to manage risk.

Responsible and accountable: taking responsibility for programme impact on communities and stakeholders, positive or negative, and carefully managing any risks we are exposing them to. Our risk management tools allow us to record these decisions, holding ourselves accountable for the consequences.

Why? Risk management, when applied proportionately and fully embedded in our decision-making, helps us ensure that programmes and projects achieve their desired objectives. It supports making judgements about acceptable risk taking, prioritise programme resources effectively to keep delivery on track, prevent failures and establish plans to respond quickly and effectively if things do go wrong. Our approach is underpinned by clear HMG standards on risk.

Who?

- SROs are accountable for ensuring effective management of risks to programme objectives. When required, the Programme SROs must escalate risks to Development Directors, Heads of Mission, Heads of Department or Directors, depending on their line management chain and the level of risk.
- PROs are responsible for leading an active risk management process in their programmes which brings risks in line with risk appetite and for ensuring that SROs are aware when risks exceed appetite or need to be escalated for information or further support.
- HoMs/Directors are accountable for ensuring effective management of risks to the delivery of country plans/business plans. Development directors are accountable for ensuring effective management of risks to the development objectives within country plans. This includes embedding the right values and behaviours; putting risk at the heart of decision-making; and ensuring appropriate resources and systematic implementation of risk policies and practices in their business areas.
- Risks must be escalated to Ministers from any level if appropriate.

How?
All programmes need to appoint clear roles with defined responsibilities for risk management. Staff should have sufficient capacity and capability to fulfil their roles. Those accountable for risk management are empowered to make judgements on how to apply the risk process proportionately and effectively in their areas.

- During programme design, a risk assessment is completed and as a minimum standard, every programme sets up:
  - A risk appetite for FCDO’s seven risk categories– which is agreed at programme approval. Risk appetite should be dynamic and can be amended when context or programme focus shifts, with the approval of the HoM/Director. If a category doesn’t apply to a particular portfolio or programme (e.g., re. consular activities), teams need to make this decision explicit and document the rationale on why it doesn’t apply. CSSF programmes, please refer to the CSSF Programme Operating Framework on risk language, risk appetites and requirements.

  - A risk register documenting risks, tracking implementation of mitigations and, when appropriate, escalations. Risk registers need to be reviewed at a minimum quarterly (monthly review is good practice for most programmes; weekly review is more appropriate for high-risk, high-pace programmes) and can be held either online in AMP (when teams have access or offline, using this Excel template). Maintaining an accurate register of programme risks and documented risk appetite supports better programme risk management and decision-making. When kept online, it also supports much stronger portfolio-level data, enabling better oversight and decision-making by senior leadership.
- Risk management is dynamic and action-oriented, with regular monitoring of risks and progress made in mitigating them within risk appetite.
- Programme SROs are expected to escalate risks which continue to exceed risk appetite even after best efforts to mitigate them, to Development Directors/HoMs/Directors, who in turn escalate to Directors General. Escalations can be ’for information’ or ‘for support’. Where appropriate, risks can be escalated to Ministers from any level through written advice; the usual clearances apply. Escalation ensures that senior managers and Ministers have appropriate oversight of significant risks and can support in their management.
For programmes on the Aid Management Platform (AMP), see above on requirements on setting risk appetites and keeping a risk register. -
Rule 19: Any suspicions and/or allegations of fraud, terrorist financing, money laundering, bribery, corruption, sexual exploitation and abuse and sexual harassment (SEAH), by any person or any partner (including downstream delivery partners) connected to a FCDO programme or project, must be reported promptly to the FCDO Fraud and Safeguarding Investigation Team in Internal Audit and Investigations Directorate.
Principles in Practice:
Responsible (avoiding harm): participation in our programmes may inadvertently put staff, partners or members of the public in danger of sexual exploitation and abuse and sexual harassment. Ensuring the prompt reporting of any concerns is one of the main ways we mitigate this risk, by identifying any suspected cases and acting as quickly as possible.
Accountable: Managing Public Money requires all HMG departments to establish "well publicized avenues for staff and members of the public to report suspicions of fraud and harm including SEAH."
Honest: speaking truthfully and empowering teams to escalate concerns at any time.

.
Why? FCDO is committed to operating with the highest standards of business integrity and ethics in line with the Civil Service Code. All staff and officials and persons engaged by FCDO to deliver goods or services must comply with laws and regulations in the jurisdictions within which FCDO operates in respect of the lawful and responsible conduct of activities.

This mechanism for reporting concerns is an integral part of FCDO's ability to manage fiduciary and safeguarding risks, while working in high risk areas of the world. Without this in place, victims of harm or abuse might go unsupported, aid diversion may go undetected, and any unreported incidents may impact on FCDO's delivery, finances or reputation.

 The scale-up of our work in fragile and conflict-affected regions means we are working in areas where known terrorist organisations or sanctioned entities operate, where formal banking services may be limited, and where financial regulations may be weak. Risks must be appropriately managed (see Rule 18) to mitigate the risk of FCDO funds being abused for terrorist purposes. The FCDO follows international standards on counter-terrorist finance and applies a risk-based, proportionate yet robust approach to mitigating these risks.
Working with multilaterals
For core funding arrangements, multilateral agencies will report to Member States in line with the processes agreed with their governing boards. This is likely to be a periodic report summarising investigations handled over the reporting period. On receipt, the FCDO programme team should promptly share that report with the FCDO Internal Audit and Investigations Directorate. More frequent reporting is unlikely to be available, but where it is supplied it should be shared promptly as well.

Who? Everyone. Protection of the people involved in our programmes and projects, including those with protected characteristics, and of our funds, is a collective responsibility of all FCDO staff and our partner organisations. Research and any other forms of data collection and analysis conducted on FCDO funded projects should be guided by the ethical principles and standards.

How? Anyone can report a concern linked to misuse of our funds, or sexual exploitation and abuse and sexual harassment (SEAH) by any person connected to our programmes, at any level of the delivery chain. Contact the confidential Hotline (+44 (0)1355843747) or e-mail: reportingconcerns@fcdo.gov.uk.

Engaging with programme constituents (beneficiaries) is important to ensure that a diverse set of voices are heard. Harnessing the power of beneficiary engagement can also improve outcomes and help programmes reach them more efficiently. It helps define and promote value for money, improve transparency and ensure that beneficiaries are safe from harm and empowered to speak out wherever harm does occur.

 FCDO has a zero-tolerance approach to inaction or mishandling of aid diversion and SEAH, and we must do everything within our power to prevent, detect and respond robustly to all forms of abuse. FCDO will take the necessary steps to investigate all allegations fully and fairly and will pursue the appropriate sanctions available in each case, including dismissal, prosecution, and suspension or cancellation of affected funding in extreme cases of misconduct.

Rule 20: All projects, programmes and portfolios must have sufficient monitoring in place to provide performance and financial oversight, manage risks and support decision-making at appropriate levels.
Principles in Practice
Professional: good monitoring is an essential component of professional, high quality programme management
Ambitious: close monitoring allows us to set stretching yet realistic targets of what we will achieve within the time and budget available, and to anticipate when adjustments will be needed.
Context-specific: monitoring needs will vary between programmes, and even during the lifetime of each programme. Programme teams will be best placed to determine the scope of monitoring required to manage their programmes to a high standard.
Evidence-based: monitoring allows us to capture data on the effectiveness of our interventions, informing adaptation and decision-making and providing a strong foundation for evaluation. A reliable evidence base is important for ensuring ministers are able to take informed and justified decisions.
Proportionate: monitoring should be proportionate to the value, risk profile and strategic importance of the investment, balancing team and implementing partner effort against the expected assurances and gains to be made – and keeping this under review. Support to benchmark these judgements can be provided by technical advisors, senior leadership and internal audit.

Why? Rigorous monitoring throughout delivery is critical for good programme management, maximising impact and value for money. It supports risk management, informed and timely decision-making and adjustments, and helps ensure funds are being used for their intended purposes. It is also an essential foundation for learning and evaluation.

Who? SROs are responsible for ensuring that the programme has a theory of change linking the programme activities to the intended outcomes and impact, recognising where there is uncertainty and untested assumptions. PROs are responsible for implementing an appropriate monitoring strategy for their programme, and ensuring proportionate use is made of available monitoring tools. SROs are responsible for ensuring that this monitoring provides sufficient information for portfolio management and to support their own decision-making: for example, to recommend closure of an underperforming programme, or to escalate a risk to their Head of Mission/Director or delegate.

How? Teams should consider what information they will need for adequate assurance and oversight of the programme over its lifetime; when and how that information will be collected; and how it will be used to inform decision-making. SROs may wish to consider applying a Delivery Framework to support this process. For monitoring to be effective, it should be considered in programme design, to ensure the necessary resources and expertise (both internal and external) are factored in. Ethical standards and risks in data collection and use should also be factored in. There are a range of tools that teams can draw on and incorporate into their monitoring strategies, including but not limited to:

- Results frameworks or logframes to track progress against targets (application and use of Key Performance Indicators (KPIs) considering expected milestones, outputs, outcomes, time and budget). These must be reviewed and updated as necessary over the life of the programme, and disaggregated by geography, sex, age and disability status, wherever possible.
- Risk registers must be used to document and monitor risks, and the effectiveness of mitigating actions.
  Working with Multilaterals
  Delivery Chain Mapping (DCM) is not required for core funding, e.g. to UN agencies.
- Delivery chain maps should be used wherever possible to capture all the actors involved in delivering a specific good, service or change, down to the end recipient.
- Engagement with primary stakeholders (including beneficiaries) to help define, track and make sense of progress towards achievement of goals.
- Partner reporting, including financial and narrative reports on activities, asset registers, fraud, corruption or safeguarding concerns, and audited financial statements. Requirements and expectations of partners should be documented in the formal funding arrangement.
- Independent or third-party monitoring arrangements can provide FCDO with an independent perspective on what is delivered or achieved through its programmes. They provide a snapshot of partner-reported deliverables, which, triangulated with other evidence, can inform partner engagement.
Rule 21 All programmes must undergo a formal review of progress and effectiveness at regular intervals (annually, as a minimum, and after completion) using an agreed results framework or logframe and the appropriate tools and templates.
Principles in practice
Transparent: publishing formal programme reviews in full on gov.uk.
Accountable: providing details of our programmes to external stakeholders, media, UK taxpayers, and the communities we work in.
Professional: frank and unbiased reviews, allowing for meaningful lesson learning and continuous improvements.
Evidence-based: review findings should draw on high quality data and contribute to building the evidence base for future interventions.
Proportionate: based on the assurance demands of the programme and the need to document lessons. Lighter-touch approaches on some programmes will be balanced by in-depth analysis of more significant investments.

Why? Regular, agreed, formal assessments of whether a programme is on track to deliver is a major control point in the programme cycle. This holds programme teams accountable for delivery against their commitments and should support organisational lesson learning. It provides an opportunity to reflect on whether delivery is proceeding as planned, how we are actioning lessons learned through implementation and what progress has been made towards meeting intended outcomes.

Who? PROs are responsible for delivering robust, proportionate, timely reviews, drawing on the available evidence of performance. Directors/Head of Mission or delegates (e.g. Development Director, for teams managing significant amounts of ODA, Heads of Department or SROs) are responsible for quality assuring and approving these formal assessments. This quality assurance and sign-off must be done objectively, by someone who did not conduct the review. For programmes on the Aid Management Platform, the PRO or the SRO can approve on the system. However, the same person cannot send for approval and then approve. It remains the case that the actual approval is given at the senior level and a clear offline audit trail of the approval must be retained.

How? A wide range of tools and templates are available to support this process based on the needs of the programme, the Annual Review template should be used as the main tool. All programme teams carrying out reviews should consider how the review fits into the bigger picture monitoring of the programme over its whole lifetime. It is also good practice to have the programme independently reviewed (i.e. by someone outside the programme team) at least once in the programme’s lifetime. As well as assessing and scoring against outputs, the review is an opportunity to revisit the programme’s theory of change, determine whether or not the programme is on track to meet its longer term objectives/outcome and recommend any changes that need to be made. Formal internal reviews might be supported and informed by independent evaluation.

The frequency and format of in-programme review will usually be determined at Business Case stage, providing approvers with assurance of how the programme will be managed. The development of a Delivery Framework at the outset including the production of Key Performance Indicators allows for evaluation and correction within the programme cycle through a formal review taking place annually. At the end of the project or programme, a final review must be carried out to assess delivery of against Business Case commitments and intended outcomes and to capture key lessons learned.

Programmes approved on AMP will have their review deadlines set automatically at 12 months from the date of approval (then annually throughout implementation), and at three months after the programme end date (when interventions finish). These reviews may be brought forward, or (with Director approval) deferred by up to 3 months, but to note deferral can only be requested once in a programmes lifecycle. Programme Completion Review (PCR) template should be uploaded to AMP for approval by their HoD (or delegate). This is due within 3 months of the programme end date and may not be deferred. As per our transparency commitments Annual Reviews and PCRs uploaded to AMP will be published to DevTracker.

In certain scenarios, teams may wish to exempt a programme from the annual review process. The criteria for an exemption (which then needs to be agreed by the Head of Department/Development Director) is if the programme’s next annual review date is within three months of the programme’s end date (or if the programme has a duration of less than 15 months).

For programmes meeting the criteria for the ‘Smaller Programmes/Projects’ typology described in the Introductory Section under 1.5, light touch Annual Review and Programme Completion Review templates are being developed. [New PrOF guide coming soon].

CSSF Programmes/Projects: The annual review process as set out in the CSSF Operating Framework should be used. For those programmes on the Aid Management Platform then a scoring conversion table is in place to support teams in uploading the annual review details to the system.

Rule 22: Any programme or project that demonstrates sustained underperformance must be subject to formal improvement measures, before a decision is taken at the appropriate level to continue, to restructure or to close it.
Principles in Practice
Do no harm: Continuing an underperforming programme could have negative consequences. At the same time, early closure or restructure can expose programme constituents (beneficiaries), staff or stakeholders to new or increased safeguarding risks, and threaten the sustainability of results already achieved. Any decision to continue or make changes to the programme should carefully consider the risks.
Honesty and Professionalism: confronting underperformance can be very difficult, particularly when needs are severe, important relationships are at stake, and significant resources have already been sunk into the programme. However, it is important for teams to be honest and objective about a programme’s chances of succeeding, and recognise when FCDO funding could be better spent elsewhere.
Innovative and agile: Projects may underperform for a variety of reasons. Teams should be prepared to flex delivery approaches at short notice on the basis of the evidence in front of them. Agility is a crucial response to underperformance, whether it is in the context of programme closure or a responsive change in approach. There is no template for a PIP or early closure plan, teams are empowered to innovate and flex to decide what is most useful in their particular context.

Why? FCDO aspires to maintain and improve portfolio performance. However, we recognise that some programmes and projects will underperform relative to expectations set out in a business case, project proposal, and/or results framework. This is not necessarily an indication that we should close them, if we can clearly demonstrate what we are doing to manage risks and get them on track (via a performance improvement plan), and are appropriately escalating issues to senior managers/ministers. It may be that an underperforming programme accompanied by robust management and learning is more valuable than an over-performing programme that has low ambition or poor management.
Good programme and project design should be clear on how they will flex in response to anticipated change. This, coupled with regular monitoring and review, will ensure that teams will have the necessary information and opportunities - whether it is due to a change in context, the realisation of major risks, delivery failures or design flaws – to identify that the programme or project is not performing as expected, and to respond quickly.

Who? The PRO is responsible for identifying and responding to underperformance, reporting to their SRO, escalating this if necessary, in accordance with FCDO’s risk appetite guidance.

How? Programmes and projects can underperform for a variety of reasons. High quality monitoring and formal reviews of progress are key to identifying underperformance. This could be by a small but persistent margin, with repeated failure to reach output targets (e.g. scoring a B at consecutive annual reviews), or a programme or project going more significantly off-track in a shorter space of time.
The improvement measures developed will depend on the drivers of underperformance. A change in context, the realisation of major risks, partner delivery failures or fundamental programme or project design flaws would all need to be addressed differently. Responses could range from renegotiating funding agreements to introducing milestone payments, restructuring the programme or project to focus on high-performing areas, or downgrading ambition, if learning shows the original goals to be unrealistic.

Having determined issues and improvement measures required, teams must develop a performance improvement plan (PIP) setting fixed targets and timeframes for decisions to be made, reducing the risk that these slip sideways (or are not escalated to the appropriate level) while issues continue to worsen. The PIP should be developed in association with the delivery partner and form part of the agreement governing programme or project activity going forward. Early closure will usually be a last resort, when all other routes of discussion, negotiation with partners and performance management have been exhausted. Proposed actions to terminate and close a project must be considered against the terms of the contract or agreement covering it, in consultation with legal advisers, before such action is taken.
Rule 23: Budgets must be accurately profiled and forecast, regularly reviewed and updated as necessary.
Principles in Practice
Ambitious: no restrictions on the number of pre and pipeline projects that can be held within a division/directorate who are encouraged to maintain an active pipeline to maximise value for money and deliver against results. Teams should feel confident to make proposals and follow a risk-based approach.
Professional: robust financial management underpins successful programme and project delivery, and we will hold our delivery partners to account for the way they manage UK taxpayer’s money.

Why? HMT Managing Public Money (see 4.5. 'Control of public expenditure') requires all departments to keep spend within agreed budgets and ensure the spending profile is sustainable. Public sector organisations should never go overdrawn. Exchequer costs rise if large payments are not forecast in advance.’

FCDO's overall budget must be allocated and accurately profiled to ensure that it contributes to the delivery of the UK ODA target and other spending commitments are in line with the Spending Review Settlement Letter (and subsequent amendments), via the Resource Allocation Round.

Who? The Programme Responsible Owner is responsible for ensuring that budgets are profiled, forecast as accurately as possible and updated regularly, according to the schedule and processes required for the programme. Forecasts should be updated whenever changes to programmes are made that have implications for the pace and timing of spending.

How? In-year financial management is vital to achieving FCDO's financial targets and to ensuring ongoing scrutiny of allocation of resources and value for money. To manage FCDO's project and programme resources and to ensure that we achieve our strategic key results, it is important that in-year financial slippage is managed effectively. PRO or programme finance teams must make sure:
- Budgets are accurately profiled at the start of each financial year and updated in year to reflect any changes.
- Financial forecasts are realistic, monitored throughout delivery and updated regularly
- Actual spend must be recorded in line with FCDO Resource Accounting rules and processes.
- Underspends can only be used in accordance with any programme-specific policies where the programme is still open but if closed then underspend needs to be returned to the FCDO central contingency budget using the manual invoice request process.
- The PRO must ensure that any relevant taxes (e.g. VAT, customs duties) are included in the budget and all financial forecasts throughout the project.
- Staff must contact the VAT Liaison Officer within Financial Accounting, FCPD, if they require advice about UK VAT. Staff must never provide tax advice to partners.
- Costs for staff managing or delivering programme activity can only be funded within the limits and conditions set for a specific programme.

Rule 24: Funds must only be paid to the intended recipient and only be used for the purposes formally agreed.
Principles in Practice:
Transparent: British taxpayers and beneficiaries and constituents in the countries where we operate have a right to know what we’re doing, why we’re doing it, how we’re doing it, how much it will cost and what it will achieve.
Responsible and accountable: We are responsible for delivering the results we have committed to, in line with the expectations set out at design and approved by ministers or their delegated officials.
Evidence-based: annual audited accounts/financial statements are one way that SROs and teams might gain assurance of the flow of funds. However, teams may decide that, in their context, an alternative approach will be more effective or better VFM – for example, a co-donor providing their own audit of downstream partners rather than contracting this out.

Why? HM Treasury's Managing Public Money sets out the standard rules and requirements when handling public finances. The nature of FCDO’s programme work, often in fragile or conflicted-affected regions where it is difficult to monitor activity, increases the risk that our funds could be diverted from their intended recipient or purposes. Therefore, SROs and programme teams will want to take additional measures (as set out below) to identify downstream partners and gain as complete assurance as possible that our funds are being used correctly. Failure to do so could lead to adverse external scrutiny, impacting the integrity of aid programming.

Who? The Programme Responsible Owner (PRO) is responsible for taking all necessary steps to ensure that funds are paid and used as agreed in the specific formal arrangements on their programme. This includes ensuring that delivery chain maps record all organisations using FCDO funding to deliver the programme outputs.
More broadly, the management of fraud and fiduciary risk is a collective responsibility of all FCDO officials and partners. Everyone is responsible for the sound management of public resources, whether working on policy, programme delivery or other resources.
How? The flow of funds from FCDO to partners, and onwards to downstream partners and recipients, must be assured by programme teams through the regular and robust scrutiny of invoices, payment receipts and partner financial reports. Annual audited accounts and financial statements can provide valuable independent assurance to supplement this.
A budget will be agreed with the partner as part of formalising the funding arrangement. The level of detail this goes to (i.e. how far the budget lines are broken down) will vary depending on the complexity of the project and how much scrutiny FCDO chooses to exercise over it. Once agreed, the partner will be expected to report their spend against these budget lines, with the frequency and format of financial reporting agreed in the funding arrangement. The PRO should discuss with the partner how any movements between budget lines (for example, to address under or over-spend, or to respond to new opportunities/lessons learned) will be managed.
Working with Multilaterals:
Multilateral bodies typically provide audited financial statements which cover the entire organisation. These statements are reviewed at a central level by the FCDO team responsible for core funding, rather than at the programme level by individual teams.

Delivery chain maps (DCM) identify and capture in visual form the names of all partners involved in delivering a specific good, service or change, ideally down to the end recipient. A DCM should be in place for all funding modalities, with the exception of core funded arrangements with multilaterals, to help identify the organisations receiving and using FCDO funding. Any organisation in receipt of FCDO funding should be included in the DCM before they receive funding from the programme.
Asset checks during field visits can be used to cross-reference asset registers provided by our partners, and deepen our understanding of partner capability to manage fiduciary risks.
An audit is a review of information, ideally by an independent body. An audit of financial statements is a review of the set of accounts of an organisation, which expresses an opinion over whether the information appears to be “true and fair”. The review will be on a sample basis (i.e. it won’t cover all of the partner’s activities), and is designed to give stakeholders reasonable assurance that the information is reliable. It is not a 100% guarantee of accuracy.
In addition to the statutory annual audit of the organisation, FCDO may require or commission specific audits of a project – either of the project as a whole or of areas of high risk within the project.

Rule 25: No payment can be made in advance of need, i.e. before the funding is required to enable activities to proceed.
Principles in Practice
Context-specific: using advance payments or paid in arrears, or on the basis of results. It is possible to have a combination of payment types within one programme or project, or even one funding agreement.
Honest: payments in advance must address a genuine need. They must not be made purely to manage a spending target.
Accountable: the VfM justification and all documentation supporting the SRO’s decision should be retained for scrutiny.

Why? HMT’s Managing Public Money requires that departments cannot make payments before they need to. This allows HMG to minimise public sector borrowing by making efficient use of cash. The budgets granted to FCDO by HMT are conditional on these requirements, and the consequences of non-compliance are severe.

This does not mean that FCDO cannot make payments in advance of actual costs being incurred by an implementing partner. With the exception of contracts (see below), advance payments may be made where the implementing partner does not have or cannot raise sufficient working capital, where it is essential to allow the programme or project to proceed as planned, and/or where the advance payment demonstrates strong value for money (VfM).

Who? The Programme Responsible Owner (PRO) is responsible for ensuring advance payments are not made in advance of need, and that approval of advance payment is given at the correct levels depending on the schedule agreed.

In programmes funded from the Conflict, Security and Stability Fund (CSSF), approval for advance payments needs to be given by the Joint Funds Unit. Programme teams must complete the advance payment request and submit this together with the completed due diligence report, project proposal and activity-based budget to the appropriate programme secretariat (JFU) for consideration/approval.

How? Requirements vary depending on the funding instrument and form of agreement. Where advance payments are likely to be made, this guidance must be considered for every single payment, not only at the business case stage or when agreeing funding arrangements.

The following principles always apply:
- Payments should not be made more than three months in advance, except in exceptional circumstances (see below). This is typically enough to allow partners to proceed with activities, while minimising public sector borrowing.
- Further payments should not be made until all previous advances have been accounted for. In practice this means a request for a payment in advance should be adjusted for any unspent funds from previous advances.
- Requests for advance payments must be assessed against any risks identified in the due diligence assessment of the partner, and the plans for managing those risks.
- Advance payments normally create an accounting ‘prepayment’ and should be discussed with Finance Managers to ensure the correct resource accounting treatment.
- CSSF need central management approval for advance payments must be given by the Joints Funds Unit.

Grant/MoU payments further than 3 months in advance require additional scrutiny. PROs must discuss these payments with their finance business partner or finance manager to ensure they are affordable and are accounted for correctly. There must be sufficient rationale for these payments and the rationale must be evidenced appropriately in case of audit. For any queries, contact Financial Accounting.
Contracts: Payments via contracts should be made in arrears, i.e. after the service or goods have been received, except for minor services (training courses, conference bookings or magazine subscriptions, where local discretion is acceptable). HMT approval via the One HMG Finance & HMT Engagement Team is required for all advance payments to contractors (both private sector and other), except for contract mobilisation payments that are payable when services commence under a contract. Payments in advance to private sector suppliers should not include management or administration fee costs.

Working with Multilaterals: The World Bank and UN agencies will often require payments six months in advance, as will some Red Cross emergency appeals. Programme teams must still ensure that the payment is not in advance of need, and VfM considerations still apply.
Rule 26: Any ODA programme foreign currency commitments above £50,000 must be agreed in advance by the Head of Financial Accounting & Policy. ODA programme foreign currency commitments below £50,000 must be agreed by the Director or Head of Mission.
Principles in Practice
Context-specific: If there is a strong case for a foreign currency commitment in your context, assess and document how you will manage the risks of this.
Proportionate: Submissions for exemption and associated risk analysis should be proportionate to the proposed spend, in order to manage the risk appropriately, while keeping the programme management burden of this process as low as possible.

Why? Most of FCDO’s ODA foreign exchange exposure is in relation to programme expenditure spanning multiple years and no ODA spend is covered by the Foreign Currency Mechanism. ODA targets are in GBP sterling so for high value programmes, committing funds in GBP sterling avoids the risk of losses due to foreign exchange movements. This, in turn, avoids uncontrollable pressure on budgets, and makes budget and ODA management and forecasting more straightforward.

Exchange rates fluctuate over time, and by making ODA commitments in sterling FCDO passes the risk to the partner. Sometimes our partners will benefit from this (as does FCDO through the achievement of increased results) when foreign exchange rates are favourable.

Who? The Programme Responsible Owner must ensure that any commitments in foreign currency are approved at the correct level before making the commitment.
In Practice: Adverse movements in exchange rates may impact on a programme’s ability to deliver results. Teams should monitor this risk throughout the life of a programme, and may need to consider a range of options including reassessment of output/outcome targets, or seeking cost extensions through the normal approvals process.

How? The “commitment” in this Rule is the financial limit in the funding arrangement – i.e. the total amount that FCDO is committing to pay. It is acceptable for an implementing partner to submit its detailed budget in the currency it primarily works in, and report expenditure in that currency, as long as the financial limit in the funding arrangement is defined in GBP Sterling. This Rule deals with the rarer situation where the financial limit is set in a foreign currency.

Commitments proposed in currencies other than sterling that exceed £50,000 must be approved by the Head of the Financial Accounting and Policy Team. Spending teams must contact Financial Accounting with their request and rationale. Decisions on commitments in local foreign currency up to £50,000 can be taken by FCDO spending departments, approved by the Director or Head of Mission.
Exceptions: Rule 26 does not apply to programmes and projects where teams receive allocations in foreign currency based on the budgeting exchange rate (i.e. where spend is covered by the Foreign Currency Mechanism)

CSSF funding is exempt from this rule. Any questions around foreign exchange should be directed to the Joint Funds Unit.

Payments: FCDO makes foreign currency payments through spot currency transactions (foreign currency deals on the day of payment). Forecast payments to partners must be made in line with the programme agreement, and must not be deferred or brought forward to offset currency fluctuation.

Managing the impact of exchange rate fluctuations: Programme teams must not include, or allow partners to include, buffers in budgets for exchange rate movements. Where budgets are based on sterling commitments, they must be managed in line with the FCDO budget policy. When agreeing a Sterling funding agreement budget, it may be appropriate for the SRO to use an exchange rate averaged over a period of time rather than the spot rate on the day that the programme is agreed.

Rule 27: FCDO staff roles charged to a Programme or Project budget (except for CSSF/ISF) must be essential for the delivery of a programme, approved in line with PrOF Rule 9, and offer better value for money than an outsourced alternative. Details must be notified to Centre for Delivery and Strategic Finance as soon as a project-funded role is being considered.
Principles in practice:
Professional: This Rule enables us to use FCDO staff in the delivery of programmes where it offers better value for money to do so.
Collaborative. Involving FCDO staff in the delivery of a project can improve information flows and collaboration between FCDO and the implementing partner, particularly where co-design or adaptive approaches are appropriate.
.
Why? FCDO operates within a Workforce Spending Target, agreed with HM Treasury, which puts a ceiling on the amount FCDO can spend on its staff. A separate element of the Workforce Spending Target puts a limit on what FCDO spend on project-funded staff. The Workforce Spending Target does not apply to ISF/CSSF-funded staff.

The criteria for insourced roles are below. Apart from CSSF/ISF, these criteria also define which staff costs may be charged to a project budget (previously known as “programme-funded staff”).
CSSF/ISF funded staff
CSSF (now part of ISF) operates under a different settlement with HMT, with different rules on project funding of staff.
Departments/posts creating CSSF-funded roles should be aware that if projects and programmes move onto the FCDO baseline in future, it may not be possible to fund those staff from the project budget. They should consider how these roles will be funded in the longer term.
1. Staff must be doing work that is essential for delivery and would (and could) be sourced externally if not delivered in-house.
2. Project-funded staff need to be approved as part of a Business Case or equivalent, and be affordable within the available budget. (i.e. they must be approved in line with PrOF Rule 9).
3. The Business Case or equivalent should give evidence that performing the work in-house is better value for money than a feasible outsourced alternative.

The criteria allow FCDO to deliver elements of programmes using FCDO staff rather than external implementers, where it offers better VFM to do so. Creation of project-funded staff roles is a delivery choice for a project within a programme, not a way to circumvent caps on Directorates’ workforce. They also have implications for FCDO’s workforce.

FCDO needs central, aggregated data on all programmes that are planning to create new project-funded staff roles, to be able to confirm that new, additional roles will not take us over the ceiling agreed with HM Treasury. HMT may agree uplifts to the Workforce Spending Target where we can make a value for money case to do so, but this needs to be agreed before FCDO commits to new staff roles that will take us over the ceiling.

Who?. The Programme SRO is accountable for ensuring that all project-funded staff roles in their programme meets the criteria above (the Solutions Hub can provide advice if needed) and that plans for in-house delivery are notified to Centre for Delivery and Strategic Finance.

Strategic Finance needs to report to HMT every six months on new project-funded roles that FCDO has created, or plans to create, with a short summary of the VFM case for them.

How? Centre for Delivery’s Solutions Hub has created a Form for programme teams to notify us and Strategic Finance of new project-funded roles that are being considered. This will normally be in the design stage of a programme when decisions are being made on delivery options.

Project-funded posts can be added during the implementation of a programme, if evidence shows this would offer better VFM. This can be approved through a business case addendum.

It is also possible to use design funds to pay for project-funded staff: this is approved in the same way as other design funds (see Rule 9).
Rule 28: A complete, accurate and up-to-date inventory must be maintained for all programme assets owned by FCDO. These assets must be disposed of in a way that represents best value for money, with a clear record of decision making and appropriate approval of transfer.
Principles in Practice
Responsible: our programme assets can be highly valued commodities in the fragile and sensitive areas we work in. Conflict or violence can be generated in pursuit of assets perceived to be up for grabs, putting vulnerable people further at risk. For example, a delivery partner's reputation for weak control of portable, high-value assets such as laptops and mobile phones could encourage violent robbery or extortion of local programme staff or beneficiaries.

Why? HMT's Managing Public Money (4.10) requires departments to set out an appropriate asset management strategy to define how it acquires, maintains, tracks, deploys and disposes of assets. For FCDO, strong asset management is an essential capability requirement for our implementing partners. Partners are required to develop and maintain accurate, up to date asset registers in order to provide FCDO with this assurance.
Weak control of assets, and inaccurate or out of date reporting, means that cases of suspected fraud may go unidentified by the partner or FCDO. This poses operational risks (such as reduction in delivery capability; financial loss) and reputational risks to FCDO, making it more likely fraud cases will be perpetrated against our programmes in future. In cases of significant loss or fraud, the Permanent Secretary will be called to answer before the Public Accounts Committee, risking a loss of public and ministerial confidence in the department.
Working with multilaterals
Assets purchased via financial aid to governments or core and non-core/multi-bi contributions to multilaterals (including multi donor trust funds) are not owned by FCDO. They will be purchased, managed and disposed of according to the government or multilateral’s own rules and procedures. As part of the due diligence process teams should ensure that partners have strong asset management processes in place. In the case of non-core/multi-bi funding, programme teams should also consult the FCDO institutional lead and, where it exists, check the overarching agreement in place between FCDO and the multilateral organisation (e.g. an MOU or Framework agreement) for further detail on asset management arrangements.

Who? Programme Responsible Owners are responsible for following all due process. Asset disposal plans and transfer agreements must be approved by Heads of Department/Development Directors. Physical asset checks against the register must be carried out at least annually by FCDO staff or partners.

How? FCDO considers any equipment or supplies purchased from FCDO funds as programme assets if they have a useful life of more than one year and the purchase price/development cost of the asset is in excess of £500. ‘Attractive assets’ such as mobile phones or laptops should be grouped where the combined value is in excess of £500. (Note that some historical funding agreements will set this threshold as £1,000.)
For legacy FCO programmes, proposed asset purchases must be considered by the Post/Directorate Programme Board before a programme/project is approved, or (if already approved) before purchase.
Any programme-funded assets or goods that have been lost or stolen must be reported to ReportingConcerns@fcdo.gov.uk, regardless of value. A plan will be developed with the partner to replace the asset or reimburse FCDO for the cost. Assets and goods replaced by the partner must still be reported.
Asset disposal: The assumption is that FCDO will get best value for money by selling programme assets via auction, transferring them for use in other FCDO programmes, or retaining them for its own use. However, if this does not represent good value for money, or if the original intention of the project was that assets should be retained by the implementer or by beneficiaries, assets can be transferred to the existing delivery partner, or to a third party. Before agreeing to a transfer of ownership, Heads of Department must be satisfied on the following points:
- the asset will be put to a relevant/appropriate purpose
- the recipient has adequate resources and controls in place to maintain and operate the asset, including purchase of any consumables
- the item will not be sold or disposed of, or diverted for another purpose, within a reasonable time period
- any local requirements or formalities (e.g. duties and taxes) on transfer will be met.
- IT Equipment is disposed of in line with EU Waste Electrical and Electronic Equipment (WEEE) Regulations and all personal data will be removed, in line with GDPR requirements.
These points must be agreed as conditions of the transfer by an exchange in writing with the recipient and must be signed by the HoD or delegate, before the transfer takes place.

Rule 29: Write-off of costs related to losses or fruitless payments, including assets lost, stolen or damaged, must be approved at the appropriate levels.
Principles in Practice
Transparent: any loss or misuse of public funds needs to be recorded as part of our license to operate.
Responsible and Accountable: In order to achieve best value for money, we should only consider writing off losses as a last resort. All reasonable actions should be taken to recover the losses before the write-off request is submitted.
Proportionality: the submission should be proportionate to the size of the loss. A missed flight might only need a brief submission, whereas a higher value or more complex loss would require a higher level of detail.

Why? Losses must be captured accurately for inclusion in the FCDO’s annual report and accounts. Errors or omissions could lead to FCDO accounts being qualified, with severe reputational consequences for the department. Write-offs occur if goods purchased with FCDO funds are lost/stolen/damaged, or where proper accounting documents for expenditure cannot be obtained. It also occurs when FCDO has incurred non-refundable expenditure but has not received the benefit of these payments, such as cancelled flights or training courses. Such items cannot be charged against FCDO's budget as normal expenditure. They must still appear in FCDO's accounts as a loss, to comply with HMT Managing Public Money Guidance (A4.10).
Depending on the scale and nature of the loss, Finance Directorate may decide to inform HMT, who may in turn decide to bring the loss before Parliament in a Public Accounts Committee hearing.

Who? The PRO must seek approval from someone at Grade 6 or above in their line management chain as well as the Programme SRO before submitting the write off to Financial Accounting through a Service Now request to ensure that the loss is recorded with FCDO central write off.
Working with Multilaterals: This rule applies to multilateral programmes where FCDO funds can be tracked. It does not apply to core funding (partners should report on any loss or misuse of funds through the appropriate channels). If the loss has occurred in a pooled programme, spending teams should provide a submission to the Financial Accounting team, who will determine the appropriate reporting requirements.

How? Internal and external auditors (National Audit Office) review the losses recorded in our Accounts. It is important that all write offs, regardless of size, are submitted to the Financial Accounting team via a Service Now request in a timely manner, covering:
- background - a short summary of the case and why the need for a write-off has arisen e.g. equipment damaged, lost or stolen.
- amount to be written off - includes the replacement value of any equipment.
- attempts made at recovery and outcomes (e.g. police reports)
- actions taken or planned to prevent reoccurrence.
- transaction details e.g. Account code, Cost Centre, Objective Code, Analysis 1, Analysis 2 and Intercompany
- project details – only provide details of the Project Number, Task Number, Expenditure Type and Expenditure Org if the original transaction on HERA is programme or capital project expenditure.
Timing: Write offs must be processed as soon as exact costs are known. For example, when seeking a refund, the final amount received could be net of processing fees. Fraud cases can take a long time to investigate, and a write-off is only a last resort when it is known that the funds cannot be recovered. Although the incident causing the loss may have happened in a previous year, the fact that there is a loss and the amount of that loss may only be known in a different financial year and so it should be written off at this point (and cannot be backdated).

Estimating loss value: If a relatively new asset is lost, then it can be valued at cost price. Older assets will have wear and tear and will no longer be worth ‘cost’. Agreed depreciation policies can calculate the ‘net book value’ – otherwise, teams (in consultation with partners) should estimate the ‘useful life’ of the lost asset.

Rule 30: All programmes and projects must be closed effectively and responsibly, even when closing early. Outstanding project payments must be made, liabilities extinguished, and underspend returned to FCDO within eighteen months of the programme’s end date. All required audited accounts and financial statements covering the full duration of every project within the programme must have been received before the programme can then be closed and archived.
Principles in Practice
Professional: How we close our programmes affects our relationship with partners/suppliers. It’s important that we close programmes responsibly and respectfully and that we plan for closure when we design options for our programmes.
It’s important that we are professional in fulfilling our responsibility of managing public money safely and accurately. Ensuring accounts are balanced within the financial closure period is a way of holding ourselves, and our partners to account.
Responsible and Accountable: Whilst teams will want to scrutinise programme spend throughout the implementation cycle, it is particularly important before final closure – as is archiving - to confirm our funds have been used appropriately, and that there are no outstanding issues to resolve.

Why? Closure is an important stage of the lifecycle and should be planned for in advance and executed methodically. This includes responsibly closing out funding arrangements with partners and capturing programme lessons and disposing of assets (see rule 28).
The 18 months following programme closure is called the financial closure period. All outstanding transactions must be completed during this time, so that the programme can be considered fully closed, before being archived.

FCDO relies on audited accounts and financial statements to determine whether our funding has been used as intended. This does not necessarily show whether objectives have been achieved, but it shows how funds have been managed and spent by the entity.

This 18-month deadline reduces the risk that unresolved issues, for example, funds owing to FCDO (unspent funds to be returned to central contingency budget – to note that when a programme is still on-going but only one of your project partners funding has ended, that any unspent funds from the partner can be returned and used on other components of the programme in a bid to achieve the programme outcome(s)) or to the partner, or missing assets, are forgotten about once delivery is complete. Non-compliance with this rule could lead to fiduciary and reputational risks to FCDO – for example, underspend remaining with the partner rather than being returned to FCDO, or assets going unaccounted for.

Who? The PRO must ensure all closure tasks are carried out in a timely manner and to a high standard, before archiving the programme, including capturing lessons. This responsibility will often extend beyond the operational closure of the programme and the loading of the Programme Completion Review (PCR) which will be due three months
Working with multilaterals
Audit provisions are set out in all formal exchanges with multilateral organisations. We require either audited statements at the project level, or an audit framework at the organisational level, e.g. the UN’s single audit framework, which provides a sufficient level of general assurance.
Contributions to multilateral trust funds in sectors such as infrastructure may involve long gaps between FCDO's money being disbursed, committed, spent and accounted for. Teams should consider how best to manage this when setting end dates, reporting requirements and results frameworks.
after the programme end date (to note PCRs cannot be deferred).

How? Setting the right programme end date is an essential part of planning. Teams should ensure that the end date provides sufficient time to gather all the information required to conduct the PCR. In some circumstances where partners have fixed reporting cycles, it may make sense to synchronise the end date.

Audit and other partner reporting requirements will be specified in the funding arrangement (e.g. contract, grant letter or MoU). Reporting requirements often require submission of a Project Completion Report, an Expenditure Report, and Audited Accounts.

If there are outstanding payments (for costs that have been agreed and incurred before the expiry of the related funding arrangement) at the point of financial closure (18 months after the programme end date), teams will need to extend the life of the programme to ensure that there is sufficient time to make any final payments. If the extension reaches the next review point (i.e. 12 months from the programme completion review), PRO should update the project completion review and reload it on AMP if appropriate.

Once a programme has been closed then it cannot be reopened as formal closure activities will have taken place. In addition, once a programme has been formally archived on AMP, it is no longer possible to carry out financial transactions between FCDO and its partners and HERA project postings cannot be processed. The FCDO team must be confident that they have gathered all the necessary information from their partners to confirm no funds are owing, and no further transactions will be required.

4. PrOF Roles and Responsibilities

This section of the Programme Operating Framework describes the types of FCDO staff that will typically be involved in programme delivery. This section will be useful to programme managers, or those with programme leadership roles or jobs, such as Portfolio SRO, Development Director, SRO or PRO.

The PrOF defines two Roles that are mandatory for every programme – the Senior Responsible Owner (SRO) and the Programme Responsible Owner (PRO). It sets out what these two roles are accountable for, who they are accountable to, and outlines how the Roles might be assigned.

The roles are defined in terms of Accountability and Responsibility, which the PrOF defines as follows:
- The accountable person is the individual who is ultimately answerable for an activity or decision. This includes ‘yes’ or ‘no’ authority and veto power. Only one accountable person can be held to account. An accountable person has to be accountable to someone for something.
- The responsible person is the individual who actually undertakes the task: in other words, they manage the action / implementation. Responsibility can be shared. The degree of responsibility is determined by the individual with the accountability.
4.1 Head of Mission/Director
The Head of Mission (HoM) or Director (HQ) holds the Portfolio SRO and Senior Budget Holder roles for the post or directorate. This means they have overall accountability for the whole portfolio of activity in the post/directorate, including programmes.

The Head of Mission must delegate in writing the responsibility for day-to-day oversight and delivery of the ODA spend to the Development Director or Head of Department (HQ), where one is present. This will include programme quality, effectiveness of related policy engagement and influencing work, compliance with programme rules and adherence to FCDO controls, and effective management and escalation of risk.

All Posts will work to a single set of HMG objectives set out in their Country Plan. The Head of Mission (HoM) is accountable for the delivery of these plans, which encompass all HMG activity and resources at Post, including programme and project activity managed at Post. The Head of Mission is therefore SRO for the country portfolio, and accountable for compliance of the portfolio with the PrOF (as set out in the Portfolio SRO delegation letter).

As Chair of the Country Board, responsible for delivering for the Country Plan, and Implementation/Programme Board (overseeing all Programme activity in-country), the HoM is supported through the following mechanisms:
1. a consultation mechanism: the HoM must be consulted on all departmental proposals on activity and resource in country. Additionally, all significant spending or policy submissions to Ministers affecting activity in country should include a comment from the relevant HoM/s reflecting the impact of proposed change on the Country Plan.
2. a review mechanism: under which the HoM may propose significant changes to activity or resource allocation (people and budget) to deliver the Country Plan. The expectation is that these decisions can be made at Post, provided all the following criteria apply:
  1. The proposal is a reallocation within a single campaign goal of the country plan;
  2. The proposal is a reallocation within a single Post’s programme spend / activity;
  3. Any associated reallocation is within delegated authorities;
  4. Any associated reallocation is within financial year or spending review/country planning period; and
  5. The proposal is supported by the Country Board.
If these criteria are not all met, then decisions must be referred to FCDO Ministers.
As Senior Budget Holder, the Head of Mission is also accountable for ensuring that programme teams have sufficient personnel to manage and oversee the programmes and projects managed at Post. The level of resourcing should be proportionate to the complexity of the programme (see more detail below in section headed Programme Team).

The HoM is accountable for all risks associated with the Country Portfolio through the Country Plan, including programme risks. The HoM must escalate risks beyond the agreed country appetite.

Where programmes are managed by an HQ Directorate, the Director plays a similar role to the Head of Mission at Post. i.e.:
- The Director is the SRO for the directorate portfolio, as set out in the Directorate Business Plan, accountable for the outcomes of projects and programmes managed by the directorate (in some cases, the thematic Director is accountable for a cross-cutting portfolio); and
- As senior budget holder for the directorate, the Director is accountable for ensuring that programme teams have sufficient personnel, proportionate to the complexity of each programme (see more detail below in section headed Programme Team).

The Head of Mission (HoM) or Director is accountable for the efficient and effective delivery of all approved programme and project activity, outputs and outcomes, including:
- defining policy-based programme objectives;
- assigning Programme SRO and PRO roles, or ensuring others (Head of Department or Development Director – for ODA Programmes) are assigning these roles; and
- chairing the Country/Regional Board and any other implementation board that oversees programme work in the Post/Directorate.

The Head of Mission (in-country) or Director (HQ) is responsible for assigning the roles of SRO and PRO to the individual(s) who are best placed to carry out the responsibilities of that role, based on the complexity of the project or programme, the personnel available and the time they are able to give to the role. This responsibility may be delegated – e.g. to Heads of Department – and should be delegated to a Development Director (where present) for teams managing significant amounts of ODA (>£1m p.a.). One person may hold the SRO or PRO role for more than one programme.

The Head of Mission (in-country) or Director (HQ) is not expected to take responsibility for day-to-day leadership or decision-making function in every programme in his/her portfolio. They are expected to ensure that, for every programme, somebody is assigned to the core programme Roles – Senior Responsible Owner and Programme Responsible Owner, and they may choose to retain the Programme SRO or PRO role themselves.

The HoM or Director does not need to be a programme or project management expert, but they need to understand the key concepts and be able to provide strategic leadership, ensuring programme spend is integrated fully into policy work at post and helps deliver clearly identified policy objectives in support of wider cross-government country plans/NSC strategies. HoMs/Directors have formal financial delegated responsibility for the programmes they manage and should ensure an enabling, empowered environment for those to whom they assign accountability and delegate responsibilities.

4.2 Development Director
In posts where they are present, the Development Director will normally report directly to the Head of Mission, and should typically lead all FCDO teams at post that manage significant amounts of ODA (£1 million per year or more). The Development Director provides oversight/is in the line of accountability for all FCDO ODA spend at post, for effective policy, delivery and assurance of ODA management, including a focus on value for money. They will be accountable to the HoM for that part of the country portfolio.

Development Directors are responsible for ensuring portfolio-level compliance and quality for all FCDO ODA programming at Post, for managing the budget in line with corporate ODA Rules and the principles of Value for Money. They are the initial point of risk escalation. There may be exceptions for blended ODA/non-ODA. The Development Director will also lead relationships with the most senior in-country international and host-country development counterparts, and will be members of the Country Board and the senior leadership team at post. Development Directors must also assign SRO and PRO roles for programmes, or be fully involved in that process.

HoMs / their Development Director delegates must be consulted on all departmental proposals on programme activity and resource in country, and may propose changes to activity or resource allocation to deliver the Country Plan where necessary. All new programmes spending ODA must be endorsed by a Development Director (where present) or an equivalent senior development expert (in HQ departments) at the approval stage.

Concept Notes and Business Cases for new programmes involving ODA need to be endorsed by the Development Director before they go to the Country Board. The Development Director should normally quality assure and sign off Annual Reviews of ODA programmes (although this may be delegated to the SRO for the programme if they are sufficiently objective and not directly involved in carrying out the review).

  1. PRO and SRO
The Programme Operating Framework defines two mandatory Roles in a programme – Senior Responsible Owner and Programme Responsible Owner. The SRO and PRO roles are both leadership roles, and have a clear hierarchy of accountability, in which:
- The Programme Responsible Owner (PRO) is accountable to the Senior Responsible Owner;
- The Programme Senior Responsible Owner (Programme SRO) is accountable to the Head of Mission or Director/Head of Department, either directly or via a Development Director (where present); and
- The HoM or Director is accountable through the management chain to the PUS, as Accounting Officer, or the 2PUS, as Accounting Officer for ODA.
Programme SRO and PRO roles operate on a foundation of empowered accountability. People taking on these roles are accountable for leadership and delivery of the programme. In return, they should be empowered to apply their professional judgement to make decisions on the programme according to the responsibilities of their role. This is based on a principle of subsidiarity – which recognises that most of FCDO’s projects and programmes will be more effective if operational decisions can be taken close to the project activities.

The expectations of the role, and the local parameters for an SRO or PRO to apply their judgement and make decisions, should be set out in a formal appointment letter. Further guidance on these is given in section 3 below. Appointment letters are not an end in themselves – their purpose is to ensure that people in SRO or PRO roles know what is expected of them and in return know what level of support they will get from the person assigning the role to them.

The SRO and PRO are not linked to specific posts in the organisational structure and will not usually form the entirety of an individual’s job. The roles should however be reflected in a post-holder’s job responsibilities.

Programme Senior Responsible Owner
Every FCDO programme must have a named Senior Responsible Owner (SRO). A person may be SRO for more than one programme. A programme can only have one SRO.

The SRO role is accountable for a programme meeting its objectives, achieving its outcomes and making the expected contribution to portfolio-level outcomes in Country/Business Plans and FCDO as a whole.

The SRO for a programme is responsible for strategic oversight of the programme(s) they are accountable for, holding the programme team to account in ensuring effective delivery, and providing overall leadership, decisions and direction.

The PrOF Guide on the SRO and PRO roles gives more detail on what is expected of the SRO, what they are accountable for, and what they should normally be empowered to do.

Programme Responsible Owner (PRO)
Every programme must also have a designated Programme Responsible Owner (PRO)[1]. A person can be PRO for more than one programme. The same person may be SRO and PRO for the same programme. In some circumstances, such as large or complex programmes, it may be appropriate to have more than one PRO, provided the accountability of each is clearly defined.
[1] Other working titles (e.g. Programme Director or Project Director) will sometimes be given to this role where they are likely to be better understood in the local context.

The PRO role is accountable for driving, on a day-to-day basis, the delivery of programme outcomes within agreed time, cost and quality constraints.

The PRO is responsible for leadership within the programme team. The role combines technical, programme management and relationship management responsibilities, with the balance of skills required likely to look different at different stages of a programme – so the role could be fulfilled by an Adviser, a Programme Manager or another member of the programme team.

Whoever fulfils the PRO role should be empowered to take operational decisions on a programme, within parameters agreed with the SRO and the Portfolio SRO. It is not efficient for the PRO to have to escalate all operational decisions up to the SRO, and this is not the way the PRO role is meant to work.

The PrOF Guide on the SRO and PRO roles gives more detail on what is expected of the PRO, what they are accountable for, and what they should normally be empowered to do.

4.4 Team Leader
Posts or Departments with a substantial portfolio of projects and programmes will usually be organised in thematic teams, each headed by a Team Leader.

As well as line management responsibilities, the Team Leader typically has a role in driving coherence across a set of projects or programmes contributing to a common strategic objective or working in a common sector, and ensuring that programme teams have the resources they need to manage the programme effectively.

Where a Team Leader is not also SRO or PRO for a programme managed by their team, the SRO or PRO appointment letters should clarify what role the Team Leader is expected to play in programme decision-making and oversight.

4.5 Programme Team
The Programme Team is made up of people with complementary skills who are responsible for managing the delivery of the programme on a day-to-day basis.

The skills, expertise and time that a programme team will need will depend on the complexity of the programme. The more complex a project or programme is, the greater level of expertise and experience, and staff time, needed to manage it. Part of the role of the SRO is to ensure that the complexity of the programme is aligned to the resources available to deliver it. Further guidance on programme complexity is available in the PrOF Guide to the SRO and PRO roles.

Within a programme team, the following roles will usually be present (unless it is a smaller team with limited resources):
- Technical Adviser(s) provide the link between programmes and policy, and external influencing work. A Lead Adviser on a programme will usually take responsibility for the technical aspects of programme design, monitoring and oversight, and for key aspects managing external relationships and influencing external partners.
- Programme Manager(s) ensure that best practice and compliance are applied across the management of a programme, and the projects within it. This includes design of the programme structure (how the programme will work), mobilisation of implementing partners, successful delivery of the required outcomes, including the establishment of appropriate governance and assurance, monitoring progress, managing risks and issues.
- Project Manager(s) take responsibility for the management of implementing partners, driving and overseeing the delivery of a project to ensure that the project outputs are clearly defined and achieved within the agreed time, cost and quality constraints.
- Project Support Officer(s) role covers a range of activities to support the delivery of the project’s objectives, enabling the smooth running of the project by supporting the programme management team.
Where programmes contain sub-projects that are themselves large, complex or risky, Heads of Mission/Directors or SROs for the programme may decide to appoint one member of the programme team a Project Lead, with agreed responsibility and decision-making authority over a specific project. There should be clear agreement on where the Project Lead is empowered to make decisions, and where decisions should be escalated to the PRO or SRO, who have accountability for the delivery of the programme as a whole.

For programmes implementing through contracts, an individual must be designated as a Contract Manager. This role, normally undertaken by a programme manager, is responsible for the day-to-day management of commercial contracts, ensuring that suppliers deliver the right goods and services as agreed within contracts. The Project Lead for a project implemented through a contract may also be the Contract Manager. The designated contract manager must have the appropriate level of accreditation according to contract value, complexity and risk.

A programme team will also draw on inputs from other specialists at key points in the programme – for example Commercial and Finance specialists, Programme Management Leads, or Technical Advisers with expertise in specific issues relevant to the programme (e.g. Gender, OSJAs, Monitoring, Evaluation). The team may also draw on Risk Management specialists in the post or department, or experts in due diligence, safeguarding or fraud investigation in central hubs or departments.

Some posts or departments with large volumes of programming, or regional departments covering smaller posts, may concentrate specialist expertise in areas like programme management, risk management or monitoring in programme support teams. Where present, these play an important role in supplementing the full-time resources in individual programme teams.

Additional guidance is available to inform decisions on the type of programme team resources that would normally be needed to manage different types of complexity in a programme.

4.6 Assignment of the SRO and PRO Roles
The Programme SRO and PRO roles should be assigned in a way that does not create unnecessary layers of hierarchy or slow down operational decision-making. The PrOF Guide on the SRO and PRO roles provides guidance on things to consider in assigning these roles, and who should be involved.

For smaller, less complex programmes, the expectation is that the SRO and PRO roles can usually be performed by the same person. For more complex programmes, particularly those that are expected to contribute to the outcomes of multiple portfolios, it will be more appropriate to assign the two roles to different people, with the SRO role assigned at a more senior level, with enough of an overview of the programme or programmes to play a constructive challenge role, and the PRO role established closer to day-to-day implementation.

The SRO role must be performed by a member of FCDO staff, and the SRO for a programme cannot be in an In-house delivery (project funded) Role – a role created as an alternative to outsourcing. The PRO role should also normally not be assigned to a member of staff in a project funding role, but there may be circumstances where this is appropriate, where the SRO is able to provide the necessary oversight.

5. Programme Operating Framework Life Cycle

This section sets out the life-cycle of a programme, as it proceeds from definition through to closure. This section will be useful to programme managers, and those with roles or jobs leading programmes, such as Development Directors, SROs and PROs.

5.1 What is programme and project management in the FCDO?
Programme and project management includes the range of activities that are required from the starting point of the initial real-world problem that is being tackled to the closure of a programme once activity is complete. It involves the design of the programme intervention, engaging with potential stakeholders and partners, monitoring that delivery is taking place as planned and reporting on the progress of the programme.

There are many steps to successful programme management and there are a range of learning resources available through Hera Learn to help FCDO staff gain the knowledge required to work throughout all stages of the programme lifecycle.

5.2 What is the lifecycle?
A Programme is made up of Projects and Activities.
- A Project is a set of discrete, time bound interventions designed to produce a set of Outputs. Projects may be managed by FCDO directly (through direct purchase of goods and services) but will more often be managed by external partners under a funding arrangement.
- Activities are everything making up a Programme that are not Projects. This may include FCDO staff salaries and costs funded from the programme, or discrete activities undertaken by others in support of the programme – for example specific pieces of monitoring or operational research, or audits.

The design, delivery and assessment of programmes and projects usually follows a common process or cycle. The Life Cycle has four stages (Fig.1) – Definition, Mobilisation, Delivery and Closure. Each stage leads to the next in a continuous cycle that rotates around a control framework. It guides design and delivery of programmes and projects from conception to completion, circling back to the definition , bringing with it any outputs, outcomes, and learning that can inform new programmes and projects.

There are a number of inputs that should be considered before the Definition stage is begun, such as business plans and UK government policies and strategies that a programme will be contributing towards. There are also a number of control points throughout the programme lifecycle which contain key documents for accountability within the programme lifecycle.

Monitoring and feedback (illustrated by the dashed lines around the cycle) takes place regularly and identifies whether each stage is delivering what is required. These feedback loops provide valuable learning that can be applied to the project itself, to the next stages of current interventions or to other concurrent or future programmes and projects. This includes feedback gained by engaging with programme constituents (beneficiaries) who can help teams validate assumptions on which the programme is based, as well as holding implementing partners accountable for the real world change resulting from the programme.

Controls*
3) Concept Note
4) Business Case
5) Formal Agreement
6) Delivery Plan
7) Annual Review
8) Programme Completion Review

DEFINITION
CLOSURE
MOBILISATION
DELIVERY
Feedback, Learn, Adapt
Feedback, Learn, Adapt
Feedback, Learn, Adapt
Feedback, Learn, Adapt
1) Outcome Delivery Plan & Policy Priorities

Portfolio Development &
2) Business Planning
International Policy Framework
Programme Operating Framework

Fig. 1

The Life Cycle does not exist in isolation. The programmes and projects within the cycle are informed and shaped by higher-level strategic objectives, across a portfolio of programmes and policy priorities.

5.2.1 Portfolio Management
The IPA defines a portfolio as the programmes, projects and related work (which may be in the form of policy development) required to meet common objectives. In a portfolio there can be choices over the activities undertaken - unlike a programme, where all activities need to be delivered to achieve the end goal. In FCDO, business and country plans describe some of our portfolios.
FCDO commissions the production of business and country plans (BCP) from Posts and Directorates. BCP is a tool for diplomatic, development and corporate teams to develop, articulate and approve their plans for delivering FCDO and HMG objectives overseas. Country posts develop one-HMG country plans that support all UK government departments’ Ministerial priorities. The BCP commissioning cycle follows the Spending Review cycle, with a regular 6-monthly check-in on progress.
FCDO Portfolios will typically be either geographic or thematic where the country or business plan sets out the portfolio plan. Some portfolios focus on a country or region, while others focus on global priorities – such as our global work on girls’ education – or a particular institution e.g., key multilaterals, or the UK development NGO sector.
A portfolio focus drives better ways of working. Portfolios include non-project activity in support of strategic objectives, as well as projects and programmes. For FCDO this will include the range of diplomatic and other non-aid levers the UK can bring to bear in support of UK policy interests, as well as the influencing work that FCDO technical specialists already do. Additionally, the finance and corporate functions play an enabling role in delivering all of FCDO’s portfolios.

A portfolio approach requires us to make decisions at a higher level – such as about strategic alignment, trade-offs, resourcing, priorities and capability etc - as opposed to doing things incrementally, one project, programme or influencing initiative at a time. Successfully managing our portfolios will help us to achieve value for money and should improve our impact and coherence. When done well, a strategic portfolio approach should drive new programmes or policy work, prompt us to stop work that undermines or is contributing little to strategic objectives, and surface tensions among conflicting objectives so they can be managed proactively.

5.3 The control framework for programmes
Programme Controls (numbered 1 to 8 in Fig.1) provides assurance that programmes and projects are being developed and delivered to the right standards and qualities.

They are the key points for control and assurance in programme and project delivery which are evidenced and subject to scrutiny and approval. Specific assurance steps may vary between different types of programmes (with specific guidance provided where this happens), but the principle of assurance gates and controls applies to all programmes. For example, some programme typologies do not require a Concept Note as well as a Business Case, but the principle of a proportionate approval document applies to all programmes.

Table 1 sets out the stages of the programme lifecycle, control types, where they fit within the programme life cycle and the actions needed. It is also a high-level step-by-step approach to programme activities that need to be taken to manage a programme in the FCDO.

Table 1:
Stage	Control	Control description	Accountable / Responsible	Actions include
DEFINITION / This stage is about understanding the strategic context, main policy issues and Country/Business Plans that are driving programme objectives. This can include outlining proposed interventions that might help achieve those objectives in a Concept Note, and, once approved, undertaking a robust design process, culminating in an articulation of the detail of interventions in a Business Case (or equivalent). This will cover the strategic context, evidence-based appraisal of intervention and delivery options, and a realistic assessment of risks, opportunities and management requirements. At this stage, it is important to think about delivery plans, monitoring, evaluation and learning needs, and anticipated results.	1. Outcome Delivery Plan and results and resource framework	Set the overall policy and resource framework for the Department’s work and allocate resources to individual business units to deliver specific results.	PUS and Executive Committee (accountable)	Drawing on evidence, know the main policy issues that your programmes and projects need to support, and the local / regional conditions that may affect design and delivery. Define objectives and develop ideas for the kind of interventions that might help achieve them. Appraise options and identify the right delivery channel or combination of delivery channels for the programme – including project funded roles. Identify and plan for management and oversight requirements.
	2. Business Plan (for UK Directorates) / Country Plan (for overseas Posts)	Individual departments/Posts develop Business Plans / Country Plans, setting out what and how they will deliver, consistent with the SDP and results and resources framework. The Business Plan/Country Plan is submitted to ministers for approval.	HoM/Director (accountable)
	3. Concept Note	The Concept Note sets out a proposal for an individual programme, explaining how it fits with the strategic objectives in a Business Plan, what the proposed intervention is and why it is recommended for ministerial approval (or approval by officials for lower value proposals).	SRO (responsible)
	4. Business Case	The Business Case (or equivalent) sets out the detail of how an individual programme will achieve its objectives and how it will contribute to delivering the Business Plan strategic objectives and results.	SRO (responsible)
MOBILISATION / This stage is about putting in place delivery mechanisms for the programme and any accompanying monitoring, evaluation and learning interventions. This might be in-house resource (Insourced roles), or a funding arrangement with an external delivery partner. (See below under Delivery Options for further detail). / This is also the stage where we establish the tone of the relationship with an external partner, and/or the expectations of project-funded FCDO staff. This includes clarity on roles, responsibilities, accountability, key stakeholders and management of finances and risks. Monitoring frameworks are also finalised, ensuring there is sufficient flexibility within interventions to adapt to changes in context and knowledge.	5. Formal Funding Arrangement (external partners). / OR / Recruitment and appointment of project-funded FCDO staff in in-house delivery roles.	The formal agreement establishes roles and responsibilities between FCDO and our implementing partner/ supplier, for delivery that is outsourced to external implementers. / Recruitment of in-house delivery roles works in the same way as any other staff role. The job profile and performance objectives for the role set out expectations of what each role will contribute to the programme.	PRO (responsible)	Where necessary, initiate early market engagement, and/orcompetition processes to generate proposals. Appraise and approve tenders and/or proposals against relevant criteria and that will deliver the required outputs and achieve the expected outcomes. Sign Contracts/Accountable Grant Agreements/MoUs as appropriate to the type of partner and how the funding is initiated.
DELIVERY / This stage covers the delivery of programmes and projects (activities and outputs), managing implementing partners and adapting interventions during delivery if the context and circumstances affecting the intervention change. Management actions range across monitoring finances, risk, issues, progress and results, engaging with stakeholders, and checking assumptions, ensuring continued relevance, strategic alignment, and value for money. In addition to ongoing monitoring and learning, an annual performance assessment provides an opportunity to reflect and take action to ensure the intervention is on track to achieve its intended outcomes. During this stage it is important to make timely and evidence-based decisions around the continuation, closure or extension of the project or programme.	6. Delivery Plan	PROs are responsible for ensuring an up to date, proportionate delivery plan that sets out for each programme: delivery priorities, key milestones, the logframe or results framework, roles and responsibilities, and risk management strategies. Where this information is held on AMP, parallel documents are not required.	PRO (responsible)	Complete all system admin procedures so that interventions can begin. Monitor activity, outputs, risks, finances and manage relationships with implementing partners, responding to issues to keep interventions focused on policy objective
	7. Annual Review	All programmes are formally reviewed at least annually, providing an assessment of performance, ongoing relevance, value for money, lessons learned and any remedial action required.	PRO (responsible)
CLOSURE / This stage is about ensuring all agreed outputs have been delivered and outcomes achieved, with any outstanding issues resolved. This includes producing completion reports, reviewing and evaluating performance and results and assessing outcomes, impact and value for money against strategic objectives. This stage is essential for bringing together lessons that can be shared with programme teams and applied to other existing and future programmes and projects. All programmes must be closed effectively and responsibly, even when closing early.	8. Programme Completion Review	All programmes must have a project completion review within three months of the programme end date on AMP.	PRO (responsible)	Receive completion reports, ensuring all agreed outputs have been delivered, resolving outstanding issues before making final payments. Review or evaluate outcomes and impact against policy objectives and VFM criteria. Identify lessons learned.

5.4 Flexing or adapting delivery
Some policy or programme priorities can be addressed by rolling out tried and tested solutions at scale. More commonly, FCDO programmes are catalytic in nature, looking to more complex challenges, with a limited evidence base on what works. Responding to uncertainty and complexity with interventions that are fully planned out risks costly failure or missed opportunities. Such problems might instead benefit from more ‘responsive or adaptive’ approaches.

Although the terms ‘flexible’, ‘responsive' and ‘adaptive’ are often conflated or used interchangeably, they are not the same. All FCDO programmes need flexibility to adjust resources and activities if needed. Many also need to be responsive to changes in the context and to local stakeholders. Being adaptive goes further, acknowledging that the end goal may be clear, but the pathways to achieving this are not. Adaptive programmes either test different options (from which the most promising is expanded and the others are dropped), or start with a set of interventions with the expectation that these will be adjusted in response to real-time evidence of what happens.

Figure 2: The Difference Between Flexible, Responsive and Adaptive Programming[2]

	Flexible	Responsive	Adaptive
Definition	Ability to increase or decrease spend and pace of implementation.	Ability to amend activities, goals or strategic intent in response to client needs or major unexpected events.	Ability to adapt activities, strategies etc based on real-time learning, changes in operating context during implementation.
In practice	Resources can be quickly adjusted, change direction if needed.	Programme has a defined outcome, but we add a new area of work or a set of activities to a programme in response to Covid-19, or a natural disaster.	Programme has a defined outcome, but strategy or approaches are adjusted along the way, drawing on political analysis or emerging evidence.
Context	Known	Known then shocked	Unknown/ Unstable/ Complex
Intervention pathways	Tried and tested, maintained throughout intervention	Tried and tested >> Pivoted	Untested /Emerging, adjusted, dropped, or scaled throughout intervention.

Where adaptive working is likely to be the best approach, it is important to make an early and informed choice, to provide a sound basis for subsequent programme design, mobilisation and implementation. When thinking about the potential to iterate, it might be helpful to:

Understand what evidence you need to inform decisions. It is only through better use and testing of evidence that you can reliably judge whether to adapt, and in what ways. Identify the key evidence gaps in the theory of change, then consider how to generate data and information to address them, including through beneficiary feedback.

Build learning to generate and test evidence. Tailor your learning strategy and monitoring, evaluation and learning (MEL) tools in light of these evidence and learning needs. You need be clear on what you need to test and why, how to complement your overall learning strategy with specific MEL tools and methods, and how to create a supportive learning environment.

Ensure clear governance and decision-making structures. Generating good evidence is not sufficient for adaptive programming: it needs be acted on. The relationship between learning, management and decision-making is therefore crucial. Focus on decision-points, appropriate decentralisation, building checks and review systems, and ensuring that your resources match your learning ambitions.

Ensure funding arrangements support a responsive and adaptive approach. The selection of implementing partners (including criteria for any competition) and payment terms for implementers need to reinforce, not undermine, an adaptive approach.

For more information on Adaptive Programming please see the Top Tips for Adaptive programming Prof Guide.

5.5 Delivery options
There is a range of delivery options for FCDO Projects. Some Programmes and Projects will be implemented by FCDO’s own staff, either in-house delivery by FCDO staff through project funded roles, or by direct purchase of goods and services. The majority of projects and programmes are implemented by external organisations, under a formal funding arrangement. These include:

Procuring a supplier on a commercial contract basis against a terms of reference defined by FCDO;

Accountable Grants to not-for-profit organisations for projects proposed by them;

Working through another UK government department, or an agency or arm’s length body of another UK government department;

Working through one of the FCDO’s arms-length bodies;

Working through multilateral agencies and partners through MoUs or framework agreements, or through delegated cooperation agreements with other bilateral donors or agencies;

Working through partner governments, including using Direct or Indirect Government to Government Financial aid, or through multilateral financial aid to partner Governments; or

Investments in private sector equity or other forms of financial instrument.

A programme may be delivered through different delivery options and funding arrangements. In all cases, the starting point for choosing delivery options should be the outcomes FCDO wants to achieve and value for taxpayers’ money. The choice of funding arrangement will also depend on the programme objectives, the expertise in the post or department, the sensitivity of the requirement and the availability of implementing partners who can deliver what the programme needs.

The delivery options chosen will determine the complexity of the programme and the amount of FCDO resource needed to oversee and manage it – so the choice of delivery options need to be balanced against the FCDO resources available to manage them. Delivery options and the FCDO resources to manage the programme should both be set out in the Business Case under the appraisal case and management case respectively.

5.5.1 In-house Delivery by FCDO Staff: Project Funded Posts
A department or post may decide that the best delivery option is to implement a project themselves, using FCDO staff, or through a hybrid model where FCDO staff deliver activities alongside external organisations. FCDO staff may also be embedded in other organisations to work in support of programme objectives. This approach was previously known as ‘Insourced Roles’.

PrOF Rule 27 sets out the criteria for FCDO staff to be funded through a programme or project, and the mandatory processes that need to be followed.

Please see the Prof Guide on Project-funded Posts and In-house delivery for more information on what to consider when designing and creating in-house delivery roles.

5.5.2 Direct Purchase of Goods and Services
Smaller projects will sometimes be implemented by FCDO posts and departments themselves, paying for goods and services directly.

5.6 Funding arrangements with external implementing partners
Most Programmes and Projects are implemented by external organisations. Where this is the case, there must be a signed funding arrangement with the external implementing partner, covering the whole period in which activities will be undertaken (PrOF Rule 14). The choice of funding arrangement is determined by the type of implementing partner, how the project is initiated, and the purpose of the funding with the key distinction being between Contracts and non-contract funding arrangements.

- Contracts are used where FCDO specifies the work to be done by the implementing partner. If the funding is intended for the acquisition of works, goods or services by the FCDO, then the procurement regulations (Public Contract Regulations 2015 (PCR 2015) or Defence and Security Public Contracts Regulations 2011) need to be followed.  Contracts are legally enforceable.  This is the case even if the purchasing relates to development spend and the ultimate beneficiaries are the recipients of ODA.
- Where the funding is given at arm’s length to a body, in support of a policy objective, and does not involve the purchase by the FCDO of works, goods or services, a non-contract funding arrangement (Accountable Grant or MOU) may be used.  These agreements are more flexible. They are governed by public law and are not contractually enforceable.

Commercial Procurement using Supplier Contracts

Contracts are used where FCDO has a clear idea of what it wants to achieve, how we want to achieve it and the price we are prepared to pay in exchange for the goods or services delivered. The Programme Team develop Terms of Reference and own the idea (the Intellectual Property / IP). These contracts normally invite competition from an open market including private sector suppliers and not-for-profit organisations. All bids must be assessed against the same criteria and contracted using the same supplier terms and conditions.

Rule 15 and the associated procurement guides sets out how the procurement regulations (Public Contracts Regulations 2015 or Defence and Security Public Contracts Regulations 2011) are applied in FCDO and the mandatory processes to be followed, including details of the transparency requirements..

5.6.1 Non-Contract Funding Arrangements
FCDO uses a range of non-contract funding arrangements, which are used to further policy. They fund projects, activities and initiatives that deliver specific outputs that support policy-based outcomes and objectives. They cannot be used where the FCDO receives a direct benefit for goods or services in exchange for payment.

The table below summarises the mandatory requirements that apply to non-contract funding arrangements. Further guidance is provided in the funding arrangement decision tree and the PrOF Guide to funding arrangements identify the most appropriate non-contract funding arrangement to use. All non-contract funding arrangement templates can be found on the ProF templates page of the intranet.

Non-contract Funding Arrangement	Details
Accountable Grants to non-profit organisations	Accountable Grants are used when FCDO is providing project or fund-specific grant support to not-for-profit, civil society and research organisations. The decision as to whether to use an Accountable Grant is made by the spending team, but the following two criteria need to be met: / We are funding a civil society, non-government or not-for-profit organisation or partnership and not a profit-making organisation, partner government or multilateral. We have verified the organisation’s not for profit status. / The organisation (or group of organisations) has approached FCDO with a proposal for funding, either as an unsolicited proposal or in response to a “call for bids/proposals”. / Accountable Grants may be awarded as a result of a competitive bidding process, or in response to an unsolicited proposal. / A competitive bidding process for an Accountable Grant is different to a tendering process for a contract, because FCDO does not specify the work to be done. Instead it sets out strategic policy-based objectives for bidders to prepare a proposal setting out how the activities, outputs and outcomes of the initiative will help FCDO achieve those objectives. / An unsolicited proposal is one that submitted to FCDO without any instruction by the FCDO programme team. FCDO may suggest changes to the proposal to improve alignment and increase value for money, but should avoid amending the proposal to such an extent that it starts to describe a different initiative or specify the work to be done. / We can fund unsolicited proposals from not-for-profit organisations without going through a competitive process, provided the programme team is able to establish and document that: / No other organisation would be able to carry out a project so well aligned with the FCDO objectives; / The proposal demonstrates value for money (for example by comparing costs with other organisations or projects operating in similar fields); and / Running a competitive process would not represent value for the taxpayer. / Unsolicited bids from commercial (for-profit) organisations cannot be considered for grant funding.
Multilateral and international organisations	FCDO formalises arrangements using funding arrangements with the implementing organisations. These can take a variety of forms and depend on the partner that we are engaging with. You should consult the FCDO team that manages the institutional relationship with a multilateral before entering into a funding arrangement to make them aware of the new funding arrangement. / We have agreed framework arrangements with a number of UN agencies and some multilateral development banks, to be used when FCDO is entering into a single donor programme with those organisations. In these cases, individual MoUs must not be negotiated, regardless of value. You must instead complete the associated ‘Contribution Arrangement’ template or agreed MoU for each specific activity with the partner. Any renegotiation of framework arrangements should involve the central team holding the institutional relationship with the multilateral bank or agency, and must involve the Finance and Control team in Finance Directorate at the earliest opportunity. / For other agencies, including the World Bank Group, FCDO has agreed standard MoU formats and templates for Trust Fund agreements. These are based on standard terms and conditions for all activities, with local specific modifications allowed only in agreed sections.
Funding the FCDO arms-length bodies (ALBs)	FCDO sponsors several ALBs (executive agencies and executive non-departmental public bodies), which are public bodies, established and publicly funded, at least in part, to deliver a public or government service in accordance with their own mandates. / The FCDO may provide project or programme-specific grant support to fund specialised delivery activities aligned with their respective mandates. The FCDO may also fund unsolicited proposals from the ALBs or the programme team may work collaboratively with the ALBs to develop a new project and programme. Such arrangements should usually take the form of a MoU. You should contact the ALB Sponsor before entering into any funding arrangement with them. / Programme teams should consult the PrOF Guide on “Working with the FCDO’s ALBs” for further guidance.
Other international donor governments	FCDO may pool resources with other government donors. As well as an arrangement with the lead partner, there will often be a need to formalise the arrangements between all members of the donor group. / The Delegated Co-operation Arrangement (DCA) can be used to agree the arrangement between the donor countries, when only the lead donor has an underlying arrangement with the implementing partner. If FCDO is the lead donor, the appropriate FCDO arrangement templates can be used.
Partner government	There are two main mechanisms by which FCDO disburses government to government financial aid: / budget support – a form of financial aid which is provided directly to partner governments. / non-budget support financial aid – FCDO may choose to provide assistance through partner government systems but not provide budget support; e.g. with targeted interventions to meet the costs of specified projects or expenditure items. / Where FCDO has a one-to-one relationship with the partner government, the partner government MoU templates must be used. / When another donor government is acting as the lead donor, we will normally sign a delegated co-operation arrangement with that donor. / When FCDO is the lead donor or all donors have separate arrangements, FCDO’s templates can be used to formalise the arrangement with the partner government. / When FCDO is acting as the lead donor and holding the funds on behalf of other donors, Crown Agents Bank is usually used by FCDO. In this scenario, spenders are advised to refer to the Third Party Money Crown Agents Guidance.

6. Programme Operating Framework – Governance

This section sets out the governance framework for our programmes. This section is relevant to those with accountability for programme delivery (such as Portfolio SRO and Development Directors), those with leadership roles (SRO and PRO) and programme managers.

6.1 Context
FCDO delivers the Government’s policy as set out in documents such as the Integrated Review (and refresh), the FCDO’s Single Departmental Plan, thematic strategies and business and country business plans.
FCDO is accountable to Parliament through the Permanent Under-Secretary (PUS) as the Principal Accounting Officer, who is personally responsible for the stewardship of the resources within the organisation’s control, including propriety, selection and appraisal of programmes, VFM, management of risk, and accurate accounting. As the additional Accounting Officer, the Second Permanent Under-Secretary manages the FCDO’s development programme portfolio, including all programme expenditure related to Official Development Assistance.
The Foreign Affairs Committee (FAC) and the International Development Committee (IDC) scrutinise the FCDO’s spending, administration and policies.
The National Audit Office and the Independent Commission for Aid Impact provide independent scrutiny and assurance to Parliament on our work.
FCDO’s internal policies and priorities are set and governed by the Supervisory Board, the Management Board and its subcommittees. Internal Audit and Investigations Directorate provides the Accounting Officers with assurance via the Audit and Risk Committee.
Choices about what we do and where we do it are considered and made by ministers through periodic Spending Reviews and Resource Allocation Rounds, through which budgets are set.
These decisions are reflected in Business/Country Plans that translate the outcomes of resource allocation decisions into detailed plans.
Individual programmes are designed and implemented to deliver the priorities and results set out in National Security Council strategies, thematic strategies and business/country plans, ensuring VFM for UK taxpayers.
The Programme Cycle Panel provides a transparent governance mechanism which ensures FCDO’s programme rules, design and delivery systems remain fit for purpose.
6.2 Funding sources
FCDO’s budget is determined by periodic Spending Reviews. The Spending Review is an HM Treasury-led process to allocate resources across all Government departments, according to the Government’s priorities. Spending Reviews set firm and fixed budgets over a single year or a period of several years. Guidance explaining the breakdown of funding received from HM Treasury can be found in the FCDO Financial Management Policy and Guidance document.

6.3 Types of Budget
There are two different types of budget that expenditure is monitored against:
- Resource allocation budget – which is delegated from PUS to DGs at the beginning of each financial year, covering both programme and operating budgets; and
- Programme planning budget, which is the lifetime budget for projects or programmes (often covering more than one financial year).

To spend FCDO programme funds, it is necessary but not sufficient to have a programme resource allocation budget. Programmes and projects also require a Programme planning budget, approved in accordance with PrOF Rules 8 and 9 and the governance process for programme approvals set out below.

Programme budgets are either ODA or non-ODA.

ODA development funding

ODA projects and programmes have promoting economic development and welfare of ODA-eligible developing countries as their primary purpose. In a typical year, over half of FCDO’s Gross Public Expenditure tends to be spent on Bilateral Aid (including debt relief, humanitarian assistance and programme funding). The rest goes to international finance and international relations, most as core funding to multilateral organisations (including support to the EU, World Bank, UN and other related agencies.

Non-ODA funding

The much smaller non-ODA programme budget (known as the International Programme) supports the UK foreign policy priorities and FCDO’s strategic Objectives, highlighted in its Outcome Delivery Plan, either on activities which cannot be counted as ODA, or in countries which are not ODA eligible. It helps FCDO to tackle complex global challenges and finances projects which have promoting economic development and welfare of developing countries at their heart. It underpins the FCDO’s wider diplomatic effort and foreign policy in support of UK interests overseas.

Cross-Government funding settlements

Conflict, Stability and Security Fund (CSSF) - Aims to help prevent conflict and tackle threats to UK interests arising from instability overseas. It came into operation on 1 April 2015. It is under the direct authority of the National Security Council (NSC), and supported by the Joint Funds Unit which is housed in FCDO, reports to the National Security Secretariat in Cabinet Office, and is staffed by officials from across the NSC departments. All NSC departments are able to access resources. Within the RDEL allocation, the CSSF is explicitly ring-fenced within FCDO’s settlement.

International Climate Finance (ICF) - A multi-departmental allocation managed by FCDO, Department for Business and Trade, Department for Energy Security and Net Zero and Department for Science Innovation and Technology, Department for Environment, Food and Rural Affairs (DEFRA). It supports international poverty reduction by helping people manage risk and build resilience to the effects of climate change now and in the future, promotes sustainable economic development, tackles deforestation and builds good governance of natural resources. Resources for the ICF are included in each department’s settlement, and each department is responsible for the delivery of its own high quality climate finance portfolios and for specific amounts each year in ways that contribute to the ICF objectives.

6.4 Internal Control Framework and Control Environment

Internal Control Framework

The Internal Control Framework covers all of FCDO’s activities across 4 pillars of corporate, delivery, protocol and consular. It provides a comprehensive and consistent approach to ensuring the risks to delivering our objectives are properly understood and addressed by effective operational processes; and that our operations comply with the relevant legislative, regulatory and policy requirements.

The Framework articulates our approach to control and assurance through a series of inter-related components: the control environment; FCDO objectives; risk assessment; control activities; and assurance activities. It is risk-based and proportionate; ensuring a high degree of control when needed but a lower level where risks are properly understood and can be accepted.

6.5 Governance Structure
FCDO is represented in the Cabinet by the Foreign Secretary and the Minister of State (Development and Africa). The Supervisory Board is chaired by the Foreign Secretary and provides strategic direction, oversight, support and challenge, to encourage the long-term health, reputation and success of the FCDO.  The Board offers a challenge and support function on how the department is performing against clear objectives, key performance indicators, and management of principal risks. It meets quarterly in formal sessions. Its members are: the Permanent Under-Secretaries, full Ministerial team, the Non-executive Directors and Director General Finance and Corporate.

The Management Board takes strategic choices for long-term departmental management where a cross-departmental view, impact or action is required. It oversees plans, the management of principal risks and performance and stewards the department to maintain its health and reputation. It oversees the Strategy, Investment & Delivery, People and Health & Safety Committees, as well as the Oversight Board. The Management Board escalates issues to the Supervisory Board when needed.

The Executive Committee (ExCo) takes decisions on strategic choices or challenges relating to sensitive or time-bound issues, day to day running of the department, emerging issues, risks or crises with departmental wide implications.

The Development Board systematically reviews the performance of the development portfolio linked to allocations and spend authorisations. Carries out quarterly reviews of the status of ODA spend and an annual strategic forward look on development.

The Investment & Delivery Committee is responsible for assessing whether the FCDO is spending on the right things for the best Value for Money. It focuses on oversight, assurance and decisions about whether major / high risk programmes should proceed, ensuring FCDO spend achieves Value for Money (VfM) and maximises impact.

At the operational level, FCDO has three mutually supportive roles or ‘lines of defence’. More information on the lines of defence can be found in the Internal Control Framework

Quality Assurance Unit
The QAU reviews business cases over £40 million and those classified as novel and contentious. Reviews provide an independent assessment of the value for money of proposed spending based on evidence of cost effectiveness and each review is agreed by the Chief or Deputy Chief Economist. Reviews are an in depth 5-week process (plus 2 weeks follow up) and assess each case on its merits analysing how evidence is applied, and providing a holistic assessment of value for money.
The QAU works with relevant professional specialists as well as financial and commercial experts to provide an integrated overall assessment. Each review contains a two-page summary which provides an overall score for value for money, recommendations and core advice. See the Quality Assurance Process Guide for more information or contact: qateam@dfid.gov.uk

Other sources of independent scrutiny include the work of the National Audit Office (NAO) which reports to Parliament through the Public Accounts Committee, the Independent Commission for Aid Impact (ICAI) reporting to the International Development Committee (IDC), the Infrastructure and Projects Authority (IPA) and HM Treasury/Cabinet Office scrutiny processes.

Figure 1: FCDO governance structures and programme control environment

6.6 Accountabilities

Directors General
Accountable for the coherence and impact of their overall portfolio and read across with others. Line Accountability for portfolios down the chain.

Directors
Accountable for the strategic coherence and impact of their own thematic, multilateral or regional portfolios, and for ensuring read across with other relevant portfolios by:
- Identifying which XHMG Ministerial priorities are relevant for their Posts, making choices over prioritisation, and drawing this into a strategic steer for Posts.
- (For thematic directors) Feeding their priorities into the appropriate geographic directors/multi-lateral leads to ensure objectives are cascaded to the relevant posts for delivery.
Geographic HQ boards
Flowing from central NSC architecture, these are accountable for drawing together XHMG thematic, multilateral, and regional priorities, and agreeing strategic trade-offs by:
- reflecting new international priorities and the FCDO’s structures, and incorporating cross cutting themes
- driving their directorate business planning process, out of which country plan priorities will flow.
Heads of Mission
Accountable for the coherence and impact of their own country portfolios by:
- standing up XHMG Country Boards at Post to oversee delivery.
- developing, with their Country Board, their country plan.
Development Directors
Where posts manage significant quantities of ODA (£1m/year), Development Directors will be accountable for the quality assurance and oversight of all FCDO ODA spend at post by:
- membership of the Country Board
- leading relationships with the most senior in-country international and host-country development counterparts
- leading all FCDO programme teams managing significant quantities of ODA.

6.7 HM Treasury levels of Delegated authority
Delegated authorities give the FCDO standing authorisation to commit resources or incur expenditure from money voted by Parliament without specific prior approval from the Treasury. The FCDO’s delegated limit for general programme spend is £200m (the whole life cost of a proposal). Notwithstanding this delegation, certain categories of spending proposal override any delegated authority and must be submitted to the Treasury. These are proposals which:

- could create pressures leading to a breach in Departmental Expenditure Limits, administration costs limits, or Estimates provision;
- would entail contractual commitments to significant levels of spending in future years for which plans have not been set;
- could set a potentially expensive precedent;
- could cause significant repercussions for others;
- require primary legislation;
- are novel and contentious; or
- where Treasury consent is a statutory requirement

‘Novel’ may be anything that is original and of a kind not seen before, perhaps including a non-standard transaction. This includes all non-fiscal programmes (and extensions) and programmes where FCDO enters into a guarantee. ‘Contentious’ might cover a proposal that could hold the potential for dispute as well as cause controversy. Novel and contentious would include spend on public–private partnerships, spend with organisations/countries subject to sanctions, spend on a complex or non-standard commercial model (e.g. joint financing) and any negotiations or legal disputes with Government’s strategic suppliers. Spend on public-private partnerships generally creates commitments beyond the current Spending Review period and requires complex contracting, would also be considered as novel or contentious.

Approvals process for programmes requiring HM Treasury approval

Ministerial approval must first be obtained before a Business Case is submitted to HMT for scrutiny. Once ministerial approval is given, HMT approval must be sought via Management Accounts Group, by completing the HMT 1-pager template and sending it to ma-groups@fcdo.gov.uk .

The SR21 and HMT allocation of budgets from 2023/24 to 2024/25, require that Business Cases (and no cost and cost extensions) over £200m for programmes before or after March 2025 must be sent to MAG, as must any programmes under £200m that will go beyond March 2025. Formal HMT approval is also needed for any activities, including new geographies, which are novel and contentious. In addition, HMT (via Management Accounts Group) must be informed of all replenishments to multilateral organisations.

Treasury levels of delegated authority

FCDO’s levels of delegated authority from HM Treasury to commit expenditure are set out in Table 1 below.

Table 1: HM Treasury delegations

Nature of delegation		Delegated limit
All programmes and projects; and announcements and policy proposals with a defined lifetime	Resources and capital	£200m (whole-life cost in today’s prices) for business case approval / £100m (whole-life cost in today’s prices) for announcement where a business case has been approved
Announcements and policy proposals creating on-going expenditure if Business Case yet to be approved by HMT	Resources and capital	Prior HMT approval is required for any announcements involving spend if related to a business case or a package of business cases, yet to be developed, totalling £100m or above across the lifetime spend of the period

- FCDO must obtain Treasury approval for internal funding allocations before any public announcement or commitment of resources, when these allocations fall outside the delegated limits set out in Table 1.
- FCDO Financial Delegated Authority is set out on the intranet
6.8 FCDO’s Internal levels of delegated authority
New internal levels of delegated authority for approval of FCDO programming have been agreed by the Foreign Secretary (see Table 2) and came into effect in February 2022. Programme teams should use the scrutiny provided by the approval process to ensure their programme is well designed and demonstrate the evidence base and value for money case. Once fully approved, the SRO and PRO are empowered to deliver the programme within the parameters of the Business Case.
Table 2: Approval and Sign-Off levels for concept notes, business cases and contracts

Programme Value	Concept Note Approval	Business Case Assurance	Business Case Approval Advice	Business Case Sign-off	Contract Approval
<£2m	Not required	Deputy Director	Country/ Regional Board	Head of Mission/HQ Director	Commercial staff with appropriate DLA
>£2m < £5m	Head of Mission/HQ Director	Deputy Director	Country/ Regional Board	Head of Mission/HQ Director	Commercial staff with appropriate DLA
>£5m <£10m	Minister	Deputy Director	Country/ Regional Board	Head of Mission/HQ Director	Commercial staff with appropriate DLA
>£10m <£20m	Minister	Deputy Director	Country/ Regional Board	Head of Mission/HQ Director	Procurement Steering Board
>£20m <£40m	Minister	Deputy Director	Country/ Regional Board	Director General	Procurement Steering Board
>£40m <£100m	Minister	QAU	Investment and Delivery Committee	Minister	Procurement Steering Board /Minister
>£100m and above, / Novel, contentious and very high risk are treated as high value	Minister (possible Foreign Secretary if escalated by Minister)	QAU	Investment and Delivery Committee	Minister	Procurement Steering Board / Minister (possible Foreign Secretary if escalated by Minister)

- For programmes developed at post, Business Cases should be routed through Country Boards for agreement before sign-off by the Head of Mission. Higher value Business Cases need agreement of the Investment and Delivery Committee.
- For programmes not developed in a post, regional or thematic scrutiny groups should be used in place of a Country Board before sign-off by the Regional or Thematic Director (HQ) responsible. A Regional Board would be an example of an appropriate scrutiny group.
- Centrally designed programmes will need to achieve country buy-in as part of the agreement process, including for any Insourced roles that are part of the programme business case.
- For ODA programmes Development Director endorsement must form part of the Country Board or regional/thematic scrutiny process.
- CSSF programmes are approved for funding through cross-HMG CSSF Portfolio Boards. In order for a new CSSF programme expected to deliver > £5m of programming on the FCDO baseline over its lifetime to be added to the FCDO portfolio, a Concept Note should be generated – to be approved in line with FCDO approvals. For CSSF programmes expected to deliver <£5m of programming on the FCDO baseline over its lifetime, the cross-HMG CSSF Portfolio Board (chaired by a HoM) will approve the Programme Document in lieu of a Concept Note. The CSSF Programme Document is a 5-case business case, approved by HM Treasury and should provide sufficient information, in lieu of the FCDO business case. See the Concept Note PrOF Guide for more information.
- Certain types of spending always require Treasury approval – see the section 6.6 on HM Treasury delegated authority.
Business Cases above £40m will not generally be seen by Ministers unless they have specifically asked to see them. Instead, they will be reviewed at official level with only the 2-page business case cover note with the Investment and Delivery Committee advice included submitted to Ministers for agreement and approval (cover note template and advice here). The cover-note will be used to collect the comments of the scrutiny reviews. Where programmes are being submitted through the Quality Assurance Unit and the Investment and Delivery Committee they will only pass through these assurance ‘gates’ once. The SRO and PRO must demonstrate that they have responded to feedback in their final submission.
Each step in the approval process will be time bounded. This process should improve predictability and allow teams to plan approval timelines. Only approvals contained within the guidance are needed and business units should not establish parallel or additional layers of sign-off.
6.9 Business Case Cost extension approvals
Table 3 sets out the levels for cost extension approvals. These are based on the new total cumulative programme value and not on the size of the extension itself.

Table 3: Cost extension approvals

Original / Approval Value	Final Business Case Sign-Off	Cost extension approval levels: based on new total (cumulative) programme value - NOT on size of extension
		Value	Approver
>£40	Minister	New total over £40m	Minister
		New total over £200m	Minister & HMT approval
£20m-40m	Director General	New total over £20m	Director General

<£20m	Head of Mission	New total up to £20m	Head of Mission (via Country Board) or Director (via HQ / Regional Board
		New total over £20m but less than £40m for the first time	Director General
		New total over £200m for the first time	Minister & HMT approval

- Cost extensions require an addendum to the business case. This should be signed by the Head of Mission, Director or Director General for below £40m (see above table). Cost extensions where the new cumulative value is over £40m must be escalated to the relevant minister for approval according to thresholds in table 3. Extensions where the cumulative value is over £200m must be approved by a Minister and additionally be sent to HM Treasury for scrutiny. Consult Management Accounts Group in Finance for advice on the HMT process.
- Re-approvals are covered in section 6.10 below.

6.10 Business Case No Cost (Time) Extensions Approvals
Unlike a cost extension there is no requirement to use a business case addendum if simply extending the end date of a programme unless there are material changes to the intent of the programme resulting in a decrease in the overall VFM of the programme.   The PRO in consultation with the programme SRO must formally request approval to extend the end date of the programme in writing to HoM/ Director or Development Director or Head of Department where they have been given the delegated authority to approve such requests.  Teams must also consult Management Accounts Group on whether HMT approval will be needed if the extension takes the programme into the next spending review period.

6.11 FS Approval of novel and contentious programmes
Approval of Concept Note and Business Cases may be required by the Foreign Secretary for any programmes that are politically sensitive, novel or contentious cases. Decisions on whether to escalate a Concept Note or Business Case to the Foreign Secretary will be made by the relevant Minister but SROs must consider if the programme is novel and contentious and ensure the Foreign Secretary’s ODA Adviser (where relevant), and SpAdS and PAds are made aware.

Novel or contentious:
A novel situation or transaction is where the organisation has limited experience or evidence of what will work and is outside the range of FCDOs normal business activity. There will normally not be a precedent for this type of activity or spend.
A contentious transaction is one that might give rise to criticism by the public or the media, a proposal that could hold the potential for dispute or one that is inconsistent with wider government policy or aims. A contentious programme does not have to be novel. It could be a standard programme but in an unusual environment, or a standard programme delivered by a supplier with which we have had difficulties.

High Political or Financial Risk:
A high political risk is where there are wider political implications to consider, there is high Parliamentary or scrutiny body interest or where it relates to issues that are likely to attract significant public attention. A high financial risk includes where the risk of misappropriation or misuse of funds is significant, where the value for money case is contested or where a non-standard financial model is being used. This includes expenditure which might set a precedent, or which might have wider cost implications.

Strategically Important:
Programmes are defined as strategically important when they are delivering in full, or making a critical contribution to, one of the Foreign Secretary’s top priorities, FCDO priority outcomes, a manifesto commitment, or an NSC strategy (including on a bilateral basis).

Programme SROs and Heads of Mission should apply this criterion judiciously. All FCDO programmes can be described as strategically important (we wouldn’t be delivering them otherwise); the question should be whether this is something that may require a decision from the Foreign Secretary through escalation by the relevant Minister.

6.12 Re-approvals
Where a team intend to change an FCDO programme such that it deviates from the original approved business case, a business case addendum must be completed and submitted with a request for re-approval. Modest changes can normally be signed off by the Head of Mission or the Director. However, where there is a material change to the programme, re-approval requests must be escalated to whoever has delegated authority to approve the change (including ensuring material changes for programmes above £200m are approved by HM Treasury) in line with the delegated authority levels set out in table 3 above. Examples of a material change include:

- Significant deterioration (e.g. due to war, new crisis or spike in existing crisis etc) in the operating context affecting the ability to effectively achieve an essential strand of work or the overall programme objectives, as designed and approved in the business case.
- Need to significantly adapt a programme based on new VfM calculations/scope of activities/Theory of Change.
- Significant deterioration in the external operating environment (e.g. a move into conflict).
- Changes to the intent or the outcome objective of a programme where this materially different from what was agreed in the business case.
- Adding a new sector or country outside those already described in the existing business case.

6.13 Commercial Approvals
Commercial Department builds a Commercial Pipeline and uses this information to forecast planned contract awards.

Following SRO approval, contracts and contract amendments:
- Below £10m are approved by the commercial staff member who has the appropriate delegated level of Authority, in line with Commercial Governance Processes, (including Procurement Steering Board (PSB) where required).
- Between £10m and £40m are approved by the Procurement Steering Board (PSB) and Cabinet Office.
- Over £40M are approved by the Procurement Steering Board (PSB) and Cabinet Office, before being submitted to the relevant FCDO Minister for approval. All FCDO Ministerial submissions for contract approval are drafted and submitted by the SRO with input/agreement from Commercial

6.14 Government Functional Standards and Cabinet Office Spend Controls

Government Functional Standards

Functional standards exist to create a coherent, effective and mutually understood way of doing business within government organisations and across organisational boundaries, and to provide a stable basis for assurance, risk management, and capability improvement. They support value for money for the taxpayer, and continuity of implementation. The functional standards set out minimum requirements and recommended practice for a range of themes including:
- Project delivery
- Digital, Data and Technology
- Finance
- Commercial
- Counter Fraud
- Grants

Cabinet Office conduct periodic assessments of maturity to ensure the rules, policies and processes government organisations develop meet the minimum requirements and are being implemented consistently.

Cabinet Office Spend Controls

Central government organisations, including departments and the bodies they sponsor, must follow the Cabinet Office spend controls process when they want approval to spend money on specific activities. The Cabinet Office controls are part of the wider government approvals process set out in the managing public money guidance, and cover a range of themes including:
- Advertising, marketing and communications
- Commercial control
- Digital and technology
- Consultancy and Professional Services
- Facilities Management
- National Property Control
- Contingent Labour – Recruitment
- Redundancy and Compensation
- Learning and Development

6.15 Programme accountability chain

Accounting Officers
The Principal Accounting Officer is the person accountable to Parliament for the stewardship of the Department’s resources. FCDO’s Principal Accounting Office is the Permanent Under-Secretary (PUS), who acts on ministers’ instructions and is supported by the Executive Committee and its subcommittees. The Accounting Officer is personally responsible to Parliament and the Public Accounts Committee (PAC) for the Department’s compliance with the principles set out in Managing Public Money. The additional Accounting Officer, the Second Permanent Under-Secretary manages the FCDO’s development programme portfolio, including all programme expenditure related to Official Development Assistance. The parliamentary committees may seek assurance on propriety, regularity, value for money and feasibility of the use of the public money provided by Parliament to their departments.

Budget holders and delegated budget holders
Budget holders and delegated budget holders include Directors General, Directors, Heads of Mission, Deputy Directors, Development Directors and Deputy Heads of Mission. These individuals are personally accountable for delivering agreed outputs and targets as effectively, efficiently and economically as possible. Budget holders are encouraged to sub-delegate to ensure that business is managed efficiently and at the right level. Budget holders are accountable at the portfolio level. For instance:
- A Director or Head of Mission is accountable for the portfolio of programmes within their Business Plan and delegated budget.
- Budget holders are accountable for ensuring that they have sufficiently qualified and capable SROs and PROs for programmes in their portfolio, and that programme teams are appropriately resourced. A budget holder may also be an SRO.
Senior Responsible Owners
SROs are accountable for the implementation and delivery of the individual programmes for which they have oversight as an SRO. They are expected to account for the programme meeting its objectives, delivering the required outcomes and making the expected contribution to portfolio-level outcomes. A programme may only have one SRO. There should be a nominated FCDO SRO even if FCDO funds are being mingled with, managed by or transferred to another UK Government Department.

Programme Responsible Owners
PROs are accountable for day-to-day leadership of a programme team, and driving the delivery of programme outcomes within agreed time, cost and quality constraints. They are expected to account for and explain the decisions and actions that have been taken to deliver the projects for which they are accountable. A programme may only have one PRO, who may be the same person as the SRO.

Separation of duties
At each point in the programme cycle, it is important to ensure separation of duties so that the person responsible for identifying or proposing a project or payment is different from the person approving it.