## Subsidy_Control_Pipeline
Contract Title	Procurement Start Date	Contract Award Date	Contract Signature Date	Value of New Contract	Procurement Route / DPS - Local / FTS - Regional / Cross-Regional	Open Market Review start date	Open Market Review end date	Link to OMR webpage	Public Review start date	Public Review end date	Link to Public Review webpage	Supplier Awarded	Subsidy amount	Premises	Subsidy Intensity (%) / To be published in due course	Technology Used	Anticipated Completion Date	Summary details of infrastructure built (when capable of serving customers) and access conditions that apply / To be updated each quarter
Lot 14.01 North Dorset	Jan-2022		Aug-2022	£6,300,000	DPS	May 2023 National Rolling Open Market Review - 19/05/2023	May 2023 National Rolling Open Market Review - 20/06/2023	https://www.gov.uk/government/collections/project-gigabit-programme-open-market-reviews	24/06/2021	23/07/2021	https://www.gov.uk/government/collections/uk-gigabit-programme-public-reviews	Wessex Internet	£6,300,000	7,000		Gigabit-capable	Aug-2032
Lot 4.01 Teesdale	Jan-2022		Sep-2022	£6,700,000	DPS				22/06/2021	22/07/2021		Gofibre	£6,700,000	4,000		Gigabit-capable	Sept-2032
Lot 34.01 North Northumberland	Jan-2022		Oct-2022	£7,400,000	DPS				22/06/2021	22/07/2021		Gofibre	£7,400,000	3,700		Gigabit-capable	Oct-2032
Lot 28 Cumbria	Oct-2021		Nov-2022	£108,500,000	Find a Tender (FTS)				09/02/2021	10/03/2021		Fibrus	£108,500,000	59,000		Gigabit-capable	Nov-2037
Lot 32.02 Central Cornwall	Apr-2022		Jan-2023	£18,000,000	DPS				15/07/2021	16/08/2021		Wildanet	£18,000,000	9,200		Gigabit-capable	Jan-2033
Lot 32.03 South West Cornwall	Mar-2022		Jan-2023	£18,000,000	DPS				15/07/2021	16/08/2021		Wildanet	£18,000,000	9,500		Gigabit-capable	Jan-2033
Lot 5 Cambridgeshire and adjacent areas	Jan-2022		Mar-2023	£69,000,000	Find a Tender (FTS)				07/05/2021	14/06/2021		CityFibre	£69,000,000	44,400		Gigabit-capable	Mar-2038
Lot 27.01 New Forest	Jul-2022		Mar-2023	£13,800,000	DPS				19/08/2021	21/09/2021		Wessex Internet	£13,800,000	10,400		Gigabit-capable	Mar-2033
Lot 25.02 North Shropshire	Jul-2022		April-2023	£24,000,000	DPS				18/08/2021	20/09/2021		Freedom Fibre	£24,000,000	12,000		Gigabit-capable	Apr-2033
Lot 7 Norfolk	Apr-2022		Jun-2023	£114,200,000	Find a Tender (FTS)				19/08/2021	21/09/2021		CityFibre	£114,200,000	62,200		Gigabit-capable	Jun-2038
Lot 2 Suffolk	Apr-2022		Jun-2023	£100,500,000	Find a Tender (FTS)				19/08/2021	21/09/2021		CityFibre	£100,500,000	79,500		Gigabit-capable	Jun-2038
Lot 27 Hampshire	Jul-2022		Jun-2023	£104,200,000	Find a Tender (FTS)				19/08/2021	21/09/2021		CityFibre	£104,200,000	75,500		Gigabit-capable	Jun-2038
Lot 19.01 North East Staffordshire	Apr-2023		Oct-2023	£16,500,000	DPS				19/08/2021	21/09/2021		Connect Fibre	£16,500,000	5,900		Gigabit-capable	Oct-2033
Lot 13.01 South Oxfordshire	Mar-2023		Oct-2023	£17,000,000	DPS				19/08/2021	21/09/2021		Gigaclear	£17,000,000	5,500		Gigabit-capable	Oct-2033
Lot 13.02 North Oxfordshire	Mar-2023		Oct-2023	£9,400,000	DPS				19/08/2021	21/09/2021		Gigaclear	£9,400,000	4,300		Gigabit-capable	Oct-2033
Lot 3 Derbyshire	Feb-2023		Dec-2023	£33,400,000	Find a Tender (FTS)				19/08/2021	21/09/2021		Connect Fibre	£33,400,000	18,200		Gigabit-capable	Dec-2038
Lot 4 North East England	Nov-2022	December 2023 / TBC		£82,700,000	Find a Tender (FTS)				22/06/2021	22/07/2021
Lot 24 Worcestershire	Oct-2022	Jan-2024		£39,400,000	Find a Tender (FTS)				04/02/2022	04/03/2022
Lot 26 Buckinghamshire, (part of) Hertfordshire, and East of Berkshire	Nov-2022	Sep-2023		£58,800,000	Find a Tender (FTS)				04/02/2022	04/03/2022
Lot 29 Kent	Dec-2022	Dec-2023 - Jan-2024		£112,300,000	Find a Tender (FTS)				04/02/2022	04/03/2022
Lots 16 & 1 East and West Sussex	Jan-2023	Dec-2023 - Jan-2024		£100,600,000	Find a Tender (FTS)				04/02/2022	04/03/2022
Lot 30 South Wiltshire	Feb-2023	Jan-2024		£24,800,000	Find a Tender (FTS)				29/03/2022	29/04/2022
Lot 12 Bedfordshire, Northamptonshire and Milton Keynes	Feb-2023	Nov-2023		£51,400,000	Find a Tender (FTS)				29/03/2022	29/04/2022
Lot 11 Leicestershire and Warwickshire	Mar-2023	Nov-2023		£71,500,000	Find a Tender (FTS)				17/06/2022	18/07/2022
Lot 10 Nottinghamshire and West of Lincolnshire	Mar-2023	Jan-2024		£58,600,000	Find a Tender (FTS)				17/06/2022	18/07/2022
Lot 8 West Yorkshire and York area	Apr-2023	Dec-2023 - Jan-2024		£60,900,000	Find a Tender (FTS)				17/06/2022	18/07/2022
Lot 20 South Yorkshire	Apr-2023	Dec-2023 - Jan-2024		£44,400,000	Find a Tender (FTS)				17/06/2022	18/07/2022
Lot 25.01 Mid West Shropshire	May-2023	Sep-2023		£12,000,000	DPS				18/08/2021	20/09/2021
Lot 14 Dorset & South Somerset	May-2023	Jan - Mar-2024		£43,200,000	Find a Tender (FTS)				04/10/2022	04/11/2022
Lot 32 Cornwall and Isles of Scilly	Jun-2023	Apr - Jun-2024		£41,200,000	Find a Tender (FTS)				04/10/2022	04/11/2022
Lot 18 East Gloucestershire	Aug-2023	Jan - Mar-2024		£16,600,000	Find a Tender (FTS)				05/09/2022	05/10/2022
Lot 15 West Herefordshire & Forest of Dean	Aug-2023	Jan - Mar-2024		£23,400,000	Find a Tender (FTS)				05/09/2022	05/10/2022
Cross-Regional Supplier Framework	Jul-2023	Jul - Sep-2024		Maximum framework value - £800,000,000	Find a Tender (FTS)				NA	NA
Cross-Regional Supplier Framework Call-Off 1	Jul-2023	Jul - Sep-2024		£149,700,000	Find a Tender (FTS)				NA	NA
Cross-Regional Supplier Framework Call-Off 2	Jul-2023	Jul - Sep-2024		£139,100,000	Find a Tender (FTS)				NA	NA
Lot 23 Lincolnshire (including NE Lincolnshire and N Lincolnshire) and East Riding	Jul-2023	Apr - Jun-2024		£118,000,000	Find a Tender (FTS)				05/09/2022	05/10/2022
Lot 17 Cheshire	Jul-2023	Jan - Mar-2024		£44,700,000	Find a Tender (FTS)				05/09/2022	05/10/2022
Lot 31 North Yorkshire	Jul-2023	Apr - Jun-2024		£73,400,000	Find a Tender (FTS)				04/10/2022	04/11/2022
Lot 6 Mid/East Devon & West Somerset	Sept-2023	Mar - May-2024		£18,400,000	Find a Tender (FTS)				04/10/2022	04/11/2022
Lot 3.01 Peak District	Aug-2023	Jan - Mar-2024		£10,700,000	DPS				29/03/2022	29/04/2022
Lot 35 Birmingham and the Black Country	TBC	TBC		TBC	Find a Tender (FTS)				04/10/2022	04/11/2022
Lot 36 Merseyside and Greater Manchester	TBC	TBC		TBC	Find a Tender (FTS)				04/10/2022	04/11/2022
Lot 37 Greater London	TBC	TBC		TBC	Find a Tender (FTS)				04/10/2022	04/11/2022
Lot 38 Newcastle and North Tyneside	TBC	TBC		TBC	Find a Tender (FTS)				04/10/2022	04/11/2022
Cross-Regional Supplier Framework Call-Off 3	Jul - Sep-2024	Mar - May-2025		£216,000,000	Find a Tender (FTS)				04/10/2022	04/11/2022