## Cover
Building Safety Remediation Data Release, England: 31 December 2023
Back to Contents
Background
This publication provides data on 1) the remediation progress across DLUHC’s Building Safety Remediation portfolio, covering buildings in the ACM programme, Building Safety Fund, Cladding Safety Scheme, developer remediation contract and reported by registered providers of social housing, 2) Progress with remediation of high-rise (18 metres and over in height) residential buildings (including student accommodation and hotels) and publicly owned buildings with ACM cladding systems unlikely to meet Building Regulations in the ACM programme, 3) the progress of the Waking Watch Relief Fund and Waking Watch Replacement Fund, 4) progress with remediation of high-rise residential buildings with non-ACM cladding systems assessed as eligible for funding from the Building Safety Fund , 5) Progress with the applications for and remediation of medium-rise (11 – 18 metres in height) residential buildings in England and high-rise residential buildings outside of London with non-ACM cladding systems in the Cladding Safety Scheme, 6) progress of remediation of residential buildings 11 metres and over in height with life-safety defects under the developer remediation contract, 7) progress of remediation of residential buildings 11 metres and over in height with unsafe cladding reported by registered providers of social housing, 8) enforcement action taken by local authorities against high-rise residential buildings with cladding defects under the Housing Act 2004.
Tables on the ACM programme, BSF, CSS, developer remediation contract and social housing surveys include buildings which can be in multiple schemes or data collections so counting across tables can result in double counting. Tab Combined_2 provides an overall summary of all remediation progress, without double counting.
Publication dates
The data tables in this spreadsheet were originally published on 18 January 2023.
The next publication is scheduled for 22 February 2024.
Useful Information
Further information on the data collection, data quality and definitions is available in the Technical Note published alongside these statistics.
Technical Note
Contact details
We are committed to improving and broadening this data release further in the months ahead and would welcome feedback both on the revised content of this data release and what could be further done in the future.
BuildingSafetyData2@levellingup.gov.uk
NewsDesk@levellingup.gov.uk
Date published: 18 January 2023

## Table_of_Contents
Building Safety Remediation Data Release Contents
Worksheet Name	Worksheet Title
Cover	Background information about the statistics.
Notes	Notes found in the tables.
ACM_1	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 December 2023
ACM_2	Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 December 2023
ACM_3	Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 December 2023
ACM_4	ACM remediation progress by local authority, England, 31 December 2023
ACM_5	ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 December 2023
ACM_6	ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 December 2023
ACM_7	Number of dwellings in buildings identified with unsafe ACM cladding by remediation status
ACM_8	ACM remediation progress by sources of funding, England, 31 December 2023
ACM_9	Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 December 2023
ACM_10	Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 December 2023
WWRF_1	Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 December 2023
WWRF_2	Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 December 2023
WWRF_3	Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 December 2023
BSF_1	Remediation status of eligible buildings within BSF by tenure, England, 31 December 2023
BSF_2	BSF remediation progress of eligible buildings by region, England, 31 December 2023
BSF_3	BSF number of eligible buildings with funding approved and expenditure amounts by tenure, England, 31 December 2023
Combined_1	Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 December 2023
Combined_2	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 December 2023
CSS_1	Application status of buildings within the CSS, England, 31 December 2023
CSS_2	CSS remediation progress by region, England, 31 December 2023
CSS_3	CSS remediation progress by height, England, 31 December 2023
CSS_4	CSS remediation progress by tenure, England, 31 December 2023
Social_1	Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 31 October 2023
Developer_1	Remediation status of buildings covered by the developer remediation contracts by height group, England, 31 October 2023
Developer_2	Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 October 2023
Developer_3	Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 October 2023
Developer_4	Developer by developer breakdown of buildings covered by the developer remediation contract, by assessment status, England, 31 October 2023
Developer_5	Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 October 2023
Developer_6	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 October 2023
Developer_7	Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation, by engagement and remediation status, England, 31 October 2023
Enforcement_1	Enforcement action taken by local authorities against high-rise buildings under the Housing Act (2004) by remediation programme status, England, 31 December 2023
Enforcement_2	Building inspections conducted by local authorities, England, 31 December 2023
Enforcement_3	Statutory notices served by local authorities under the Housing Act (2004), England, 31 December 2023
Enforcement_4	Number of building inspections by local authorities supported by the Joint Inspection Team, England, 31 December 2023
JIT_1	Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 December 2023

## Notes
Notes
Back to Contents
Note	Note Explanation	Note Location
[note 1]	Vacant buildings detailed in this table are included in table ACM_1 and ACM_2.	ACM_3
[note 2]	This table excludes local authorities with fewer than 10 high-rise residential buildings, regardless of whether they have unsafe cladding, and groups local authority figures into bands. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	ACM_4, Enforcement_1, Enforcement_2, Enforcement_3, Enforcement_4
[note 3]	Yet to complete remediation includes all dwellings in buildings that are yet to complete remediation works on-site	ACM_7
[note 4]	Social Sector Fund: Payments are made as cash grants, and will be payable in two tranches. The government will pay 80% of eligible costs at stage one. Once building owners confirm that they have tendered for the removal and replacement of cladding systems and work has started on site, we will make the first payment. Then we will pay the remaining 20% of eligible costs once building owners have submitted further evidence and confirmed final costs.	ACM_8
[note 5]	Private Sector Fund: The majority of private sector buildings receiving government funding for ACM remediation are funded through the Private Sector Cladding Remediation Fund. Payments from the Private Sector Cladding Remediation Fund will be made as cash grants and will be made on the basis of monthly valuations of work carried out on site, with an appropriate degree of due diligence, mirroring industry standard practice. Following Practical Completion the government will withhold a final payment which will be made on completion of the defects liability period. Four private sector buildings are receving government funding from the Building Safety Fund, so do not appear in the totals in table ACM_9, but do in ACM_8.	ACM_8, ACM_9
[note 6]	The approved figure for the Private and Social Sector ACM Cladding Remediation Funds incorporates tendering support for applicants and approved project cost overrun. This figure reflects funding for the costs of remediation of unsafe ACM cladding only.	ACM_10
[note 7]	The Private Sector ACM Cladding Remediation Fund approved funding figure does not yet include any funds that will be reimbursed by developers who have signed the Pledge in relation to buildings they had a role in developing or refurbishing which have received government funding. All eligible applications to the Private Sector ACM Cladding Remediation Fund will be funded.	ACM_10
[note 8]	Expenditure for the Private and Social Sector ACM Cladding Remediation Funds is based on grant payments made by Delivery Partners to the applicant.	ACM_10
[note 9]	Private Sector ACM Cladding Remediation Fund (PSCRF) expenditure includes spend for non-ACM remediation works on buildings with unsafe ACM cladding funded through the PSCRF and therefore can exceed the amount approved which reflects unsafe ACM cladding remediation costs only.	ACM_10
[note 10]	Total figures may not sum due to rounding.	WWRF_1, WWRF_2, WWRF_3
[note 11]	The first tranche of the Waking Watch Relief Fund was administered by eight local/combined authorities alongside DLUHC. Further information on funding allocations by administering authority is available in the Waking Watch Relief Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_2
[note 12]	The Waking Watch Replacement Fund was administered by five local/combined authorities alongside DLUHC. Further information on funding allocations by administering authority is available in the Waking Watch Replacement Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_3
[note 13]	Remediation complete figures in this table include buildings that have completed remediation but are still awaiting building control sign off.	BSF_2
[note 14]	Private sector buildings can receive pre-tender support allocation in addition to their full applications funding, but not all buildings receive this therefore these numbers cannot be added together to directly give a total.	BSF_3
[note 15]	This table includes allocation figures for buildings which have only non-ACM cladding and buildings which have both non-ACM and ACM cladding.	BSF_3
[note 16]	For buildings with both ACM and non-ACM cladding in this table, 'Remediation not Started' is assigned for buildings that have not started works on either type of cladding. 'Remediation Started' is assigned for buildings where work has started on remediating at least one type of cladding. 'Remediation complete: awaiting building control sign off' is assigned for buildings that have completed remediation but sign off is required for work on remediating at least one type of cladding. 'Remediation complete' is assigned for buildings that have completed, and received sign off, on works for the remediation of both types of cladding.	Combined_1, Combined_2
[note 17]	Buildings can be in multiple schemes and data collections. These tables show the unique number of buildings across the schemes without double counting buildings where they are in multiple schemes. The total here will be lower than the summed total number of buildings reported in each scheme.	Combined_1, Combined_2
[note 18]	Where buildings are in multiple schemes or data collections, the remediation stage assigned follows the rules in Note_16 for buildings in both the BSF and ACM programme. For further overlaps, remediation stages are assigned from schemes in this priority order: ACM, BSF, (or combined ACM and BSF), CSS, developer returns, social housing returns	Combined_2
[note 19]	Enforcement action is where an inspection under the Housing Act 2004's Housing Health and Safety Rating System has been organised/undertaken, and includes where a statutory notice has also then been served.	Enforcement_1
[note 20]	The Housing Health and Safety Rating System (HHSRS) is a risk-based assessment evaluation tool to help local authorities identify and protect against potential risks and hazards to health and safety from any deficiencies identified in residential premises. Each hazard has a weighting which will help determine whether the building is rated as having risks which are either category 1 or category 2. Where a risk is deemed to be category 1, a local authority has a duty to take enforcement action; where a risk is deemed to be category 2, an authority has the power to take action.	Enforcement_2
[note 21]	The Government-funded Joint inspection Team, hosted by the Local Government Association, provides expert advice to local authorities on enforcement on buildings with unsafe cladding.	Enforcement_4
[note 22]	The number of training sessions for Wandsworth and Richmond are combined as Merton, Wandsworth and Richmond operate a joint service where Merton officers attend training on behalf of Richmond and Wandsworth.	JIT_1
[note 23]	Buildings confirmed by delivery partners to be transferred to developers have been withdrawn from the Building Safety Fund, this has led to a decrease in the number of eligible buildings in the Fund. The number of eligible buildings may continue to decrease as more buildings are confirmed by developers and transferred out of the fund.	BSF_1, BSF_2
[note 24]	The Building Safety Fund first opened to registrations from June to July 2020 receiving registrations from 3,488 buildings. In July 2022 the Building Safety Fund reopened to new applications, this remains open therefore the number of buildings will continue to increase. Buildings from both application periods are now combined as one Building Safety Fund, so numbers include both application periods.	BSF_1, BSF_2, BSF_3
[note 25]	Some buildings have an unknown remediation status reported by the developer. These have been interpreted as ‘Remediation not started – no plans in place’.	Developer_1
[note 26]	The buildings reported in this table as requiring remediation are estimated by DHLUC using information provided by developers in their data return and other data available within the department. In this table, a building is defined as requiring works under the developer remediation contract if it is either self-reported by the developer as requiring works; is an eligible building in the BSF or ACM and the developer has agreed to re-imburse the funds; has had money paid out by the BSF or ACM; or has a self-reported work status of either: works completed, works started, or works not started but plans in place. / They therefore differ from other published tables which reference only to the number of 'self-reported' buildings requiring works.	Developer_1
[note 27]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which are not being completed through government funds. The tables shows the number of buildings which have not yet started works; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place'. The table shows the estimated or actual start date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet started remediation work, but have an estimated or actual start date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_6
[note 28]	This table covers only buildings which have been self-reported by the developer as requiring works under the data return field Does this building require works?. This differs from the total figure of buildings requiring remediation in Developer_1, as that number is an estimate and includes the subset of buildings developers have self-reported. Please see [note 26] for further information)	Developer_3, Developer_4
[note 29]	The table holds data for 50 developers who have signed the contract. Data for three developers who signed the contract on the 16 November, 29 November 2023 and 6 December 2023 and data for a developer who has gone into administration are not included in this release. Data for the recent signatories will be added to future releases. / Some data has been supressed, as seen in the row 'Other (combined total for all developers with 5 or fewer buildings each' summarises information of 12 developers with five or fewer buildings, this includes: Abbey Developments, Allison Homes, Bloor, CG Fry, Courdace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata and William Davis. This data has been supressed due to the number of buildings being fewer than six and is represented in the data with a dash (-) in the data.	Developer_3, Developer_4, Developer_5, Developer_6, Developer_7
[note 30]	A building is interpreted as having an assessment if one or more of the following fields show as 'Yes' in the developer data return: Have you carried out an assessment of whether External Wall System (EWS) works are required on this building?; Have you carried out an assessment of whether non-EWS (other fire safety defects) works are required on this building?; Does the Building have an FSA?; Does the Building have an FRAEW?; or Does this building require works?	Developer_4
[note 31]	This column removes buildings requiring works which are being completed through government funds and reimbursed by the developer, as the developer cannot influence the pace of remediation on these buildings.	Developer_3
[note 32]	The data here is comprised of 'Don't know' and blanks in response to the field 'Does this building require works?' regardless of whether the building has had an assessment or not.	Developer_3
[note 33]	The total estimated cost of remediation is based on the actual or estimated cost reported by developers, and an assumed average where a cost has not been reported (averages are based on the developer-reported costs, by height).	Developer_2
[note 34]	Data is taken from The Fire Safety Remediation Survey (FRS) for 11 metre plus buildings, which opened to all landlords on 23 August 2023 and closed on 15 September 2023. / Landlords were asked to respond to the survey for buildings in which they are the responsible entity. A 'Responsible Entity' is the organisation that has the legal obligation or right to carry out the remediation works. The Responsible Entity may be the building’s freeholder or head leaseholder, registered provider of social housing or a management company or Right To Manage (RTM) company that has primary responsibility for the repair of the property. / As a result, buildings within the The Fire Safety Remediation Survey may comprise of mixed tenure dwellings e.g., private leasehold and social rented dwellings, however remedial works will fall under the responsibility of the responding landlord. / Furthermore, landlords were asked to provide information on any life critical fire safety (LCFS) defects, which the survey defined as defects, shrinkages, faults or other failings in a building that give rise to fire safety risks. These are identified by: / 1) a Fire Risk Appraisal of External Wall construction (FRAEW) undertaken in accordance with PAS 9980 that assesses the external wall construction or cladding as not “medium - tolerable” (or better); or / 2) a fire risk assessment (FRA) that assesses the relevant parts of the building as high risk or medium risk or equivalent according to industry standards.	Social_1
[note 35]	A building with 'cladding defects reported by Registered Providers of social housing' is defined as a building which has at least one Life-critical Fire-safety defect relating to an External Wall System (EWS) cladding defect. These buildings may also include non-cladding associated defects.	Social_1
[note 36]	The number of buildings identified as 'Remediation complete' may not match the number of social buildings being reported and complete under the BSF, ACM, CSS or developer contract due to the following: / 1) Non-responses to The Fire Safety Remediation Survey - a small number or landlords did not respond to the survey, which means some buildings remediated through other remediation schemes may not be captured. / 2) Differences in how buildings are reported in The Fire Safety Remediation Survey - some buildings which have already completed remediation via other schemes have been reported as having no Life-Critical Fire-Safety defects in The Fire Safety Remediation Survey, as the latest fire safety assessment has concluded that the the building is safe. Subsequently, the landlord has reported that no defects are present in the survey and have left the remediation category blank.	Social_1
[note 37]	The data here includes buildings in The Fire Safety Remediation Survey which may have also applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract. These are not excluded from the Management Information tabe (Social_1) but are excluded from 'Overall Remediation' estimates in the Building Safety Remediation Data Release.	Social_1
[note 38]	From November 2023 BSF_3 and BSF_4 have been combined into one sheet. Figures can be compared to previous publications by looking at sheets BSF_3 and BSF_4 in previous months' publications.	BSF_3
[note 39]	The total number of social high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 3 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 40]	The total number of social high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 1 building that falls under the developer remediation contract.	ACM_8
[note 41]	The total number of private high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 22 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 42]	The total number of private high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 63 buildings that fall under the developer remediation contract.	ACM_8
[note 43]	The data for the following schemes are up to the 30 November 2023: ACM, BSF, CSS, whilst Developer data is up to the 31 October 2023 and Social Housing data from 31 August 2023. Developer and Social Housing data are based on quaterly data returns, falling in different months, whereas the ACM, BSF and CSS have updated data monthly.	Combined_2
[note 44]	The number of buildings associated with particular expenditures paid out may also include buildings where a full reimbursement of funding has taken place, including those where required under the developer contract.	BSF_3
[note 45]	Buildings receive expenditure funding in stages and therefore these figures should not be used to calculate the average expenditure paid out to each building.	BSF_3

## ACM_1
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Tenure	Number of buildings this month	Number of buildings last month	Monthly change
Social sector residential	161	161	0
Private sector residential	238	238	0
Student accommodation	58	58	0
Hotels	31	31	0
Publicly-owned buildings	8	8	0
Total buildings	496	496	0

## ACM_2
Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Completed Remediation	132	82%	182	76%	52	90%	24	77%	7	88%	397	80%
Works complete awaiting building control signoff	10	6%	12	5%	2	3%	3	10%	1	13%	28	6%
Remediation started - cladding removed	19	12%	15	6%	1	2%	2	6%	0	0%	37	7%
Remediation started	0	0%	13	5%	0	0%	1	3%	0	0%	14	3%
Remediation plans in place	0	0%	10	4%	3	5%	0	0%	0	0%	13	3%
Reported an intent to remediate	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Remediation plan unclear	0	0%	5	2%	0	0%	0	0%	0	0%	5	1%
Total buildings	161	100%	238	100%	58	100%	31	100%	8	100%	496	100%

## ACM_3
Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 December 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff - Vacant	0	1	0	0	0
Remediation started - cladding removed - Vacant	0	1	0	0	0
Remediation started - Vacant	0	0	0	0	0
Remediation plans in place - Vacant	0	0	0	0	0
Reported an intent to remediate - Vacant	0	1	0	1	0
Remediation plan unclear - Vacant	0	0	0	0	0
Total vacant buildings [note_1]	0	3	0	1	0

Remediation Category for occupied buildings	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff	10	11	2	3	1
Remediation started - cladding removed	19	14	1	2	0
Remediation started	0	13	0	1	0
Remediation plans in place	0	10	3	0	0
Reported an intent to remediate	0	0	0	0	0
Remediation plan unclear	0	5	0	0	0
Total occupied buildings	29	53	6	6	1

## ACM_4
ACM remediation progress by local authority, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_2]	Number of buildings identified with ACM cladding systems (unlikely to meet Building Regulations)	Number of buildings with ACM cladding systems (unlikely to meet Building Regulations) yet to be remediated	Percentage of buildings with ACM cladding systems completed remediation	Percentage of buildings with ACM cladding systems started or completed remediation
Barking and Dagenham	1 to 5	1 to 5	Between 50% and 99%	100%
Barnet	6 to 10	1 to 5	Less than 50%	100%
Bedford	1 to 5	None	100%	100%
Birmingham	6 to 10	1 to 5	Between 50% and 99%	100%
Bournemouth, Christchurch and Poole	1 to 5	1 to 5	Less than 50%	100%
Bradford	1 to 5	None	100%	100%
Brent	11 to 20	11 to 20	Less than 50%	Between 50% and 99%
Brighton and Hove	1 to 5	None	100%	100%
Bristol, City of	6 to 10	None	100%	100%
Bromley	1 to 5	1 to 5	Less than 50%	100%
Calderdale	1 to 5	None	100%	100%
Camden	6 to 10	6 to 10	Less than 50%	Between 50% and 99%
City of London	1 to 5	None	100%	100%
Croydon	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Dacorum	1 to 5	None	100%	100%
Doncaster	1 to 5	None	100%	100%
Ealing	1 to 5	1 to 5	Between 50% and 99%	100%
Elmbridge	1 to 5	None	100%	100%
Gateshead	1 to 5	None	100%	100%
Greenwich	Over 20	1 to 5	Between 50% and 99%	100%
Hackney	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Hammersmith and Fulham	6 to 10	None	100%	100%
Haringey	6 to 10	1 to 5	Between 50% and 99%	100%
Harrow	1 to 5	None	100%	100%
Havering	1 to 5	None	100%	100%
Hillingdon	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Hounslow	1 to 5	None	100%	100%
Islington	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Kensington and Chelsea	1 to 5	None	100%	100%
Kingston upon Thames	1 to 5	None	100%	100%
Kirklees	1 to 5	None	100%	100%
Lambeth	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Leeds	6 to 10	None	100%	100%
Leicester	1 to 5	None	100%	100%
Lewisham	1 to 5	1 to 5	Between 50% and 99%	100%
Lincoln	1 to 5	None	100%	100%
Liverpool	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Luton	1 to 5	1 to 5	Less than 50%	100%
Manchester	Over 20	1 to 5	Between 50% and 99%	100%
Medway	1 to 5	None	100%	100%
Merton	1 to 5	None	100%	100%
Milton Keynes	1 to 5	1 to 5	Less than 50%	100%
Newcastle upon Tyne	6 to 10	None	100%	100%
Newham	Over 20	1 to 5	Between 50% and 99%	100%
Norwich	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Nottingham	6 to 10	1 to 5	Between 50% and 99%	100%
Oldham	1 to 5	None	100%	100%
Plymouth	1 to 5	None	100%	100%
Portsmouth	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Reading	1 to 5	1 to 5	Between 50% and 99%	100%
Redbridge	1 to 5	None	100%	100%
Salford	Over 20	6 to 10	Between 50% and 99%	100%
Sandwell	1 to 5	None	100%	100%
Sefton	1 to 5	None	100%	100%
Sheffield	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Slough	1 to 5	1 to 5	Between 50% and 99%	100%
Southwark	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Stockton-on-Tees	1 to 5	None	100%	100%
Sunderland	1 to 5	None	100%	100%
Sutton	1 to 5	1 to 5	Between 50% and 99%	100%
Tower Hamlets	Over 20	6 to 10	Between 50% and 99%	Between 50% and 99%
Trafford	1 to 5	None	100%	100%
Waltham Forest	1 to 5	None	100%	100%
Wandsworth	11 to 20	1 to 5	Between 50% and 99%	100%
Westminster	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Windsor and Maidenhead	1 to 5	None	100%	100%
Wolverhampton	1 to 5	None	100%	100%

## ACM_5
ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 December 2023
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Greater Manchester	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	38	81%	13	72%	5	100%	1	50%	0	0%	57	79%
Works complete awaiting building control signoff	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation started - cladding removed	9	19%	3	17%	0	0%	1	50%	0	0%	13	18%
Remediation started	0	0%	2	11%	0	0%	0	0%	0	0%	2	3%
Plans in place	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	47	100%	18	100%	5	100%	2	100%	0	0%	72	100%

London	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	62	76%	128	77%	11	85%	11	73%	0	0%	212	77%
Works complete awaiting building control signoff	10	12%	4	2%	1	8%	2	13%	1	100%	18	6%
Remediation started - cladding removed	10	12%	10	6%	0	0%	1	7%	0	0%	21	8%
Remediation started	0	0%	11	7%	0	0%	1	7%	0	0%	12	4%
Plans in place	0	0%	7	4%	1	8%	0	0%	0	0%	8	3%
Responded with intent	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	5	3%	0	0%	0	0%	0	0%	5	2%
Total buildings	82	100%	166	100%	13	100%	15	100%	1	100%	277	100%

Rest of England	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	32	100%	41	76%	36	90%	12	86%	7	100%	128	87%
Works complete awaiting building control signoff	0	0%	8	15%	1	3%	1	7%	0	0%	10	7%
Remediation started - cladding removed	0	0%	2	4%	1	3%	0	0%	0	0%	3	2%
Remediation started	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Plans in place	0	0%	3	6%	2	5%	0	0%	0	0%	5	3%
Responded with intent	0	0%	0	0%	0	0%	1	7%	0	0%	1	1%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	32	100%	54	100%	40	100%	14	100%	7	100%	147	100%

## ACM_6
ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 December 2023
Back to Contents
This worksheet contains four tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Identified by 31 December 2019	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	126	82%	162	87%	50	96%	22	81%	7	88%	367	86%
Works complete awaiting building control signoff	9	6%	7	4%	1	2%	2	7%	1	13%	20	5%
Remediation started - cladding removed	19	12%	8	4%	1	2%	2	7%	0	0%	30	7%
Remediation started	0	0%	8	4%	0	0%	0	0%	0	0%	8	2%
Plans in place	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Responded with intent	0	0%	1	1%	0	0%	1	4%	0	0%	2	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	154	100%	187	100%	52	100%	27	100%	8	100%	428	100%

Identified by 31 December 2020	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	127	81%	177	83%	51	94%	23	79%	7	88%	385	84%
Works complete awaiting building control signoff	10	6%	9	4%	2	4%	3	10%	1	13%	25	5%
Remediation started - cladding removed	19	12%	11	5%	1	2%	2	7%	0	0%	33	7%
Remediation started	0	0%	11	5%	0	0%	0	0%	0	0%	11	2%
Plans in place	0	0%	3	1%	0	0%	0	0%	0	0%	3	1%
Responded with intent	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	156	100%	212	100%	54	100%	29	100%	8	100%	459	100%

Identified by 31 December 2021	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	131	82%	180	80%	52	93%	24	77%	7	88%	394	82%
Works complete awaiting building control signoff	10	6%	10	4%	2	4%	3	10%	1	13%	26	5%
Remediation started - cladding removed	19	12%	14	6%	1	2%	2	6%	0	0%	36	7%
Remediation started	0	0%	12	5%	0	0%	1	3%	0	0%	13	3%
Plans in place	0	0%	9	4%	1	2%	0	0%	0	0%	10	2%
Responded with intent	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	160	100%	226	100%	56	100%	31	100%	8	100%	481	100%

All buildings identified	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	132	82%	182	76%	52	90%	24	77%	7	88%	397	80%
Works complete awaiting building control signoff	10	6%	12	5%	2	3%	3	10%	1	13%	28	6%
Remediation started - cladding removed	19	12%	15	6%	1	2%	2	6%	0	0%	37	7%
Remediation started	0	0%	13	5%	0	0%	1	3%	0	0%	14	3%
Plans in place	0	0%	10	4%	3	5%	0	0%	0	0%	13	3%
Responded with intent	0	0%	1	0%	0	0%	1	3%	0	0%	2	0%
Remediation plan unclear	0	0%	5	2%	0	0%	0	0%	0	0%	5	1%
Total buildings	161	100%	238	100%	58	100%	31	100%	8	100%	496	100%

## ACM_7
Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, 31 December 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed	9,700	14,500	17,400	24,200	27,100
Works complete awaiting building control signoff	400	800	900	1,200	1,300
Yet to complete remediation [note_3]	1,800	4,100	4,600	5,900	6,400
Occupied and yet to complete remediation	1,800	4,000	4,500	5,800	6,300

Leasehold dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed	2,700	14,500	17,400	17,200	20,100
Works complete awaiting building control signoff	100	800	900	900	1,000
Yet to complete remediation [note_3]	500	4,100	4,600	4,600	5,100
Occupied and yet to complete remediation	500	4,000	4,500	4,500	5,000

## ACM_8
ACM remediation progress by sources of funding, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	In social fund / [note_4], [note_39]	Social: Not in social fund / [note_40]	Private: government funded / [note_5], [note_41]	Private: not government funded / [note_42]
Remediation completed	125	7	79	103
Works complete awaiting building control signoff	10	0	5	7
Remediation started - cladding removed	9	10	12	3
Remediation started	0	0	11	2
Plans in place	0	0	8	2
Responded with intent	0	0	0	1
Remediation plan unclear	0	0	0	5
Total	144	17	115	123

## ACM_9
Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Category	Number of buildings inside London	Number of buildings outside London
No contact with delivery partners	0	0
Preparing application	0	0
Eligibility application submitted	0	0
Eligibility approved	3	0
Applications approved: for pre-contract support	3	1
Full cost application submitted	0	0
Applications approved: for full costs	65	39
Total [note_5]	71	40

## ACM_10
Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Funding	Social Sector / (£ million)	Private Sector / (£ million)
Approved [note_6, note_7]	292	230
Expenditure [note_8, note_9]	270	276

## WWRF_1
Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 December 2023
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Tranche	Applications	Buildings	Approved Applications	Approved Buildings	Application approval rate / Percentage (%)	Building approval rate / Percentage (%)	Leasehold dwellings in approved buildings	Approved Funding / (£ million)	Mean funding per building / (£)	Mean funding per leashold dwelling / (£)	Mean Waking Watch cost per month per dwelling in approved buildings / (£)	Median Waking Watch cost per month per dwelling in approved buildings / (£)	Buildings with alarm installation complete	Buildings with alarm installation complete / Percentage (%)
Waking Watch Relief Fund	329	468	212	320	64%	68%	24,700	27.3	85,371	1,105	169	104	301	94%
Waking Watch Replacement Fund	38	67	25	47	66%	70%	2,200	2.4	50,369	1,066	216	210	41	87%
Total [note_10]	367	535	237	367	65%	69%	26,900	29.7	80,889	1,101	172	106	342	93%

## WWRF_2
Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 December 2023
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_11]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	9	8	1	0	0	11%	89%	9	8	89%	3%	1.6	200,826	180,147
Bristol	3	2	1	0	0	33%	67%	3	2	67%	1%	0.1	46,256	46,256
Greater London Authority	110	65	29	16	0	26%	59%	171	111	65%	35%	8.3	74,911	64,551
Greater Manchester Combined Authority	25	20	5	0	0	20%	80%	38	33	87%	10%	2.5	75,477	76,928
Leeds	10	9	0	1	0	0%	90%	12	11	92%	3%	1.8	162,466	124,500
Liverpool	18	17	1	0	0	6%	94%	19	18	95%	6%	1.7	94,400	63,784
Newcastle	3	3	0	0	0	0%	100%	3	3	100%	1%	0.4	128,496	163,181
Sheffield	6	5	0	1	0	0%	83%	7	6	86%	2%	0.5	88,753	87,828
DLUHC (1st Tranche)	35	21	14	0	0	40%	60%	55	39	71%	12%	2.7	69,807	65,577
DLUHC (2nd Tranche)	60	27	32	1	0	53%	45%	70	34	49%	11%	3.8	112,303	81,624
DLUHC (3rd Tranche)	50	35	14	1	0	28%	70%	81	55	68%	17%	3.9	70,341	57,389
DLUHC Total	145	83	60	2	0	41%	57%	206	128	62%	40%	10.4	81,324	65,486
Total [note_10]	329	212	97	20	0	29%	64%	468	320	68%	100%	27.3	85,371	67,894

## WWRF_3
Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 December 2023
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_12]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	2	2	0	0	0	0%	100%	4	4	100%	9%	0.4	89,328	87,683
DLUHC	25	21	1	3	0	4%	84%	46	40	87%	85%	1.8	45,360	26,643
Greater Manchester Combined Authority	11	2	9	0	0	82%	18%	17	3	18%	6%	0.2	65,206	46,743
Leeds	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Liverpool	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Sheffield	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Total [note_10]	38	25	10	3	0	26%	66%	67	47	70%	100%	2.4	50,369	30,209

## BSF_1
Remediation status of eligible buildings within BSF by tenure, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note 23]	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Total residential Number	Total residential Percentage (%)
Remediation complete	30	18%	111	14%	141	15%
Remediation complete: awaiting building control sign-off	9	6%	81	10%	90	9%
Remediation started	67	41%	188	24%	255	27%
Remediation not yet started	57	35%	407	52%	464	49%
Total buildings	163	100%	787	100%	950	100%

## BSF_2
BSF remediation progress of eligible buildings by region, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note 23]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF / Percentage(%)	Not Started Remediation / Number	Not Started Remediation / Percentage(%)	Started Remediation / Number	Started Remediation / Percentage(%)	Completed Remediation [note_13] / Number	Completed Remediation [note_13] / Percentage(%)	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible BSF buildings that have started or completed remediation / Percentage (%)
North West	137	14%	54	12%	46	18%	37	16%	27%	61%
London	555	58%	293	63%	147	58%	115	50%	21%	47%
East of England	31	3%	16	3%	6	2%	9	4%	29%	48%
East Midlands	29	3%	18	4%	7	3%	4	2%	14%	38%
North East	14	1%	11	2%	1	0%	2	1%	14%	21%
South East	71	7%	23	5%	14	5%	34	15%	48%	68%
South West	34	4%	20	4%	9	4%	5	2%	15%	41%
West Midlands	19	2%	8	2%	8	3%	3	1%	16%	58%
Yorkshire and The Humber	60	6%	21	5%	17	7%	22	10%	37%	65%
Total	950	100%	464	100%	255	100%	231	100%	24%	51%

## BSF_3
BSF number of eligible buildings by funding allocations, expenditure and tenure, England, 31 December 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. [note 38]
All figures are for number of buildings or financial amounts in GBP £ million.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Some cells in this table are empty because data is not available for these variables.
Table BSF_3a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the BSF .
Funding Allocations [note_15]	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Funding / (£ millions)
Full Applications Approved	470	1,798
Pre-Tender Support Allocations	701	269
Total		2,067	107	214	2,280

Table BSF_3b: Amount of expenditure from the BSF by tenure.
Expenditure [note_44][note_45]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	730	1,210	84	165	814	1,375

## Combined_1
Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17]	ACM cladding only / Number	ACM cladding only / Percentage (%)	Non-ACM cladding only in the BSF / Number	Non-ACM cladding only in the BSF / Percentage (%)	Both ACM and non-ACM cladding in the BSF / Number	Both ACM and non-ACM cladding in the BSF / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation completed	336	84%	108	13%	33	34%	477	35%
Works complete awaiting building control signoff	24	6%	85	10%	4	4%	113	8%
Remediation started	29	7%	228	27%	50	51%	307	23%
Remediation not started	9	2%	431	51%	11	11%	451	33%
Total	398	100%	852	100%	98	100%	1,348	100%

## Combined_2
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17, note_18, note_43]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	112	8%	685	28%	797	21%
Remediation underway	277	19%	534	22%	811	21%
In programme	1,040	73%	1,191	49%	2,231	58%
Total	1,429	100%	2,410	100%	3,839	100%

## CSS_1
Application status of buildings within the CSS, England, 31 December 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Application category for pre-eligible buildings	Number
Pre - application	615

Application category for pre-eligbile live applications	Number	Percentage (%)
Initial Application	411	77%
FRAEW	63	12%
Eligibility in review	60	11%
Total pre-eligible live applications	534	100%

Pre - eligible buildings total	Number
Total pre - eligible buildings	1,149

Application category for eligible buildings	Number	Percentage (%)
Grant Funding Agreement	72	69%
Pre - works package	13	13%
Works package	19	18%
Works started	0	0%
Works completed	0	0%
Total eligible buildings	104	100%

## CSS_2
CSS remediation progress by region, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region	Eligible Buildings in the CSS / Number	Not Started Remediation / Number	Started Remediation / Number	Completed Remediation / Number	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible CSS buildings that have started or completed remediation / Percentage (%)
North West	15	15	0	0	0%	0%
London	43	43	0	0	0%	0%
East of England	13	13	0	0	0%	0%
East Midlands	5	5	0	0	0%	0%
North East	0	0	0	0	0%	0%
South East	11	11	0	0	0%	0%
South West	7	7	0	0	0%	0%
West Midlands	1	1	0	0	0%	0%
Yorkshire and The Humber	9	9	0	0	0%	0%
Total	104	104	0	0	0%	0%

## CSS_3
CSS remediation progress by height, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)
Remediation complete	0	0%	0	0%
Remediation started	0	0%	0	0%
In programme	88	100%	16	100%
Total buildings	88	100%	16	100%

## CSS_4
CSS remediation progress by tenure, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)
Remediation complete	0	0%	0	0%
Remediation started	0	0%	0	0%
In programme	20	100%	84	100%
Total buildings	20	100%	84	100%

## Developer_1
Remediation status of buildings requiring works under the developer remediation contract by height group, England, 31 October 2023
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - All Defect Types [Note_25, Note_26]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	96	18%	166	21%	262	19%
Remediation started	62	11%	149	19%	211	16%
Remediation not Started - Plans in Place	241	44%	265	33%	506	38%
Remediation not Started - No Plans in Place	145	27%	221	28%	366	27%
Total buildings	544	100%	801	100%	1345	100%

Remediation Category - Cladding Defects [Note_25, Note_26]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	81	16%	164	21%	245	19%
Remediation started	54	11%	146	19%	200	16%
Remediation not Started - Plans in Place	224	45%	252	32%	476	37%
Remediation not Started - No Plans in Place	134	27%	218	28%	352	28%
Total buildings	493	100%	780	100%	1273	100%

## Developer_2
Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for estimated cost of buildings identified as requiring works under the Developer Remediation Contract in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Cost Category [Note_33]	11-18m / (£ millions)	18m+ / (£ millions)	Total / (£ millions)
Total estimated cost of works	587	2,153	2,740

## Developer_3
Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29]	Number of buildings for which the developer has accepted responsibility under the contract	Number of buildings assessed and found to require remediation [Note_28]	Number of buildings assessed and found to require remediation, and which will be remediated by the developer directly (rather than being remediated through a government fund, with cost re-imbursed by developer) [Note 31]	Number of buildings where it is not known whether remediation is required [Note 32]
Abbey Developments Limited(*)	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	53	0	0	53
Ballymore Limited	85	32	17	1
Barratt Developments PLC	708	128	116	0
Bellway PLC	502	195	170	245
The Berkeley Group Holdings PLC	815	68	57	0
Bewley Group Limited	9	2	0	0
Bloor Investments Limited	-	-	-	-
The British Land Company PLC	16	2	2	0
Cala Group (Holdings) Limited	26	1	1	3
Canary Wharf Group PLC	13	0	0	9
C.G. Fry and Son Limited (*)	-	-	-	-
Churchill Retirement PLC	8	0	0	8
Crest Nicholson Holdings PLC	282	116	110	152
Croudace Homes Group Limited (*)	-	-	-	-
Dandara Living Holdings Limited	24	19	13	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-
Fairview Holdings Limited	136	53	50	8
Frasers Property (UK) Ltd	23	0	0	0
Galliard Group Limited	96	16	16	65
MJ Gleeson PLC	17	8	7	9
Grosvenor Group Limited	17	2	2	1
Hill Holdings Limited	87	7	6	1
Hopkins Home Group Limited (*)	-	-	-	-
Jelson Holdings Limited	7	3	3	4
Keepmoat Limited (*)	-	-	-	-
Land Securities Group PLC	43	4	3	23
Lendlease Europe Holdings Limited	94	15	14	46
Lifestory Holdings Limited (also covers Anthology Group)	18	1	1	0
London Square Development (Holdings) Limited	43	0	0	0
Miller Homes Limited	36	17	17	19
Morris Homes Group Limited	6	2	2	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	119	13	13	9
Persimmon Public Limited Company	64	42	35	5
Redrow PLC	120	43	29	77
Regal Holdco Limited (parent company for Regal London)	15	1	1	0
Rowland Group Limited (*)	-	-	-	-
Rydon Group Holdings Limited	25	14	11	0
Sorbon Group Limited (parent company for Shanly Homes)	26	5	5	9
St Modwen Group Holdings Company Limited	13	3	0	0
Story Homes Limited (*)	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-
Taylor Wimpey PLC	384	171	164	3
Telford Homes Limited	148	61	50	81
Tilia Homes Limited	8	5	5	3
Vistry Group PLC	288	85	80	27
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-
Weston Group PLC	88	21	21	10
McCarthy & Stone Limited	61	12	12	15
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	21	3	2	5
Total	4544	1170	1035	891

## Developer_4
Developer by developer breakdown of buildings covered by the developer remediation contract, by assessment status, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29]	Progress with assessments
	Buildings that…
	…have had an Assessment [Note 30]		…have not had an assessment		…have been assessed and confirmed to require remediation
					out of total buildings [Note_28]	out of total buildings	out of assessed buildings
Abbey Developments Limited(*)	-	-	-	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	9	17%	44	83%	0	0%	0%
Ballymore Limited	72	85%	13	15%	32	38%	44%
Barratt Developments PLC	457	65%	251	35%	128	18%	28%
Bellway PLC	274	55%	228	45%	195	39%	71%
The Berkeley Group Holdings PLC	755	93%	60	7%	68	8%	9%
Bewley Group Limited	9	100%	0	0%	2	22%	22%
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	16	100%	0	0%	2	13%	13%
Cala Group (Holdings) Limited	8	31%	18	69%	1	4%	13%
Canary Wharf Group PLC	13	100%	0	0%	0	0%	0%
C.G. Fry and Son Limited (*)	-	-	-	-	-	-	-
Churchill Retirement PLC	8	100%	0	0%	0	0%	0%
Crest Nicholson Holdings PLC	140	50%	142	50%	116	41%	83%
Croudace Homes Group Limited (*)	-	-	-	-	-	-	-
Dandara Living Holdings Limited	21	88%	3	13%	19	79%	90%
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-	-	-	-
Fairview Holdings Limited	136	100%	0	0%	53	39%	39%
Frasers Property (UK) Ltd	10	43%	13	57%	0	0%	0%
Galliard Group Limited	75	78%	21	22%	16	17%	21%
MJ Gleeson PLC	14	82%	3	18%	8	47%	57%
Grosvenor Group Limited	9	53%	8	47%	2	12%	22%
Hill Holdings Limited	78	90%	9	10%	7	8%	9%
Hopkins Home Group Limited (*)	-	-	-	-	-	-	-
Jelson Holdings Limited	7	100%	0	0%	3	43%	43%
Keepmoat Limited (*)	-	-	-	-	-	-	-
Land Securities Group PLC	17	40%	26	60%	4	9%	24%
Lendlease Europe Holdings Limited	72	77%	22	23%	15	16%	21%
Lifestory Holdings Limited (also covers Anthology Group)	18	100%	0	0%	1	6%	6%
London Square Development (Holdings) Limited	43	100%	0	0%	0	0%	0%
Miller Homes Limited	33	92%	3	8%	17	47%	52%
Morris Homes Group Limited	6	100%	0	0%	2	33%	33%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	112	94%	7	6%	13	11%	12%
Persimmon Public Limited Company	61	95%	3	5%	42	66%	69%
Redrow PLC	120	100%	0	0%	43	36%	36%
Regal Holdco Limited (parent company for Regal London)	15	100%	0	0%	1	7%	7%
Rowland Group Limited (*)	-	-	-	-	-	-	-
Rydon Group Holdings Limited	25	100%	0	0%	14	56%	56%
Sorbon Group Limited (parent company for Shanly Homes)	26	100%	0	0%	5	19%	19%
St Modwen Group Holdings Company Limited	8	62%	5	38%	3	23%	38%
Story Homes Limited (*)	-	-	-	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-	-	-	-
Taylor Wimpey PLC	257	67%	127	33%	171	45%	67%
Telford Homes Limited	75	51%	73	49%	61	41%	81%
Tilia Homes Limited	8	100%	0	0%	5	63%	63%
Vistry Group PLC	119	41%	169	59%	85	30%	71%
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-	-	-	-
Weston Group PLC	78	89%	10	11%	21	24%	27%
McCarthy & Stone Limited	61	100%	0	0%	12	20%	20%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	14	67%	7.00	0.33	3	14%	21%
Total	3279	72%	1265	28%	1170	26%	36%

## Developer_5
Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29]	Remediation Status
	Proportion of buildings being remediated by the developer directly where remediation is...
	…not yet started		…started		…complete
Abbey Developments Limited(*)	-	-	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	-	0	-	0	-
Ballymore Limited	8	47%	2	12%	7	41%
Barratt Developments PLC	74	64%	21	18%	21	18%
Bellway PLC	122	72%	37	22%	11	6%
The Berkeley Group Holdings PLC	15	26%	8	14%	34	60%
Bewley Group Limited	0	-	0	-	0	-
Bloor Investments Limited	-	-	-	-	-	-
The British Land Company PLC	2	100%	0	0%	0	0%
Cala Group (Holdings) Limited	1	100%	0	0%	0	0%
Canary Wharf Group PLC	0	-	0	-	0	-
C.G. Fry and Son Limited (*)	-	-	-	-	-	-
Churchill Retirement PLC	0	-	0	-	0	-
Crest Nicholson Holdings PLC	99	90%	7	6%	4	4%
Croudace Homes Group Limited (*)	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0%	13	100%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-	-	-
Fairview Holdings Limited	28	56%	9	18%	13	26%
Frasers Property (UK) Ltd	0	-	0	-	0	-
Galliard Group Limited	4	25%	1	6%	11	69%
MJ Gleeson PLC	7	100%	0	0%	0	0%
Grosvenor Group Limited	1	50%	1	50%	0	0%
Hill Holdings Limited	2	33%	1	17%	3	50%
Hopkins Home Group Limited (*)	-	-	-	-	-	-
Jelson Holdings Limited	3	100%	0	0%	0	0%
Keepmoat Limited (*)	-	-	-	-	-	-
Land Securities Group PLC	3	100%	0	0%	0	0%
Lendlease Europe Holdings Limited	12	86%	2	14%	0	0%
Lifestory Holdings Limited (also covers Anthology Group)	1	100%	0	0%	0	0%
London Square Development (Holdings) Limited	0	-	0	-	0	-
Miller Homes Limited	12	71%	0	0%	5	29%
Morris Homes Group Limited	0	0%	2	100%	0	0%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	10	77%	2	15%	1	8%
Persimmon Public Limited Company	33	94%	2	6%	0	0%
Redrow PLC	22	76%	5	17%	2	7%
Regal Holdco Limited (parent company for Regal London)	0	0%	0	0%	1	100%
Rowland Group Limited (*)	-	-	-	-	-	-
Rydon Group Holdings Limited	2	18%	7	64%	2	18%
Sorbon Group Limited (parent company for Shanly Homes)	5	100%	0	0%	0	0%
St Modwen Group Holdings Company Limited	0	-	0	-	0	-
Story Homes Limited (*)	-	-	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-	-	-
Taylor Wimpey PLC	114	70%	11	7%	39	24%
Telford Homes Limited	50	100%	0	0%	0	0%
Tilia Homes Limited	5	100%	0	0%	0	0%
Vistry Group PLC	77	96%	3	4%	0	0%
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-	-	-
Weston Group PLC	15	71%	6	29%	0	0%
McCarthy & Stone Limited	9	75%	1	8%	2	17%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	1	50%	1	50%	0	0%
Total	737	71%	142	14%	156	15%

## Developer_6
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_27, Note_29]	Buildings that require remediation by the developer which have not yet started, with a start date…

	...at all		…within the next 12 months
Abbey Developments Limited(*)	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	-	0	-
Ballymore Limited	2	25%	2	25%
Barratt Developments PLC	73	99%	44	59%
Bellway PLC	88	72%	23	19%
The Berkeley Group Holdings PLC	14	93%	14	93%
Bewley Group Limited	0	-	0	-
Bloor Investments Limited	-	-	-	-
The British Land Company PLC	2	100%	2	100%
Cala Group (Holdings) Limited	0	0%	0	0%
Canary Wharf Group PLC	0	-	0	-
C.G. Fry and Son Limited (*)	-	-	-	-
Churchill Retirement PLC	0	-	0	-
Crest Nicholson Holdings PLC	95	96%	84	85%
Croudace Homes Group Limited (*)	-	-	-	-
Dandara Living Holdings Limited	0	-	0	-
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-
Fairview Holdings Limited	23	82%	18	64%
Frasers Property (UK) Ltd	0	-	0	-
Galliard Group Limited	4	100%	4	100%
MJ Gleeson PLC	4	57%	4	57%
Grosvenor Group Limited	0	0%	0	0%
Hill Holdings Limited	0	0%	0	0%
Hopkins Home Group Limited (*)	-	-	-	-
Jelson Holdings Limited	0	0%	0	0%
Keepmoat Limited (*)	-	-	-	-
Land Securities Group PLC	0	0%	0	0%
Lendlease Europe Holdings Limited	7	58%	3	25%
Lifestory Holdings Limited (also covers Anthology Group)	1	100%	1	100%
London Square Development (Holdings) Limited	0	-	0	-
Miller Homes Limited	11	92%	6	50%
Morris Homes Group Limited	0	-	0	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	7	70%	7	70%
Persimmon Public Limited Company	32	97%	29	88%
Redrow PLC	22	100%	15	68%
Regal Holdco Limited (parent company for Regal London)	0	-	0	-
Rowland Group Limited (*)	-	-	-	-
Rydon Group Holdings Limited	0	0%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	2	40%	2	40%
St Modwen Group Holdings Company Limited	0	-	0	-
Story Homes Limited (*)	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-
Taylor Wimpey PLC	102	89%	95	83%
Telford Homes Limited	18	36%	7	14%
Tilia Homes Limited	5	100%	5	100%
Vistry Group PLC	60	78%	39	51%
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-
Weston Group PLC	15	100%	5	33%
McCarthy & Stone Limited	1	11%	0	0%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	0	0%	0	0%
Total	588	80%	409	55%

## Developer_7
Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation, by engagement and remediation status, England, 31 October 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 October 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29]	where the developer or ‘responsible entity’ has engaged with the leaseholders, freeholders, residents, occupiers or other users regarding works for…
	…buildings requiring works, including those that have completed remediation	…buildings requiring works, excluding those that have completed remediation
Abbey Developments Limited(*)	-	-
Allison Homes Group Limited(*)	-	-
Viva Midco Limited (parent company for Avant Homes)	-	-
Ballymore Limited	65%	40%
Barratt Developments PLC	89%	96%
Bellway PLC	95%	96%
The Berkeley Group Holdings PLC	100%	100%
Bewley Group Limited	-	-
Bloor Investments Limited	-	-
The British Land Company PLC	100%	100%
Cala Group (Holdings) Limited	0%	0%
Canary Wharf Group PLC	-	-
C.G. Fry and Son Limited (*)	-	-
Churchill Retirement PLC	-	-
Crest Nicholson Holdings PLC	100%	100%
Croudace Homes Group Limited (*)	-	-
Dandara Living Holdings Limited	100%	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	100%	100%
Fairview Holdings Limited	100%	100%
Frasers Property (UK) Ltd	-	-
Galliard Group Limited	31%	100%
MJ Gleeson PLC	100%	100%
Grosvenor Group Limited	100%	100%
Hill Holdings Limited	100%	100%
Hopkins Home Group Limited (*)	-	-
Jelson Holdings Limited	100%	100%
Keepmoat Limited (*)	-	-
Land Securities Group PLC	100%	100%
Lendlease Europe Holdings Limited	79%	79%
Lifestory Holdings Limited (also covers Anthology Group)	100%	100%
London Square Development (Holdings) Limited	-	-
Miller Homes Limited	94%	92%
Morris Homes Group Limited	100%	100%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	100%	100%
Persimmon Public Limited Company	100%	100%
Redrow PLC	100%	100%
Regal Holdco Limited (parent company for Regal London)	100%	-
Rowland Group Limited (*)	-	-
Rydon Group Holdings Limited	82%	78%
Sorbon Group Limited (parent company for Shanly Homes)	100%	100%
St Modwen Group Holdings Company Limited	-	-
Story Homes Limited (*)	-	-
Strata Homes Group Limited (*)	-	-
Taylor Wimpey PLC	100%	100%
Telford Homes Limited	98%	98%
Tilia Homes Limited	100%	100%
Vistry Group PLC	93%	93%
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-
Weston Group PLC	100%	100%
McCarthy & Stone Limited	100%	100%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	100%	100%
Total	95%	96%

## Social_1
Remediation status of buildings with cladding defects reported by Registered Providers of social housing, England, 31 August 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [Note 34] [Note 35]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete [Note 37]	47	5%	59	8%	106	7%
Remediation started	212	23%	182	26%	394	25%
Remediation works planned	320	35%	271	39%	591	37%
Remediation plans unclear from survey	327	36%	183	26%	510	32%
Work is not required – planned for demolition	3	0.3%	4	0.6%	7	0.4%
Total buildings [Note 36]	909	100%	699	100%	1608	100%

## Enforcement_1
Enforcement action taken by local authorities against high-rise buildings under the Housing Act (2004) by remediation programme status, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for the number of enforcement actions by local authority and by the type of remediation programme each building is in [note_15].
Local Authority [note_2]	BSF only (non-ACM cladding only) / Number	ACM cladding only / Number	BSF (non-ACM) and ACM cladding / Number	Not in any remediation fund (non-ACM cladding only) / Number	Total / Number
Barking and Dagenham	0	0	0	0	0
Barnet	1	3	1	2	7
Birmingham	2	0	0	0	2
Bournemouth, Christchurch and Poole	2	2	0	1	5
Bradford	0	1	0	0	1
Brent	0	2	0	0	2
Brighton and Hove	0	0	0	0	0
Bristol, City of	0	1	0	0	1
Bromley	0	0	0	0	0
Calderdale	0	0	0	0	0
Camden	15	1	0	19	35
City of London	1	0	0	1	2
Croydon	2	0	1	0	3
Dacorum	0	0	0	0	0
Ealing	2	1	1	0	4
Gateshead	0	0	0	0	0
Greenwich	4	0	0	1	5
Hackney	3	4	0	4	11
Hammersmith and Fulham	3	0	0	10	13
Haringey	0	0	0	0	0
Harrow	0	0	0	0	0
Hillingdon	3	0	0	2	5
Hounslow	0	0	0	1	1
Ipswich	0	0	0	0	0
Islington	1	0	0	0	1
Kensington and Chelsea	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0
Kirklees	0	0	0	0	0
Lambeth	2	2	0	0	4
Leeds	0	0	0	0	0
Leicester	0	0	0	0	0
Lewisham	0	0	0	0	0
Liverpool	2	3	2	1	8
Maidstone	0	0	0	0	0
Manchester	0	0	0	0	0
Medway	0	1	0	0	1
Merton	0	0	0	0	0
Milton Keynes	0	0	0	0	0
Newcastle upon Tyne	6	0	0	5	11
Newham	12	1	1	10	24
North Somerset	0	0	0	0	0
Norwich	0	0	0	0	0
Nottingham	2	1	0	1	4
Plymouth	0	0	0	1	1
Portsmouth	0	1	0	1	2
Reading	0	0	0	0	0
Redbridge	2	0	0	0	2
Salford	1	0	0	0	1
Sheffield	0	0	0	0	0
Slough	0	0	0	0	0
Southampton	3	0	0	0	3
Southwark	13	4	2	7	26
Sunderland	0	0	0	0	0
Sutton	0	0	1	0	1
Thanet	0	0	0	0	0
Tower Hamlets	10	1	4	5	20
Trafford	0	0	0	0	0
Waltham Forest	1	0	0	0	1
Wandsworth	1	2	1	0	4
Westminster	32	5	5	11	53
Windsor and Maidenhead	0	0	0	0	0
Others	14	0	2	13	29
Total	140	36	21	96	293

## Enforcement_2
Building inspections conducted by local authorities, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for the number of inspections by type of rating outcome.
Local Authority [note_2]	Inspections with the building rated Category 1 [note_16] / Number	Inspections with the building rated Category 2 [note_16] / Number	Rating outcome to be confirmed / Number	Total / Number
Barking and Dagenham	0	0	0	0
Barnet	4	3	0	7
Birmingham	0	1	1	2
Bournemouth, Christchurch and Poole	5	0	0	5
Bradford	0	1	0	1
Brent	1	1	0	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	1	0	1
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	0	34	1	35
City of London	0	0	1	1
Croydon	1	1	1	3
Dacorum	0	0	0	0
Ealing	1	3	0	4
Gateshead	0	0	0	0
Greenwich	2	0	3	5
Hackney	5	2	4	11
Hammersmith and Fulham	0	9	4	13
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	0	5	0	5
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	0	1	1
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	3	4	1	8
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	0	9	2	11
Newham	10	9	7	26
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	1	3	0	4
Plymouth	1	0	0	1
Portsmouth	0	1	2	3
Reading	0	0	0	0
Redbridge	0	1	1	2
Salford	0	1	0	1
Sheffield	0	0	1	1
Slough	0	0	0	0
Southampton	0	0	3	3
Southwark	10	15	1	26
Sunderland	0	0	0	0
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	0	9	11	20
Trafford	0	0	0	0
Waltham Forest	0	1	0	1
Wandsworth	1	3	0	4
Westminster	5	48	0	53
Windsor and Maidenhead	0	0	0	0
Others	11	13	2	26
Total	66	180	47	293

## Enforcement_3
Statutory notices served by local authorities under the Housing Act (2004), England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for number of statutory notices served, broken down by type of notice, for each Local Authority.
Local Authority [note_2]	Improvement notices / Number	Hazard awareness notices / Number	Prohibition orders / Number	Total / Number
Barking and Dagenham	0	0	0	0
Barnet	5	0	0	5
Birmingham	0	0	0	0
Bournemouth, Christchurch and Poole	3	0	0	3
Bradford	1	0	0	1					5
Brent	0	0	0	0
Brighton and Hove	0	0	0	0
Bristol, City of	0	0	0	0
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	8	2	0	10
City of London	0	0	0	0
Croydon	0	0	0	0
Dacorum	0	0	0	0
Ealing	2	0	0	2
Gateshead	0	0	0	0
Greenwich	1	0	0	1
Hackney	7	0	0	7
Hammersmith and Fulham	0	2	0	2
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	2	1	0	3
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	0	0	0
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	4	0	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	5	0	0	5
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	2	3	0	5
Newham	8	0	0	8
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	2	0	0	2
Plymouth	1	0	0	1
Portsmouth	1	0	0	1
Reading	0	0	0	0
Redbridge	0	0	0	0
Salford	0	0	0	0
Sheffield	0	0	0	0
Slough	0	0	0	0
Southampton	0	0	0	0
Southwark	8	0	0	8
Sunderland	0	0	0	0
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	4	2	0	6
Trafford	0	0	0	0
Waltham Forest	0	0	0	0
Wandsworth	1	0	0	1
Westminster	1	14	1	16
Windsor and Maidenhead	0	0	0	0
Others	14	0	0	14
Total	83	24	1	108

## Enforcement_4
Number of building inspections by local authorities supported by the Joint Inspection Team, England, 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for the number of inspections supported by the Joint Inspection Team.
Local Authority [note_2]	Inspections supported by the Joint Inspection Team [note_17] / Number
Barking and Dagenham	0
Barnet	4
Birmingham	2
Bournemouth, Christchurch and Poole	2
Bradford	0
Brent	2
Brighton and Hove	0
Bristol, City of	0
Bromley	0
Calderdale	0
Camden	5
City of London	0
Croydon	3
Dacorum	0
Ealing	4
Gateshead	0
Greenwich	5
Hackney	8
Hammersmith and Fulham	1
Haringey	0
Harrow	0
Hillingdon	2
Hounslow	1
Ipswich	0
Islington	1
Kensington and Chelsea	0
Kingston upon Thames	0
Kirklees	0
Lambeth	2
Leeds	0
Leicester	0
Lewisham	0
Liverpool	6
Maidstone	0
Manchester	0
Medway	0
Merton	0
Milton Keynes	0
Newcastle upon Tyne	1
Newham	17
North Somerset	0
Norwich	0
Nottingham	2
Plymouth	1
Portsmouth	2
Reading	0
Redbridge	2
Salford	1
Sheffield	1
Slough	0
Southampton	3
Southwark	4
Sunderland	0
Sutton	1
Thanet	0
Tower Hamlets	8
Trafford	0
Waltham Forest	1
Wandsworth	4
Westminster	2
Windsor and Maidenhead	0
Others	8
Total	106

## JIT_1
Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 December 2023
Back to Contents
This worksheet contains one table. All figures are for the number of Joint Inspection Team training sessions attended by local authority officers.
Local Authority [note_18]	Intro to Fire Safety (Level 1) Number	Intermediate Fire Safety: Theoretical HHSRS assessments (Level 2 Part 1) Number	Intermediate Fire Safety: Practical HHSRS assessments (Level 2 Part 2) Number
Barking and Dagenham	0	0	0
Barnet	4	3	3
Birmingham	10	6	7
Bournemouth, Christchurch and Poole	10	4	1
Bradford	24	4	1
Brent	1	4	0
Brighton and Hove	0	0	0
Bristol, City of	10	4	2
Bromley	3	0	0
Calderdale	3	1	0
Camden	16	12	5
City of London	8	4	1
Croydon	26	3	4
Dacorum	4	2	1
Ealing	10	3	2
Gateshead	6	3	0
Greenwich	2	4	5
Hackney	18	3	4
Hammersmith and Fulham	20	3	9
Haringey	4	2	0
Harrow	1	0	0
Hillingdon	3	1	0
Hounslow	4	3	0
Ipswich	0	0	0
Islington	11	6	1
Kensington and Chelsea	0	0	1
Kingston upon Thames	3	0	0
Kirklees	2	1	0
Lambeth	16	3	7
Leeds	6	1	1
Leicester	0	0	0
Lewisham	5	2	1
Liverpool	32	12	3
Maidstone	0	0	0
Manchester	8	4	1
Merton	6	2	0
Medway	12	5	0
Milton Keynes	6	4	3
Newcastle upon Tyne	6	3	2
Newham	10	5	0
North Somerset	8	3	2
Norwich	11	7	0
Nottingham	34	8	6
Plymouth	3	2	1
Portsmouth	2	5	0
Richmond and Wandsworth	8	5	4
Reading	15	3	1
Redbridge	4	1	1
Salford	11	7	0
Sheffield	0	0	0
Slough	5	7	0
Southampton	1	0	0
Southwark	7	0	0
Sunderland	3	3	2
Sutton	2	0	0
Thanet	2	1	0
Tower Hamlets	9	9	1
Trafford	7	3	0
Waltham Forest	6	2	3
Westminster	17	5	1
Windsor and Maidenhead	8	4	0
Others	414	123	58
Total	887	315	145