## Procurement_Pipeline_Dec_2023
Business Area	Reference Number	Procurement/Contract: Contract Name	Contract Summary	Recommended Procurement Start Date	Date New Contract is Needed By	Contract Start Date	Contract End Date	Procurement Value	Procurement Route	Level Of Competition	Category (CCS)	Service Provider	Programme or Project
ASRA	C24753	Asylum Support Payments Contract (2023)	The contract is to set out terms related to delivery of Support Payment Card (SPC) Services. The services are intended to provide a payment dispersal solution in the form of a prepaid payment card to eligible Service Users.	28/07/2022	26/02/2024			16000000	CCS Framework	Mini Competition	Professional Services Other>Business and Commercial Services>Commercial Services		Other
ASRA	C25212	Construction Professional Services (RIBA 0-2)	Construction professional services	31/12/2021	01/08/2023	18/08/2023		10000000	Framework	Competed	Professional Services Other>Technical Services>Technical Services		Other
ASRA	C25349	Wethersfield Modular Accommodation	Provision of Modular Accommodation at Wethersfield	29/11/2021	30/06/2023	04/10/2023	01/10/2025	9293869	Framework	Mini Competition	Construction		Operations
ASRA	C25736	Future & FWC Modular	Provision of non-detained accommodation an ancillary facilities using modular buildings	02/06/2022	01/01/2024			320000000	Framework	Mini Competition	Construction>Construction Supplies>Prefabricated buildings and structures		Other
Border Force	C17051	Maritime Capabilities Replacement Programme	Replacement of existing Cutter and CPV Fleet	01/03/2026	01/03/2026	TBD	TBD	224000000	Not Yet Decided	Competed	Engineering Goods>Non-Military Vehicles>Non-Military Vehicles		BF – MCRP
Border Force	C18766	The Supply and Maintenance of Mobile Freight Scanning Equipment	Purchase of mobile freight scanners at BF ports	18/09/2021	18/04/2024	18/04/2024	17/04/2035	23000000	OJEU Restricted	Competed	Operational Goods>Security Equipment>Physical Security Equipment		BF - Detection Technology Equipment
Border Force	C24506	The Supply and Maintenance of Baggage Scanning in a Van Equipment	Purchase of baggage scanners in a van at BF ports	25/03/2024	25/03/2024	22/04/2024	21/04/2028	6000000	Not Yet Decided	Competed	Operational Goods>Security Equipment>Physical Security Equipment		BF - Detection Technology Equipment
Border Force	C24507	The Supply and Maintenance of Baggage Scanning - Over-belt Equipment	Purchase of Over-belt baggage scanners at BF ports	20/04/2024	20/04/2024	22/04/2024	21/04/2028	4000000	Not Yet Decided	Competed	Operational Goods>Security Equipment>Physical Security Equipment		BF - Detection Technology Equipment
Border Force	C24512	The Supply and Maintenance of Static Pallet Scanner Equipment	Purchase of static pallet scanners at BF ports	21/04/2024	21/04/2024	22/04/2024	21/04/2028	2000000	Not Yet Decided	Competed	Operational Goods>Security Equipment>Physical Security Equipment		BF - Detection Technology Equipment
Border Force	C25133	C25133 - SLEP - CPVs	Ship Life Extension Programme to enable the BF fleet of Coastal Patrol Vessels to continue in service for up to five further years	01/11/2021	01/06/2024	01/07/2024	30/06/2025	3000000	OJEU Open	Competed	Industrial Services>Transportation Support>Maintenance of Marine Craft		BF - Maritime Command
Border Force	C25139	C25139 - SLEP - Cutters	Ship Life Extension Programme to enable the BF fleet of Cutters to continue in service for up to five further years	01/11/2021	01/06/2024	01/07/2024	30/06/2025	6000000	OJEU Open	Not Yet Decided	Industrial Services>Transportation Support>Maintenance of Marine Craft		BF - Maritime Command
Border Force	C25603	JMSC Coastal Radar Data Integration	JMSC is seeking a lead radar data integrator to manage the commercial relationship with radar providers, undertake the engineering effort needed to acquire individual radar tracks, process these, and provide these to the MDA Programme.	06/10/2022	06/05/2024	06/05/2024	05/05/2029	16000000	Framework	Competed	ICT>IT Managed / Outsourced Services>Systems Management		BF - JMSC
Border Force	C25929	Charter of Vessel(s) to Support Small Boats Operations in the Dover Straits	Charter of Vessel(s) to Support Small Boats Operations in the Dover Straits	31/08/2022	31/03/2024	01/04/2024	31/03/2025	36000000	Framework	Competed	Industrial Services>Transportation Support >Marine Coastal and Inland Waterway		BF – SBOC
Corporate Services	C23909	Creative and Campaign Partner	Provision of Creative and Campaign delivery for strategic communication Directorate within the Home Office	01/01/2024	01/06/2024	01/06/2024	30/08/2026	4950000	Framework	Competed	Communications>Marketing>Marketing Services	Not awarded	Partnerships and Communications
DDaT	C15099	Future eGates	Supply and Maintenance of Future eGates at UK and juxtaposed Ports in Europe.	31/08/2024	31/08/2024	31/08/2024	31/08/2029	132000000	Competitive Dialogue	Competed	Operational Goods>Security Equipment>Physical Security Equipment		Borders IT
DDaT	C22642	Proc712: EBSA Capability Framework	Environment Build Support and Administration (EBSA) – Infrastructure and Integration (previously known as Business Services)	31/01/2024	30/04/2025	01/05/2025	30/04/2028	170000000	OJEU Restricted	Competed	ICT>Software>Software		Digital Team
DDaT	C23755	Proc772 MBTP Cyber Security Support Services	The supplier is asked to provide the following services, Security Architecture, Security Risk Management & Assurance, Security Operations.	01/02/2023	01/09/2024	01/10/2024	30/09/2027	30000000	CCS Framework	Competed	ICT>IT Managed / Outsourced Services>IT Managed / Outsourced Services		Immigration IT
DDaT	C23974	Proc 786 - MBTP Technical Architecture	The Supplier will be responsible for providing strong technical architecture leadership and delivery capability to MBTP Programmes and Projects, to enable technical delivery of Migration and Borders Vision.	31/10/2021	31/05/2024	01/06/2024	31/05/2027	85000000	OJEU Restricted	Competed	ICT>IT Managed / Outsourced Services>IT Managed / Outsourced Services		Immigration IT
DDaT	C24003	Radiological Nuclear Border Detection	A new contract for the fixed and non-fixed detection capability at borders. This will be a service and maintenance contract.	02/03/2024	31/08/2026	01/09/2026	30/09/2031	200000000	OJEU Negotiated	Competed	ICT>IT Managed / Outsourced Services>Systems Management		Cyclamen
DDaT	C24262	Central Delivery Management Services	A central contract for cross-home office call off of delivery services. RM6263	31/01/2024	24/01/2024	31/01/2024	30/01/2028	48000000	CCS Framework	Mini Competition	ICT>ICT Services>ICT Services		Cross DDaT – Optimus
DDaT	C24378	Police National Database	Contract for the continued support and maintenance of the cloud-based PND.	31/08/2024	31/03/2025	01/04/2025	31/03/2031	99900000	OJEU Restricted	Competed	Technology Services		Digital Team
DDaT	C24801	Matching Entity Resolution Engine	Provision of a Data Matching Entity Resolution Engine in support of Home Office operations	03/03/2023	01/10/2024	01/10/2024	30/09/2027	9950000	Other CCS Framework	Competed	ICT>Software>Application Software		Data Services & Analytics
DDaT	C25160	IAM Delivery Partner	Delivery partner to assist with IAM	19/05/2022	18/12/2023			3000000	CCS Framework	Mini Competition	Resources		Corporate Services
DDaT	C25441	Common Business Application Support		01/03/2024	01/09/2024			4000000					Cyclamen
DDaT	C25530	Hardware & Software Support Service Supplier	Re-procurement of scope currently in 4 contracts into one single contract for Home Office Hardware and Software Support.	01/09/2022	01/04/2024	01/04/2023	31/03/2028	30000000	Other CCS Framework	Competed	ICT>IT Managed / Outsourced Services>IT Managed / Outsourced Services		Cross-DDaT
DDaT	C25655	Software Channel Partner Contract	The contract will be a non-exclusive call-off over a 5-year term. It will have a maximum cumulative value of £90m (including non-recoverable VAT) but will have no minimum spend commitments. Moreover it is an enabling contract only.	01/03/2024	01/03/2024	08/01/2024	08/01/2029	75000000	RM6068	Mini Competition	Software and associated services		Cross DDaT – Optimus
DDaT	C25667	Data Sets for Global Trader	Shipping (container, shipping, manifest, etc) data sets (from Dun & Bradstreet, Inc) as part of the Global Trader project; which undertakes to procure services for US ONI.	03/07/2023	01/02/2024	04/03/2024	03/03/2028	5103800	Direct Award	Direct Award	ICT>ICT >ICT		MBTP DDaT – T3
DDaT	C25723	Crossing the Border Services		31/03/2024	01/04/2023			50000000					DSaB
DDaT	C25766	MBTP Cyber Security Support Services - STA	The supplier is asked to provide the following services, Security Architecture, Security Risk Management & Assurance, Security Operations.	01/06/2022	31/12/2023	01/10/2023	31/08/2024	10500000	Direct Award	Direct Award	ICT>IT Managed / Outsourced Services>IT Managed / Outsourced Services	6POINT6 LTD	Immigration IT
DDaT	C25774	MBTP Test & Release Management	The provision of a Test & Release Management Service which will include the provision of appropriately skilled resources to perform test and release management activities with MBTP	31/12/2023	01/05/2024	01/05/2024	30/04/2026	2500000	Not Known	Competed	ICT>IT Managed / Outsourced Services>IT Managed / Outsourced Services	CAPGEMINI UK PLC	Delivery
DDaT	C25909	Level 2 support for HM Passport Office Digital Services	2nd line engineering support, security monitoring services and common support services such as event monitoring.	14/12/2022	14/07/2024	14/07/2024	13/07/2026	5000000	Not Known	Not Yet Decided	ICT>IT Managed / Outsourced Services>IT Managed / Outsourced Services		HMPO DDaT
DDaT	C25979	Extension of the PSNfP contract for CAID Hosting and Associated Services	An extension to the Termination Assistance Phase of the PSNfP contract for CAID Hosting service. This will allow continuation of a service while a Procurement exercise is conducted during 2024.	31/07/2022	29/02/2024	29/02/2024	31/03/2026	7000000	Extension	Not Yet Decided		VODAFONE LTD	PPPT
Enablers	C21328	Occupational Health	Provides a range of occupational health services.	03/10/2021	04/05/2023	04/05/2023	03/05/2026	5100000	CCS Framework	Mini Competition	Personnel Related>HR Services>HR Services		LCGS (Legacy Common Goods & Services)
Enablers	C23696	Managed Print Services	Consolidated requirement for HO managed print services, combining separate HMPO and HO Central accounts. / Excludes secure printing services for UKVI (Visas) and GRO (Birth Certs etc).	20/06/2025	20/06/2025			9000000					LCGS (Legacy Common Goods & Services)
Enablers	C23769	HO Central Postal Services-Premium_Lot A	Outbound postal services for HMPO & Mail & Messenger key sites, including Premium (1st class) , Standard (2nd class) and Special Delivery (tracked and signed for).	15/09/2025	15/09/2025			20000000					LCGS (Legacy Common Goods & Services)
Enablers	C23770	HO Central Postal Services-Premium_Lot B	Outbound postal services for HMPO & Mail & Messenger key sites, including Premium (1st class) , Standard (2nd class) and Special Delivery (tracked and signed for).	15/09/2025	15/09/2025	25/09/2026	25/09/2031	20000000			Office Solutions>Post>Post Services		LCGS (Legacy Common Goods & Services)
Enablers	C23772	Provision of Fleet Management Service		31/10/2024	31/10/2024			5100000					LCGS (Legacy Common Goods & Services)
Enablers	C23778	Crown Office Supplies (Electronic office consumables)	Electronic office consumables	01/01/2024	05/04/2023			2450000					LCGS (Legacy Common Goods & Services)
Enablers	C23782	Uniforms - BF/IE, UKVI/HMPO, MoE clothing/equipment.	Home Office wide requirement to provide Uniforms for 13,00 BF & IE front-line staff as well as 1,000 HMPO & UKVI personnel. In addition, includes method of entry clothing and equipment such as Hi-viz, Batons, handcuffs and PPE Equipment	31/01/2025	31/01/2025			30000000	MOU- Cross Government Department				LCGS (Legacy Common Goods & Services)
Enablers	C23783	Vehicle Conversion Services	The Provision of Vehicle Conversion Service	01/02/2024	16/05/2023			2000000	CCS Framework	Not Yet Decided	Fleet>Vehicle Conversion>Vehicle Conversion Services		LCGS (Legacy Common Goods & Services)
Enablers	C23810	Language Services Interpreters (Translation/ Transcription Services)	Provision for Interpretation Service for HO operations / Provision of Translation/ Transcription Service	01/04/2024	28/02/2025			55000000	Framework		Professional Services>Interpretation and Translation>Translation		Common Goods and Services
Enablers	C23787	Employee Benefits and Services	Fully managed service for employee benefits and services.	16/01/2024	01/12/2024	01/12/2024	01/12/2025	23000000	Framework	Mini Competition	Personnel Related>HR Services>Benefits Administration	Not awarded	LCGS (Legacy Common Goods & Services)
Enablers	C24135	Strategic HO Recruitment Partner	End to end recruitment delivery incl. contact centre services, ATS, onboarding and IDV services for seamless candidate experience during HO recruitment process	01/05/2022	30/11/2023	30/11/2023	30/11/2024	40000000	CCS Framework		Personnel Related>HR Services>HR Services		Corporate Services
ESMCP	C17893	ESN WAN (DNSP Replacement Contract) 2024	Control rooms require wide area network to connect to ESN.		01/10/2024	01/10/2024	30/09/2029	25000000	Not Yet Decided	Not Yet Decided	Communications>Communication Services>Communication Services	Not Yet Decided	ESMCP
ESMCP	C9297	Ruggedised ESN Smartphone Handheld Device 2025	The supply of a rugged smartphone device with ESN Public Safety software enabled.		31/07/2025	31/07/2025	31/07/2032	200000000	Not Yet Decided	Not Yet Decided	ICT>Telecoms>Telecoms Equipment	Not Yet Decided	ESMCP
ESMCP	C15579	Device Logistics Services 2025	Provision of services to support the deployment and management of ESN devices on ESN network.		31/07/2025	31/07/2025	31/07/2032	10000000	Not Yet Decided	Not Yet Decided	ICT>Telecoms>Telecoms Facilities and Services	Not Yet Decided	ESMCP
ESMCP	C25250	ESN Interim Release End User Device 2025	Interim Release Handheld Device.		15/03/2025	15/03/2025	14/03/2026	5000000	Not Yet Decided	Not Yet Decided	ICT>Telecoms>Telecoms Equipment	Not Yet Decided	ESMCP
ESMCP	C24990	Interworking Gateway 2024	Interworking Gateway to bridge between ESN and Airwave.		01/07/2024	01/07/2024	30/06/2028	15000000	Not Yet Decided	Not Yet Decided	ICT>Software>Application Software	Not Yet Decided	ESMCP
ESMCP	C22926	Dual Mode Device 2025	The supply of Dual Mode devices integrating ESN and D2D capabilities.		31/07/2025	31/07/2025	31/07/2032	200000000	Not Yet Decided	Not Yet Decided	ICT>Telecoms>Telecoms Equipment	Not Yet Decided	ESMCP
ESMCP	C19730	Intrinsically Safe Device (ISD) 2025	Intrinsically safe handheld LTE device with ESN Public Safety software.		31/07/2025	31/07/2025	31/07/2032	4900000	Not Yet Decided	Not Yet Decided	ICT>Telecoms>Telecoms Equipment	Not Yet Decided	ESMCP
ESMCP	C19466	Standalone Dispatcher 2024	Control Rooms Dispatcher Solution to support future ICCS rollout.		01/07/2024	01/07/2024	30/06/2028	13600000	Not Yet Decided	Not Yet Decided	ICT>Software>Application Software	Not Yet Decided	ESMCP
ESMCP	C17894	Fixed Vehicle Devices (FVD) (Replacement Contract) 2025	Supply of Fixed Vehicle Devices (FVD), accessories and associated services.		31/03/2025	01/04/2025	31/03/2030	130000000	Not Yet Decided	Not Yet Decided	ICT>Telecoms>Telecoms Equipment	Not Yet Decided	ESMCP
ESMCP	C16362	Non-Ruggedised ESN Smartphone Handheld Device 2025	The supply of a handheld smartphone with ESN Public Safety software integrated.		31/07/2025	31/07/2025	31/07/2032	20000000	Not Yet Decided	Not Yet Decided	ICT>Telecoms>Telecoms Equipment	Not Yet Decided	ESMCP
ESMCP	C24783	ESN Calibrated Testing Solution 2024	Calibrated Testing Solution for ESN.		01/09/2024	01/09/2024	31/08/2026	7000000	Not Yet Decided	Not Yet Decided	ICT>Software>Application Software	Not Yet Decided	ESMCP
ESMCP	C25959	ESN Digital Training Application 2024	Digital app based training for ESN end users.		01/09/2024	01/09/2024	31/08/2027	9000000	Not Yet Decided	Not Yet Decided	Learning and Development>Development and Training>Development and Training	Not Yet Decided	ESMCP
HMPO	C23846	HMPO SVS procurement	Provision of Document Handling, scanning, validation and storage of documents submitted with passport applications and also the passport application if a paper application.	17/10/2022	17/05/2025	18/05/2025	17/05/2028	64000000	OJEU Restricted	Competed	Office Solutions>Record Management>Scanning Services		HMPO BPT
HMPO	C24223	HMPO Passport International Secure Delivery Service	Secure delivery of passports outside of the UK	31/01/2025	01/09/2027	01/09/2027	28/02/2028	65800000	OJEU Open	Competed	Office Solutions>Courier>Courier		HMPO SPT
HSG	C23597	Prevent- RICU Research & Evaluation Social Media Analysis	Research and Evaluation of Social media content and use for Research Information and Communications Unit (RICU) which is part of Prevent. Start date could be delayed up to 2 years subject to whether the existing contract is extended	20/08/2022	20/03/2024	22/01/2024	21/01/2028	8750000	Framework	Competed	Research		RICU
HSG	C23598	Prevent- RICU Research and Evaluation-Social Quantitative & Qualitative Analysis	Social evaluative and quantitative research for Research Information and Communications Unit (RICU) which is part of Prevent. Start date could be delayed up to 2 years subject to whether the existing contract is extended	15/10/2024	15/10/2024	15/04/2024	15/04/2028	14700000	Framework	competed	Research		RICU
HSG	C23797	DEAA (Drug Exploitation and Abuse) Research and Evaluation Services	Research and Analysis of substance and drug abuse and its effects and roles in society assessed and analysed. Start date could be earlier subject to whether the existing contract is extended	01/06/2025	01/06/2025	01/06/2025	31/05/2029	7750000	Open	Competed	Testing		Prevent
HSG	C24410	RNSP - Radiological Nuclear (RN) Detection Framework Agreement (C24410)	Framework Agreement for the supply of RN Detection Equipment including the continued service and maintenance arrangements.	31/08/2021	31/03/2024	31/03/2024	31/03/2029	70000000	OJEU Open	Competed	Radiological Nuclear		CBRNE
HSG	C25964	TO Technical Assurance	A contract for the provision of a Technical Assurance Service (TAS) to provide technical assurance of UK Telecommunication Operator (TO) systems and services that supply data to the National Communications Data Service (NCDS) end user organisations.	01/12/2022	01/07/2024	01/07/2024		4000000	Framework	Competed	Professional service		NCDS
Immigration Enforcement	C25952	Travel Services for Immigration Purposes	Contract to provide scheduled flight tickets + charters for Immigration removals.	02/04/2022	31/10/2024			20000000	OJEU Restricted	competed	Travel		Other
Migration & Borders Group	C25787	IMA Legal Support Services - GLD	Provide GLD lawyers with an effective and efficient means of securing additional legal capacity and expertise in order to augment and support the delivery of the New Plan for Immigration (NPI) with a particular focus on construction and projects.	27/02/2022	28/09/2023	13/10/2023	13/11/2024	2500000	Framework	Mini Competition	Professional Services Other>Legal>Legal Services		Commercial Team
UKVI	C19512	Customer - Secure English Language Testing (STS24)	Procurement to replace the following commercial Agreements: / SELT (2019) - 8 Concessions awarded in 2019 - C17300, C17296, C17371, C17297, C17298, C17370, C17372, C17299 (Expire 11/24)	03/04/2022	01/11/2024	01/09/2023	31/08/2026	440000000	OJEU Open	Not Yet Decided	Uncategorised>Uncategorised>Uncategorised		Other
UKVI	C21624	Customer - LitUK Test Preparation Materials Replacement (STS24)	Service concession for the Official Life in the UK Test Handbook & other digital learning materials including promotion and marketing.	21/03/2024	21/05/2025			4482448	Open	Not Yet Decided	Testing		Cust Serv & Invest
UKVI	C25313	European National Information Centre	Provides a checking services for PHD for routing points	02/04/2022	31/10/2024	01/08/2024	31/10/2029	30000000	OJEU Open	Competed	Professional Services Other>Business and Commercial Services>Business Services		Immigration IT
UKVI	C25282	Global Talent Visa	Review of existing commercial governance arrangements ie. MOU	01/10/2024	01/10/2024	01/05/2025	31/08/2027	5000000	MOU- Cross Government Department	Not Yet Decided	Uncategorised>Uncategorised>Uncategorised		Operations