Call for Proposals
FCDO statement of need – February 2024
Secondary research on the effectiveness and comparative cost-effectiveness of school feeding in low- and middle-income countries
1. Purpose
The Foreign, Commonwealth and Development Office (FCDO) requests proposals for research on the effectiveness and comparative cost-effectiveness of school feeding interventions in low- and middle-income countries.
The research is intended to:
- Provide comprehensive analysis of the effectiveness of school feeding on nutrition, education and social protection outcomes in low- and middle-income countries.
- Provide robust estimates of the cost-effectiveness of school feeding, for individual outcomes and an aggregate level.
- Compare the effectiveness and cost-effectiveness of school feeding with that of other interventions intended to achieve the same outcomes.
- Identify the circumstances in which school feeding is effective and cost-effective with regards to achieving nutrition, education and social protection outcomes, both individually and combined.
The research is expected to provide the latest evidence on school feeding along with an assessment of the quality of available evidence and any evidence gaps. Findings will be used to inform FCDO’s policy position on school feeding as well as global dialogue on school feeding programmes.
2. Background
School feeding is a popular intervention that is supported by many governments and development agencies to produce impacts on nutrition and education outcomes among children as well as broader social protection effects in low- and middle-income countries (LMICs). It has been referenced in G7 and G20 statements and brought together an international School Meals Coalition.
The most recent review of school feeding was conducted in 2021 and suggested that these programmes produce mixed effects on outcomes of interest. Wang et al. (2021) find that while school feeding has a positive impact on weight and height it has no statistically significant effect on weight-for-age or height-for-age. Similarly, school feeding was found to have a positive impact on school attendance, but programmes have no impact on learning.[1] Other interventions may be more effective in achieving these outcomes in LMICs. In the area of nutrition, for example, school feeding does not focus on the age group (first 1,000 days) in which malnutrition can be most effectively prevented. For education, teaching children at the right level is likely to be a more cost-effective intervention to improve learning outcomes.
[1] Wang D, Shinde S, Young T, Fawzi WW. Impacts of school feeding on educational and health outcomes of school-age children and adolescents in low- and middle-income countries: A systematic review and meta-analysis. J Glob Health. 2021 Sep 4;11:04051. doi: 10.7189/jogh.11.04051. PMID: 34552720; PMCID: PMC8442580.
In terms of cost-effectiveness, current evidence (Verguet et al. 2020) estimates a return of US$7 per US$ invested in school feeding in light of the multi-outcome, multi-sector returns from feeding programmes.[2] However, disaggregated data on the cost-effectiveness for each of the three different outcomes (nutrition, education, social protection) is lacking. In addition, the evidence , suffers from significant methodological limitations, reducing certainty in value for money, and school feeding programmes are often very high cost. The Global Education Evidence Advisory Panel (2023) therefore label them as ‘effective but relatively expensive’.
[2] Verguet S, Limasalle P, Chakrabarti A, Husain A, Burbano C, Drake L and Bundy DAP (2020) The Broader Economic Value of School Feeding Programs in Low- and Middle-Income Countries: Estimating the Multi-Sectoral Returns to Public Health, Human Capital, Social Protection, and the Local Economy. Front. Public Health 8:587046. doi: 10.3389/fpubh.2020.587046
This research will build on the current body of literature, integrating new primary studies, and adding a comparative lens, to provide the best possible evidence on school feeding to inform decision-making. Initial searches suggest that a number of impact evaluations of school feeding programmes have been conducted since 2020. The research will ensure that FCDO policy on this issue continues to be based on rigorous evidence.
3. Research questions and scope
FCDO has identified the following priority questions for the research. The research team should discuss the research questions with FCDO and the broader stakeholder group that FCDO intends to engage on this research topic, challenge where this is appropriate and finalise the research questions as part of the development of the approach to the research.
- How effective are school feeding programmes in LMICs in improving:
  - nutrition outcomes (nutritional status, e.g., prevention or reductions in stunting, wasting, underweight, micronutrient deficiencies, improved dietary diversity),
  - education outcomes (attendance, learning), and
  - social protection outcomes (poverty, food security, access to healthcare)?
- How cost-effective are school feeding programme in LMICs when considering nutrition, education and social protection outcomes both individually and collectively?
- How does the effectiveness and cost-effectiveness of school feeding for nutrition, education and social protection outcomes compare with other interventions that deliver these outcomes in LMICs?
- In what circumstances and for which groups is school feeding effective and cost-effective in LMICs?
FCDO has established the following preliminary criteria for the research. As with the research questions, we welcome discussion and challenge in finalising the parameters.
Criteria	Description
Population	School-age children, including adolescent girls, in low- and middle-income countries (nutrition and education outcomes) and their families (social protection outcomes); Women and children under five for comparator interventions on nutrition
Intervention	School feeding interventions, defined as interventions which include the provision of meals in schools
Outcomes	Nutrition outcomes (nutritional status, e.g., prevention or reductions in stunting, wasting, underweight, micronutrient deficiencies, improved dietary diversity) / Education outcomes (attendance, learning) / Social protection outcomes (poverty, food security, access to healthcare)

4. Key requirements
Approach to the research
FCDO expects the research to require multiple methods to fully answer the priority research questions. We are looking for research teams to propose methods that best suit the research questions, timeframe and resources available, and are open to innovative ideas. We imagine, however, that the effectiveness question might best be answered through rapid systematic review, building on recent reviews by Wang et al. (2021), Wall et al. (2022)[3], Yussuf et al. (2020)[4], and the Global Education Evidence Advisory Panel[5], among others. We anticipate that the cost-effectiveness question is likely to require an additional approach, building on the work of Verguet (2020), Kristjansson et al. (2016)[6], and others. The same is the case for the question of comparing school feeding to other interventions to achieve the same individual and collective outcomes.
[3] Wall, C.; Tolar-Peterson, T.; Reeder, N.; Roberts, M.; Reynolds, A.; Rico Mendez, G. The Impact of School Meal Programs on Educational Outcomes in African Schoolchildren: A Systematic Review. Int. J. Environ. Res. Public Health 2022, 19, 3666. https://doi.org/10.3390/ijerph19063666
[4] Yussif MT, Vong L, Pilkington K (2020) The Impact of School Feeding Programmes in Reducing Iron Deficiency Anaemia among Primary School Children in Developing Countries: A Systematic Review and Meta-Analysis of Randomized Controlled Trials. J Hum Nutr 4(1):87-105
[5] Global Education Evidence Advisory Panel (2023) Cost-effective approaches to improve global learning: what does the evidence tell us are “Smart Buys” for improving learning in low- and middle-income countries? Recommendations of the Global Education Evidence Advisory Panel (GEEAP)
[6] E.A. Kristjansson, A. Gelli, V. Welch, T. Greenhalgh, S. Liberato, D. Francis, F. Espejo, Costs, and cost-outcome of school feeding programmes and feeding programmes for young children. Evidence and recommendations, International Journal of Educational Development, Volume 48, 2016, Pages 79-83, ISSN 0738-0593, https://doi.org/10.1016/j.ijedudev.2015.11.011.
Application of methods chosen by the research team should follow relevant methodical guidelines. For example, if rapid systematic review is used, the team should refer to published guidance from organisations such as the Cochrane Rapid Reviews Methods Group[7], WHO[8] and the UK Department for Environment, Food and Rural Affairs[9], or another source listed in the recent publication on the commissioning of rapid evidence assessments published by the International Public Policy Observatory[10], or elsewhere.
[7] Rapid Reviews Methods Group Interim guidance on producing rapid reviews, Cochrane Collaboration 2020 https://methods.cochrane.org/rapidreviews/cochrane-rr-methods
[8] Rapid Reviews to Strengthen Health Policy and Systems: a Practical Guide, World Health Organization 2017 https://apps.who.int/iris/bitstream/hand le/10665/258698/9789241512763-eng.pdf
[9] The Production of Quick Scoping Reviews and Rapid Evidence Assessments; A How to Guide, UK Department for Food, Environment and Rural Affairs/ Natural Environment Research Council, 2015 https://www.gov.uk/government/publications/the-production-ofquick-scoping-reviews-and-rapid-evidence-assessments
[10] Breckon, J., Oliver, S., Vindrola, C., Moniz, T. (2023). Rapid Evidence Assessments: A guide for commissioners, funders, and policymakers CAPE, University College London.
All work must comply with FCDO ethical guidance for research, evaluation and monitoring activities.
Co-production
A successful research project will involve FCDO and other users, i.e., key UK and international organisations that work on or have an interest in school feeding interventions, such as members of the School Meals Coalition) in the design and delivery of the research. At a minimum, the research team will be expected to:
- Understand the need for the research, how it is intended to be used in FCDO and ensure that the research is asking the right questions to meet the policy need.
- Involve users in the development of the approach, gathering of data where useful, and the finalisation of research outputs to ensure the research meets needs.
- Support users to digest and apply the findings of the research in their decision-making, e.g., via the development of supplementary products and provision of advice.
We expect the research team to engage in regular meetings with FCDO’s steering group (consisting of policy leads from FCDO’s Nutrition Policy, Education Policy, and Social Protection Teams as well as oversight from FCDO’s Research and Evidence Directorate) to discuss and agree milestones in design and delivery of this work, and to consult with external stakeholders through an FCDO-led process to gather information and discuss findings. The team should deliver at least two presentations of findings during the duration of the grant. This includes a first presentation to a smaller group to facilitate debate based on draft report(s) and a second presentation to a wider group including external participants.
To maximise impact on FCDO policy-making, we expect the research team to set aside several days to engage with FCDO decision-makers via email or over calls / meetings to inform their policy processes. This would most likely occur after written outputs have been produced but could also be required at earlier stages, with possible feedback loops into the research process.
The research team is expected to identify and set out in their proposal a range of written outputs they will produce to meet FCDO and global needs. The final list of outputs will be agreed with FCDO prior to or at the start of the assignment. At minimum, they should include:
- Inception report with research protocol
- Research report(s) suitable for publication in reputable academic journals
- A policy brief – with potential for publication
- Slide decks for presentation
5. Budget and timelines
FCDO expects the project to start in April 2024, with completion by the end of the year. An expected timeline for outputs is as follows:
Table 1. Project outputs
Output	Expected date
Document/protocol setting out approach	May 2024
Draft report(s) for FCDO	August 2024
Final report(s) for FCDO	October 2024
All other outputs	December 2024

The total funding available for this research is £120,000.
6. Competition process and timeline
FCDO aims to appoint a not-for-profit organisation to deliver this research. This organisation will be selected through an accountable grant competition.
The competition will be conducted in a fair, open and transparent manner. The competition is launched with a call for proposals and the publishing of this statement of need.
Proposals will be reviewed by FCDO – and the winning bidder will be the organisation that demonstrates best fit with FCDO’s needs. An indicative timeline for the competition is set out below.
Table 2. Indicative competition timeline
Stages	Target Date
Call for proposals launched	5 February 2024
Proposal submission deadline	By 5pm 1 March 2024
Proposal moderation	W/c 4 March 2024
Outcome decided	8 March 2024
Work begins	1 April 2024

We expect to receive variety of bids from academic and other not-for profit institutions. Organisations may submit proposals either as a single entity or in partnership with other not-for-profit and private organisations. Bidding organisations will be able to withdraw at any point in the process to join a partnership. Equally, competition will not exclude unsuccessful bidders from joining the winning bidder later in the process.
8. Who we are looking for
We are looking for organisations registered as a not-for-profit, including academic institutions and think tanks, with subject matter and methodological expertise.
The accountable grant will be with one organisation - either as a single delivery partner or as a lead organisation which manages third parties in a consortium. Note that the third-party organisations may be either not-for-profit or private organisations. Organisations may be included in more than one consortium bid, but as lead delivery partner in only one of those. In others, they would need to be a third party employed by the lead partner.
It is important that all organisations (both lead and third party) share details of any conflicts of interest that may impact their proposal and set out how these would be managed.
The successful organisation must pass a due diligence assessment in areas including, but not restricted to: governance, finance, safeguarding and capacity to manage the proposed project. Consortium partners and other downstream delivery partners are likely to feature in this due diligence assessment, e.g., to test that adequate safeguarding measures are in place throughout the delivery chain.
While we welcome innovative proposals, we are looking for organisations that can meet the requirements below. Proposals will be assessed according to the three categories below:
Expertise	A strong research team would demonstrate considerable experience of the following: / Undertaking research in the fields of nutrition, education and social protection in low- and middle-income countries (essential) / Experience with school feeding, either via research or in practice (ideal) / Conducting rigorous evidence syntheses, including systematic reviews and/or rapid reviews, and/or economic evaluations / The range of empirical research methods used to evaluate and assess value for money of education, nutrition and social protection interventions / Facilitating research uptake among policy audiences, including communicating and packaging findings in effective ways, and developing clear, practical recommendations for practice and future research / Leading and/or contributing effectively to multi-disciplinary research teams
Approach to the delivery of the research	A strong proposal would set out the proposed methodological approach and deliverables. It would give confidence that the research team would: / Deliver methodologically-sound research within the timeframe provided / Demonstrate a thorough understanding of the subject matter i.e. nutrition, education and social protection interventions and outcomes / Produce both policy-relevant and publishable research outputs / Engage effectively in supporting FCDO decision-making, maximising the impact of the research in FCDO
Value for money	The budget for this piece of work should demonstrate good value for money.

9. How to apply
In addition to a completed budget using the template mentioned above, please submit a technical proposal which outlines your suitability and approach to delivering the key requirements set out in sections 4 and 5 of this statement of need, not exceeding 15 pages plus relevant annexes.
Completed proposals should be submitted to uk_evidence_fund_administration@pwc.com by 5pm GMT on Friday 1 March 2024.