## Contents
Equipment Plan 2022 supplementary data tables

	Contents
	Assessment of affordability
	Table 1 Summary of forecast cost, available spending and affordability
	Table 2 £239.8 billion forecast cost (central estimate)
	Table 3 Expected cost of foreign currency in the Plan and sensitivity to changes in exchange rates
	Table 4 Efficiency savings targets and expected delivery over the 10 years of the plan
	Table 5 Risks and opportunities detail
	Table 6 £242.3 billion available spending for the Equipment Plan
	Table 7 Planned spending split by Commands
	Table 8 Planned spending split by Operating Centres
	Table 9 Planned spending and outturn for the Equipment Plan since 2015/16
	Project Performance Summary Table 2022

	UK Ministry of Defence © Crown copyright 2022
	This publication is licensed under the terms of the Open Government Licence v3.0 except where otherwise stated. To view this licence, visit nationalarchives.gov.uk/doc/open-government-licence/version/3
	Where we have identified any third party copyright information you will need to obtain permission from the copyright holders concerned.

	Note that figures may not sum due to rounding

## Affordability
EP22: assessment of affordability and Sector Analysis

ASSESSMENT OF AFFORDABILITY
Table 1 presents the Department's assessment of the affordability of the Equipment Plan at April 2022. This is based on the central estimate of costs (detail in Table 2) and indicative variations from this cost forecast if risks or opportunities materialise. The central estimate of costs is presented in more detail in Table 2, with assumptions on foreign currency demand and efficiency savings shown in Tables 3 and 4. The potential sources of variations in costs are presented in Table 5. The available spending for the EP is shown in Table 6. Comparisons are provided with equivalent figures from Equipment Plan 2021.

Table 1 Summary of forecast cost, available spending and affordability
£billions	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30	30/31	31/32	EP22 10 year total	EP21 10 year total	Change from EP21
Forecast cost (central estimate)	21.6	21.9	22.4	23.0	24.3	24.8	26.3	25.3	25.2	24.9	239.8	233.6	6.2
Total available spending (indicative budget)	22.0	21.7	22.3	22.4	23.5	24.4	25.4	26.2	26.8	27.7	242.3	237.9	4.4
Implied variance to budget	(0.4)	0.2	0.0	0.6	0.8	0.5	0.9	(1.0)	(1.5)	(2.7)	(2.6)	(4.3)	1.8
as % budget	-1.96%	0.84%	0.13%	2.87%	3.54%	1.88%	3.70%	-3.66%	-5.71%	-9.91%	-1.06%	-1.83%
Additional cost if all risks materialise	0.8	1.1	1.3	1.7	1.5	0.9	0.4	0.6	1.1	0.6	9.9	11.5	(1.6)
Revised variance if all risks materialise	0.4	1.3	1.4	2.3	2.3	1.4	1.3	(0.4)	(0.5)	(2.2)	7.3	7.2	0.2
as % budget	1.81%	5.91%	6.08%	10.28%	9.79%	5.56%	5.29%	-1.35%	-1.72%	-7.90%	3.03%	3.02%
Reduction in costs if all opportunities materialise	(0.3)	(0.4)	(0.5)	(0.5)	(0.5)	(0.5)	(0.5)	(0.5)	(0.5)	(0.4)	(4.4)	(3.1)	(1.3)
Revised variance if all opportunities materialise	(0.7)	(0.2)	(0.4)	0.1	0.3	(0.0)	0.5	(1.4)	(2.0)	(3.1)	(7.0)	(7.4)	0.4
as % budget	-3.11%	-1.00%	-1.98%	0.44%	1.38%	-0.03%	1.82%	-5.46%	-7.44%	-11.28%	-2.89%	-3.13%

Table 2 £239.8 billion forecast cost (central estimate)

£billions	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30	30/31	31/32	EP22 10 year total	EP21 10 year total	Change from EP21
Project cost estimates assured by delivery agents	23.2	23.6	23.6	23.3	22.9	22.9	23.7	21.9	21.2	20.4	226.7	214.9	11.8
of which cost estimates before in-delivery efficiencies	24.7	25.0	25.0	24.5	23.9	23.9	24.6	22.6	21.9	20.8	236.8	225.2	11.6
of which in-delivery efficiency benefits	(1.4)	(1.3)	(1.3)	(1.2)	(1.0)	(1.0)	(0.9)	(0.7)	(0.6)	(0.5)	(10.1)	(10.3)	0.2
Project cost estimates not yet delegated to delivery agents (inc corrections and transfers)	0.8	1.1	1.4	2.0	3.5	3.8	4.7	5.1	5.4	5.6	33.3	40.6	(7.2)
Adjustment for delivery realism	(1.8)	(1.8)	(1.6)	(1.4)	(1.3)	(1.2)	(1.2)	(1.1)	(1.0)	(0.9)	(13.2)	(12.0)	(1.2)
Planned cost reductions (not yet included in project cost estimates)	(0.4)	(0.8)	(0.8)	(0.7)	(0.4)	(0.3)	(0.4)	(0.2)	(0.0)	0.3	(3.7)	(7.0)	3.3
Further efficiencies (not yet included in project cost estimates)	(0.2)	(0.3)	(0.3)	(0.3)	(0.3)	(0.3)	(0.5)	(0.5)	(0.4)	(0.4)	(3.4)	(2.8)	(0.5)
Forecast cost (central estimate)	21.6	21.9	22.4	23.0	24.3	24.8	26.3	25.3	25.2	24.9	239.8	233.6	6.2
Notes: TLBs are responsible for providing 10-year cost forecasts to Head Office for the Plan. These forecasts have three components: 1) Forecasts generated and assured by delivery organisations, for projects delegated by TLBs; 2) Forecasts generated and assured by TLBs for elements of the Plan not delegated to delivery organisations and 3) central technical adjustments. Both TLBs and delivery organisations adjust forecasts to reflect likely delivery across their portfolios of projects based on experience from previous years - these adjustments are referred to as management adjustments for delivery realism.

Table 3 Expected cost of foreign currency in the Plan and sensitivity to changes in exchange rates

£ billions	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30	30/31	31/32	EP22 10 year total	EP21 10 year total	Change from EP21
Expected cost at most likely rates (April -21)	3.9	3.9	3.7	3.5	3.3	2.9	2.8	2.6	2.4	2.0	31.2	31.8	(0.6)
10% weakening	0.0	0.2	0.3	0.4	0.4	0.3	0.3	0.3	0.3	0.2	2.8	2.6	0.2
10% strengthening	(0.0)	(0.2)	(0.3)	(0.3)	(0.3)	(0.3)	(0.3)	(0.2)	(0.2)	(0.2)	(2.3)	(2.2)	(0.1)

Table 4 Efficiency savings targets and expected delivery over the 10 years of the plan

£ billions	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30	30/31	31/32	EP22 10 year total	EP21 10 year total	Change from EP21
Total forecast benefits	(1.6)	(1.6)	(1.6)	(1.5)	(1.4)	(1.3)	(1.3)	(1.2)	(1.0)	(0.9)	(13.5)	(13.1)	(0.4)
of which high confidence initiatives included in forecast costs	(1.4)	(1.3)	(1.3)	(1.2)	(1.0)	(1.0)	(0.9)	(0.7)	(0.6)	(0.5)	(10.1)	(10.3)	0.2
of which lower confidence initiatives included in forecast costs	(0.2)	(0.3)	(0.3)	(0.3)	(0.3)	(0.3)	(0.5)	(0.5)	(0.4)	(0.4)	(3.4)	(2.8)	(0.5)

Table 5 Risks and opportunities detail

£billions	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30	30/31	31/32	EP22 10 year total	EP21 10 year total	Change from EP21
Plausible potential increases in cost
Project cost estimates assured by delivery agents *	0.6	0.7	0.8	1.1	0.9	0.4	(0.1)	0.1	0.6	0.2	5.2	7.6	(2.4)
Adjustment for delivery realism	0.2	0.2	0.2	0.1	0.1	0.1	0.1	0.1	0.1	0.1	1.5	1.1	0.4
Further efficiencies (not yet included in project cost estimates)	0.0	0.0	0.0	0.1	0.1	0.1	0.1	0.1	0.1	0.0	0.5	0.2	0.3
Unfavourable changes in exchange rates for foreign currencies (up to 10%)	0.0	0.2	0.3	0.4	0.4	0.3	0.3	0.3	0.3	0.2	2.8	2.6	0.2
Total plausible increase in costs (comparable to EP20)	0.8	1.1	1.3	1.7	1.5	0.9	0.4	0.6	1.1	0.6	9.9	11.5	(1.6)
Further potential increases and adjustments
Project cost estimates not yet delegated to delivery agents (inc corrections and transfers)	0.1	0.3	0.2	0.2	0.2	0.3	0.3	0.3	0.4	0.3	2.7	5.7	(3.1)
Planned cost reductions (not yet included in project cost estimates)	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.3	1.9	(1.6)
Dreadnought contingency arrangement **	(0.4)	(0.6)	(0.5)	(0.4)	(0.4)	(0.2)	0.1	0.3	0.3	0.3	(1.5)	(2.6)	1.1

Plausible potential reductions in cost
Project cost estimates assured by delivery agents	-	-	-	-	-	-	-	-	-	-	-	-	-
Adjustment for delivery realism	(0.2)	(0.2)	(0.2)	(0.1)	(0.1)	(0.1)	(0.1)	(0.1)	(0.1)	(0.1)	(1.5)	(0.7)	(0.7)
Further efficiencies (not yet included in project cost estimates)	(0.0)	(0.0)	(0.0)	(0.1)	(0.1)	(0.1)	(0.1)	(0.1)	(0.1)	(0.1)	(0.7)	(0.2)	(0.5)
Favourable changes in exchange rates for foreign currencies (up to 10%)	(0.0)	(0.2)	(0.3)	(0.3)	(0.3)	(0.3)	(0.3)	(0.2)	(0.2)	(0.2)	(2.3)	(2.2)	(0.1)
Total plausible decrease in costs (comparable to EP20)	(0.3)	(0.4)	(0.5)	(0.5)	(0.5)	(0.5)	(0.5)	(0.5)	(0.5)	(0.4)	(4.4)	(3.1)	(1.3)
Further potential reductions
Project cost estimates not yet delegated to delivery agents (inc corrections and transfers)	(0.1)	(0.3)	(0.2)	(0.2)	(0.3)	(0.3)	(0.4)	(0.4)	(0.4)	(0.4)	(3.0)	(3.8)	0.8
Planned cost reductions (not yet included in project cost estimates)	(0.0)	(0.1)	(0.1)	(0.0)	(0.0)	(0.0)	(0.0)	(0.0)	(0.0)	(0.0)	(0.5)	(0.9)	0.4
* The Department’s Cost Assurance and Analysis Service (CAAS), carry out an independent assessment of the cost of the Plan each year. Their estimate of expected outturn for the 10 years from 2021/22 was £7.6 billion above project team cost forecasts in total. / ** £2.6bn of the difference between CAAS estimates and project forecasts was attributable to the Dreadnought programme, which has a £10 billion contingency held by HM Treasury available to manage cost changes. This line assumes the contingency would be available to manage this pressure.

Table 6 £242.3 billion available spending for the Equipment Plan

£billions	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30	30/31	31/32	EP22 10 year total	EP21 10 year total	Change from EP21
Equipment Procurement Planning	10.0	10.6	10.7	11.1	12.1	13.1	13.4	12.8	12.6	10.8	117.2	114.5	2.8
Equipment Support Plan	11.5	11.1	11.5	11.3	11.4	11.3	11.9	12.2	12.5	14.5	119.3	115.7	3.6
Head office funding	0.5	0.0	0.1	0.0	-0.1	0.0	0.0	1.3	1.6	2.3	5.8	7.7	-2.0
Total planned spending	22.0	21.7	22.3	22.4	23.5	24.4	25.4	26.2	26.8	27.7	242.3	237.9	4.4

SECTOR ANALYSIS OF PLANNED SPENDING
Top Level Budgets (TLB) in MOD allocate their equipment budget to the individual delivery organisation teams responsible for delivering equipment and support projects. In DE&S these project teams are grouped into / ‘Operating Centres’ based on the type of equipment delivered. Table 7 shows the breakdown of TLB planned spending for the Plan by TLB, while Table 8 presents their planned spending by the seven main DE&S operating centres, Defence Digital and the SDA. / Table 9 shows spending on the Equipment Plan since 2015/16 and presents this in the context of 10-year spending plans over time.

Table 7 Planned spending split by Commands

Commands £billions	Plan	Committed/Uncommitted	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30	30/31	31/32	EP22 10 year total	EP21 10 year total	Change from EP21
Air Command	EPP	Committed	1.1	0.8	0.7	0.2	0.2	0.1	0.1	0.1	0.1	0.1	3.6	5.5	(2.0)
		Uncommitted	0.9	0.6	0.4	0.7	0.6	0.8	0.7	0.7	1.0	1.0	7.4	6.1	1.7
	ESP	Committed	2.1	1.8	1.7	1.7	1.5	1.3	1.4	1.4	1.5	1.5	15.8	16.8	(1.0)
		Uncommitted	0.1	0.5	0.5	0.5	0.9	1.2	1.2	1.2	1.0	1.2	8.3	7.8	0.6
Army Command	EPP	Committed	1.1	1.2	1.2	1.2	1.0	0.9	0.7	0.4	0.1	0.0	7.7	5.8	1.9
		Uncommitted	0.4	1.0	1.3	1.5	2.4	2.7	2.7	3.0	2.9	3.0	20.9	22.9	(2.2)
	ESP	Committed	1.2	0.7	0.6	0.4	0.1	0.0	0.0	0.0	0.0	0.0	2.9	2.8	0.1
		Uncommitted	0.3	0.4	0.5	0.8	1.2	1.1	1.1	1.3	1.3	1.3	9.1	9.7	(0.6)
DNO	EPP	Committed	0.9	0.4	0.3	0.2	0.1	0.1	0.1	0.1	0.1	0.0	2.3	3.0	(0.7)
		Uncommitted	2.1	2.7	2.7	2.9	3.1	3.3	3.6	3.5	3.4	3.5	30.9	28.3	0.6
	ESP	Committed	2.1	2.1	2.1	2.1	2.0	1.8	1.8	1.6	1.4	1.4	18.5	16.3	2.2
		Uncommitted	0.4	0.4	0.5	0.6	0.6	0.8	0.9	1.2	1.3	1.3	8.1	10.5	(2.5)
Navy Command	EPP	Committed	1.0	0.8	0.6	0.5	0.3	0.2	0.1	(0.0)	(0.0)	(0.0)	3.4	4.1	(0.7)
		Uncommitted	0.5	0.8	1.1	1.3	1.4	1.7	1.8	1.6	1.4	1.6	13.0	10.9	2.1
	ESP	Committed	1.6	1.1	1.0	0.7	0.4	0.4	0.4	0.3	0.3	0.3	6.4	5.3	1.1
		Uncommitted	0.8	1.2	1.5	1.4	1.9	1.9	2.3	2.3	2.6	2.5	18.4	17.8	0.6
Strategic Command	EPP	Committed	0.4	0.3	0.2	0.1	0.0	0.0	0.0	0.0	0.0	0.0	1.0	0.9	0.1
		Uncommitted	0.5	0.9	1.2	1.4	1.4	1.3	0.9	0.9	0.8	0.8	9.9	9.5	1.3
	ESP	Committed	1.2	0.7	0.6	0.5	0.5	0.4	0.4	0.4	0.3	0.3	5.2	4.2	1.1
		Uncommitted	1.5	1.9	2.2	2.1	1.9	2.0	2.1	2.1	2.1	2.1	20.2	20.4	(0.2)
Strategic Programmes	EPP	Committed	0.7	0.6	0.5	0.4	0.4	0.5	0.1	0.0	0.0	-	3.2	3.5	(0.4)
		Uncommitted	0.4	0.5	0.7	0.8	1.2	1.6	2.7	2.5	3.0	0.8	14.1	13.8	9.0
	ESP	Committed	0.2	0.2	0.1	0.1	0.1	0.0	0.0	0.0	0.0	0.0	0.7	0.3	0.4
		Uncommitted	0.2	0.2	0.3	0.3	0.3	0.4	0.4	0.5	0.6	2.7	5.7	3.9	(7.2)
Unallocated EP	ESP	Committed	-	-	-	-	-	-	-	-	-	-	-	1.3	(1.3)
		Uncommitted	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	(1.3)	1.3
Grand Total			21.5	21.8	22.2	22.3	23.6	24.4	25.3	25.0	25.1	25.3	236.5	230.2	5.2

Table 8 Planned spending split by Operating Centres

OC £billions	Plan	Commitment level	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30	30/31	31/32	EP22 10 year total	EP21 10 year total	Change from EP21
Air Support	EPP	Committed	0.3	0.3	0.2	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.8	1.7	(0.9)
		Uncommitted	0.3	0.3	0.1	0.1	0.1	0.1	0.1	0.1	0.0	0.0	1.2	1.4	(0.0)
	ESP	Committed	1.0	1.0	0.9	0.9	0.9	0.8	0.9	0.9	0.9	0.9	9.2	9.1	0.1
		Uncommitted	0.2	0.3	0.3	0.4	0.6	0.5	0.5	0.5	0.5	0.6	4.5	4.6	(0.2)
Combat Air	EPP	Committed	0.8	0.5	0.4	0.2	0.1	0.1	0.1	0.1	0.1	0.1	2.6	3.5	(1.0)
		Uncommitted	0.3	0.5	0.4	0.6	0.4	0.4	0.6	0.7	0.8	0.8	5.6	1.4	4.4
	ESP	Committed	0.8	0.6	0.5	0.5	0.5	0.3	0.3	0.3	0.3	0.3	4.5	5.3	(0.8)
		Uncommitted	0.3	0.5	0.5	0.5	0.6	0.8	0.9	0.9	0.9	0.9	6.7	6.2	(0.1)
Defence Digital	EPP	Committed	0.2	0.2	0.1	0.1	0.0	0.0	0.0	0.0	0.0	0.0	0.5	0.7	(0.1)
		Uncommitted	0.5	0.7	0.9	1.1	1.2	1.3	1.2	1.1	0.9	0.8	9.8	9.6	(0.0)
	ESP	Committed	0.8	0.2	0.2	0.1	0.1	0.0	0.0	0.0	0.0	0.0	1.6	2.4	(0.8)
		Uncommitted	1.2	1.7	1.7	1.7	1.8	1.6	1.6	1.6	1.6	1.7	16.1	14.2	1.9
Helicopters	EPP	Committed	0.3	0.2	0.2	0.3	0.4	0.2	0.1	0.0	0.0	-	1.7	0.8	1.0
		Uncommitted	0.1	0.3	0.2	0.1	(0.0)	(0.0)	0.1	0.2	0.2	0.4	1.6	1.8	(0.3)
	ESP	Committed	0.6	0.5	0.5	0.3	0.0	0.0	0.0	0.0	0.0	0.0	1.9	2.0	(0.1)
		Uncommitted	0.2	0.2	0.2	0.5	0.8	0.7	0.8	0.8	0.8	0.5	5.6	6.0	(0.3)
Integrated Battlespace	EPP	Committed	0.2	0.1	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.0	0.3	0.4	(0.1)
		Uncommitted	0.3	0.4	0.4	0.4	0.3	0.2	0.1	0.1	0.1	0.1	2.4	2.5	(0.1)
	ESP	Committed	0.1	0.1	0.1	0.1	0.1	0.1	0.1	0.1	0.1	0.1	0.9	0.8	0.0
		Uncommitted	0.2	0.3	0.4	0.3	0.3	0.3	0.3	0.3	0.3	0.3	2.9	2.9	0.0
Land Equipment	EPP	Committed	0.8	1.0	0.9	0.9	0.7	0.7	0.6	0.4	0.1	0.0	6.0	5.0	0.9
		Uncommitted	0.2	0.5	0.5	0.6	0.6	0.5	0.6	0.5	0.6	0.5	5.0	5.6	(0.6)
	ESP	Committed	0.4	0.3	0.3	0.1	0.1	0.0	0.0	0.0	0.0	0.0	1.3	1.5	(0.2)
		Uncommitted	0.3	0.4	0.4	0.6	0.6	0.6	0.6	0.6	0.5	0.5	5.1	5.7	(0.6)
Nuclear Enterprise	EPP	Committed	0.9	0.5	0.3	0.2	0.1	0.1	0.1	0.1	0.1	0.0	2.4	3.0	(0.6)
		Uncommitted	2.1	2.7	2.7	2.9	3.1	3.3	3.6	3.5	3.4	3.5	30.9	28.3	0.6
	ESP	Committed	2.5	2.4	2.4	2.3	2.1	1.9	1.8	1.6	1.5	1.5	20.0	16.9	3.1
		Uncommitted	0.8	1.0	1.2	1.1	1.3	1.5	1.7	1.9	2.0	2.0	14.5	14.6	(2.2)
Ships	EPP	Committed	1.0	0.8	0.6	0.5	0.3	0.2	0.1	(0.0)	(0.0)	(0.0)	3.4	4.0	(0.5)
		Uncommitted	0.2	0.4	0.6	0.8	0.8	1.0	1.0	1.0	0.8	0.7	7.3	5.6	1.4
	ESP	Committed	0.6	0.4	0.3	0.3	0.2	0.1	0.2	0.1	0.0	0.0	2.2	1.4	0.7
		Uncommitted	0.6	0.8	0.8	0.8	0.9	1.0	1.1	1.1	1.2	1.2	9.4	9.9	(0.8)
Weapons	EPP	Committed	0.8	0.7	0.6	0.4	0.4	0.5	0.1	0.0	0.0	-	3.4	3.8	(0.4)
		Uncommitted	0.1	0.2	0.4	0.5	0.6	0.7	1.4	0.9	1.0	0.8	6.7	6.8	0.1
	ESP	Committed	0.7	0.2	0.1	0.1	0.1	0.0	0.0	0.0	0.0	(0.0)	1.3	1.0	0.3
		Uncommitted	(0.0)	0.4	0.5	0.5	0.6	0.7	0.7	0.8	0.9	1.0	6.0	5.9	0.0
Other	EPP	Committed	0.0	0.0	0.0	0.0	-	-	-	-	-	-	0.0	0.0	0.0
		Uncommitted	0.7	0.3	0.9	1.4	2.9	3.7	3.8	4.1	4.7	3.0	25.6	28.7	7.0
	ESP	Committed	0.8	0.7	0.7	0.7	0.7	0.6	0.6	0.6	0.6	0.6	6.7	6.6	0.2
		Uncommitted	(0.7)	(0.9)	(0.6)	(0.8)	(0.4)	(0.3)	(0.1)	0.1	0.4	2.3	(1.0)	(1.0)	(5.8)
Grand Total			21.5	21.8	22.2	22.3	23.6	24.4	25.3	25.0	25.1	25.3	236.5	230.2	5.2

Table 9 Outturn for the Equipment Plan since 2015/16

£ billions	15/16	16/17	17/18	18/19	19/20	20/21	21/22	22/23	23/24	24/25	25/26	26/27	27/28	28/29	29/30	30/31	31/32
Outturn	14.7	14.7	15.3	16.2	16.3	18.1	19.9
EP16		14.6	15.9	16.5	17.3	18.5	19.1	18.9	19.1	19.0	18.9
EP17			15.3	16.0	17.2	18.4	18.8	18.6	19.1	18.8	18.7	19.0
EP18				15.9	17.2	18.7	19.2	18.8	19.5	19.1	18.9	19.1	20.1
EP19					16.2	18.6	19.8	19.4	19.5	19.6	19.1	19.0	18.9	18.4
EP20					17.1	18.3	18.8	19.4	20.0	19.6	19.6	19.4	19.0	19.1
EP21					21.3	22.3	22.1	22.4	22.4	23.5	24.8	25.3	26.7	27.1
EP22					22.0	21.7	22.3	22.4	23.5	24.4	25.4	26.2	26.8	27.7

## PPST
Project Performance Summary Table 2022

Portfolio	Project	Description		Cost					Time					Key User Requirements (KURs)
				Expected cost / to completion / at approval	Current forecast / cost to / completion	Total cost / variation to / completion		In-year variations attributed to FOREIGN EXCHANGE (FOREX)	In-year variations not attributed to 'Delivery Organisations' (exc FOREX)	In-year variations attributed to 'Delivery Organisations' (exc FOREX)	In-year change on costs to completion		Expected / In-Service / Date / at approval	Current forecast / In-Service / Date	Total time / variation / against / approval	In-year variations not attributed to 'Delivery Organisations'	In-year variations attributed to 'Delivery Organisations'	Total / In-year / change to / In-Service / Date		Number of Key User Reqts	To be met	To be met, with risks	Total number of Key User Reqts to be met	Not to be met	In-year change, to be met, with risks	In-year change - not to be met
				(£m)	(£m)	(£m)		(£m)	(£m)	(£m)	(£m)				(months)	(months)	(months)	(months)

DEFENCE EQUIPMENT & SUPPORT (DE&S)
-	AJAX (Specialist Vehicles)	Armoured Fighting Vehicle		5,480	5,379	-101		0	0	24	24		Jul-20	Mar-22	20	0	9	9		11	0	11	11	0	0	0
-	Apache Capability Sustainment Programme	Sustainment of Attack Helicopter		1,778	1,680	-98		-7	0	-4	-10		Apr-22	May-23	13	9	4	13		0	0	0	0	0	0	0
-	Challenger Life Extension Programme	Main Battle Tank		1,422	1,408	-14		-12	0	-2	-14		Nov-27	Nov-27	0	0	0	0		10	10	0	10	0	0	0
-	E7 Wedgetail	Airborne Early Warning and Control Aircraft		2,156	1,890	-265		2	-195	-1	-194		Dec-23	Mar-24	3	0	3	3		8	8	0	8	0	0	0
Complex Weapons	Brimstone Capability Sustainment Programme	Sustainment Programme of Air to Ground Missile		521	519	-2		0	0	1	1		Oct-22	Feb-25	28	0	16	16		8	8	0	8	0	0	0
	Brimstone 3B	Sustainment Programme of Air to Ground Missile		347	317	-31		0	11	0	11		ISD not set at Main Gate					11	8	1	9	2	0	0
	Spear Capability 3	Fighter Air to Ground Missile		1,401	1,384	-17		-6	0	1	-5		Jun-27	Jun-27	0	0	0	0		8	8	0	8	0	0	0
	ASRAAM Sustainment (MG1)	Sustainment Programme of Air to Air Missile		415	411	-4		0	0	1	1		Nov-18	Apr-22	41	0	1	1		8	8	0	8	0	0	0
-	Marshall	Air Traffic Control System		1,890	1,969	79		0	0	-19	-19		Feb-17	Jan-21	47	19	0	19		7	7	0	7	0	-1	0
-	Mechanised Infantry Vehicle (MIV)	Mechanised Infantry Vehicle		4,076	3,919	-157		15	716	-188	543		Oct-25	Oct-25	0	0	0	0		13	13	0	13	0	0	0
-	Protector	Unmanned Aircraft		704	1,058	354		-15	0	0	-15		Jul-21	Nov-23	28	0	0	0		14	14	0	14	0	0	0
-	Sky Sabre	Ground Based Air Defence System		618	666	48		0	0	0	0		Mar-20	Aug-21	17	0	0	0		10	10	0	10	0	0	0
-	Type 26 Frigates	Global Combat Ship		3,700	3,933	233		0	0	259	259		Oct-27	Oct-28	12	0	12	12		10	1	9	10	0	0	0
-	Type 31 Frigates	General Purpose Frigate		1,986	1,985	-1		0	0	2	2		May-27	May-27	0	0	0	0		11	11	0	11	0	0	0
DEFENCE EQUIPMENT AND SUPPORT (DE&S) TOTAL				26,494	26,518	24		-22	532	75	584		-	-	209	28	45	73		129	106	21	127	2	-1	0
SUBMARINE DELIVERY AGENCY (SDA)
-	Astute Boats 4-7	Attack Submarine		5,859	6,967	1,108		0	0	10	10
-	Core Production Capability	Core Manufacturing Facility		1,385	1,822	437		0	0	46	46		Jun-26	Oct-25	-8	0	0	0		2	2	0	2	0	0	0
-	Dreadnought	Ballistic Submarine		21,938	21,938	0		0	0	0	0
SUBMARINE DELIVERY AGENCY (SDA) TOTAL				29,182	30,728	1,546		0	0	56	56				-8	0	0	0		2	2	0	2	0	0	0
DEFENCE DIGITAL (DD)
-	New Style of IT (Deployed)	Information Capability to the Frontline		722	788	67		0	26	9	35		Jun-19	Dec-21	30	0	-4	-4		9	9	0	9	0	0	-1
-	SKYNET 6A	UK Military Satellite Communication Capability		844	808	-36		0	0	-28	-28		Aug-26	Aug-26	0	0	0	0		6	0	6	6	0	6	0
DEFENCE DIGITAL (DD) TOTAL				1,566	1,596	30		0	26	-19	7				30	0	-4	-4		15	9	6	15	0	6	-1
TOTALS				57,242	58,841	1,600		-22	558	112					231	28	41	69		146	117	27	144	2	5	-1
					OVERALL TOTAL		647					OVERALL TOTAL					99%

Publication notes:

Rounding: The values within each field in the cost table are rounded to the nearest £1m.

In-Service Date (ISD): is defined by each project within its Business Case and can be Initial Operating Capability (IOC) or Equipment Delivery Date (EDD).

Defence Equipment & Support

Ajax: The current forecasted delays to ISD are up to 31st March 22, due to the ongoing noise and vibration issues work is continuing to re-baseline the programme which will then be reflected in a revised ISD for PPST23 publication.
Brimstone 3B: As an outcome of the Defence Integrated 21 Review an ISD will no longer be set at Main Gate 2 due to the decision to Off-Ramp B3B from Apache.
Mechanised Infrantry Vehicle: Includes an increase of £23.44m to approvals since PPST 21 to deliver an additional 100 Boxer Vehicles in line with Defence Integrated 21 Review outcomes.
Type 26 Frigates: Information relates to Batch 1 approvals only and covers the manufacture of the first batch of three ships through a single source contract with BAE Systems, Batch 2 approvals will be reported in PPST 23.

Submarine Delivery Agency

Dreadnought: Information reflects the phased approval regime and the current Approved Budgetary Limit (up to and including Delivery Phase 3+) for the programme. The overall budget envelope for the Dreadnought programme was set at SDSR15 at £31Bn plus a £10Bn contingency.

Foreign Exchange Rate (FOREX)

Seven projects within the PPST population have a separate foreign exchange rate (FOREX) risk provision held outside of their approvals to deal with potential FOREX volatility. Where there have been FOREX variations on projects since approval these have been included in the projects “Current forecast cost to completion” figures to provide an aggregate forecast cost to deliver the EP 22.

Apache: £197m FOREX variations incurred since approval. Apache has a separate FOREX risk provision held outside of approval of £142m.

E7 Wedge Tail: £88m of FOREX variations incurred since approval. E7 Wedge Tail has a separate FOREX risk provision held outside of approval of £113m.

Protector: £116m of FOREX forecast costs incurred since approval. Protector has a separate FOREX risk provision held outside of approval of £58m.

Four further projects have a FOREX risk provision held outside their approval’s limit but have not yet exceeded their FOREX risk provision held inside their ABL of :

Challenger Life Extension Programme: £35m

Brimstone 3B: £4m

Spear Capability 3: £12m

Mechanised Infantry Vehicle: £92m
To note - In reference to Mechanised Infantry Vehicle in-year variation of £543m, this is the difference between a forecast outturn of £3,376m which should have been reported in the “forecast to completion column” in PPST 21.