## Cover Sheet
[5 empty] | OGP2023 | OGP2022
Reference Class Forecasting and Benchmarking Workbook
Version 1.2
Introduction
This workbook will enable you to generate an RCF and benchmark cost for your project; positioning current project statistics within a range
For further background on the principles and how to use RCF refer to Optimism Bias and Contingency at Homes England
Guidance: In the Input Tab:
1 | Note project title, maturity, what costs are based on, your name and the date of completing this workbook
2 | Enter the cost composition for your scheme - only costs to go should be included (no historical/sunk costs)
3 | Note which elements of work will be affected by Modern Methods of Construction (MMC) and the extent as a %age (use a general average across all aspects affected - advise if this is difficult to determine)
4 | If you wish to see a filtered RCF, open Columns I to L and exclude the items that you wish to ignore
5 | Add key schedule information
Outputs
6 | View the outputs in the Output tab.
Outputs
1 | You can extract key information for your project in the Analysis Stats tab - select your general type of project from the drop down menu under "Project Type" and the type of information you would like
2 | Consider the output of the curves
3 | Print the Input and Output and Analysis Stats tabs as necessary
Considerations:
| a) | How do the RCF suggested levels of contingency/ float compare to current provisions?
| b) | Will you reset cost/time to the analysis outputs by adding further cost or time or find cost or time within current expectations?
| c) | Have you identified key risks to manage?
| d) | How will you track management of these risks?

## Input
| Scheme: | [6 empty] | Filtered RCF |  |  | Open for filtering costs
| Maturity: | Point of Contract | Cost based on: | [7 empty] | This can be used to overlay an RCF for a subset of the costs (eg HE costs only)
Further internal approvals at the point of contract.
| Completed by: |  | Date: | [5 empty] | RCF Comp Recalc.
Copy data from cost build up
| Cost Category | Primary Headings | Further breakdown (where relevant) | Cost | %age total | MMC Effect |  | Exclude in RCF: | Cost | %age total
Notes Open rows to populate relevant areas | Development Costs: serviced Development platform (core components of a Development appraisal) |  |  | £ |  |  |  |  | £k
| Land Costs | Acquisition Cost |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Agent and Legal fees |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | SDLT |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Access Rights |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Ransom Payments |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Option Fees |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Overage |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Additional Land Acquisition |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
| Planning | Outline Planning |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Reserved Matters Planning |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Other Planning Costs |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
This is cost not percentage | Build Cost (Base build total cost) | Standard construction and foundations |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Preliminaries apportioned |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Contractors' overheads and profits (not developers’) |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
Breakdown if feasible | Building | Total | Nature unspecified |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  | Breakdown if feasible: | Residential |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  |  | Custom build properties |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  |  | Building affordable housing |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  |  | Commercial (shop units/ offices space |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  |  | Light industrial (warehousing/ distribution) |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  |  | Film studios/ creative space |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  |  | Community/ public buildings |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
| External Works | Site preparation works, Roads, paths, paving’s and surfacing, Soft landscaping, planting and irrigation systems, fencing, external drainage and utilities and minor building works and ancillary building works | Associated with houses |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  |  | Associated with apartments |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
| Management costs |  | General |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  |  | Maintenance & protection of a heritage asset |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
|  |  | Other holding costs/ estate management |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
| Fees | Professional Fees: General |  |  | #DIV/0! |  | 0 |  | 0 | #DIV/0!
| Subtotal (direct costs): |  |  | 0 |  |  |  |  | 0
| Contingency | Contingency on build cost and Externals
| Sales and Marketing (%age uplifts) | Marketing
Agent Fees
Legal Fees
Letting Agent Fees
Letting Legal Fees
| Finance Costs | % rate of finance and amount of finance
| Purchasers Costs | % of Gross Commercial Value
| Subtotal (contingencies/ uplifts): |  |  | 0
| Subtotal (Development costs): |  |  | 0 |  |  |  |  | 0
Modern Methods of Construction:
| MMC (Quantum of above costs using MMC methods) | Cat 1 - Pre-manufacturing 3D Structural Systems | Enter as proportions of costs (included in other items) |  | On (proportion of costs): | 0%
Cat 2 - Pre-manufacturing 2D Structural Systems - open and closed panel
Cat 3 - Pre-manufacturing Structural Assemblies and Sub-Assemblies
Cat 4 - Additive Manufacturing - Structural and non-structural
Cat 5 - Pre-manufacturing non structural pods and sub-assemblies
Cat 6 – Traditional Building Product Led Site Labour reduction/ productivity improvements
Cat 7 – Site Process Led Site Labour reduction/ productivity/ assurance improvements
Site Works and Abnormal Costs [may not be required on all sites, may be undertaken by plot developer or a Master Developer]
| Site Preparation | Demolition |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Enabling works |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Remediation and Decontamination [Select if simple, complex/ brownfield or heavily contaminated] |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Due Diligence (survey works) |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Archaeology/Heritage surveys |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Foundations | Standard foundations |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Abnormal Foundations |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Infrastructure and highways | Highway and Transport Design Works |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Noise and Vibration Design Works |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | S278 works |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
Breakdown as feasible |  | Offsite Highways works (breakdown by type of works as feasible) | Unspecified or mixed |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Footpaths |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Cycle paths |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Parking (surface) |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Urban roads - standard |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Urban roads - complex |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Rural roads - standard |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Rural roads - complex |  | #DIV/0! |  |  |  | 0 | #DIV/0!
Breakdown as feasible |  | Public Transport | Unspecified or mixed |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Rail |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Stations |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Buslanes |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Spine Road |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Roundabouts |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Junctions |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
Breakdown as feasible |  | Other civil works | Unspecified or mixed |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Bridges/ other structures |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Tunnels |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Earthworks |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Part 1 Claims |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
Breakdown as feasible | Utilities | Unspecified (general allowance) |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
Breakdown as feasible |  | Electricity | General |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Disconnection and abandonment cost |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Diversion cost |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | New supplies which includes substations, reinforcement, etc. |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Services and connection costs legal fees for wayleaves, licences, supply agreements, compensation claims |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Easement costs |  | #DIV/0! |  |  |  | 0 | #DIV/0!
Breakdown as feasible |  | Gas | General |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Disconnection and abandonment cost |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Diversion cost |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | New supplies which includes substations, reinforcement, etc. |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Services and connection costs |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Legal fees for wayleaves, licences, supply agreements, Compensation claims |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Easement costs |  | #DIV/0! |  |  |  | 0 | #DIV/0!
Breakdown as feasible |  | Water | General |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Disconnection and abandonment cost |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Diversion cost |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | New supplies which includes substations, reinforcement, etc. |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Services and connection costs |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Legal fees for wayleaves, licences, supply agreements, compensation claims |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Easement Costs |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | District Heating | Capital cost, plot costs, legals and heat charger |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Telecoms | Upgrading cables |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Renewable Energy | CHP, non plot specific EV charging or solar |  | #DIV/0! |  |  |  | 0 | #DIV/0!
Breakdown as feasible | Drainage | General |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Pumping Station |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | SUDS/Swales/Tanks/Attenuation | Includes landscaping features associated with attenuation ponds |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  |  | Beyond plot specific measures included in externals (such as permeable drives) |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Sewers | Includes Surface and Foul beyond standard included in Externals and/or spine road |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Flood Risk | Includes land raising/barriers/defence |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Ecology | Ecology Design Work |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Arboriculture | Covers tree surgery and/or tree protection works |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Mitigation | i.e. offsite contribution, Habitat Regulation Assessment, |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Nitrogen neutrality |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Water Neutrality |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Biodiversity Net Gain (BNG) |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Invasive Species |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Birds and Bats |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | SANGS |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Invertebrates/vertebrates | Newts – including fencing and ladders |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Mammals | Dormice, badgers |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Landscaping/ Public Realm | Public Realm / Public Open Space | Estate costs/shared areas not included in external works including landscaping wildflower meadows. |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Play areas / Outdoor sports | in addition to any S. 106 requirements |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Endowment | for long term management |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Public Art | in addition to any S. 106 requirements |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Surveys and Fees | Valuation and Appraisal Advice | (beyond standard house building Professional fees and not included in specialist categories above) |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Legal Advice | state aid advice, specific questions on ransoms etc. |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Development Management / Master Developer Fees | These include fees paid to development managers/ Master Developers of the site or collaboration costs. |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Health and Safety Advice | e.g. highways, reservoirs |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Communications Fees | Fees for example related to any PR on the site but not planning related costs. |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Sales and Marketing | Agent Fees | Master Developer Disposal Fees as a percentage of Receipts |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Legal Fees | Master Developer Disposal Fees as a percentage of receipts |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Profit (inclusive of any developer Overheads, aftercare and sales incentives) | Profit on Market Sale |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Profit on Affordable | Broken down by sub-tenures |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Profit on Commercial |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Profit on PRS |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Total Blended Profit |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Internal Rate of Return (IRR) |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Development Management Fee |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Return On Capital Employed (ROCE) |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Community Infrastructure Levy (CIL) | CIL Residential | Exclude or filter CIL if paid or amount agreed and no risk of being greater than estimated. See note. |  | #DIV/0! |  |  | Exclude | 0 | #DIV/0!
|  | CIL Commercial |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Section 106 Obligations | Roof Tax | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Affordable Housing Offsite Payment | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Community Facilities | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Employment and Skills | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Healthcare | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Highways / Transport | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Education (primary and secondary) | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Libraries | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Public Realm/Open Space | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Monitoring Fee | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Play areas | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
|  | Sports Fields | Only use for funding for S106, not building infrastructure directly |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Other Abnormal Costs |  |  |  | #DIV/0! |  |  |  | 0 | #DIV/0!
| Subtotal (site works and abnormal costs - direct costs): |  |  | 0 |  |  |  |  | 0
Contingencies etc
| Project Contingency Allowance | Contingency | Include the total amount here
Non Recoverable VAT
| Subtotal contingencies and VAT |  |  | 0
| Total (Site Works and Abnormal Costs) |  |  | 0 |  |  |  |  | 0
ALL WORKS
| Total excluding contingencies and percentage add ons |  |  | 0 |  |  |  |  | 0
| Total contingencies and percentage add ons |  |  | 0 |  |  |  |  | 0
| Grand Total |  |  | 0 |  |  |  |  | 0
Schedule Input
| Date now: |  | 0
Planned date for work to start:
| Is there any free float in this period (with no planned activities): |  |  | Months
Planned work completion:
| State any further free float in this period |  |  | Months
Note on B6: This is the heading that we propose to use across all relevant systems/documents/processes
Note on C8: Purchase price including Planning Risk discounts (Actual price to be paid)
Note on C9: Purchasers Agent and Legal fees
Note on C10: SDLT rates as appropriate
Note on C11: Easements, Wayleaves
Note on C16: Costs for securing Outline Planning Permission
Note on C17: Costs for securing Reserved Matters planning
Note on C18: Pre-app, allocation promotion, SPD/planning brief, design incl B4Life, Listed Buildings surveys, fees associated with S278,38 or 104, highway, noise, and desk top archaeology surveys.
Note on C35: All fees for professionals typically involved with standard house building e.g. Architect, QS, engineer, PM, Highway Design, and NHBC/equivalent costs
Note on C40: Marketing cost per unit or % of private GDV
Note on C41: Disposal Fees as a percentage of private GDV
Note on C42: Disposal Fees as a percentage of private GDV
Note on C53: A systemised approach based on volumetric construction involving the production of three-dimensional units in controlled factory conditions prior to final installation. Volumetric units can be brought to final site in a variety of forms ranging from a basic structure only to one with all internal and external finishes and services installed, all ready for installation.
Note on C54: A systemised approach using flat panel units used for basic floor, wall and roof structures of varying materials which are produced in a factory environment and assembled at the final workface to produce a three-dimensional structure. The most common approach is to use open panels, or frames, which consist of a skeletal structure only, with services, insulation, external cladding and internal finishing being installed on-site. More complex panels - typically referred to as closed panels - involve more factory-based fabrication and include lining materials and insulation. These may also include services, windows, doors, internal wall finishes and external claddings. The system includes structural performance for primary walls and all floors(note-this excludes unitised or composite external walling systems that are not load bearing included in category 5)
Note on C55: Use of pre-manufactured structural members made of framed or mass engineered timber, cold rolled or hot rolled steel or pre-caste concrete. Members to include load bearing beams, columns, walls, core structures
Note on C56: The remote, site based or final workface based on printing of parts of buildings through various materials based on digital design and manufacturing techniques.
Note on C57: A series of different pre-manufacturing approaches that includes unitised non-structural walling systems, roofing finish cassettes or assemblies (where not part of a wider structural building system), non-load bearing mini-volumetric units (sometimes referred to as 'pods') utility cupboards, risers, plant rooms as well as pre-formed wiring looms, mechanical engineering composites, would fall into this category.
Note on C58: Includes traditional single building products manufactured in large format, pre-cut configurations or with easy jointing features to reduce extent of site labour required to install.
Note on C59: This category is intended to encompass approaches utilising innovative site-based construction techniques that harness site process improvements falling outside the five main pre-manufacturing categories 1-5 or materials innovation in Category 6. This category would also include factory standard workface encapsulation measures, lean construction techniques, physical and digital worker augmentation, workface robotics, exoskeletons and other wearables, drones, verification tools and adoption of new technology led plant and machinery.
Note on C62: includes demolition to slab and or below ground, substructures. Planning costs for demolition should be included in planning fees.
Note on C63: Including cut and fill and ground stabilisation, preparing sub-surfaces, site clearance, including all works to existing trees and TPOs etc.
Note on C64: Remediation and decontamination including monitoring costs
Note on C65: Incl site investigations, topo survey, noise surveys, UXO, building condition survey
Note on C69: Including Transport and Highway Assessments
Note on C71: Means works undertaken by developer
Note on C72: incl. contribution to strategic infrastructure; works undertaken by others
Note on C80: Works to be carried out by the developer on Public Transport not included in S106 Costs
Note on C84: Infrastructure not serving individual plots directly i.e. not local infrastructure included under externals. Including standard sewers. Will include fees, contingencies and prelims
Note on C86: Additional junctions or junctions works over and above standard
Note on C91: compensation for depreciation in the value of an interest in land which is attributable to the use of public works i.e construction of a highway
Note on D115: (likely to be removed in due course as costs become standard and are reflected within base build costs)
Note on B152: Sam Franzen: Exclude if CIL is already paid. If there is no risk of CIL being greater than expected (CIL already agreed), then use filter columns opposite to remove CIL risk from the calculation.
Note on B154: Section 106 should only be used for funding towards S106 works carried out by others. If HE are directly building works required by S106 and hold the construction risk then the cost of said works should be included in the approrpiate infrastructure budget line. All should include refs to indexation and timing.
Note on C171: Can be applied to any site works cost. Different rates can be applied to different items. Supporting reports etc. should identify whether individual costs elements include contingency allowances or whether these should be added globally. Nb overarching Contingency and Risk framework under preparation which will provide further guidance here

## Output
Homes England 1.0 Mar 23 | [6 empty] | Output | [16 empty] | OGP2020
| Scheme name: | 0
| Ref: | [6 empty] | Desired RCF Values: |  |  |  |  | Blended | RCF50 | %age Contingency: |  | #DIV/0! | RCF80 | %age Contingency: | #DIV/0! |  | Mean: (1) | #DIV/0!
[13 empty] | MMC Factored |  |  |  | #DIV/0! |  |  | #DIV/0! |  |  | #DIV/0!
| Total budget (€): | 0 |  | Filtered costs (if used) | [8 empty] | Filtered |  |  |  | #DIV/0! |  |  | #DIV/0! | #DIV/0! |  | #DIV/0!
|  |  | RCF used: | [6 empty] | All Costs |  | Filtered
| Development Stage: | Point of Contract | FBC |  |  |  |  | Pvalue | %age | Blended RCF | MMC Factored | Filtered RCF (no MMC effect) |  | RCF50 | RCF80 | Cited Risk/ Cont % |  | RCF80 | [7 empty] | Risk/contingency
| Scheme Composition | Estimated £ | or %age | Estimated £ | or %age
| Land Costs | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P5 | 5% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Planning | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P10 | 10% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Build Cost (Base build total cost) | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P15 | 15% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Building | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P20 | 20% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| External Works | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P25 | 25% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Management costs | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P30 | 30% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Site Preparation | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P35 | 35% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Foundations | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P40 | 40% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Infrastructure and highways | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P45 | 45% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Utilities | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P50 | 50% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Drainage | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P55 | 55% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Ecology | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P60 | 60% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Landscaping/ Public Realm | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P65 | 65% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Surveys and Fees | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P70 | 70% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Sales and Marketing | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P75 | 75% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Profit (inclusive of any developer Overheads, aftercare and sales incentives) | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P80 | 80% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Community Infrastructure Levy (CIL) | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P85 | 85% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Section 106 Obligations | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P90 | 90% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Other Abnormal Costs | 0 | #DIV/0! | 0 | #DIV/0! |  |  | P95 | 95% | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| Total direct costs (exc %age uplifts) | 0 | #DIV/0! | 0 | #DIV/0! |  |  | Mean |  | #DIV/0! | #DIV/0! | #DIV/0!
| MMC Proportion | Extent of MMC | 0%
|  | On %age of works: | 0%
| VAT | 0
| Fees & costs (%age addition) | 0 | #DIV/0!
| Total | 0 | [5 empty] | Confidence in cited contingency:
[8 empty] | Amount |  | Blended RCF | MMC Factored | Filtered RCF
| Contingencies | 0 | #DIV/0! |  |  |  |  | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0!
| Total Estimate | 0 | TRUE
Project notes
RCF Modelling Notes
1. Mean is trimmed arithmetic average (P5-95)
RCF50
RCF80
RCF80
Schedule RCF
[13 empty] | Blended | RCF50 | %age float: |  | #DIV/0! | RCF80 | %age float: | #DIV/0! |  | Mean: (1) | #DIV/0!
| Timenow: | 0 | [17 empty] | 0%
Key Dates
[8 empty] | Pvalue | %age | Blended RCF |  |  |  |  | RCF50 | RCF80
| Planned date for work to start: | 0
| Planned work completion: | 0 | [5 empty] | P0 | 0%
[8 empty] | P5 | 5% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
[8 empty] | P10 | 10% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| Durations: | Months | [5 empty] | P15 | 15% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| Timenow to completion | 0 | [5 empty] | P20 | 20% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| Delivery period (e.g. work start to end): |  | 0 |  |  |  |  | P25 | 25% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| Float within schedule (months): | 0 | 0 |  |  |  |  | P30 | 30% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| As %age: | #DIV/0! | #DIV/0! |  |  |  |  | P35 | 35% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
[8 empty] | P40 | 40% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| Schedule RCF Effects | [6 empty] | P45 | 45% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| The desired float (determined by risk appetite) can be either added to the cited durations or plan durations should allow this much float prior to the cited end date. I.e: | [6 empty] | P50 | 50% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
[8 empty] | P55 | 55% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
|  |  | Risk Appetite: | RCF50 | Choose RCFxx |  | P50 | P60 | 60% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
[8 empty] | P65 | 65% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| By cost composition | Blended RCF | [5 empty] | P70 | 70% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
|  | Timenow to completion |  | Delivery Phase |  |  |  | P75 | 75% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| Either: | [6 empty] | P80 | 80% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| Add further float to anticpated duration of: | #DIV/0! |  | #DIV/0! |  | Months |  | P85 | 85% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
[8 empty] | P90 | 90% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
| Giving a forecast end date of: | #DIV/0! |  | #DIV/0! |  |  |  | P95 | 95% | #DIV/0! |  |  |  |  | #DIV/0! | #DIV/0!
[8 empty] | P100 | 100%
Or
[8 empty] | Mean |  | #DIV/0!
| Maintain end date by adding further float into duration of: | #DIV/0! |  | #DIV/0! |  | Months
| Giving a target duration of: | #DIV/0! |  | #DIV/0! |  | Months

## RCF Calc (hidden)
This sheet collates the relevant RCF data (cost)
Selector | FBC |  |  |  | %ages: | Total |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Example: SOBC/ OBC/ FBC
[6 empty] | Filtered |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
|  |  | Compound: Scheme Specific RCF | Filtered Cost RCF | P50 | P80 | General L&P | Acquisition Cost | Agent and Legal fees | SDLT | Access Rights | Ransom Payments | Option Fees | Overage | Additional Land Acquisition | Planning general | Outline Planning | Reserved Matters Planning | Other Planning Costs | Standard construction and foundations | Preliminaries apportioned | Contractors' overheads and profits (not developers’) | General: unspecified | Residential | Custom build properties | Building affordable housing | Commercial (shop units/ offices space | Light industrial (warehousing/ distribution) | Film studios/ creative space | Community/ public buildings | Associated with houses | Associated with apartments | General | Maintenance & protection of a heritage asset | Other holding costs/ estate management | Professional Fees: General | Demolition | Enabling works | Remediation and Decontamination | complex/ brownfield | heavily contaminated | Due Diligence (survey works) | Archaeology/Heritage surveys | Standard foundations | Abnormal Foundations | Highway and Transport Design Works | Noise and Vibration Design Works | S278 works | Offsite Highways works (breakdown by type of works as feasible) | Footpaths | Cycle paths | Parking (surface) | Urban roads - standard | Urban roads - complex | Rural roads - standard | Rural roads - complex | Public Transport | Rail | Stations | Buslanes | Spine Road | Roundabouts | Junctions | Other civil works | Bridges/ other structures | Tunnels | Earthworks | Part 1 Claims | Unspecified | Electricity | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs legal fees for wayleaves, licences, supply agreements, compensation claims | Easement costs | Gas | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, Compensation claims | Easement costs | Water | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, compensation claims | Easement Costs | District Heating | Telecoms | Renewable Energy | General | Pumping Station | SUDS/Swales/Tanks/Attenuation | Beyond plot specific measures included in externals (such as permeable drives) | Sewers | Flood Risk | General | Ecology Design Work | Arboriculture | Mitigation | Nitrogen neutrality | Water Neutrality | Biodiversity Net Gain (BNG) | Invasive Species | Birds and Bats | SANGS | Invertebrates/vertebrates | Mammals | Public Realm / Public Open Space | Play areas / Outdoor sports | Endowment | Public Art | Valuation and Appraisal Advice | Legal Advice | Development Management / Master Developer Fees | Health and Safety Advice | Communications Fees | Agent Fees | Legal Fees | Profit on Market Sale | Profit on Affordable | Profit on Commercial | Profit on PRS | Total Blended Profit | Internal Rate of Return (IRR) | Development Management Fee | Return On Capital Employed (ROCE) | CIL Residential | CIL Commercial | General | Roof Tax | Affordable Housing Offsite Payment | Community Facilities | Employment and Skills | Healthcare | Highways / Transport | Education (primary and secondary) | Libraries | Public Realm/Open Space | Monitoring Fee | Play areas | Sports Fields | Other Abnormal Costs |  | Copy data from Col D for each stage
COST RCF
| P0 | 0% |  |  | #DIV/0! | #DIV/0! | [140 empty] | SOBC | OBC | FBC
| P5 | 5% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -63.35% | -63.35% | -63.35% | -63.35% | -23.43% | -23.43% | -23.43% | -23.43% | -23.43% | -18.86% | -23.43% | -23.43% | -23.43% | -23.43% | -23.43% | -17.83% | -17.83% | -63.35% | -63.35% | -63.35% | -63.35% | -15% | -17.83% | -17.83% | -16.41% | -15% | -17.83% | -17.83% | -23.43% | -18.86% | -63.35% | -63.35% | -7% | -7% | -6.3% | -6.3% | -6.3% | -7% | -8.4% | -7% | -8.4% | -19.65% | -19.65% | -11.3% | -7% | -7% | -8.4% | -8.4% | -18.21% | -21% | -21% | -19.8% | -7% | -24.74% | -28.69% | -28.69% | -28.69% | -28.69% | -28.69% | -28.69% | -13.34% | -13.34% | -13.34% | -13.34% | -13.34% | -13.34% | -13.34% | -32.2% | -32.2% | -32.2% | -32.2% | -32.2% | -32.2% | -32.2% | -24.74% | -24.74% | -24.74% | -32.26% | -32.26% | -32.26% | -32.26% | -32.26% | -19.8% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -7% | -7% | -7% | -7% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -25.78% | #DIV/0! | -37.99% | -37.7% | -28.81%
| P10 | 10% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -40.56% | -40.56% | -40.56% | -40.56% | -17.18% | -17.18% | -17.18% | -17.18% | -17.18% | -13.82% | -17.18% | -17.18% | -17.18% | -17.18% | -17.18% | -10.6% | -10.6% | -40.56% | -40.56% | -40.56% | -40.56% | -10.15% | -10.6% | -10.6% | -10.37% | -10.15% | -10.6% | -10.6% | -17.18% | -13.82% | -40.56% | -40.56% | 1% | 1% | 0.9% | 0.9% | 0.9% | 1% | 1.2% | 1% | 1.2% | -11.44% | -11.44% | -6.614% | 1% | 1% | 1.2% | 1.2% | -11.27% | -15.35% | -15.35% | -11% | 1% | -16.1% | -16.09% | -16.09% | -16.09% | -16.09% | -16.09% | -16.09% | -7.47% | -7.47% | -7.47% | -7.47% | -7.47% | -7.47% | -7.47% | -24.75% | -24.75% | -24.75% | -24.75% | -24.75% | -24.75% | -24.75% | -16.1% | -16.1% | -16.1% | -28.91% | -28.91% | -28.91% | -28.91% | -28.91% | -11% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | 1% | 1% | 1% | 1% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -18.89% | #DIV/0! | -28.41% | -27.77% | -19.21%
| P15 | 15% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -27.64% | -27.64% | -27.64% | -27.64% | -13.62% | -13.62% | -13.62% | -13.62% | -13.62% | -5.617% | -13.62% | -13.62% | -13.62% | -13.62% | -13.62% | -4.291% | -4.291% | -27.64% | -27.64% | -27.64% | -27.64% | -7.956% | -4.291% | -4.291% | -6.123% | -7.956% | -4.291% | -4.291% | -13.62% | -5.617% | -27.64% | -27.64% | 3% | 3% | 2.7% | 2.7% | 2.7% | 3% | 3.6% | 3% | 3.6% | -7.431% | -7.431% | -4.436% | 3% | 3% | 3.6% | 3.6% | -6.468% | -10% | -10% | -6.319% | 3% | -7.949% | -7.42% | -7.42% | -7.42% | -7.42% | -7.42% | -7.42% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -16.03% | -16.03% | -16.03% | -16.03% | -16.03% | -16.03% | -16.03% | -7.949% | -7.949% | -7.949% | -23.13% | -23.13% | -23.13% | -23.13% | -23.13% | -6.319% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | 3% | 3% | 3% | 3% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -14.99% | #DIV/0! | -18.31% | -17.76% | -12.73%
| P20 | 20% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -17.43% | -17.43% | -17.43% | -17.43% | -8.995% | -8.995% | -8.995% | -8.995% | -8.995% | 0% | -8.995% | -8.995% | -8.995% | -8.995% | -8.995% | -0.3492% | -0.3492% | -17.43% | -17.43% | -17.43% | -17.43% | -5.307% | -0.3492% | -0.3492% | -2.828% | -5.307% | -0.3492% | -0.3492% | -8.995% | 0% | -17.43% | -17.43% | 5.105% | 5.105% | 4.594% | 4.594% | 4.594% | 5.105% | 6.126% | 5.105% | 6.126% | -2.946% | -2.946% | -2.435% | 5.105% | 5.105% | 6.126% | 6.126% | -2.733% | -5.281% | -5.281% | -2.807% | 5.105% | -4.198% | -4.568% | -4.568% | -4.568% | -4.568% | -4.568% | -4.568% | 4.09% | 4.09% | 4.09% | 4.09% | 4.09% | 4.09% | 4.09% | -12.11% | -12.11% | -12.11% | -12.11% | -12.11% | -12.11% | -12.11% | -4.198% | -4.198% | -4.198% | -16.92% | -16.92% | -16.92% | -16.92% | -16.92% | -2.807% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | 5.105% | 5.105% | 5.105% | 5.105% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -9.894% | #DIV/0! | -13.89% | -9.457% | -6.412%
| P25 | 25% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -10.51% | -10.51% | -10.51% | -10.51% | -3.161% | -3.161% | -3.161% | -3.161% | -3.161% | 0% | -3.161% | -3.161% | -3.161% | -3.161% | -3.161% | 0% | 0% | -10.51% | -10.51% | -10.51% | -10.51% | 13.12% | 0% | 0% | 6.561% | 13.12% | 0% | 0% | -3.161% | 0% | -10.51% | -10.51% | 7% | 7% | 6.3% | 6.3% | 6.3% | 7% | 8.4% | 7% | 8.4% | -0.001784% | -0.001784% | -1.861% | 7% | 7% | 8.4% | 8.4% | 0% | -1.713% | -1.713% | -0.3264% | 7% | -1.51% | -2.84% | -2.84% | -2.84% | -2.84% | -2.84% | -2.84% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -1.51% | -1.51% | -1.51% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -0.3264% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7% | 7% | 7% | 7% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -3.477% | #DIV/0! | -6.733% | -3.511% | -2.882%
| P30 | 30% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -9.25% | -9.25% | -9.25% | -9.25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4% | 1.4% | -9.25% | -9.25% | -9.25% | -9.25% | 21.77% | 1.4% | 1.4% | 11.59% | 21.77% | 1.4% | 1.4% | 0% | 0% | -9.25% | -9.25% | 9% | 9% | 8.1% | 8.1% | 8.1% | 9% | 10.8% | 9% | 10.8% | 0.9166% | 0.9166% | 0.2737% | 9% | 9% | 10.8% | 10.8% | 0.0396% | 0% | 0% | 0% | 9% | 2.097% | -0.756% | -0.756% | -0.756% | -0.756% | -0.756% | -0.756% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | 2.097% | 2.097% | 2.097% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 0% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 9% | 9% | 9% | 9% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | 0% | #DIV/0! | -0.6252% | -0.06312% | 0.499%
| P35 | 35% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -8.076% | -8.076% | -8.076% | -8.076% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.6314% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 3.966% | 3.966% | -8.076% | -8.076% | -8.076% | -8.076% | 24.46% | 3.966% | 3.966% | 14.21% | 24.46% | 3.966% | 3.966% | 0.3062% | 0.6314% | -8.076% | -8.076% | 11% | 11% | 9.9% | 9.9% | 9.9% | 11% | 13.2% | 11% | 13.2% | 4% | 4% | 4.16% | 11% | 11% | 13.2% | 13.2% | 3.361% | 2.492% | 2.492% | 0% | 11% | 4.1% | 0% | 0% | 0% | 0% | 0% | 0% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | 4.1% | 4.1% | 4.1% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 0% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 11% | 11% | 11% | 11% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | 0.3368% | #DIV/0! | 2.962% | 3.333% | 3.703%
| P40 | 40% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -6.941% | -6.941% | -6.941% | -6.941% | 1.544% | 1.544% | 1.544% | 1.544% | 1.544% | 2.686% | 1.544% | 1.544% | 1.544% | 1.544% | 1.544% | 9% | 9% | -6.941% | -6.941% | -6.941% | -6.941% | 25% | 9% | 9% | 17% | 25% | 9% | 9% | 1.544% | 2.686% | -6.941% | -6.941% | 13.4% | 13.4% | 12.06% | 12.06% | 12.06% | 13.4% | 16.08% | 13.4% | 16.08% | 8% | 8% | 9.418% | 13.4% | 13.4% | 16.08% | 16.08% | 7.32% | 7.636% | 7.636% | 0% | 13.4% | 5.944% | 0% | 0% | 0% | 0% | 0% | 0% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 5.944% | 5.944% | 5.944% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 0% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 13.4% | 13.4% | 13.4% | 13.4% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | 1.699% | #DIV/0! | 6.488% | 6.729% | 6.97%
| P45 | 45% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.392% | -4.392% | -4.392% | -4.392% | 2.788% | 2.788% | 2.788% | 2.788% | 2.788% | 5.25% | 2.788% | 2.788% | 2.788% | 2.788% | 2.788% | 12% | 12% | -4.392% | -4.392% | -4.392% | -4.392% | 25.72% | 12% | 12% | 18.86% | 25.72% | 12% | 12% | 2.788% | 5.25% | -4.392% | -4.392% | 16% | 16% | 14.4% | 14.4% | 14.4% | 16% | 19.2% | 16% | 19.2% | 11.75% | 11.75% | 11.03% | 16% | 16% | 19.2% | 19.2% | 11.16% | 15% | 15% | 2% | 16% | 7.509% | 0% | 0% | 0% | 0% | 0% | 0% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 7.509% | 7.509% | 7.509% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 2% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 16% | 16% | 16% | 16% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | 3.067% | #DIV/0! | 10.16% | 10.3% | 10.43%
| P50 | 50% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -2.156% | -2.156% | -2.156% | -2.156% | 4.197% | 4.197% | 4.197% | 4.197% | 4.197% | 8.941% | 4.197% | 4.197% | 4.197% | 4.197% | 4.197% | 13.33% | 13.33% | -2.156% | -2.156% | -2.156% | -2.156% | 31.5% | 13.33% | 13.33% | 22.42% | 31.5% | 13.33% | 13.33% | 4.197% | 8.941% | -2.156% | -2.156% | 18% | 18% | 16.2% | 16.2% | 16.2% | 18% | 21.6% | 18% | 21.6% | 15.14% | 15.14% | 15.88% | 18% | 18% | 21.6% | 21.6% | 15% | 20.15% | 20.15% | 4.836% | 18% | 10.35% | 0% | 0% | 0% | 0% | 0% | 0% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 10.35% | 10.35% | 10.35% | 10.82% | 10.82% | 10.82% | 10.82% | 10.82% | 4.836% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 18% | 18% | 18% | 18% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | 4.616% | #DIV/0! | 14.07% | 13.9% | 13.73%
| P55 | 55% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 7.413% | 7.413% | 7.413% | 7.413% | 7.413% | 14.43% | 7.413% | 7.413% | 7.413% | 7.413% | 7.413% | 18.38% | 18.38% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 37.41% | 18.38% | 18.38% | 27.89% | 37.41% | 18.38% | 18.38% | 7.413% | 14.43% | 0.6532% | 0.6532% | 20.55% | 20.55% | 18.5% | 18.5% | 18.5% | 20.55% | 24.66% | 20.55% | 24.66% | 20% | 20% | 20.96% | 20.55% | 20.55% | 24.66% | 24.66% | 20% | 23% | 23% | 8% | 20.55% | 12.29% | 0% | 0% | 0% | 0% | 0% | 0% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 12.29% | 12.29% | 12.29% | 15.51% | 15.51% | 15.51% | 15.51% | 15.51% | 8% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 20.55% | 20.55% | 20.55% | 20.55% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 8.155% | #DIV/0! | 17.2% | 17.01% | 16.83%
| P60 | 60% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | 3.111% | 3.111% | 3.111% | 3.111% | 11.31% | 11.31% | 11.31% | 11.31% | 11.31% | 18.04% | 11.31% | 11.31% | 11.31% | 11.31% | 11.31% | 22% | 22% | 3.111% | 3.111% | 3.111% | 3.111% | 38.53% | 22% | 22% | 30.27% | 38.53% | 22% | 22% | 11.31% | 18.04% | 3.111% | 3.111% | 23% | 23% | 20.7% | 20.7% | 20.7% | 23% | 27.6% | 23% | 27.6% | 28.12% | 28.12% | 26.15% | 23% | 23% | 27.6% | 27.6% | 26% | 26% | 26% | 11.32% | 23% | 14.85% | 0.952% | 0.952% | 0.952% | 0.952% | 0.952% | 0.952% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 14.85% | 14.85% | 14.85% | 17.3% | 17.3% | 17.3% | 17.3% | 17.3% | 11.32% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 23% | 23% | 23% | 23% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 12.45% | #DIV/0! | 20.86% | 20.65% | 20.45%
| P65 | 65% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 4.563% | 4.563% | 4.563% | 4.563% | 12.52% | 12.52% | 12.52% | 12.52% | 12.52% | 30.36% | 12.52% | 12.52% | 12.52% | 12.52% | 12.52% | 34.89% | 34.89% | 4.563% | 4.563% | 4.563% | 4.563% | 40.31% | 34.89% | 34.89% | 37.6% | 40.31% | 34.89% | 34.89% | 12.52% | 30.36% | 4.563% | 4.563% | 25.65% | 25.65% | 23.09% | 23.09% | 23.09% | 25.65% | 30.78% | 25.65% | 30.78% | 33.05% | 33.05% | 34.63% | 25.65% | 25.65% | 30.78% | 30.78% | 33% | 31.7% | 31.7% | 14.94% | 25.65% | 18.83% | 5.757% | 5.757% | 5.757% | 5.757% | 5.757% | 5.757% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 18.83% | 18.83% | 18.83% | 30.04% | 30.04% | 30.04% | 30.04% | 30.04% | 14.94% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 25.65% | 25.65% | 25.65% | 25.65% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 13.78% | #DIV/0! | 40.74% | 27.21% | 26.68%
| P70 | 70% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 5.862% | 5.862% | 5.862% | 5.862% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 38.57% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 44.74% | 44.74% | 5.862% | 5.862% | 5.862% | 5.862% | 44.99% | 44.74% | 44.74% | 44.87% | 44.99% | 44.74% | 44.74% | 16.23% | 38.57% | 5.862% | 5.862% | 29% | 29% | 26.1% | 26.1% | 26.1% | 29% | 34.8% | 29% | 34.8% | 43% | 43% | 41.67% | 29% | 29% | 34.8% | 34.8% | 42.86% | 33.6% | 33.6% | 18.04% | 29% | 21.45% | 8.737% | 8.737% | 8.737% | 8.737% | 8.737% | 8.737% | 31.66% | 31.66% | 31.66% | 31.66% | 31.66% | 31.66% | 31.66% | 23.95% | 23.95% | 23.95% | 23.95% | 23.95% | 23.95% | 23.95% | 21.45% | 21.45% | 21.45% | 35.57% | 35.57% | 35.57% | 35.57% | 35.57% | 18.04% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 29% | 29% | 29% | 29% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 17.85% | #DIV/0! | 47.06% | 34.68% | 32.57%
| P75 | 75% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 16.23% | 16.23% | 16.23% | 16.23% | 21.6% | 21.6% | 21.6% | 21.6% | 21.6% | 62.94% | 21.6% | 21.6% | 21.6% | 21.6% | 21.6% | 57% | 57% | 16.23% | 16.23% | 16.23% | 16.23% | 50.28% | 57% | 57% | 53.64% | 50.28% | 57% | 57% | 21.6% | 62.94% | 16.23% | 16.23% | 33% | 33% | 29.7% | 29.7% | 29.7% | 33% | 39.6% | 33% | 39.6% | 50.56% | 50.56% | 49.44% | 33% | 33% | 39.6% | 39.6% | 51% | 48.35% | 48.35% | 23% | 33% | 27.02% | 12.44% | 12.44% | 12.44% | 12.44% | 12.44% | 12.44% | 38.93% | 38.93% | 38.93% | 38.93% | 38.93% | 38.93% | 38.93% | 29.69% | 29.69% | 29.69% | 29.69% | 29.69% | 29.69% | 29.69% | 27.02% | 27.02% | 27.02% | 40.59% | 40.59% | 40.59% | 40.59% | 40.59% | 23% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 33% | 33% | 33% | 33% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 23.76% | #DIV/0! | 86.6% | 52.64% | 41.27%
| P80 | 80% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 18.2% | 18.2% | 18.2% | 18.2% | 32.12% | 32.12% | 32.12% | 32.12% | 32.12% | 68.74% | 32.12% | 32.12% | 32.12% | 32.12% | 32.12% | 83.95% | 83.95% | 18.2% | 18.2% | 18.2% | 18.2% | 53.92% | 83.95% | 83.95% | 68.93% | 53.92% | 83.95% | 83.95% | 32.12% | 68.74% | 18.2% | 18.2% | 37% | 37% | 33.3% | 33.3% | 33.3% | 37% | 44.4% | 37% | 44.4% | 56.93% | 56.93% | 60.02% | 37% | 37% | 44.4% | 44.4% | 60.4% | 62.09% | 62.09% | 28% | 37% | 31.78% | 15.31% | 15.31% | 15.31% | 15.31% | 15.31% | 15.31% | 45.03% | 45.03% | 45.03% | 45.03% | 45.03% | 45.03% | 45.03% | 35.01% | 35.01% | 35.01% | 35.01% | 35.01% | 35.01% | 35.01% | 31.78% | 31.78% | 31.78% | 44.73% | 44.73% | 44.73% | 44.73% | 44.73% | 28% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 37% | 37% | 37% | 37% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 35.34% | #DIV/0! | 114.8% | 68.76% | 50.97%
| P85 | 85% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 21.48% | 21.48% | 21.48% | 21.48% | 61.21% | 61.21% | 61.21% | 61.21% | 61.21% | 73.4% | 61.21% | 61.21% | 61.21% | 61.21% | 61.21% | 127.2% | 127.2% | 21.48% | 21.48% | 21.48% | 21.48% | 57.17% | 127.2% | 127.2% | 92.16% | 57.17% | 127.2% | 127.2% | 61.21% | 73.4% | 21.48% | 21.48% | 40.85% | 40.85% | 36.76% | 36.76% | 36.76% | 40.85% | 49.02% | 40.85% | 49.02% | 67.7% | 67.7% | 85% | 40.85% | 40.85% | 49.02% | 49.02% | 75% | 71.26% | 71.26% | 38.04% | 40.85% | 43.81% | 17.39% | 17.39% | 17.39% | 17.39% | 17.39% | 17.39% | 67.93% | 67.93% | 67.93% | 67.93% | 67.93% | 67.93% | 67.93% | 46.1% | 46.1% | 46.1% | 46.1% | 46.1% | 46.1% | 46.1% | 43.81% | 43.81% | 43.81% | 51.32% | 51.32% | 51.32% | 51.32% | 51.32% | 38.04% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 40.85% | 40.85% | 40.85% | 40.85% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 67.33% | #DIV/0! | 130.5% | 84.06% | 65.21%
| P90 | 90% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 23.77% | 23.77% | 23.77% | 23.77% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 97.61% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 200% | 200% | 23.77% | 23.77% | 23.77% | 23.77% | 79.12% | 200% | 200% | 139.6% | 79.12% | 200% | 200% | 105.6% | 97.61% | 23.77% | 23.77% | 50.8% | 50.8% | 45.72% | 45.72% | 45.72% | 50.8% | 60.96% | 50.8% | 60.96% | 83% | 83% | 129.9% | 50.8% | 50.8% | 60.96% | 60.96% | 102.8% | 100.6% | 100.6% | 56.21% | 50.8% | 52.04% | 24.1% | 24.1% | 24.1% | 24.1% | 24.1% | 24.1% | 76.38% | 76.38% | 76.38% | 76.38% | 76.38% | 76.38% | 76.38% | 55.63% | 55.63% | 55.63% | 55.63% | 55.63% | 55.63% | 55.63% | 52.04% | 52.04% | 52.04% | 54.55% | 54.55% | 54.55% | 54.55% | 54.55% | 56.21% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 50.8% | 50.8% | 50.8% | 50.8% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 116.2% | #DIV/0! | 270.4% | 115.4% | 90.32%
| P95 | 95% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 79.21% | 79.21% | 79.21% | 79.21% | 208.3% | 208.3% | 208.3% | 208.3% | 208.3% | 147.9% | 208.3% | 208.3% | 208.3% | 208.3% | 208.3% | 271.2% | 271.2% | 79.21% | 79.21% | 79.21% | 79.21% | 106% | 271.2% | 271.2% | 188.6% | 106% | 271.2% | 271.2% | 208.3% | 147.9% | 79.21% | 79.21% | 66.92% | 66.92% | 60.23% | 60.23% | 60.23% | 66.92% | 80.3% | 66.92% | 80.3% | 115.1% | 115.1% | 185.4% | 66.92% | 66.92% | 80.3% | 80.3% | 187.2% | 144.6% | 144.6% | 82.6% | 66.92% | 78.33% | 33.01% | 33.01% | 33.01% | 33.01% | 33.01% | 33.01% | 123.6% | 123.6% | 123.6% | 123.6% | 123.6% | 123.6% | 123.6% | 78.34% | 78.34% | 78.34% | 78.34% | 78.34% | 78.34% | 78.34% | 78.33% | 78.33% | 78.33% | 69.82% | 69.82% | 69.82% | 69.82% | 69.82% | 82.6% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 66.92% | 66.92% | 66.92% | 66.92% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 229.1% | #DIV/0! | 363% | 212.6% | 180%
| P100 | 100% |  |  | #DIV/0! | #DIV/0! | [140 empty] | 53.62% | 30.06% | 25.77%
|  | Mean: | #DIV/0!
| Schedule RCF | [5 empty] | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
| P0 | 0% |  |  | #DIV/0! | #DIV/0!
| P5 | 5% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -5.397% | -5.397% | -5.397% | -5.397% | -5.397% | -5.397% | -5.397% | -5.397% | -5.397% | -28% | -28% | -28% | -28% | -6.044% | -6.044% | -6.044% | -6.044% | -6.044% | 0% | -6.044% | -6.044% | -6.044% | -6.044% | -6.044% | 0% | 0% | -28% | -28% | -28% | -28% | 0.8% | 0% | 0% | 0.4% | 0.8% | 0% | 0% | -6.044% | 0% | -28% | -28% | -29.12% | -29.12% | -26.21% | -26.21% | -26.21% | -29.12% | -34.94% | -29.12% | -34.94% | -28.59% | -28.59% | -11.86% | -29.12% | -29.12% | -34.94% | -34.94% | -6.737% | -13% | -13% | -28.18% | -29.12% | -2.854% | 0% | 0% | 0% | 0% | 0% | 0% | -0.2766% | -0.2766% | -0.2766% | -0.2766% | -0.2766% | -0.2766% | -0.2766% | -8.285% | -8.285% | -8.285% | -8.285% | -8.285% | -8.285% | -8.285% | -2.854% | -2.854% | -2.854% | -8.285% | -8.285% | -8.285% | -8.285% | -8.285% | -28.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -29.12% | -29.12% | -29.12% | -29.12% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -6.648%
| P10 | 10% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -19% | -19% | -19% | -19% | -4.938% | -4.938% | -4.938% | -4.938% | -4.938% | 0% | -4.938% | -4.938% | -4.938% | -4.938% | -4.938% | 0% | 0% | -19% | -19% | -19% | -19% | 1.6% | 0% | 0% | 0.8% | 1.6% | 0% | 0% | -4.938% | 0% | -19% | -19% | -20% | -20% | -18% | -18% | -18% | -20% | -24% | -20% | -24% | -19.9% | -19.9% | -8.1% | -20% | -20% | -24% | -24% | -2.818% | -11.11% | -11.11% | -19% | -20% | -1.461% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -4.383% | -4.383% | -4.383% | -4.383% | -4.383% | -4.383% | -4.383% | -1.461% | -1.461% | -1.461% | -4.383% | -4.383% | -4.383% | -4.383% | -4.383% | -19% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -20% | -20% | -20% | -20% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -5.432%
| P15 | 15% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -11.91% | -11.91% | -11.91% | -11.91% | -0.6371% | -0.6371% | -0.6371% | -0.6371% | -0.6371% | 0% | -0.6371% | -0.6371% | -0.6371% | -0.6371% | -0.6371% | 0% | 0% | -11.91% | -11.91% | -11.91% | -11.91% | 3.6% | 0% | 0% | 1.8% | 3.6% | 0% | 0% | -0.6371% | 0% | -11.91% | -11.91% | -14.58% | -14.58% | -13.12% | -13.12% | -13.12% | -14.58% | -17.49% | -14.58% | -17.49% | -11.9% | -11.9% | 1.45% | -14.58% | -14.58% | -17.49% | -17.49% | 0% | -4.542% | -4.542% | -13.34% | -14.58% | -0.4804% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -1.441% | -1.441% | -1.441% | -1.441% | -1.441% | -1.441% | -1.441% | -0.4804% | -0.4804% | -0.4804% | -1.441% | -1.441% | -1.441% | -1.441% | -1.441% | -13.34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -14.58% | -14.58% | -14.58% | -14.58% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -0.7008%
| P20 | 20% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6% | -6% | -6% | -6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6% | -6% | -6% | -6% | 6.8% | 0% | 0% | 3.4% | 6.8% | 0% | 0% | 0% | 0% | -6% | -6% | -10.18% | -10.18% | -9.162% | -9.162% | -9.162% | -10.18% | -12.22% | -10.18% | -12.22% | -6.8% | -6.8% | 7.2% | -10.18% | -10.18% | -12.22% | -12.22% | 0% | -2.371% | -2.371% | -9.26% | -10.18% | 1.409% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 1.409% | 1.409% | 1.409% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | -9.26% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -10.18% | -10.18% | -10.18% | -10.18% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | 0%
| P25 | 25% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -1.443% | -1.443% | -1.443% | -1.443% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -1.443% | -1.443% | -1.443% | -1.443% | 10% | 0% | 0% | 5% | 10% | 0% | 0% | 0% | 0% | -1.443% | -1.443% | -3.541% | -3.541% | -3.187% | -3.187% | -3.187% | -3.541% | -4.249% | -3.541% | -4.249% | -0.9424% | -0.9424% | 9.289% | -3.541% | -3.541% | -4.249% | -4.249% | 0% | 0% | 0% | -3.061% | -3.541% | 3.292% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 3.292% | 3.292% | 3.292% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | -3.061% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -3.541% | -3.541% | -3.541% | -3.541% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | 0%
| P30 | 30% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.67% | 0% | 0% | 6.333% | 12.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.65% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.139% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 6.139% | 6.139% | 6.139% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| P35 | 35% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15.33% | 0% | 0% | 7.667% | 15.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.089% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 7.089% | 7.089% | 7.089% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| P40 | 40% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0% | 0% | 0% | 0% | 0% | 0.9624% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 18.93% | 0% | 0% | 9.467% | 18.93% | 0% | 0% | 0% | 0.9624% | 0.3573% | 0.3573% | 3.259% | 3.259% | 2.933% | 2.933% | 2.933% | 3.259% | 3.911% | 3.259% | 3.911% | 7.397% | 7.397% | 15% | 3.259% | 3.259% | 3.911% | 3.911% | 0% | 0% | 0% | 2% | 3.259% | 7.822% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 7.822% | 7.822% | 7.822% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.259% | 3.259% | 3.259% | 3.259% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0%
| P45 | 45% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 6.013% | 6.013% | 6.013% | 6.013% | 0% | 0% | 0% | 0% | 0% | 3.08% | 0% | 0% | 0% | 0% | 0% | 0.9632% | 0.9632% | 6.013% | 6.013% | 6.013% | 6.013% | 23.47% | 0.9632% | 0.9632% | 12.21% | 23.47% | 0.9632% | 0.9632% | 0% | 3.08% | 6.013% | 6.013% | 8.063% | 8.063% | 7.257% | 7.257% | 7.257% | 8.063% | 9.676% | 8.063% | 9.676% | 14.1% | 14.1% | 18.9% | 8.063% | 8.063% | 9.676% | 9.676% | 0% | 1.829% | 1.829% | 7.183% | 8.063% | 10.02% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 10.02% | 10.02% | 10.02% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 7.183% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 8.063% | 8.063% | 8.063% | 8.063% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 0%
| P50 | 50% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 12.27% | 12.27% | 12.27% | 12.27% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 17.5% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 4.692% | 4.692% | 12.27% | 12.27% | 12.27% | 12.27% | 28% | 4.692% | 4.692% | 16.35% | 28% | 4.692% | 4.692% | 0.2635% | 17.5% | 12.27% | 12.27% | 13% | 13% | 11.7% | 11.7% | 11.7% | 13% | 15.6% | 13% | 15.6% | 19.09% | 19.09% | 26% | 13% | 13% | 15.6% | 15.6% | 1.658% | 3.449% | 3.449% | 11.65% | 13% | 10.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 10.97% | 10.97% | 10.97% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 11.65% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 13% | 13% | 13% | 13% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 0.2899%
| P55 | 55% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 16% | 16% | 16% | 16% | 2.652% | 2.652% | 2.652% | 2.652% | 2.652% | 26% | 2.652% | 2.652% | 2.652% | 2.652% | 2.652% | 14.05% | 14.05% | 16% | 16% | 16% | 16% | 28.8% | 14.05% | 14.05% | 21.42% | 28.8% | 14.05% | 14.05% | 2.652% | 26% | 16% | 16% | 16.67% | 16.67% | 15% | 15% | 15% | 16.67% | 20% | 16.67% | 20% | 26.27% | 26.27% | 29.72% | 16.67% | 16.67% | 20% | 20% | 4% | 7.169% | 7.169% | 15.76% | 16.67% | 17.24% | 0% | 0% | 0% | 0% | 0% | 0% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 17.24% | 17.24% | 17.24% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 15.76% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 16.67% | 16.67% | 16.67% | 16.67% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 2.918%
| P60 | 60% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 21.87% | 21.87% | 21.87% | 21.87% | 3.263% | 3.263% | 3.263% | 3.263% | 3.263% | 32.95% | 3.263% | 3.263% | 3.263% | 3.263% | 3.263% | 18.57% | 18.57% | 21.87% | 21.87% | 21.87% | 21.87% | 29.6% | 18.57% | 18.57% | 24.08% | 29.6% | 18.57% | 18.57% | 3.263% | 32.95% | 21.87% | 21.87% | 22.63% | 22.63% | 20.37% | 20.37% | 20.37% | 22.63% | 27.16% | 22.63% | 27.16% | 30.6% | 30.6% | 44.3% | 22.63% | 22.63% | 27.16% | 27.16% | 14% | 12% | 12% | 21.47% | 22.63% | 21.44% | 0% | 0% | 0% | 0% | 0% | 0% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 21.44% | 21.44% | 21.44% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 21.47% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 22.63% | 22.63% | 22.63% | 22.63% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 3.589%
| P65 | 65% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 27% | 27% | 27% | 27% | 4.324% | 4.324% | 4.324% | 4.324% | 4.324% | 48.71% | 4.324% | 4.324% | 4.324% | 4.324% | 4.324% | 29.81% | 29.81% | 27% | 27% | 27% | 27% | 39.2% | 29.81% | 29.81% | 34.51% | 39.2% | 29.81% | 29.81% | 4.324% | 48.71% | 27% | 27% | 27.36% | 27.36% | 24.62% | 24.62% | 24.62% | 27.36% | 32.83% | 27.36% | 32.83% | 36.7% | 36.7% | 49.65% | 27.36% | 27.36% | 32.83% | 32.83% | 19.87% | 16% | 16% | 27% | 27.36% | 24.41% | 0% | 0% | 0% | 0% | 0% | 0% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 24.41% | 24.41% | 24.41% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 27% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 27.36% | 27.36% | 27.36% | 27.36% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 4.756%
| P70 | 70% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 23.75% | 23.75% | 23.75% | 23.75% | 23.75% | 23.75% | 23.75% | 23.75% | 23.75% | 35.97% | 35.97% | 35.97% | 35.97% | 9.8% | 9.8% | 9.8% | 9.8% | 9.8% | 50% | 9.8% | 9.8% | 9.8% | 9.8% | 9.8% | 47.61% | 47.61% | 35.97% | 35.97% | 35.97% | 35.97% | 57.6% | 47.61% | 47.61% | 52.6% | 57.6% | 47.61% | 47.61% | 9.8% | 50% | 35.97% | 35.97% | 35.93% | 35.93% | 32.34% | 32.34% | 32.34% | 35.93% | 43.12% | 35.93% | 43.12% | 40% | 40% | 50% | 35.93% | 35.93% | 43.12% | 43.12% | 25.96% | 22% | 22% | 35.1% | 35.93% | 27.39% | 0% | 0% | 0% | 0% | 0% | 0% | 32.17% | 32.17% | 32.17% | 32.17% | 32.17% | 32.17% | 32.17% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 27.39% | 27.39% | 27.39% | 50% | 50% | 50% | 50% | 50% | 35.1% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 35.93% | 35.93% | 35.93% | 35.93% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 10.78%
| P75 | 75% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 27.61% | 27.61% | 27.61% | 27.61% | 27.61% | 27.61% | 27.61% | 27.61% | 27.61% | 45.71% | 45.71% | 45.71% | 45.71% | 22.64% | 22.64% | 22.64% | 22.64% | 22.64% | 67% | 22.64% | 22.64% | 22.64% | 22.64% | 22.64% | 57.5% | 57.5% | 45.71% | 45.71% | 45.71% | 45.71% | 76% | 57.5% | 57.5% | 66.75% | 76% | 57.5% | 57.5% | 22.64% | 67% | 45.71% | 45.71% | 50% | 50% | 45% | 45% | 45% | 50% | 60% | 50% | 60% | 46% | 46% | 50% | 50% | 50% | 60% | 60% | 35.75% | 35% | 35% | 48% | 50% | 31.31% | 0% | 0% | 0% | 0% | 0% | 0% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 58.92% | 58.92% | 58.92% | 58.92% | 58.92% | 58.92% | 58.92% | 31.31% | 31.31% | 31.31% | 58.92% | 58.92% | 58.92% | 58.92% | 58.92% | 48% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 50% | 50% | 50% | 50% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 24.91%
| P80 | 80% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 32.22% | 32.22% | 32.22% | 32.22% | 32.22% | 32.22% | 32.22% | 32.22% | 32.22% | 59.4% | 59.4% | 59.4% | 59.4% | 28.99% | 28.99% | 28.99% | 28.99% | 28.99% | 87.2% | 28.99% | 28.99% | 28.99% | 28.99% | 28.99% | 67.8% | 67.8% | 59.4% | 59.4% | 59.4% | 59.4% | 80.8% | 67.8% | 67.8% | 74.3% | 80.8% | 67.8% | 67.8% | 28.99% | 87.2% | 59.4% | 59.4% | 63.4% | 63.4% | 57.06% | 57.06% | 57.06% | 63.4% | 76.08% | 63.4% | 76.08% | 50% | 50% | 65% | 63.4% | 63.4% | 76.08% | 76.08% | 51.1% | 38% | 38% | 62.2% | 63.4% | 39.96% | 0% | 0% | 0% | 0% | 0% | 0% | 56% | 56% | 56% | 56% | 56% | 56% | 56% | 63.87% | 63.87% | 63.87% | 63.87% | 63.87% | 63.87% | 63.87% | 39.96% | 39.96% | 39.96% | 63.87% | 63.87% | 63.87% | 63.87% | 63.87% | 62.2% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 63.4% | 63.4% | 63.4% | 63.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 31.89%
| P85 | 85% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 45.47% | 45.47% | 45.47% | 45.47% | 45.47% | 45.47% | 45.47% | 45.47% | 45.47% | 75% | 75% | 75% | 75% | 37.97% | 37.97% | 37.97% | 37.97% | 37.97% | 100% | 37.97% | 37.97% | 37.97% | 37.97% | 37.97% | 100% | 100% | 75% | 75% | 75% | 75% | 85.6% | 100% | 100% | 92.81% | 85.6% | 100% | 100% | 37.97% | 100% | 75% | 75% | 80.96% | 80.96% | 72.86% | 72.86% | 72.86% | 80.96% | 97.15% | 80.96% | 97.15% | 65.9% | 65.9% | 86.27% | 80.96% | 80.96% | 97.15% | 97.15% | 68.75% | 51.5% | 51.5% | 75.86% | 80.96% | 43.77% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 64.66% | 64.66% | 64.66% | 64.66% | 64.66% | 64.66% | 64.66% | 43.77% | 43.77% | 43.77% | 64.66% | 64.66% | 64.66% | 64.66% | 64.66% | 75.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80.96% | 80.96% | 80.96% | 80.96% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 41.77%
| P90 | 90% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 54.96% | 54.96% | 54.96% | 54.96% | 54.96% | 54.96% | 54.96% | 54.96% | 54.96% | 100% | 100% | 100% | 100% | 69.76% | 69.76% | 69.76% | 69.76% | 69.76% | 138% | 69.76% | 69.76% | 69.76% | 69.76% | 69.76% | 133.3% | 133.3% | 100% | 100% | 100% | 100% | 96.55% | 133.3% | 133.3% | 114.9% | 96.55% | 133.3% | 133.3% | 69.76% | 138% | 100% | 100% | 113% | 113% | 101.7% | 101.7% | 101.7% | 113% | 135.6% | 113% | 135.6% | 100% | 100% | 88.89% | 113% | 113% | 135.6% | 135.6% | 86% | 75.5% | 75.5% | 105.4% | 113% | 58.15% | 12.32% | 12.32% | 12.32% | 12.32% | 12.32% | 12.32% | 80.04% | 80.04% | 80.04% | 80.04% | 80.04% | 80.04% | 80.04% | 82.09% | 82.09% | 82.09% | 82.09% | 82.09% | 82.09% | 82.09% | 58.15% | 58.15% | 58.15% | 82.09% | 82.09% | 82.09% | 82.09% | 82.09% | 105.4% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 113% | 113% | 113% | 113% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 76.73%
| P95 | 95% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 83.53% | 83.53% | 83.53% | 83.53% | 83.53% | 83.53% | 83.53% | 83.53% | 83.53% | 146.1% | 146.1% | 146.1% | 146.1% | 139% | 139% | 139% | 139% | 139% | 192.3% | 139% | 139% | 139% | 139% | 139% | 170.6% | 170.6% | 146.1% | 146.1% | 146.1% | 146.1% | 113.7% | 170.6% | 170.6% | 142.1% | 113.7% | 170.6% | 170.6% | 139% | 192.3% | 146.1% | 146.1% | 152.8% | 152.8% | 137.5% | 137.5% | 137.5% | 152.8% | 183.4% | 152.8% | 183.4% | 132% | 132% | 91.84% | 152.8% | 152.8% | 183.4% | 183.4% | 129.8% | 86% | 86% | 145.3% | 152.8% | 77.88% | 43.32% | 43.32% | 43.32% | 43.32% | 43.32% | 43.32% | 97.13% | 97.13% | 97.13% | 97.13% | 97.13% | 97.13% | 97.13% | 93.19% | 93.19% | 93.19% | 93.19% | 93.19% | 93.19% | 93.19% | 77.88% | 77.88% | 77.88% | 93.19% | 93.19% | 93.19% | 93.19% | 93.19% | 145.3% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 152.8% | 152.8% | 152.8% | 152.8% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 152.9%
| P100 | 100% |  |  | #DIV/0! | #DIV/0!
|  | Mean: | #DIV/0!

## Cost RCF (MMC) (hidden)
This sheet collates the relevant RCF data (cost)
Selector | FBC |  |  |  | %ages: |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! |  | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | Example: SOBC/ OBC/ FBC
|  |  | Compound: Scheme Specific RCF | P50 | P80 | General L&P | Acquisition Cost | Agent and Legal fees | SDLT | Access Rights | Ransom Payments | Option Fees | Overage | Additional Land Acquisition | Planning general | Outline Planning | Reserved Matters Planning | Other Planning Costs | Standard construction and foundations | Preliminaries apportioned | Contractors' overheads and profits (not developers’) | General: unspecified | Residential | Custom build properties | Building affordable housing | Commercial (shop units/ offices space | Light industrial (warehousing/ distribution) | Film studios/ creative space | Community/ public buildings | Associated with houses | Associated with apartments | General | Maintenance & protection of a heritage asset | Other holding costs/ estate management | Professional Fees: General | Demolition | Enabling works | Remediation and Decontamination | complex/ brownfield | heavily contaminated | Due Diligence (survey works) | Archaeology/Heritage surveys | Standard foundations | Abnormal Foundations | Highway and Transport Design Works | Noise and Vibration Design Works | S278 works | Offsite Highways works (breakdown by type of works as feasible) | Footpaths | Cycle paths | Parking (surface) | Urban roads - standard | Urban roads - complex | Rural roads - standard | Rural roads - complex | Public Transport | Rail | Stations | Buslanes | Spine Road | Roundabouts | Junctions | Other civil works | Bridges/ other structures | Tunnels | Earthworks | Part 1 Claims | Unspecified | Electricity | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs legal fees for wayleaves, licences, supply agreements, compensation claims | Easement costs | Gas | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, Compensation claims | Easement costs | Water | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, compensation claims | Easement Costs | District Heating | Telecoms | Renewable Energy | General | Pumping Station | SUDS/Swales/Tanks/Attenuation | Beyond plot specific measures included in externals (such as permeable drives) | Sewers | Flood Risk | General | Ecology Design Work | Arboriculture | Mitigation | Nitrogen neutrality | Water Neutrality | Biodiversity Net Gain (BNG) | Invasive Species | Birds and Bats | SANGS | Invertebrates/vertebrates | Mammals | Public Realm / Public Open Space | Play areas / Outdoor sports | Endowment | Public Art | Valuation and Appraisal Advice | Legal Advice | Development Management / Master Developer Fees | Health and Safety Advice | Communications Fees | Agent Fees | Legal Fees | Profit on Market Sale | Profit on Affordable | Profit on Commercial | Profit on PRS | Total Blended Profit | Internal Rate of Return (IRR) | Development Management Fee | Return On Capital Employed (ROCE) | CIL Residential | CIL Commercial | General | Roof Tax | Affordable Housing Offsite Payment | Community Facilities | Employment and Skills | Healthcare | Highways / Transport | Education (primary and secondary) | Libraries | Public Realm/Open Space | Monitoring Fee | Play areas | Sports Fields | Other Abnormal Costs | Copy data from Col D for each stage
MMC Factor:
| P0 | 0% |  | #DIV/0! | #DIV/0! | [139 empty] | SOBC | OBC | FBC
| P5 | 5% | #DIV/0! | #DIV/0! | #DIV/0! | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -63.35% | -63.35% | -63.35% | -63.35% | -23.43% | -23.43% | -23.43% | -23.43% | -23.43% | -18.86% | -23.43% | -23.43% | -23.43% | -23.43% | -23.43% | -17.83% | -17.83% | -63.35% | -63.35% | -63.35% | -63.35% | -15% | -17.83% | -17.83% | -16.41% | -15% | -17.83% | -17.83% | -23.43% | -18.86% | -63.35% | -63.35% | -7% | -7% | -6.3% | -6.3% | -6.3% | -7% | -8.4% | -7% | -8.4% | -19.65% | -19.65% | -11.3% | -7% | -7% | -8.4% | -8.4% | -18.21% | -21% | -21% | -19.8% | -7% | -24.74% | -28.69% | -28.69% | -28.69% | -28.69% | -28.69% | -28.69% | -13.34% | -13.34% | -13.34% | -13.34% | -13.34% | -13.34% | -13.34% | -32.2% | -32.2% | -32.2% | -32.2% | -32.2% | -32.2% | -32.2% | -24.74% | -24.74% | -24.74% | -32.26% | -32.26% | -32.26% | -32.26% | -32.26% | -19.8% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -7% | -7% | -7% | -7% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -25.78% | -37.99% | -37.7% | -28.81%
| P10 | 10% | #DIV/0! | #DIV/0! | #DIV/0! | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -40.56% | -40.56% | -40.56% | -40.56% | -17.18% | -17.18% | -17.18% | -17.18% | -17.18% | -13.82% | -17.18% | -17.18% | -17.18% | -17.18% | -17.18% | -10.6% | -10.6% | -40.56% | -40.56% | -40.56% | -40.56% | -10.15% | -10.6% | -10.6% | -10.37% | -10.15% | -10.6% | -10.6% | -17.18% | -13.82% | -40.56% | -40.56% | 1% | 1% | 0.9% | 0.9% | 0.9% | 1% | 1.2% | 1% | 1.2% | -11.44% | -11.44% | -6.614% | 1% | 1% | 1.2% | 1.2% | -11.27% | -15.35% | -15.35% | -11% | 1% | -16.1% | -16.09% | -16.09% | -16.09% | -16.09% | -16.09% | -16.09% | -7.47% | -7.47% | -7.47% | -7.47% | -7.47% | -7.47% | -7.47% | -24.75% | -24.75% | -24.75% | -24.75% | -24.75% | -24.75% | -24.75% | -16.1% | -16.1% | -16.1% | -28.91% | -28.91% | -28.91% | -28.91% | -28.91% | -11% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | 1% | 1% | 1% | 1% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -18.89% | -28.41% | -27.77% | -19.21%
| P15 | 15% | #DIV/0! | #DIV/0! | #DIV/0! | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -27.64% | -27.64% | -27.64% | -27.64% | -13.62% | -13.62% | -13.62% | -13.62% | -13.62% | -5.617% | -13.62% | -13.62% | -13.62% | -13.62% | -13.62% | -4.291% | -4.291% | -27.64% | -27.64% | -27.64% | -27.64% | -7.956% | -4.291% | -4.291% | -6.123% | -7.956% | -4.291% | -4.291% | -13.62% | -5.617% | -27.64% | -27.64% | 3% | 3% | 2.7% | 2.7% | 2.7% | 3% | 3.6% | 3% | 3.6% | -7.431% | -7.431% | -4.436% | 3% | 3% | 3.6% | 3.6% | -6.468% | -10% | -10% | -6.319% | 3% | -7.949% | -7.42% | -7.42% | -7.42% | -7.42% | -7.42% | -7.42% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -16.03% | -16.03% | -16.03% | -16.03% | -16.03% | -16.03% | -16.03% | -7.949% | -7.949% | -7.949% | -23.13% | -23.13% | -23.13% | -23.13% | -23.13% | -6.319% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | 3% | 3% | 3% | 3% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -14.99% | -18.31% | -17.76% | -12.73%
| P20 | 20% | #DIV/0! | #DIV/0! | #DIV/0! | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -17.43% | -17.43% | -17.43% | -17.43% | -8.995% | -8.995% | -8.995% | -8.995% | -8.995% | 0% | -8.995% | -8.995% | -8.995% | -8.995% | -8.995% | -0.3492% | -0.3492% | -17.43% | -17.43% | -17.43% | -17.43% | -5.307% | -0.3492% | -0.3492% | -2.828% | -5.307% | -0.3492% | -0.3492% | -8.995% | 0% | -17.43% | -17.43% | 5.105% | 5.105% | 4.594% | 4.594% | 4.594% | 5.105% | 6.126% | 5.105% | 6.126% | -2.946% | -2.946% | -2.435% | 5.105% | 5.105% | 6.126% | 6.126% | -2.733% | -5.281% | -5.281% | -2.807% | 5.105% | -4.198% | -4.568% | -4.568% | -4.568% | -4.568% | -4.568% | -4.568% | 4.09% | 4.09% | 4.09% | 4.09% | 4.09% | 4.09% | 4.09% | -12.11% | -12.11% | -12.11% | -12.11% | -12.11% | -12.11% | -12.11% | -4.198% | -4.198% | -4.198% | -16.92% | -16.92% | -16.92% | -16.92% | -16.92% | -2.807% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | 5.105% | 5.105% | 5.105% | 5.105% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -9.894% | -13.89% | -9.457% | -6.412%
| P25 | 25% | #DIV/0! | #DIV/0! | #DIV/0! | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -10.51% | -10.51% | -10.51% | -10.51% | -3.161% | -3.161% | -3.161% | -3.161% | -3.161% | 0% | -3.161% | -3.161% | -3.161% | -3.161% | -3.161% | 0% | 0% | -10.51% | -10.51% | -10.51% | -10.51% | 13.12% | 0% | 0% | 6.561% | 13.12% | 0% | 0% | -3.161% | 0% | -10.51% | -10.51% | 7% | 7% | 6.3% | 6.3% | 6.3% | 7% | 8.4% | 7% | 8.4% | -0.001784% | -0.001784% | -1.861% | 7% | 7% | 8.4% | 8.4% | 0% | -1.713% | -1.713% | -0.3264% | 7% | -1.51% | -2.84% | -2.84% | -2.84% | -2.84% | -2.84% | -2.84% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -1.51% | -1.51% | -1.51% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -0.3264% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7% | 7% | 7% | 7% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -3.477% | -6.733% | -3.511% | -2.882%
| P30 | 30% | #DIV/0! | #DIV/0! | #DIV/0! | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -9.25% | -9.25% | -9.25% | -9.25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4% | 1.4% | -9.25% | -9.25% | -9.25% | -9.25% | 21.77% | 1.4% | 1.4% | 11.59% | 21.77% | 1.4% | 1.4% | 0% | 0% | -9.25% | -9.25% | 9% | 9% | 8.1% | 8.1% | 8.1% | 9% | 10.8% | 9% | 10.8% | 0.9166% | 0.9166% | 0.2737% | 9% | 9% | 10.8% | 10.8% | 0.0396% | 0% | 0% | 0% | 9% | 2.097% | -0.756% | -0.756% | -0.756% | -0.756% | -0.756% | -0.756% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | 2.097% | 2.097% | 2.097% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 0% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 9% | 9% | 9% | 9% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | 0% | -0.6252% | -0.06312% | 0.499%
| P35 | 35% | #DIV/0! | #DIV/0! | #DIV/0! | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -8.076% | -8.076% | -8.076% | -8.076% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.6314% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 3.966% | 3.966% | -8.076% | -8.076% | -8.076% | -8.076% | 24.46% | 3.966% | 3.966% | 14.21% | 24.46% | 3.966% | 3.966% | 0.3062% | 0.6314% | -8.076% | -8.076% | 11% | 11% | 9.9% | 9.9% | 9.9% | 11% | 13.2% | 11% | 13.2% | 4% | 4% | 4.16% | 11% | 11% | 13.2% | 13.2% | 3.361% | 2.492% | 2.492% | 0% | 11% | 4.1% | 0% | 0% | 0% | 0% | 0% | 0% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | 4.1% | 4.1% | 4.1% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 0% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 11% | 11% | 11% | 11% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | 0.3368% | 2.962% | 3.333% | 3.703%
| P40 | 40% | #DIV/0! | #DIV/0! | #DIV/0! | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -6.941% | -6.941% | -6.941% | -6.941% | 1.544% | 1.544% | 1.544% | 1.544% | 1.544% | 2.686% | 1.544% | 1.544% | 1.544% | 1.544% | 1.544% | 9% | 9% | -6.941% | -6.941% | -6.941% | -6.941% | 25% | 9% | 9% | 17% | 25% | 9% | 9% | 1.544% | 2.686% | -6.941% | -6.941% | 13.4% | 13.4% | 12.06% | 12.06% | 12.06% | 13.4% | 16.08% | 13.4% | 16.08% | 8% | 8% | 9.418% | 13.4% | 13.4% | 16.08% | 16.08% | 7.32% | 7.636% | 7.636% | 0% | 13.4% | 5.944% | 0% | 0% | 0% | 0% | 0% | 0% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 5.944% | 5.944% | 5.944% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 0% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 13.4% | 13.4% | 13.4% | 13.4% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | 1.699% | 6.488% | 6.729% | 6.97%
| P45 | 45% | #DIV/0! | #DIV/0! | #DIV/0! | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.392% | -4.392% | -4.392% | -4.392% | 2.788% | 2.788% | 2.788% | 2.788% | 2.788% | 5.25% | 2.788% | 2.788% | 2.788% | 2.788% | 2.788% | 12% | 12% | -4.392% | -4.392% | -4.392% | -4.392% | 25.72% | 12% | 12% | 18.86% | 25.72% | 12% | 12% | 2.788% | 5.25% | -4.392% | -4.392% | 16% | 16% | 14.4% | 14.4% | 14.4% | 16% | 19.2% | 16% | 19.2% | 11.75% | 11.75% | 11.03% | 16% | 16% | 19.2% | 19.2% | 11.16% | 15% | 15% | 2% | 16% | 7.509% | 0% | 0% | 0% | 0% | 0% | 0% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 7.509% | 7.509% | 7.509% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 2% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 16% | 16% | 16% | 16% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | 3.067% | 10.16% | 10.3% | 10.43%
| P50 | 50% | #DIV/0! | #DIV/0! | #DIV/0! | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -2.156% | -2.156% | -2.156% | -2.156% | 4.197% | 4.197% | 4.197% | 4.197% | 4.197% | 8.941% | 4.197% | 4.197% | 4.197% | 4.197% | 4.197% | 13.33% | 13.33% | -2.156% | -2.156% | -2.156% | -2.156% | 31.5% | 13.33% | 13.33% | 22.42% | 31.5% | 13.33% | 13.33% | 4.197% | 8.941% | -2.156% | -2.156% | 18% | 18% | 16.2% | 16.2% | 16.2% | 18% | 21.6% | 18% | 21.6% | 15.14% | 15.14% | 15.88% | 18% | 18% | 21.6% | 21.6% | 15% | 20.15% | 20.15% | 4.836% | 18% | 10.35% | 0% | 0% | 0% | 0% | 0% | 0% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 10.35% | 10.35% | 10.35% | 10.82% | 10.82% | 10.82% | 10.82% | 10.82% | 4.836% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 18% | 18% | 18% | 18% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | 4.616% | 14.07% | 13.9% | 13.73%
| P55 | 55% | #DIV/0! | #DIV/0! | #DIV/0! | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 7.413% | 7.413% | 7.413% | 7.413% | 7.413% | 14.43% | 7.413% | 7.413% | 7.413% | 7.413% | 7.413% | 18.38% | 18.38% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 37.41% | 18.38% | 18.38% | 27.89% | 37.41% | 18.38% | 18.38% | 7.413% | 14.43% | 0.6532% | 0.6532% | 20.55% | 20.55% | 18.5% | 18.5% | 18.5% | 20.55% | 24.66% | 20.55% | 24.66% | 20% | 20% | 20.96% | 20.55% | 20.55% | 24.66% | 24.66% | 20% | 23% | 23% | 8% | 20.55% | 12.29% | 0% | 0% | 0% | 0% | 0% | 0% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 12.29% | 12.29% | 12.29% | 15.51% | 15.51% | 15.51% | 15.51% | 15.51% | 8% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 20.55% | 20.55% | 20.55% | 20.55% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 8.155% | 17.2% | 17.01% | 16.83%
| P60 | 60% | #DIV/0! | #DIV/0! | #DIV/0! | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | 3.111% | 3.111% | 3.111% | 3.111% | 11.31% | 11.31% | 11.31% | 11.31% | 11.31% | 18.04% | 11.31% | 11.31% | 11.31% | 11.31% | 11.31% | 22% | 22% | 3.111% | 3.111% | 3.111% | 3.111% | 38.53% | 22% | 22% | 30.27% | 38.53% | 22% | 22% | 11.31% | 18.04% | 3.111% | 3.111% | 23% | 23% | 20.7% | 20.7% | 20.7% | 23% | 27.6% | 23% | 27.6% | 28.12% | 28.12% | 26.15% | 23% | 23% | 27.6% | 27.6% | 26% | 26% | 26% | 11.32% | 23% | 14.85% | 0.952% | 0.952% | 0.952% | 0.952% | 0.952% | 0.952% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 14.85% | 14.85% | 14.85% | 17.3% | 17.3% | 17.3% | 17.3% | 17.3% | 11.32% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 23% | 23% | 23% | 23% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 12.45% | 20.86% | 20.65% | 20.45%
| P65 | 65% | #DIV/0! | #DIV/0! | #DIV/0! | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 4.563% | 4.563% | 4.563% | 4.563% | 12.52% | 12.52% | 12.52% | 12.52% | 12.52% | 30.36% | 12.52% | 12.52% | 12.52% | 12.52% | 12.52% | 34.89% | 34.89% | 4.563% | 4.563% | 4.563% | 4.563% | 40.31% | 34.89% | 34.89% | 37.6% | 40.31% | 34.89% | 34.89% | 12.52% | 30.36% | 4.563% | 4.563% | 25.65% | 25.65% | 23.09% | 23.09% | 23.09% | 25.65% | 30.78% | 25.65% | 30.78% | 33.05% | 33.05% | 34.63% | 25.65% | 25.65% | 30.78% | 30.78% | 33% | 31.7% | 31.7% | 14.94% | 25.65% | 18.83% | 5.757% | 5.757% | 5.757% | 5.757% | 5.757% | 5.757% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 18.83% | 18.83% | 18.83% | 30.04% | 30.04% | 30.04% | 30.04% | 30.04% | 14.94% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 25.65% | 25.65% | 25.65% | 25.65% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 13.78% | 40.74% | 27.21% | 26.68%
| P70 | 70% | #DIV/0! | #DIV/0! | #DIV/0! | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 5.862% | 5.862% | 5.862% | 5.862% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 38.57% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 44.74% | 44.74% | 5.862% | 5.862% | 5.862% | 5.862% | 44.99% | 44.74% | 44.74% | 44.87% | 44.99% | 44.74% | 44.74% | 16.23% | 38.57% | 5.862% | 5.862% | 29% | 29% | 26.1% | 26.1% | 26.1% | 29% | 34.8% | 29% | 34.8% | 43% | 43% | 41.67% | 29% | 29% | 34.8% | 34.8% | 42.86% | 33.6% | 33.6% | 18.04% | 29% | 21.45% | 8.737% | 8.737% | 8.737% | 8.737% | 8.737% | 8.737% | 31.66% | 31.66% | 31.66% | 31.66% | 31.66% | 31.66% | 31.66% | 23.95% | 23.95% | 23.95% | 23.95% | 23.95% | 23.95% | 23.95% | 21.45% | 21.45% | 21.45% | 35.57% | 35.57% | 35.57% | 35.57% | 35.57% | 18.04% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 29% | 29% | 29% | 29% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 17.85% | 47.06% | 34.68% | 32.57%
| P75 | 75% | #DIV/0! | #DIV/0! | #DIV/0! | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 16.23% | 16.23% | 16.23% | 16.23% | 21.6% | 21.6% | 21.6% | 21.6% | 21.6% | 62.94% | 21.6% | 21.6% | 21.6% | 21.6% | 21.6% | 57% | 57% | 16.23% | 16.23% | 16.23% | 16.23% | 50.28% | 57% | 57% | 53.64% | 50.28% | 57% | 57% | 21.6% | 62.94% | 16.23% | 16.23% | 33% | 33% | 29.7% | 29.7% | 29.7% | 33% | 39.6% | 33% | 39.6% | 50.56% | 50.56% | 49.44% | 33% | 33% | 39.6% | 39.6% | 51% | 48.35% | 48.35% | 23% | 33% | 27.02% | 12.44% | 12.44% | 12.44% | 12.44% | 12.44% | 12.44% | 38.93% | 38.93% | 38.93% | 38.93% | 38.93% | 38.93% | 38.93% | 29.69% | 29.69% | 29.69% | 29.69% | 29.69% | 29.69% | 29.69% | 27.02% | 27.02% | 27.02% | 40.59% | 40.59% | 40.59% | 40.59% | 40.59% | 23% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 33% | 33% | 33% | 33% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 23.76% | 86.6% | 52.64% | 41.27%
| P80 | 80% | #DIV/0! | #DIV/0! | #DIV/0! | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 18.2% | 18.2% | 18.2% | 18.2% | 32.12% | 32.12% | 32.12% | 32.12% | 32.12% | 68.74% | 32.12% | 32.12% | 32.12% | 32.12% | 32.12% | 83.95% | 83.95% | 18.2% | 18.2% | 18.2% | 18.2% | 53.92% | 83.95% | 83.95% | 68.93% | 53.92% | 83.95% | 83.95% | 32.12% | 68.74% | 18.2% | 18.2% | 37% | 37% | 33.3% | 33.3% | 33.3% | 37% | 44.4% | 37% | 44.4% | 56.93% | 56.93% | 60.02% | 37% | 37% | 44.4% | 44.4% | 60.4% | 62.09% | 62.09% | 28% | 37% | 31.78% | 15.31% | 15.31% | 15.31% | 15.31% | 15.31% | 15.31% | 45.03% | 45.03% | 45.03% | 45.03% | 45.03% | 45.03% | 45.03% | 35.01% | 35.01% | 35.01% | 35.01% | 35.01% | 35.01% | 35.01% | 31.78% | 31.78% | 31.78% | 44.73% | 44.73% | 44.73% | 44.73% | 44.73% | 28% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 37% | 37% | 37% | 37% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 35.34% | 114.8% | 68.76% | 50.97%
| P85 | 85% | #DIV/0! | #DIV/0! | #DIV/0! | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 21.48% | 21.48% | 21.48% | 21.48% | 61.21% | 61.21% | 61.21% | 61.21% | 61.21% | 73.4% | 61.21% | 61.21% | 61.21% | 61.21% | 61.21% | 127.2% | 127.2% | 21.48% | 21.48% | 21.48% | 21.48% | 57.17% | 127.2% | 127.2% | 92.16% | 57.17% | 127.2% | 127.2% | 61.21% | 73.4% | 21.48% | 21.48% | 40.85% | 40.85% | 36.76% | 36.76% | 36.76% | 40.85% | 49.02% | 40.85% | 49.02% | 67.7% | 67.7% | 85% | 40.85% | 40.85% | 49.02% | 49.02% | 75% | 71.26% | 71.26% | 38.04% | 40.85% | 43.81% | 17.39% | 17.39% | 17.39% | 17.39% | 17.39% | 17.39% | 67.93% | 67.93% | 67.93% | 67.93% | 67.93% | 67.93% | 67.93% | 46.1% | 46.1% | 46.1% | 46.1% | 46.1% | 46.1% | 46.1% | 43.81% | 43.81% | 43.81% | 51.32% | 51.32% | 51.32% | 51.32% | 51.32% | 38.04% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 40.85% | 40.85% | 40.85% | 40.85% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 67.33% | 130.5% | 84.06% | 65.21%
| P90 | 90% | #DIV/0! | #DIV/0! | #DIV/0! | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 23.77% | 23.77% | 23.77% | 23.77% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 97.61% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 200% | 200% | 23.77% | 23.77% | 23.77% | 23.77% | 79.12% | 200% | 200% | 139.6% | 79.12% | 200% | 200% | 105.6% | 97.61% | 23.77% | 23.77% | 50.8% | 50.8% | 45.72% | 45.72% | 45.72% | 50.8% | 60.96% | 50.8% | 60.96% | 83% | 83% | 129.9% | 50.8% | 50.8% | 60.96% | 60.96% | 102.8% | 100.6% | 100.6% | 56.21% | 50.8% | 52.04% | 24.1% | 24.1% | 24.1% | 24.1% | 24.1% | 24.1% | 76.38% | 76.38% | 76.38% | 76.38% | 76.38% | 76.38% | 76.38% | 55.63% | 55.63% | 55.63% | 55.63% | 55.63% | 55.63% | 55.63% | 52.04% | 52.04% | 52.04% | 54.55% | 54.55% | 54.55% | 54.55% | 54.55% | 56.21% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 50.8% | 50.8% | 50.8% | 50.8% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 116.2% | 270.4% | 115.4% | 90.32%
| P95 | 95% | #DIV/0! | #DIV/0! | #DIV/0! | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 79.21% | 79.21% | 79.21% | 79.21% | 208.3% | 208.3% | 208.3% | 208.3% | 208.3% | 147.9% | 208.3% | 208.3% | 208.3% | 208.3% | 208.3% | 271.2% | 271.2% | 79.21% | 79.21% | 79.21% | 79.21% | 106% | 271.2% | 271.2% | 188.6% | 106% | 271.2% | 271.2% | 208.3% | 147.9% | 79.21% | 79.21% | 66.92% | 66.92% | 60.23% | 60.23% | 60.23% | 66.92% | 80.3% | 66.92% | 80.3% | 115.1% | 115.1% | 185.4% | 66.92% | 66.92% | 80.3% | 80.3% | 187.2% | 144.6% | 144.6% | 82.6% | 66.92% | 78.33% | 33.01% | 33.01% | 33.01% | 33.01% | 33.01% | 33.01% | 123.6% | 123.6% | 123.6% | 123.6% | 123.6% | 123.6% | 123.6% | 78.34% | 78.34% | 78.34% | 78.34% | 78.34% | 78.34% | 78.34% | 78.33% | 78.33% | 78.33% | 69.82% | 69.82% | 69.82% | 69.82% | 69.82% | 82.6% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 66.92% | 66.92% | 66.92% | 66.92% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 229.1% | 363% | 212.6% | 180%
| P100 | 100% |  | #DIV/0! | #DIV/0! | [139 empty] | 53.62% | 30.06% | 25.77%
|  | Mean: | #DIV/0!

## RCF SOBC data (hidden)
SOBC
| Primary RCF Data |  | Land Costs | [8 empty] | Planning |  |  |  | Build Cost (Base build total cost) |  |  | Building | [7 empty] | External Works |  | Management costs |  |  |  | Site Preparation | [6 empty] | Foundations |  | Infrastructure and highways | [22 empty] | Utilities | [23 empty] | Drainage | [5 empty] | Ecology | [11 empty] | Landscaping/ Public Realm |  |  |  | Surveys and Fees |  |  |  |  | Sales and Marketing |  | Profit (inclusive of any developer Overheads, aftercare and sales incentives) | [7 empty] | Community Infrastructure Levy (CIL) |  | Section 106 Obligations | [12 empty] | Other Abnormal Costs
|  |  | General L&P | Acquisition Cost | Agent and Legal fees | SDLT | Access Rights | Ransom Payments | Option Fees | Overage | Additional Land Acquisition | Planning general | Outline Planning | Reserved Matters Planning | Other Planning Costs | Standard construction and foundations | Preliminaries apportioned | Contractors' overheads and profits (not developers’) | General: unspecified | Residential | Custom build properties | Building affordable housing | Commercial (shop units/ offices space | Light industrial (warehousing/ distribution) | Film studios/ creative space | Community/ public buildings | Associated with houses | Associated with apartments | General | Maintenance & protection of a heritage asset | Other holding costs/ estate management | Professional Fees: General | Demolition | Enabling works | Remediation and Decontamination |  |  | Due Diligence (survey works) | Archaeology/Heritage surveys | Standard foundations | Abnormal Foundations | Highway and Transport Design Works | Noise and Vibration Design Works | S278 works | Offsite Highways works (breakdown by type of works as feasible) | [7 empty] | Public Transport |  |  |  | Spine Road | Roundabouts | Junctions | Other civil works |  |  |  | Part 1 Claims | Unspecified | Electricity | [5 empty] | Gas | [6 empty] | Water | [6 empty] | District Heating | Telecoms | Renewable Energy | General | Pumping Station | SUDS/Swales/Tanks/Attenuation |  | Sewers | Flood Risk | General | Ecology Design Work | Arboriculture | Mitigation | Nitrogen neutrality | Water Neutrality | Biodiversity Net Gain (BNG) | Invasive Species | Birds and Bats | SANGS | Invertebrates/vertebrates | Mammals | Public Realm / Public Open Space | Play areas / Outdoor sports | Endowment | Public Art | Valuation and Appraisal Advice | Legal Advice | Development Management / Master Developer Fees | Health and Safety Advice | Communications Fees | Agent Fees | Legal Fees | Profit on Market Sale | Profit on Affordable | Profit on Commercial | Profit on PRS | Total Blended Profit | Internal Rate of Return (IRR) | Development Management Fee | Return On Capital Employed (ROCE) | CIL Residential | CIL Commercial | General | Roof Tax | Affordable Housing Offsite Payment | Community Facilities | Employment and Skills | Healthcare | Highways / Transport | Education (primary and secondary) | Libraries | Public Realm/Open Space | Monitoring Fee | Play areas | Sports Fields
| RCF Values | [33 empty] | Simple | complex/ brownfield | heavily contaminated | [7 empty] | Unspecified or mixed | Footpaths | Cycle paths | Parking (surface) | Urban roads - standard | Urban roads - complex | Rural roads - standard | Rural roads - complex | Unspecified or mixed | Rail | Stations | Buslanes |  |  |  | Unspecified or mixed | Bridges/ other structures | Tunnels | Earthworks |  |  | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs legal fees for wayleaves, licences, supply agreements, compensation claims | Easement costs | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, Compensation claims | Easement costs | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, compensation claims | Easement Costs | Capital cost, plot costs, legals and heat charger | Upgrading cables | CHP, non plot specific EV charging or solar |  |  | Includes landscaping features associated with attenuation ponds | Beyond plot specific measures included in externals (such as permeable drives) | Includes Surface and Foul beyond standard included in Externals and/or spine road | Includes land raising/barriers/defence |  |  | Covers tree surgery and/or tree protection works | i.e. offsite contribution, Habitat Regulation Assessment, | [6 empty] | Newts – including fencing and ladders | Dormice, badgers | Estate costs/shared areas not included in external works including landscaping wildflower meadows. | in addition to any S. 106 requirements | for long term management | in addition to any S. 106 requirements | (beyond standard house building Professional fees and not included in specialist categories above) | state aid advice, specific questions on ransoms etc. | These include fees paid to development managers/ Master Developers of the site or collaboration costs. | e.g. highways, reservoirs | Fees for example related to any PR on the site but not planning related costs.
| Notes |  | L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | Design | Same | Same | Same | Bldg | Same | Same | Bldg | Same | Bld 0-5 y | Same | Same | Same | Same | Same | EW | EW | Mngt | Same | Same | Same | Demolition | EW | EW | (EW+Facil W)/2 | Facil Works | EW x | EW x | Bldg x | Bld 0-5 y | Design | Design | Roads | Roads | Roads x | Roads x | Roads x | Urban roads std | Urban roads cx | Rural std | Rural cx | As Rail | Rail | Stations | Roads | Spine roads | Roads | Junctions | Civils | Bridges | Tunnels | Earthworks | Roads | Gen Utilities | Elec | Elec x | Elec x | Elec x | Elec x | Elec x | Gas | Gas x | Gas x | Gas x | Gas x | Gas x | Gas x | Water | Water x | Water x | Water x | Water x | Water x | Water x | Gen x | Gen x | Gen x | Drng | Drng x | Drng x | Drng x | Drng x | Landraising | Enab W x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Roads x | Roads x | Roads x | Roads x | Mngt | Fees x | Fees x | Fees x | Fees x | Fees x | Fees x | As mngt | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Mngt x | Mngt x | Mngt | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | Bldg
| Factor |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | [5 empty] | 1 | 1 | 1 |  |  |  | 1 |  | 0.9 | 0.9 | 0.9 | 1 | 1.2 | 1 | 1.2 | 1 |  |  | 1 | 1 | 1.2 | 1.2 |  |  |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1
Cost RCF
| P0 | 0%
| P5 | 5% | -92.48% | -92.48% | -92.48% | -92.48% | -92.48% | -92.48% | -92.48% | -92.48% | -92.48% | -50.26% | -50.26% | -50.26% | -50.26% | -33.26% | -33.26% | -33.26% | -33.26% | -33.26% | -28.69% | -33.26% | -33.26% | -33.26% | -33.26% | -33.26% | -27.65% | -27.65% | -50.26% | -50.26% | -50.26% | -50.26% | -24.82% | -27.65% | -27.65% | -26.24% | -24.82% | -27.65% | -27.65% | -33.26% | -28.69% | -50.26% | -50.26% | -16.82% | -16.82% | -15.14% | -15.14% | -15.14% | -16.82% | -20.19% | -16.82% | -20.19% | -29.47% | -29.47% | -21.12% | -16.82% | -16.82% | -20.19% | -20.19% | -25.95% | -30.82% | -30.82% | -29.63% | -16.82% | -34.57% | -38.51% | -38.51% | -38.51% | -38.51% | -38.51% | -38.51% | -23.16% | -23.16% | -23.16% | -23.16% | -23.16% | -23.16% | -23.16% | -42.03% | -42.03% | -42.03% | -42.03% | -42.03% | -42.03% | -42.03% | -34.57% | -34.57% | -34.57% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -29.63% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -16.82% | -16.82% | -16.82% | -16.82% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -50.26% | -36.58%
| P10 | 10% | -86.95% | -86.95% | -86.95% | -86.95% | -86.95% | -86.95% | -86.95% | -86.95% | -86.95% | -42.08% | -42.08% | -42.08% | -42.08% | -27% | -27% | -27% | -27% | -27% | -23.65% | -27% | -27% | -27% | -27% | -27% | -20.42% | -20.42% | -42.08% | -42.08% | -42.08% | -42.08% | -19.97% | -20.42% | -20.42% | -20.2% | -19.97% | -20.42% | -20.42% | -27% | -23.65% | -42.08% | -42.08% | -8.824% | -8.824% | -7.942% | -7.942% | -7.942% | -8.824% | -10.59% | -8.824% | -10.59% | -21.27% | -21.27% | -16.44% | -8.824% | -8.824% | -10.59% | -10.59% | -19.18% | -25.17% | -25.17% | -20.82% | -8.824% | -25.93% | -25.91% | -25.91% | -25.91% | -25.91% | -25.91% | -25.91% | -17.29% | -17.29% | -17.29% | -17.29% | -17.29% | -17.29% | -17.29% | -34.57% | -34.57% | -34.57% | -34.57% | -34.57% | -34.57% | -34.57% | -25.93% | -25.93% | -25.93% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -20.82% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -8.824% | -8.824% | -8.824% | -8.824% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -42.08% | -29.7%
| P15 | 15% | -72.36% | -72.36% | -72.36% | -72.36% | -72.36% | -72.36% | -72.36% | -72.36% | -72.36% | -24.86% | -24.86% | -24.86% | -24.86% | -19.45% | -19.45% | -19.45% | -19.45% | -19.45% | -11.44% | -19.45% | -19.45% | -19.45% | -19.45% | -19.45% | -10.12% | -10.12% | -24.86% | -24.86% | -24.86% | -24.86% | -13.78% | -10.12% | -10.12% | -11.95% | -13.78% | -10.12% | -10.12% | -19.45% | -11.44% | -24.86% | -24.86% | -2.825% | -2.825% | -2.543% | -2.543% | -2.543% | -2.825% | -3.39% | -2.825% | -3.39% | -13.26% | -13.26% | -10.26% | -2.825% | -2.825% | -3.39% | -3.39% | -1% | -15.83% | -15.83% | -12.14% | -2.825% | -13.77% | -13.24% | -13.24% | -13.24% | -13.24% | -13.24% | -13.24% | -6.22% | -6.22% | -6.22% | -6.22% | -6.22% | -6.22% | -6.22% | -21.86% | -21.86% | -21.86% | -21.86% | -21.86% | -21.86% | -21.86% | -13.77% | -13.77% | -13.77% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -12.14% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -2.825% | -2.825% | -2.825% | -2.825% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -24.86% | -21.39%
| P20 | 20% | -60.84% | -60.84% | -60.84% | -60.84% | -60.84% | -60.84% | -60.84% | -60.84% | -60.84% | -14.16% | -14.16% | -14.16% | -14.16% | -15.74% | -15.74% | -15.74% | -15.74% | -15.74% | -6.745% | -15.74% | -15.74% | -15.74% | -15.74% | -15.74% | -7.094% | -7.094% | -14.16% | -14.16% | -14.16% | -14.16% | -12.05% | -7.094% | -7.094% | -9.573% | -12.05% | -7.094% | -7.094% | -15.74% | -6.745% | -14.16% | -14.16% | -1.64% | -1.64% | -1.476% | -1.476% | -1.476% | -1.64% | -1.968% | -1.64% | -1.968% | -9.691% | -9.691% | -9.18% | -1.64% | -1.64% | -1.968% | -1.968% | 1% | -12.03% | -12.03% | -9.551% | -1.64% | -10.94% | -11.31% | -11.31% | -11.31% | -11.31% | -11.31% | -11.31% | -2.655% | -2.655% | -2.655% | -2.655% | -2.655% | -2.655% | -2.655% | -18.86% | -18.86% | -18.86% | -18.86% | -18.86% | -18.86% | -18.86% | -10.94% | -10.94% | -10.94% | -23.66% | -23.66% | -23.66% | -23.66% | -23.66% | -9.551% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -1.64% | -1.64% | -1.64% | -1.64% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -14.16% | -17.31%
| P25 | 25% | -43.73% | -43.73% | -43.73% | -43.73% | -43.73% | -43.73% | -43.73% | -43.73% | -43.73% | -5.324% | -5.324% | -5.324% | -5.324% | -5.891% | -5.891% | -5.891% | -5.891% | -5.891% | -2.73% | -5.891% | -5.891% | -5.891% | -5.891% | -5.891% | -2.73% | -2.73% | -5.324% | -5.324% | -5.324% | -5.324% | 10.39% | -2.73% | -2.73% | 3.831% | 10.39% | -2.73% | -2.73% | -5.891% | -2.73% | -5.324% | -5.324% | 4.27% | 4.27% | 3.843% | 3.843% | 3.843% | 4.27% | 5.124% | 4.27% | 5.124% | -2.732% | -2.732% | -4.591% | 4.27% | 4.27% | 5.124% | 5.124% | 4% | -4.443% | -4.443% | -3.056% | 4.27% | -4.24% | -5.57% | -5.57% | -5.57% | -5.57% | -5.57% | -5.57% | 2.943% | 2.943% | 2.943% | 2.943% | 2.943% | 2.943% | 2.943% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -4.24% | -4.24% | -4.24% | -6.144% | -6.144% | -6.144% | -6.144% | -6.144% | -3.056% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | 4.27% | 4.27% | 4.27% | 4.27% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -5.324% | -6.48%
| P30 | 30% | -39.84% | -39.84% | -39.84% | -39.84% | -39.84% | -39.84% | -39.84% | -39.84% | -39.84% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4% | 1.4% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | 21.77% | 1.4% | 1.4% | 11.59% | 21.77% | 1.4% | 1.4% | 0% | 0% | -0.9091% | -0.9091% | 9% | 9% | 8.1% | 8.1% | 8.1% | 9% | 10.8% | 9% | 10.8% | 0.9166% | 0.9166% | 0.2737% | 9% | 9% | 10.8% | 10.8% | 0.0396% | 0% | 0% | 0% | 9% | 2.097% | -0.756% | -0.756% | -0.756% | -0.756% | -0.756% | -0.756% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | 2.097% | 2.097% | 2.097% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 0% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 9% | 9% | 9% | 9% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | -0.9091% | 0%
| P35 | 35% | -24.74% | -24.74% | -24.74% | -24.74% | -24.74% | -24.74% | -24.74% | -24.74% | -24.74% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.6314% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 3.966% | 3.966% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 24.46% | 3.966% | 3.966% | 14.21% | 24.46% | 3.966% | 3.966% | 0.3062% | 0.6314% | 0.5478% | 0.5478% | 11% | 11% | 9.9% | 9.9% | 9.9% | 11% | 13.2% | 11% | 13.2% | 4% | 4% | 4.16% | 11% | 11% | 13.2% | 13.2% | 3.361% | 2.492% | 2.492% | 0% | 11% | 4.1% | 0% | 0% | 0% | 0% | 0% | 0% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | 4.1% | 4.1% | 4.1% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 0% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 11% | 11% | 11% | 11% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.5478% | 0.3368%
| P40 | 40% | -15.52% | -15.52% | -15.52% | -15.52% | -15.52% | -15.52% | -15.52% | -15.52% | -15.52% | 2.137% | 2.137% | 2.137% | 2.137% | 1.544% | 1.544% | 1.544% | 1.544% | 1.544% | 2.686% | 1.544% | 1.544% | 1.544% | 1.544% | 1.544% | 9% | 9% | 2.137% | 2.137% | 2.137% | 2.137% | 25% | 9% | 9% | 17% | 25% | 9% | 9% | 1.544% | 2.686% | 2.137% | 2.137% | 13.4% | 13.4% | 12.06% | 12.06% | 12.06% | 13.4% | 16.08% | 13.4% | 16.08% | 8% | 8% | 9.418% | 13.4% | 13.4% | 16.08% | 16.08% | 7.32% | 7.636% | 7.636% | 0% | 13.4% | 5.944% | 0% | 0% | 0% | 0% | 0% | 0% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 5.944% | 5.944% | 5.944% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 0% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 13.4% | 13.4% | 13.4% | 13.4% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 2.137% | 1.699%
| P45 | 45% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | 3.061% | 3.061% | 3.061% | 3.061% | 2.788% | 2.788% | 2.788% | 2.788% | 2.788% | 5.25% | 2.788% | 2.788% | 2.788% | 2.788% | 2.788% | 12% | 12% | 3.061% | 3.061% | 3.061% | 3.061% | 25.72% | 12% | 12% | 18.86% | 25.72% | 12% | 12% | 2.788% | 5.25% | 3.061% | 3.061% | 16% | 16% | 14.4% | 14.4% | 14.4% | 16% | 19.2% | 16% | 19.2% | 11.75% | 11.75% | 11.03% | 16% | 16% | 19.2% | 19.2% | 11.16% | 15% | 15% | 2% | 16% | 7.509% | 0% | 0% | 0% | 0% | 0% | 0% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 7.509% | 7.509% | 7.509% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 2% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 16% | 16% | 16% | 16% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.061% | 3.067%
| P50 | 50% | 3.423% | 3.423% | 3.423% | 3.423% | 3.423% | 3.423% | 3.423% | 3.423% | 3.423% | 8.123% | 8.123% | 8.123% | 8.123% | 4.197% | 4.197% | 4.197% | 4.197% | 4.197% | 8.941% | 4.197% | 4.197% | 4.197% | 4.197% | 4.197% | 13.33% | 13.33% | 8.123% | 8.123% | 8.123% | 8.123% | 31.5% | 13.33% | 13.33% | 22.42% | 31.5% | 13.33% | 13.33% | 4.197% | 8.941% | 8.123% | 8.123% | 18% | 18% | 16.2% | 16.2% | 16.2% | 18% | 21.6% | 18% | 21.6% | 15.14% | 15.14% | 15.88% | 18% | 18% | 21.6% | 21.6% | 15% | 20.15% | 20.15% | 4.836% | 18% | 10.35% | 0% | 0% | 0% | 0% | 0% | 0% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 10.35% | 10.35% | 10.35% | 10.82% | 10.82% | 10.82% | 10.82% | 10.82% | 4.836% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 18% | 18% | 18% | 18% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 8.123% | 4.616%
| P55 | 55% | 5.623% | 5.623% | 5.623% | 5.623% | 5.623% | 5.623% | 5.623% | 5.623% | 5.623% | 13.59% | 13.59% | 13.59% | 13.59% | 7.413% | 7.413% | 7.413% | 7.413% | 7.413% | 14.43% | 7.413% | 7.413% | 7.413% | 7.413% | 7.413% | 18.38% | 18.38% | 13.59% | 13.59% | 13.59% | 13.59% | 37.41% | 18.38% | 18.38% | 27.89% | 37.41% | 18.38% | 18.38% | 7.413% | 14.43% | 13.59% | 13.59% | 20.55% | 20.55% | 18.5% | 18.5% | 18.5% | 20.55% | 24.66% | 20.55% | 24.66% | 20% | 20% | 20.96% | 20.55% | 20.55% | 24.66% | 24.66% | 20% | 23% | 23% | 8% | 20.55% | 12.29% | 0% | 0% | 0% | 0% | 0% | 0% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 12.29% | 12.29% | 12.29% | 15.51% | 15.51% | 15.51% | 15.51% | 15.51% | 8% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 20.55% | 20.55% | 20.55% | 20.55% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 13.59% | 8.155%
| P60 | 60% | 8.066% | 8.066% | 8.066% | 8.066% | 8.066% | 8.066% | 8.066% | 8.066% | 8.066% | 17.57% | 17.57% | 17.57% | 17.57% | 11.31% | 11.31% | 11.31% | 11.31% | 11.31% | 18.04% | 11.31% | 11.31% | 11.31% | 11.31% | 11.31% | 22% | 22% | 17.57% | 17.57% | 17.57% | 17.57% | 38.53% | 22% | 22% | 30.27% | 38.53% | 22% | 22% | 11.31% | 18.04% | 17.57% | 17.57% | 23% | 23% | 20.7% | 20.7% | 20.7% | 23% | 27.6% | 23% | 27.6% | 28.12% | 28.12% | 26.15% | 23% | 23% | 27.6% | 27.6% | 26% | 26% | 26% | 11.32% | 23% | 14.85% | 0.952% | 0.952% | 0.952% | 0.952% | 0.952% | 0.952% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 14.85% | 14.85% | 14.85% | 17.3% | 17.3% | 17.3% | 17.3% | 17.3% | 11.32% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 23% | 23% | 23% | 23% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 17.57% | 12.45%
| P65 | 65% | 22.01% | 22.01% | 22.01% | 22.01% | 22.01% | 22.01% | 22.01% | 22.01% | 22.01% | 23.35% | 23.35% | 23.35% | 23.35% | 26.06% | 26.06% | 26.06% | 26.06% | 26.06% | 43.9% | 26.06% | 26.06% | 26.06% | 26.06% | 26.06% | 48.43% | 48.43% | 23.35% | 23.35% | 23.35% | 23.35% | 53.85% | 48.43% | 48.43% | 51.14% | 53.85% | 48.43% | 48.43% | 26.06% | 43.9% | 23.35% | 23.35% | 39.19% | 39.19% | 35.27% | 35.27% | 35.27% | 39.19% | 47.03% | 39.19% | 47.03% | 46.59% | 46.59% | 48.17% | 39.19% | 39.19% | 47.03% | 47.03% | 49.86% | 45.24% | 45.24% | 28.48% | 39.19% | 32.37% | 19.3% | 19.3% | 19.3% | 19.3% | 19.3% | 19.3% | 43.71% | 43.71% | 43.71% | 43.71% | 43.71% | 43.71% | 43.71% | 34.12% | 34.12% | 34.12% | 34.12% | 34.12% | 34.12% | 34.12% | 32.37% | 32.37% | 32.37% | 43.58% | 43.58% | 43.58% | 43.58% | 43.58% | 28.48% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 39.19% | 39.19% | 39.19% | 39.19% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 23.35% | 28.67%
| P70 | 70% | 52.77% | 52.77% | 52.77% | 52.77% | 52.77% | 52.77% | 52.77% | 52.77% | 52.77% | 33.66% | 33.66% | 33.66% | 33.66% | 28.74% | 28.74% | 28.74% | 28.74% | 28.74% | 51.08% | 28.74% | 28.74% | 28.74% | 28.74% | 28.74% | 57.25% | 57.25% | 33.66% | 33.66% | 33.66% | 33.66% | 57.5% | 57.25% | 57.25% | 57.37% | 57.5% | 57.25% | 57.25% | 28.74% | 51.08% | 33.66% | 33.66% | 41.51% | 41.51% | 37.36% | 37.36% | 37.36% | 41.51% | 49.81% | 41.51% | 49.81% | 55.51% | 55.51% | 54.18% | 41.51% | 41.51% | 49.81% | 49.81% | 60.15% | 46.11% | 46.11% | 30.55% | 41.51% | 33.96% | 21.25% | 21.25% | 21.25% | 21.25% | 21.25% | 21.25% | 44.17% | 44.17% | 44.17% | 44.17% | 44.17% | 44.17% | 44.17% | 36.46% | 36.46% | 36.46% | 36.46% | 36.46% | 36.46% | 36.46% | 33.96% | 33.96% | 33.96% | 48.08% | 48.08% | 48.08% | 48.08% | 48.08% | 30.55% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 41.51% | 41.51% | 41.51% | 41.51% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 33.66% | 31.61%
| P75 | 75% | 69.84% | 69.84% | 69.84% | 69.84% | 69.84% | 69.84% | 69.84% | 69.84% | 69.84% | 57.71% | 57.71% | 57.71% | 57.71% | 65.47% | 65.47% | 65.47% | 65.47% | 65.47% | 106.8% | 65.47% | 65.47% | 65.47% | 65.47% | 65.47% | 100.9% | 100.9% | 57.71% | 57.71% | 57.71% | 57.71% | 94.16% | 100.9% | 100.9% | 97.52% | 94.16% | 100.9% | 100.9% | 65.47% | 106.8% | 57.71% | 57.71% | 76.88% | 76.88% | 69.19% | 69.19% | 69.19% | 76.88% | 92.25% | 76.88% | 92.25% | 94.43% | 94.43% | 93.31% | 76.88% | 76.88% | 92.25% | 92.25% | 109.9% | 92.23% | 92.23% | 66.88% | 76.88% | 70.9% | 56.32% | 56.32% | 56.32% | 56.32% | 56.32% | 56.32% | 82.81% | 82.81% | 82.81% | 82.81% | 82.81% | 82.81% | 82.81% | 73.57% | 73.57% | 73.57% | 73.57% | 73.57% | 73.57% | 73.57% | 70.9% | 70.9% | 70.9% | 84.46% | 84.46% | 84.46% | 84.46% | 84.46% | 66.88% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 76.88% | 76.88% | 76.88% | 76.88% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 57.71% | 72.02%
| P80 | 80% | 113.1% | 113.1% | 113.1% | 113.1% | 113.1% | 113.1% | 113.1% | 113.1% | 113.1% | 71.69% | 71.69% | 71.69% | 71.69% | 93.27% | 93.27% | 93.27% | 93.27% | 93.27% | 129.9% | 93.27% | 93.27% | 93.27% | 93.27% | 93.27% | 145.1% | 145.1% | 71.69% | 71.69% | 71.69% | 71.69% | 115.1% | 145.1% | 145.1% | 130.1% | 115.1% | 145.1% | 145.1% | 93.27% | 129.9% | 71.69% | 71.69% | 98.15% | 98.15% | 88.33% | 88.33% | 88.33% | 98.15% | 117.8% | 98.15% | 117.8% | 118.1% | 118.1% | 121.2% | 98.15% | 98.15% | 117.8% | 117.8% | 139% | 123.2% | 123.2% | 89.15% | 98.15% | 92.93% | 76.46% | 76.46% | 76.46% | 76.46% | 76.46% | 76.46% | 106.2% | 106.2% | 106.2% | 106.2% | 106.2% | 106.2% | 106.2% | 96.15% | 96.15% | 96.15% | 96.15% | 96.15% | 96.15% | 96.15% | 92.93% | 92.93% | 92.93% | 105.9% | 105.9% | 105.9% | 105.9% | 105.9% | 89.15% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 98.15% | 98.15% | 98.15% | 98.15% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 71.69% | 102.6%
| P85 | 85% | 120.8% | 120.8% | 120.8% | 120.8% | 120.8% | 120.8% | 120.8% | 120.8% | 120.8% | 105.6% | 105.6% | 105.6% | 105.6% | 124.2% | 124.2% | 124.2% | 124.2% | 124.2% | 136.4% | 124.2% | 124.2% | 124.2% | 124.2% | 124.2% | 190.2% | 190.2% | 105.6% | 105.6% | 105.6% | 105.6% | 120.2% | 190.2% | 190.2% | 155.2% | 120.2% | 190.2% | 190.2% | 124.2% | 136.4% | 105.6% | 105.6% | 103.8% | 103.8% | 93.46% | 93.46% | 93.46% | 103.8% | 124.6% | 103.8% | 124.6% | 130.7% | 130.7% | 148% | 103.8% | 103.8% | 124.6% | 124.6% | 155.1% | 134.3% | 134.3% | 101% | 103.8% | 106.8% | 80.39% | 80.39% | 80.39% | 80.39% | 80.39% | 80.39% | 130.9% | 130.9% | 130.9% | 130.9% | 130.9% | 130.9% | 130.9% | 109.1% | 109.1% | 109.1% | 109.1% | 109.1% | 109.1% | 109.1% | 106.8% | 106.8% | 106.8% | 114.3% | 114.3% | 114.3% | 114.3% | 114.3% | 101% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 103.8% | 103.8% | 103.8% | 103.8% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 136.6%
| P90 | 90% | 239.2% | 239.2% | 239.2% | 239.2% | 239.2% | 239.2% | 239.2% | 239.2% | 239.2% | 167.3% | 167.3% | 167.3% | 167.3% | 282.1% | 282.1% | 282.1% | 282.1% | 282.1% | 274.1% | 282.1% | 282.1% | 282.1% | 282.1% | 282.1% | 376.5% | 376.5% | 167.3% | 167.3% | 167.3% | 167.3% | 255.6% | 376.5% | 376.5% | 316% | 255.6% | 376.5% | 376.5% | 282.1% | 274.1% | 167.3% | 167.3% | 227.3% | 227.3% | 204.5% | 204.5% | 204.5% | 227.3% | 272.7% | 227.3% | 272.7% | 259.5% | 259.5% | 306.4% | 227.3% | 227.3% | 272.7% | 272.7% | 361.6% | 277.1% | 277.1% | 232.7% | 227.3% | 228.5% | 200.6% | 200.6% | 200.6% | 200.6% | 200.6% | 200.6% | 252.8% | 252.8% | 252.8% | 252.8% | 252.8% | 252.8% | 252.8% | 232.1% | 232.1% | 232.1% | 232.1% | 232.1% | 232.1% | 232.1% | 228.5% | 228.5% | 228.5% | 231% | 231% | 231% | 231% | 231% | 232.7% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 227.3% | 227.3% | 227.3% | 227.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 167.3% | 310.3%
| P95 | 95% | 310.4% | 310.4% | 310.4% | 310.4% | 310.4% | 310.4% | 310.4% | 310.4% | 310.4% | 211.3% | 211.3% | 211.3% | 211.3% | 384.7% | 384.7% | 384.7% | 384.7% | 384.7% | 324.4% | 384.7% | 384.7% | 384.7% | 384.7% | 384.7% | 447.6% | 447.6% | 211.3% | 211.3% | 211.3% | 211.3% | 282.5% | 447.6% | 447.6% | 365% | 282.5% | 447.6% | 447.6% | 384.7% | 324.4% | 211.3% | 211.3% | 243.4% | 243.4% | 219% | 219% | 219% | 243.4% | 292.1% | 243.4% | 292.1% | 291.6% | 291.6% | 361.8% | 243.4% | 243.4% | 292.1% | 292.1% | 617.6% | 321.1% | 321.1% | 259.1% | 243.4% | 254.8% | 209.5% | 209.5% | 209.5% | 209.5% | 209.5% | 209.5% | 300.1% | 300.1% | 300.1% | 300.1% | 300.1% | 300.1% | 300.1% | 254.8% | 254.8% | 254.8% | 254.8% | 254.8% | 254.8% | 254.8% | 254.8% | 254.8% | 254.8% | 246.3% | 246.3% | 246.3% | 246.3% | 246.3% | 259.1% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 243.4% | 243.4% | 243.4% | 243.4% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 211.3% | 423.2%
| P100 | 100%
Schedule RCF
|  |  |  | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | MB added | Same | Same | Same | Bld | Same | Same | Bld | Same | Bldg 0-5y | Same | Same | Same | Same | Same | EW | EW | MB added | Same | Same | Same |  | EW | EW | (EW+Facil W)/2 | Facil Works | EW x | EW x | Bld | Bldg 0-5y | MB added | MB added | Roads | roads | Roads x | Roads x | Roads x | Urban roads std | Urban roads cx | Rural std | Rural cx | as rail |  |  | Roads | Spine roads | Roads | Junctions | Civils | Bridges | Tunnels | Earthworks | Unspec x |  |  | Elec x | Elec x | Elec x | Elec x | Elec x | Gas | Gas x | Gas x | Gas x | Gas x | Gas x | Gas x |  | Water x | Water x | Water x | Water x | Water x | Water x |  |  |  | simple drainage | Drng x | Drng x | Drng x | Drng x | Landraising | Enab W x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Roads x | Roads x | Roads x | Roads x | Mngt | Fees x | Fees x | Fees x | Fees x | Fees x | Fees x | As mngt | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Mngt x | Mngt x | Mngt | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | Bldg
| Notes |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | [5 empty] | 1 | 1 |  |  |  |  | 1 | 0 | 0.9 | 0.9 | 0.9 | 1 | 1.2 | 1 | 1.2 | 1 | 0 | 0 | 1 | 1 | 1.2 | 1.2 |  |  |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1
| P0 | 0%
| P5 | 5% | -12.4% | -12.4% | -12.4% | -12.4% | -12.4% | -12.4% | -12.4% | -12.4% | -12.4% | -35% | -35% | -35% | -35% | -13.04% | -13.04% | -13.04% | -13.04% | -13.04% | -7% | -13.04% | -13.04% | -13.04% | -13.04% | -13.04% | -7% | -7% | -35% | -35% | -35% | -35% | -6.2% | -7% | -7% | -6.6% | -6.2% | -7% | -7% | -13.04% | -7% | -35% | -35% | -36.12% | -36.12% | -32.51% | -32.51% | -32.51% | -36.12% | -43.34% | -36.12% | -43.34% | -35.59% | -35.59% | -18.86% | -36.12% | -36.12% | -43.34% | -43.34% | -8.313% | -20% | -20% | -35.18% | -36.12% | -9.854% | -7% | -7% | -7% | -7% | -7% | -7% | -7.277% | -7.277% | -7.277% | -7.277% | -7.277% | -7.277% | -7.277% | -15.29% | -15.29% | -15.29% | -15.29% | -15.29% | -15.29% | -15.29% | -9.854% | -9.854% | -9.854% | -15.29% | -15.29% | -15.29% | -15.29% | -15.29% | -35.18% | -7% | -7% | -7% | -7% | -7% | -7% | -7% | -7% | -7% | -7% | -7% | -7% | -36.12% | -36.12% | -36.12% | -36.12% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -35% | -14.35%
| P10 | 10% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -19% | -19% | -19% | -19% | -7.938% | -7.938% | -7.938% | -7.938% | -7.938% | -3% | -7.938% | -7.938% | -7.938% | -7.938% | -7.938% | 0% | 0% | -19% | -19% | -19% | -19% | -1.4% | 0% | 0% | -0.7% | -1.4% | 0% | 0% | -7.938% | -3% | -19% | -19% | -23% | -23% | -20.7% | -20.7% | -20.7% | -23% | -27.6% | -23% | -27.6% | -22.9% | -22.9% | -11.1% | -23% | -23% | -27.6% | -27.6% | -2.818% | -14.11% | -14.11% | -22% | -23% | -4.461% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -7.383% | -7.383% | -7.383% | -7.383% | -7.383% | -7.383% | -7.383% | -4.461% | -4.461% | -4.461% | -7.383% | -7.383% | -7.383% | -7.383% | -7.383% | -22% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -23% | -23% | -23% | -23% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -8.732%
| P15 | 15% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -11.91% | -11.91% | -11.91% | -11.91% | -0.7781% | -0.7781% | -0.7781% | -0.7781% | -0.7781% | -0.141% | -0.7781% | -0.7781% | -0.7781% | -0.7781% | -0.7781% | 0% | 0% | -11.91% | -11.91% | -11.91% | -11.91% | 3.459% | 0% | 0% | 1.729% | 3.459% | 0% | 0% | -0.7781% | -0.141% | -11.91% | -11.91% | -14.72% | -14.72% | -13.25% | -13.25% | -13.25% | -14.72% | -17.66% | -14.72% | -17.66% | -12.04% | -12.04% | 1.309% | -14.72% | -14.72% | -17.66% | -17.66% | 0% | -4.683% | -4.683% | -13.48% | -14.72% | -0.6214% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -1.582% | -1.582% | -1.582% | -1.582% | -1.582% | -1.582% | -1.582% | -0.6214% | -0.6214% | -0.6214% | -1.582% | -1.582% | -1.582% | -1.582% | -1.582% | -13.48% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -14.72% | -14.72% | -14.72% | -14.72% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -0.8559%
| P20 | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6% | -6% | -6% | -6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6% | -6% | -6% | -6% | 6.8% | 0% | 0% | 3.4% | 6.8% | 0% | 0% | 0% | 0% | -6% | -6% | -10.18% | -10.18% | -9.162% | -9.162% | -9.162% | -10.18% | -12.22% | -10.18% | -12.22% | -6.8% | -6.8% | 7.2% | -10.18% | -10.18% | -12.22% | -12.22% | 0% | -2.371% | -2.371% | -9.26% | -10.18% | 1.409% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 1.409% | 1.409% | 1.409% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | -9.26% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -10.18% | -10.18% | -10.18% | -10.18% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | 0%
| P25 | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -4.443% | -4.443% | -4.443% | -4.443% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -4.443% | -4.443% | -4.443% | -4.443% | 10% | 0% | 0% | 5% | 10% | 0% | 0% | 0% | 0% | -4.443% | -4.443% | -3.541% | -3.541% | -3.187% | -3.187% | -3.187% | -3.541% | -4.249% | -3.541% | -4.249% | -0.9424% | -0.9424% | 9.289% | -3.541% | -3.541% | -4.249% | -4.249% | 0% | 0% | 0% | -3.061% | -3.541% | 3.292% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 3.292% | 3.292% | 3.292% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | -3.061% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -3.541% | -3.541% | -3.541% | -3.541% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | 0%
| P30 | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.67% | 0% | 0% | 6.333% | 12.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.65% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.139% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 6.139% | 6.139% | 6.139% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| P35 | 35% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15.33% | 0% | 0% | 7.667% | 15.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.089% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 7.089% | 7.089% | 7.089% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| P40 | 40% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | 0% | 0% | 0% | 0% | 0% | 0.9624% | 0% | 0% | 0% | 0% | 0% | -1% | -1% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | 18.93% | -1% | -1% | 8.967% | 18.93% | -1% | -1% | 0% | 0.9624% | -0.6427% | -0.6427% | 3.259% | 3.259% | 2.933% | 2.933% | 2.933% | 3.259% | 3.911% | 3.259% | 3.911% | 7.397% | 7.397% | 15% | 3.259% | 3.259% | 3.911% | 3.911% | 0% | 0% | 0% | 2% | 3.259% | 7.822% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 7.822% | 7.822% | 7.822% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 2% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | 3.259% | 3.259% | 3.259% | 3.259% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | 0%
| P45 | 45% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 6.013% | 6.013% | 6.013% | 6.013% | 0% | 0% | 0% | 0% | 0% | 3.08% | 0% | 0% | 0% | 0% | 0% | 0.9632% | 0.9632% | 6.013% | 6.013% | 6.013% | 6.013% | 23.47% | 0.9632% | 0.9632% | 12.21% | 23.47% | 0.9632% | 0.9632% | 0% | 3.08% | 6.013% | 6.013% | 8.063% | 8.063% | 7.257% | 7.257% | 7.257% | 8.063% | 9.676% | 8.063% | 9.676% | 14.1% | 14.1% | 18.9% | 8.063% | 8.063% | 9.676% | 9.676% | 0% | 1.829% | 1.829% | 7.183% | 8.063% | 10.02% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 10.02% | 10.02% | 10.02% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 7.183% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 8.063% | 8.063% | 8.063% | 8.063% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 0%
| P50 | 50% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 12.27% | 12.27% | 12.27% | 12.27% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 17.5% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 4.692% | 4.692% | 12.27% | 12.27% | 12.27% | 12.27% | 28% | 4.692% | 4.692% | 16.35% | 28% | 4.692% | 4.692% | 0.2635% | 17.5% | 12.27% | 12.27% | 13% | 13% | 11.7% | 11.7% | 11.7% | 13% | 15.6% | 13% | 15.6% | 19.09% | 19.09% | 26% | 13% | 13% | 15.6% | 15.6% | 1.658% | 3.449% | 3.449% | 11.65% | 13% | 10.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 10.97% | 10.97% | 10.97% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 11.65% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 13% | 13% | 13% | 13% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 0.2899%
| P55 | 55% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 16% | 16% | 16% | 16% | 2.652% | 2.652% | 2.652% | 2.652% | 2.652% | 26% | 2.652% | 2.652% | 2.652% | 2.652% | 2.652% | 14.05% | 14.05% | 16% | 16% | 16% | 16% | 28.8% | 14.05% | 14.05% | 21.42% | 28.8% | 14.05% | 14.05% | 2.652% | 26% | 16% | 16% | 16.67% | 16.67% | 15% | 15% | 15% | 16.67% | 20% | 16.67% | 20% | 26.27% | 26.27% | 29.72% | 16.67% | 16.67% | 20% | 20% | 4% | 7.169% | 7.169% | 15.76% | 16.67% | 17.24% | 0% | 0% | 0% | 0% | 0% | 0% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 17.24% | 17.24% | 17.24% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 15.76% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 16.67% | 16.67% | 16.67% | 16.67% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 2.918%
| P60 | 60% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 21.87% | 21.87% | 21.87% | 21.87% | 3.263% | 3.263% | 3.263% | 3.263% | 3.263% | 32.95% | 3.263% | 3.263% | 3.263% | 3.263% | 3.263% | 18.57% | 18.57% | 21.87% | 21.87% | 21.87% | 21.87% | 29.6% | 18.57% | 18.57% | 24.08% | 29.6% | 18.57% | 18.57% | 3.263% | 32.95% | 21.87% | 21.87% | 22.63% | 22.63% | 20.37% | 20.37% | 20.37% | 22.63% | 27.16% | 22.63% | 27.16% | 30.6% | 30.6% | 44.3% | 22.63% | 22.63% | 27.16% | 27.16% | 14% | 12% | 12% | 21.47% | 22.63% | 21.44% | 0% | 0% | 0% | 0% | 0% | 0% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 21.44% | 21.44% | 21.44% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 21.47% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 22.63% | 22.63% | 22.63% | 22.63% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 3.589%
| P65 | 65% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 27% | 27% | 27% | 27% | 4.324% | 4.324% | 4.324% | 4.324% | 4.324% | 48.71% | 4.324% | 4.324% | 4.324% | 4.324% | 4.324% | 29.81% | 29.81% | 27% | 27% | 27% | 27% | 39.2% | 29.81% | 29.81% | 34.51% | 39.2% | 29.81% | 29.81% | 4.324% | 48.71% | 27% | 27% | 27.36% | 27.36% | 24.62% | 24.62% | 24.62% | 27.36% | 32.83% | 27.36% | 32.83% | 36.7% | 36.7% | 49.65% | 27.36% | 27.36% | 32.83% | 32.83% | 19.87% | 16% | 16% | 27% | 27.36% | 24.41% | 0% | 0% | 0% | 0% | 0% | 0% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 24.41% | 24.41% | 24.41% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 27% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 27.36% | 27.36% | 27.36% | 27.36% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 4.756%
| P70 | 70% | 26.75% | 26.75% | 26.75% | 26.75% | 26.75% | 26.75% | 26.75% | 26.75% | 26.75% | 38.97% | 38.97% | 38.97% | 38.97% | 12.8% | 12.8% | 12.8% | 12.8% | 12.8% | 53% | 12.8% | 12.8% | 12.8% | 12.8% | 12.8% | 50.61% | 50.61% | 38.97% | 38.97% | 38.97% | 38.97% | 60.6% | 50.61% | 50.61% | 55.6% | 60.6% | 50.61% | 50.61% | 12.8% | 53% | 38.97% | 38.97% | 38.93% | 38.93% | 35.04% | 35.04% | 35.04% | 38.93% | 46.72% | 38.93% | 46.72% | 43% | 43% | 53% | 38.93% | 38.93% | 46.72% | 46.72% | 28.81% | 25% | 25% | 38.1% | 38.93% | 30.39% | 3% | 3% | 3% | 3% | 3% | 3% | 35.17% | 35.17% | 35.17% | 35.17% | 35.17% | 35.17% | 35.17% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 30.39% | 30.39% | 30.39% | 53% | 53% | 53% | 53% | 53% | 38.1% | 50.61% | 50.61% | 50.61% | 50.61% | 50.61% | 50.61% | 50.61% | 50.61% | 50.61% | 50.61% | 50.61% | 50.61% | 38.93% | 38.93% | 38.93% | 38.93% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 38.97% | 14.08%
| P75 | 75% | 35.61% | 35.61% | 35.61% | 35.61% | 35.61% | 35.61% | 35.61% | 35.61% | 35.61% | 53.71% | 53.71% | 53.71% | 53.71% | 30.64% | 30.64% | 30.64% | 30.64% | 30.64% | 75% | 30.64% | 30.64% | 30.64% | 30.64% | 30.64% | 65.5% | 65.5% | 53.71% | 53.71% | 53.71% | 53.71% | 84% | 65.5% | 65.5% | 74.75% | 84% | 65.5% | 65.5% | 30.64% | 75% | 53.71% | 53.71% | 58% | 58% | 52.2% | 52.2% | 52.2% | 58% | 69.6% | 58% | 69.6% | 54% | 54% | 58% | 58% | 58% | 69.6% | 69.6% | 42.77% | 43% | 43% | 56% | 58% | 39.31% | 8% | 8% | 8% | 8% | 8% | 8% | 43% | 43% | 43% | 43% | 43% | 43% | 43% | 66.92% | 66.92% | 66.92% | 66.92% | 66.92% | 66.92% | 66.92% | 39.31% | 39.31% | 39.31% | 66.92% | 66.92% | 66.92% | 66.92% | 66.92% | 56% | 65.5% | 65.5% | 65.5% | 65.5% | 65.5% | 65.5% | 65.5% | 65.5% | 65.5% | 65.5% | 65.5% | 65.5% | 58% | 58% | 58% | 58% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 53.71% | 33.71%
| P80 | 80% | 44.22% | 44.22% | 44.22% | 44.22% | 44.22% | 44.22% | 44.22% | 44.22% | 44.22% | 71.4% | 71.4% | 71.4% | 71.4% | 40.99% | 40.99% | 40.99% | 40.99% | 40.99% | 99.2% | 40.99% | 40.99% | 40.99% | 40.99% | 40.99% | 79.8% | 79.8% | 71.4% | 71.4% | 71.4% | 71.4% | 92.8% | 79.8% | 79.8% | 86.3% | 92.8% | 79.8% | 79.8% | 40.99% | 99.2% | 71.4% | 71.4% | 75.4% | 75.4% | 67.86% | 67.86% | 67.86% | 75.4% | 90.48% | 75.4% | 90.48% | 62% | 62% | 77% | 75.4% | 75.4% | 90.48% | 90.48% | 61.82% | 50% | 50% | 74.2% | 75.4% | 51.96% | 12% | 12% | 12% | 12% | 12% | 12% | 68% | 68% | 68% | 68% | 68% | 68% | 68% | 75.87% | 75.87% | 75.87% | 75.87% | 75.87% | 75.87% | 75.87% | 51.96% | 51.96% | 51.96% | 75.87% | 75.87% | 75.87% | 75.87% | 75.87% | 74.2% | 79.8% | 79.8% | 79.8% | 79.8% | 79.8% | 79.8% | 79.8% | 79.8% | 79.8% | 79.8% | 79.8% | 79.8% | 75.4% | 75.4% | 75.4% | 75.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 45.09%
| P85 | 85% | 59.47% | 59.47% | 59.47% | 59.47% | 59.47% | 59.47% | 59.47% | 59.47% | 59.47% | 89% | 89% | 89% | 89% | 51.97% | 51.97% | 51.97% | 51.97% | 51.97% | 114% | 51.97% | 51.97% | 51.97% | 51.97% | 51.97% | 114% | 114% | 89% | 89% | 89% | 89% | 99.6% | 114% | 114% | 106.8% | 99.6% | 114% | 114% | 51.97% | 114% | 89% | 89% | 94.96% | 94.96% | 85.46% | 85.46% | 85.46% | 94.96% | 113.9% | 94.96% | 113.9% | 79.9% | 79.9% | 100.3% | 94.96% | 94.96% | 113.9% | 113.9% | 82.69% | 65.5% | 65.5% | 89.86% | 94.96% | 57.77% | 14% | 14% | 14% | 14% | 14% | 14% | 80.67% | 80.67% | 80.67% | 80.67% | 80.67% | 80.67% | 80.67% | 78.66% | 78.66% | 78.66% | 78.66% | 78.66% | 78.66% | 78.66% | 57.77% | 57.77% | 57.77% | 78.66% | 78.66% | 78.66% | 78.66% | 78.66% | 89.86% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 94.96% | 94.96% | 94.96% | 94.96% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 57.17%
| P90 | 90% | 74.96% | 74.96% | 74.96% | 74.96% | 74.96% | 74.96% | 74.96% | 74.96% | 74.96% | 120% | 120% | 120% | 120% | 89.76% | 89.76% | 89.76% | 89.76% | 89.76% | 158% | 89.76% | 89.76% | 89.76% | 89.76% | 89.76% | 153.3% | 153.3% | 120% | 120% | 120% | 120% | 116.6% | 153.3% | 153.3% | 134.9% | 116.6% | 153.3% | 153.3% | 89.76% | 158% | 120% | 120% | 133% | 133% | 119.7% | 119.7% | 119.7% | 133% | 159.6% | 133% | 159.6% | 120% | 120% | 108.9% | 133% | 133% | 159.6% | 159.6% | 103.2% | 95.5% | 95.5% | 125.4% | 133% | 78.15% | 32.32% | 32.32% | 32.32% | 32.32% | 32.32% | 32.32% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 102.1% | 102.1% | 102.1% | 102.1% | 102.1% | 102.1% | 102.1% | 78.15% | 78.15% | 78.15% | 102.1% | 102.1% | 102.1% | 102.1% | 102.1% | 125.4% | 153.3% | 153.3% | 153.3% | 153.3% | 153.3% | 153.3% | 153.3% | 153.3% | 153.3% | 153.3% | 153.3% | 153.3% | 133% | 133% | 133% | 133% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 120% | 98.73%
| P95 | 95% | 98.53% | 98.53% | 98.53% | 98.53% | 98.53% | 98.53% | 98.53% | 98.53% | 98.53% | 161.1% | 161.1% | 161.1% | 161.1% | 154% | 154% | 154% | 154% | 154% | 207.3% | 154% | 154% | 154% | 154% | 154% | 185.6% | 185.6% | 161.1% | 161.1% | 161.1% | 161.1% | 128.7% | 185.6% | 185.6% | 157.1% | 128.7% | 185.6% | 185.6% | 154% | 207.3% | 161.1% | 161.1% | 167.8% | 167.8% | 151% | 151% | 151% | 167.8% | 201.4% | 167.8% | 201.4% | 147% | 147% | 106.8% | 167.8% | 167.8% | 201.4% | 201.4% | 144.9% | 101% | 101% | 160.3% | 167.8% | 92.88% | 58.32% | 58.32% | 58.32% | 58.32% | 58.32% | 58.32% | 112.1% | 112.1% | 112.1% | 112.1% | 112.1% | 112.1% | 112.1% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 92.88% | 92.88% | 92.88% | 108.2% | 108.2% | 108.2% | 108.2% | 108.2% | 160.3% | 185.6% | 185.6% | 185.6% | 185.6% | 185.6% | 185.6% | 185.6% | 185.6% | 185.6% | 185.6% | 185.6% | 185.6% | 167.8% | 167.8% | 167.8% | 167.8% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 161.1% | 169.4%
| P100 | 100%
Note on AB2: Site preparation works, Roads, paths, paving’s and surfacing, Soft landscaping, planting and irrigation systems, fencing, external drainage and utilities and minor building works and ancillary building works
Note on E3: Purchase price including Planning Risk discounts (Actual price to be paid)
Note on F3: Purchasers Agent and Legal fees
Note on G3: SDLT rates as appropriate
Note on H3: Easements, Wayleaves
Note on M3: Costs for securing Outline Planning Permission
Note on N3: Costs for securing Outline Planning Permission
Note on O3: Costs for securing Reserved Matters planning
Note on P3: Pre-app, allocation promotion, SPD/planning brief, design incl B4Life, Listed Buildings surveys, fees associated with S278,38 or 104, highway, noise, and desk top archaeology surveys.
Note on AH3: includes demolition to slab and or below ground, substructures. Planning costs for demolition should be included in planning fees.
Note on AI3: Including cut and fill and ground stabilisation, preparing sub-surfaces, site clearance, including all works to existing trees and TPOs etc.
Note on AJ3: Remediation and decontamination including monitoring costs
Note on AM3: Incl site investigations, topo survey, noise surveys, UXO, building condition survey
Note on AQ3: Including Transport and Highway Assessments
Note on AS3: Means works undertaken by developer
Note on AT3: incl. contribution to strategic infrastructure; works undertaken by others
Note on BB3: Works to be carried out by the developer on Public Transport not included in S106 Costs
Note on BF3: Infrastructure not serving individual plots directly i.e. not local infrastructure included under externals. Including standard sewers. Will include fees, contingencies and prelims
Note on BH3: Additional junctions or junctions works over and above standard
Note on BM3: compensation for depreciation in the value of an interest in land which is attributable to the use of public works i.e construction of a highway
Note on CK4: (likely to be removed in due course as costs become standard and are reflected within base build costs)
Note on D5: From EW Rail "L&P"
Note on M5: From BusConnects "Prelims"
Note on AB5: From EW Rail "civils"
Note on AD5: From Busconnects "Management"
Note on AH5: EW Rail "Temp Works"
Note on AQ5: Mr Bartlett: BusConnects Design - change to SW Design?
Note on AR5: Mr Bartlett: BusConnects Design - change to SW Design?
Note on AT5: BusConnects roads
Note on BB5: As rail
Note on BC5: EW Rail "Track"
Note on BD5: EW Rail "Stations"
Note on BI5: EW Rail "Civils"
Note on BJ5: EW Rail "Bridges"
Note on BK5: EW Rail "Tunnels"
Note on CM5: Data from Sydney Water
Note on DO5: Use margin from SW work?
Note on D33: From EW Rail "L&P"
Note on M33: From EW Rail "Prelims etc"
Note on Q33: From BusConnects "Building"
Note on T33: From BusConnects "Building"
Note on V33: From BusConnects "Building"
Note on AB33: From EW Rail "civils"
Note on AD33: From EW Rail "Prelims etc"
Note on AH33: EW Rail "Temp Works"
Note on AQ33: From EW Rail "Prelims etc"
Note on AR33: From EW Rail "Prelims etc"
Note on AT33: BusConnects roads
Note on BB33: As rail
Note on BC33: EW Rail "Track"
Note on BD33: EW Rail "Stations"
Note on BI33: EW Rail "Civils"
Note on BJ33: EW Rail "Bridges"
Note on BK33: EW Rail "Tunnels"
Note on CM33: Data from Sydney Water
Note on DO33: Use margin from SW work?

## RCF OBC data (hidden)
OBC
| Primary RCF Data |  | Land Costs | [8 empty] | Planning |  |  |  | Build Cost (Base build total cost) |  |  | Building | [7 empty] | External Works |  | Management costs |  |  |  | Site Preparation | [6 empty] | Foundations |  | Infrastructure and highways | [22 empty] | Utilities | [23 empty] | Drainage | [5 empty] | Ecology | [11 empty] | Landscaping/ Public Realm |  |  |  | Surveys and Fees |  |  |  |  | Sales and Marketing |  | Profit (inclusive of any developer Overheads, aftercare and sales incentives) | [7 empty] | Community Infrastructure Levy (CIL) |  | Section 106 Obligations | [12 empty] | Other Abnormal Costs
|  |  | General L&P | Acquisition Cost | Agent and Legal fees | SDLT | Access Rights | Ransom Payments | Option Fees | Overage | Additional Land Acquisition | Planning general | Outline Planning | Reserved Matters Planning | Other Planning Costs | Standard construction and foundations | Preliminaries apportioned | Contractors' overheads and profits (not developers’) | General: unspecified | Residential | Custom build properties | Building affordable housing | Commercial (shop units/ offices space | Light industrial (warehousing/ distribution) | Film studios/ creative space | Community/ public buildings | Associated with houses | Associated with apartments | General | Maintenance & protection of a heritage asset | Other holding costs/ estate management | Professional Fees: General | Demolition | Enabling works | Remediation and Decontamination |  |  | Due Diligence (survey works) | Archaeology/Heritage surveys | Standard foundations | Abnormal Foundations | Highway and Transport Design Works | Noise and Vibration Design Works | S278 works | Offsite Highways works (breakdown by type of works as feasible) | [7 empty] | Public Transport |  |  |  | Spine Road | Roundabouts | Junctions | Other civil works |  |  |  | Part 1 Claims | Unspecified | Electricity | [5 empty] | Gas | [6 empty] | Water | [6 empty] | District Heating | Telecoms | 0 | General | Pumping Station | SUDS/Swales/Tanks/Attenuation |  | Sewers | Flood Risk | General | Ecology Design Work | Arboriculture | Mitigation | Nitrogen neutrality | Water Neutrality | Biodiversity Net Gain (BNG) | Invasive Species | Birds and Bats | SANGS | Invertebrates/vertebrates | Mammals | Public Realm / Public Open Space | Play areas / Outdoor sports | Endowment | Public Art | Valuation and Appraisal Advice | Legal Advice | Development Management / Master Developer Fees | Health and Safety Advice | Communications Fees | Agent Fees | Legal Fees | Profit on Market Sale | Profit on Affordable | Profit on Commercial | Profit on PRS | Total Blended Profit | Internal Rate of Return (IRR) | Development Management Fee | Return On Capital Employed (ROCE) | CIL Residential | CIL Commercial | General | Roof Tax | Affordable Housing Offsite Payment | Community Facilities | Employment and Skills | Healthcare | Highways / Transport | Education (primary and secondary) | Libraries | Public Realm/Open Space | Monitoring Fee | Play areas | Sports Fields
| RCF Values | [33 empty] | Simple | complex/ brownfield | heavily contaminated | [7 empty] | Unspecified or mixed | Footpaths | Cycle paths | Parking (surface) | Urban roads - standard | Urban roads - complex | Rural roads - standard | Rural roads - complex | Unspecified or mixed | Rail | Stations | Buslanes |  |  |  | Unspecified or mixed | Bridges/ other structures | Tunnels | Earthworks |  |  | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs legal fees for wayleaves, licences, supply agreements, compensation claims | Easement costs | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, Compensation claims | Easement costs | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, compensation claims | Easement Costs | Capital cost, plot costs, legals and heat charger | Upgrading cables | CHP, non plot specific EV charging or solar |  |  | Includes landscaping features associated with attenuation ponds | Beyond plot specific measures included in externals (such as permeable drives) | Includes Surface and Foul beyond standard included in Externals and/or spine road | Includes land raising/barriers/defence |  |  | Covers tree surgery and/or tree protection works | i.e. offsite contribution, Habitat Regulation Assessment, | [6 empty] | Newts – including fencing and ladders | Dormice, badgers | Estate costs/shared areas not included in external works including landscaping wildflower meadows. | in addition to any S. 106 requirements | for long term management | in addition to any S. 106 requirements | (beyond standard house building Professional fees and not included in specialist categories above) | state aid advice, specific questions on ransoms etc. | These include fees paid to development managers/ Master Developers of the site or collaboration costs. | e.g. highways, reservoirs | Fees for example related to any PR on the site but not planning related costs.
| Notes |  | L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | Design | Same | Same | Same | Bldg | Same | Same | Bldg | Same | Bld 0-5 y | Same | Same | Same | Same | Same | EW | EW | Mngt | Same | Same | Same | Demolition | EW | EW | (EW+Facil W)/2 | Facil Works | EW x | EW x | Bldg | Bld 0-5 y | Design | Design | Roads | Roads | Roads x | Roads x | Roads x | Urban roads std | Urban roads cx | Rural std | Rural cx | As Rail |  |  | Roads | Spine roads | Roads | Junctions | Civils | Bridges | Tunnels | Earthworks | Roads | Gen Utilities | Elec | Elec x | Elec x | Elec x | Elec x | Elec x | Gas | Gas x | Gas x | Gas x | Gas x | Gas x | Gas x | Water | Water x | Water x | Water x | Water x | Water x | Water x | Gen x | Gen x | Gen x | Drng | Drng x | Drng x | Drng x | Drng x | Landraising | Enab W x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Roads x | Roads x | Roads x | Roads x | Mngt | Fees x | Fees x | Fees x | Fees x | Fees x | Fees x | As mngt | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Mngt x | Mngt x | Mngt | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | Bldg
| Factor |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 |  |  | 1 | 1 |  |  | 0 | 0 | 1 | 0 | 0.9 | 0.9 | 0.9 | 1 | 1.2 | 1 | 1.2 | 1 |  |  | 1 | 1 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1
Cost RCF
| P0 | 0%
| P5 | 5% | -94.04% | -94.04% | -94.04% | -94.04% | -94.04% | -94.04% | -94.04% | -94.04% | -94.04% | -70.19% | -70.19% | -70.19% | -70.19% | -33.26% | -33.26% | -33.26% | -33.26% | -33.26% | -28.69% | -33.26% | -33.26% | -33.26% | -33.26% | -33.26% | -27.65% | -27.65% | -70.19% | -70.19% | -70.19% | -70.19% | -24.82% | -27.65% | -27.65% | -26.24% | -24.82% | -27.65% | -27.65% | -33.26% | -28.69% | -70.19% | -70.19% | -16.82% | -16.82% | -15.14% | -15.14% | -15.14% | -16.82% | -20.19% | -16.82% | -20.19% | -29.47% | -29.47% | -21.12% | -16.82% | -16.82% | -20.19% | -20.19% | -25.95% | -30.82% | -30.82% | -29.63% | -16.82% | -34.57% | -38.51% | -38.51% | -38.51% | -38.51% | -38.51% | -38.51% | -23.16% | -23.16% | -23.16% | -23.16% | -23.16% | -23.16% | -23.16% | -42.03% | -42.03% | -42.03% | -42.03% | -42.03% | -42.03% | -42.03% | -34.57% | -34.57% | -34.57% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -29.63% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -16.82% | -16.82% | -16.82% | -16.82% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -70.19% | -36.58%
| P10 | 10% | -88.3% | -88.3% | -88.3% | -88.3% | -88.3% | -88.3% | -88.3% | -88.3% | -88.3% | -61.65% | -61.65% | -61.65% | -61.65% | -27% | -27% | -27% | -27% | -27% | -23.65% | -27% | -27% | -27% | -27% | -27% | -20.42% | -20.42% | -61.65% | -61.65% | -61.65% | -61.65% | -19.97% | -20.42% | -20.42% | -20.2% | -19.97% | -20.42% | -20.42% | -27% | -23.65% | -61.65% | -61.65% | -8.824% | -8.824% | -7.942% | -7.942% | -7.942% | -8.824% | -10.59% | -8.824% | -10.59% | -21.27% | -21.27% | -16.44% | -8.824% | -8.824% | -10.59% | -10.59% | -19.18% | -25.17% | -25.17% | -20.82% | -8.824% | -25.93% | -25.91% | -25.91% | -25.91% | -25.91% | -25.91% | -25.91% | -17.29% | -17.29% | -17.29% | -17.29% | -17.29% | -17.29% | -17.29% | -34.57% | -34.57% | -34.57% | -34.57% | -34.57% | -34.57% | -34.57% | -25.93% | -25.93% | -25.93% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -20.82% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -8.824% | -8.824% | -8.824% | -8.824% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -61.65% | -29.7%
| P15 | 15% | -71.91% | -71.91% | -71.91% | -71.91% | -71.91% | -71.91% | -71.91% | -71.91% | -71.91% | -53.22% | -53.22% | -53.22% | -53.22% | -19.45% | -19.45% | -19.45% | -19.45% | -19.45% | -11.44% | -19.45% | -19.45% | -19.45% | -19.45% | -19.45% | -10.12% | -10.12% | -53.22% | -53.22% | -53.22% | -53.22% | -13.78% | -10.12% | -10.12% | -11.95% | -13.78% | -10.12% | -10.12% | -19.45% | -11.44% | -53.22% | -53.22% | -2.825% | -2.825% | -2.543% | -2.543% | -2.543% | -2.825% | -3.39% | -2.825% | -3.39% | -13.26% | -13.26% | -10.26% | -2.825% | -2.825% | -3.39% | -3.39% | -1% | -15.83% | -15.83% | -12.14% | -2.825% | -13.77% | -13.24% | -13.24% | -13.24% | -13.24% | -13.24% | -13.24% | -6.22% | -6.22% | -6.22% | -6.22% | -6.22% | -6.22% | -6.22% | -21.86% | -21.86% | -21.86% | -21.86% | -21.86% | -21.86% | -21.86% | -13.77% | -13.77% | -13.77% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -12.14% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -2.825% | -2.825% | -2.825% | -2.825% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -53.22% | -21.39%
| P20 | 20% | -50.18% | -50.18% | -50.18% | -50.18% | -50.18% | -50.18% | -50.18% | -50.18% | -50.18% | -45.44% | -45.44% | -45.44% | -45.44% | -11.95% | -11.95% | -11.95% | -11.95% | -11.95% | -2.955% | -11.95% | -11.95% | -11.95% | -11.95% | -11.95% | -3.305% | -3.305% | -45.44% | -45.44% | -45.44% | -45.44% | -8.262% | -3.305% | -3.305% | -5.783% | -8.262% | -3.305% | -3.305% | -11.95% | -2.955% | -45.44% | -45.44% | 2.149% | 2.149% | 1.934% | 1.934% | 1.934% | 2.149% | 2.579% | 2.149% | 2.579% | -5.902% | -5.902% | -5.391% | 2.149% | 2.149% | 2.579% | 2.579% | 2% | -8.237% | -8.237% | -5.762% | 2.149% | -7.153% | -7.523% | -7.523% | -7.523% | -7.523% | -7.523% | -7.523% | 1.134% | 1.134% | 1.134% | 1.134% | 1.134% | 1.134% | 1.134% | -15.07% | -15.07% | -15.07% | -15.07% | -15.07% | -15.07% | -15.07% | -7.153% | -7.153% | -7.153% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -5.762% | -3.305% | -3.305% | -3.305% | -3.305% | -3.305% | -3.305% | -3.305% | -3.305% | -3.305% | -3.305% | -3.305% | -3.305% | 2.149% | 2.149% | 2.149% | 2.149% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -45.44% | -13.15%
| P25 | 25% | -31.17% | -31.17% | -31.17% | -31.17% | -31.17% | -31.17% | -31.17% | -31.17% | -31.17% | -37.66% | -37.66% | -37.66% | -37.66% | -3.161% | -3.161% | -3.161% | -3.161% | -3.161% | 0% | -3.161% | -3.161% | -3.161% | -3.161% | -3.161% | 0% | 0% | -37.66% | -37.66% | -37.66% | -37.66% | 13.12% | 0% | 0% | 6.561% | 13.12% | 0% | 0% | -3.161% | 0% | -37.66% | -37.66% | 7% | 7% | 6.3% | 6.3% | 6.3% | 7% | 8.4% | 7% | 8.4% | -0.001784% | -0.001784% | -1.861% | 7% | 7% | 8.4% | 8.4% | 0% | -1.713% | -1.713% | -0.3264% | 7% | -1.51% | -2.84% | -2.84% | -2.84% | -2.84% | -2.84% | -2.84% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -1.51% | -1.51% | -1.51% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -0.3264% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7% | 7% | 7% | 7% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -37.66% | -3.477%
| P30 | 30% | -28.59% | -28.59% | -28.59% | -28.59% | -28.59% | -28.59% | -28.59% | -28.59% | -28.59% | -29.38% | -29.38% | -29.38% | -29.38% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4% | 1.4% | -29.38% | -29.38% | -29.38% | -29.38% | 21.77% | 1.4% | 1.4% | 11.59% | 21.77% | 1.4% | 1.4% | 0% | 0% | -29.38% | -29.38% | 9% | 9% | 8.1% | 8.1% | 8.1% | 9% | 10.8% | 9% | 10.8% | 0.9166% | 0.9166% | 0.2737% | 9% | 9% | 10.8% | 10.8% | 0.0396% | 0% | 0% | 0% | 9% | 2.097% | -0.756% | -0.756% | -0.756% | -0.756% | -0.756% | -0.756% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | 2.097% | 2.097% | 2.097% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 0% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 9% | 9% | 9% | 9% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | -29.38% | 0%
| P35 | 35% | -17.33% | -17.33% | -17.33% | -17.33% | -17.33% | -17.33% | -17.33% | -17.33% | -17.33% | -19.84% | -19.84% | -19.84% | -19.84% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.6314% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 3.966% | 3.966% | -19.84% | -19.84% | -19.84% | -19.84% | 24.46% | 3.966% | 3.966% | 14.21% | 24.46% | 3.966% | 3.966% | 0.3062% | 0.6314% | -19.84% | -19.84% | 11% | 11% | 9.9% | 9.9% | 9.9% | 11% | 13.2% | 11% | 13.2% | 4% | 4% | 4.16% | 11% | 11% | 13.2% | 13.2% | 3.361% | 2.492% | 2.492% | 0% | 11% | 4.1% | 0% | 0% | 0% | 0% | 0% | 0% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | 4.1% | 4.1% | 4.1% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 0% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 11% | 11% | 11% | 11% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | -19.84% | 0.3368%
| P40 | 40% | -10.7% | -10.7% | -10.7% | -10.7% | -10.7% | -10.7% | -10.7% | -10.7% | -10.7% | -10.3% | -10.3% | -10.3% | -10.3% | 1.544% | 1.544% | 1.544% | 1.544% | 1.544% | 2.686% | 1.544% | 1.544% | 1.544% | 1.544% | 1.544% | 9% | 9% | -10.3% | -10.3% | -10.3% | -10.3% | 25% | 9% | 9% | 17% | 25% | 9% | 9% | 1.544% | 2.686% | -10.3% | -10.3% | 13.4% | 13.4% | 12.06% | 12.06% | 12.06% | 13.4% | 16.08% | 13.4% | 16.08% | 8% | 8% | 9.418% | 13.4% | 13.4% | 16.08% | 16.08% | 7.32% | 7.636% | 7.636% | 0% | 13.4% | 5.944% | 0% | 0% | 0% | 0% | 0% | 0% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 5.944% | 5.944% | 5.944% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 0% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 13.4% | 13.4% | 13.4% | 13.4% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | -10.3% | 1.699%
| P45 | 45% | -7.342% | -7.342% | -7.342% | -7.342% | -7.342% | -7.342% | -7.342% | -7.342% | -7.342% | -4.573% | -4.573% | -4.573% | -4.573% | 2.788% | 2.788% | 2.788% | 2.788% | 2.788% | 5.25% | 2.788% | 2.788% | 2.788% | 2.788% | 2.788% | 12% | 12% | -4.573% | -4.573% | -4.573% | -4.573% | 25.72% | 12% | 12% | 18.86% | 25.72% | 12% | 12% | 2.788% | 5.25% | -4.573% | -4.573% | 16% | 16% | 14.4% | 14.4% | 14.4% | 16% | 19.2% | 16% | 19.2% | 11.75% | 11.75% | 11.03% | 16% | 16% | 19.2% | 19.2% | 11.16% | 15% | 15% | 2% | 16% | 7.509% | 0% | 0% | 0% | 0% | 0% | 0% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 7.509% | 7.509% | 7.509% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 2% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 16% | 16% | 16% | 16% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | -4.573% | 3.067%
| P50 | 50% | -0.03982% | -0.03982% | -0.03982% | -0.03982% | -0.03982% | -0.03982% | -0.03982% | -0.03982% | -0.03982% | -3.938% | -3.938% | -3.938% | -3.938% | 4.197% | 4.197% | 4.197% | 4.197% | 4.197% | 8.941% | 4.197% | 4.197% | 4.197% | 4.197% | 4.197% | 13.33% | 13.33% | -3.938% | -3.938% | -3.938% | -3.938% | 31.5% | 13.33% | 13.33% | 22.42% | 31.5% | 13.33% | 13.33% | 4.197% | 8.941% | -3.938% | -3.938% | 18% | 18% | 16.2% | 16.2% | 16.2% | 18% | 21.6% | 18% | 21.6% | 15.14% | 15.14% | 15.88% | 18% | 18% | 21.6% | 21.6% | 15% | 20.15% | 20.15% | 4.836% | 18% | 10.35% | 0% | 0% | 0% | 0% | 0% | 0% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 10.35% | 10.35% | 10.35% | 10.82% | 10.82% | 10.82% | 10.82% | 10.82% | 4.836% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 18% | 18% | 18% | 18% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | -3.938% | 4.616%
| P55 | 55% | 1.903% | 1.903% | 1.903% | 1.903% | 1.903% | 1.903% | 1.903% | 1.903% | 1.903% | -3.303% | -3.303% | -3.303% | -3.303% | 7.413% | 7.413% | 7.413% | 7.413% | 7.413% | 14.43% | 7.413% | 7.413% | 7.413% | 7.413% | 7.413% | 18.38% | 18.38% | -3.303% | -3.303% | -3.303% | -3.303% | 37.41% | 18.38% | 18.38% | 27.89% | 37.41% | 18.38% | 18.38% | 7.413% | 14.43% | -3.303% | -3.303% | 20.55% | 20.55% | 18.5% | 18.5% | 18.5% | 20.55% | 24.66% | 20.55% | 24.66% | 20% | 20% | 20.96% | 20.55% | 20.55% | 24.66% | 24.66% | 20% | 23% | 23% | 8% | 20.55% | 12.29% | 0% | 0% | 0% | 0% | 0% | 0% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 12.29% | 12.29% | 12.29% | 15.51% | 15.51% | 15.51% | 15.51% | 15.51% | 8% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 20.55% | 20.55% | 20.55% | 20.55% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | -3.303% | 8.155%
| P60 | 60% | 3.893% | 3.893% | 3.893% | 3.893% | 3.893% | 3.893% | 3.893% | 3.893% | 3.893% | -2.424% | -2.424% | -2.424% | -2.424% | 11.31% | 11.31% | 11.31% | 11.31% | 11.31% | 18.04% | 11.31% | 11.31% | 11.31% | 11.31% | 11.31% | 22% | 22% | -2.424% | -2.424% | -2.424% | -2.424% | 38.53% | 22% | 22% | 30.27% | 38.53% | 22% | 22% | 11.31% | 18.04% | -2.424% | -2.424% | 23% | 23% | 20.7% | 20.7% | 20.7% | 23% | 27.6% | 23% | 27.6% | 28.12% | 28.12% | 26.15% | 23% | 23% | 27.6% | 27.6% | 26% | 26% | 26% | 11.32% | 23% | 14.85% | 0.952% | 0.952% | 0.952% | 0.952% | 0.952% | 0.952% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 14.85% | 14.85% | 14.85% | 17.3% | 17.3% | 17.3% | 17.3% | 17.3% | 11.32% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 23% | 23% | 23% | 23% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | -2.424% | 12.45%
| P65 | 65% | 11.41% | 11.41% | 11.41% | 11.41% | 11.41% | 11.41% | 11.41% | 11.41% | 11.41% | -1.364% | -1.364% | -1.364% | -1.364% | 12.52% | 12.52% | 12.52% | 12.52% | 12.52% | 30.36% | 12.52% | 12.52% | 12.52% | 12.52% | 12.52% | 34.89% | 34.89% | -1.364% | -1.364% | -1.364% | -1.364% | 40.31% | 34.89% | 34.89% | 37.6% | 40.31% | 34.89% | 34.89% | 12.52% | 30.36% | -1.364% | -1.364% | 25.65% | 25.65% | 23.09% | 23.09% | 23.09% | 25.65% | 30.78% | 25.65% | 30.78% | 33.05% | 33.05% | 34.63% | 25.65% | 25.65% | 30.78% | 30.78% | 33% | 31.7% | 31.7% | 14.94% | 25.65% | 18.83% | 5.757% | 5.757% | 5.757% | 5.757% | 5.757% | 5.757% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 18.83% | 18.83% | 18.83% | 30.04% | 30.04% | 30.04% | 30.04% | 30.04% | 14.94% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 25.65% | 25.65% | 25.65% | 25.65% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | -1.364% | 13.78%
| P70 | 70% | 27.9% | 27.9% | 27.9% | 27.9% | 27.9% | 27.9% | 27.9% | 27.9% | 27.9% | -0.303% | -0.303% | -0.303% | -0.303% | 17.03% | 17.03% | 17.03% | 17.03% | 17.03% | 39.37% | 17.03% | 17.03% | 17.03% | 17.03% | 17.03% | 45.54% | 45.54% | -0.303% | -0.303% | -0.303% | -0.303% | 45.79% | 45.54% | 45.54% | 45.67% | 45.79% | 45.54% | 45.54% | 17.03% | 39.37% | -0.303% | -0.303% | 29.8% | 29.8% | 26.82% | 26.82% | 26.82% | 29.8% | 35.76% | 29.8% | 35.76% | 43.8% | 43.8% | 42.47% | 29.8% | 29.8% | 35.76% | 35.76% | 43.96% | 34.4% | 34.4% | 18.84% | 29.8% | 22.25% | 9.538% | 9.538% | 9.538% | 9.538% | 9.538% | 9.538% | 32.46% | 32.46% | 32.46% | 32.46% | 32.46% | 32.46% | 32.46% | 24.75% | 24.75% | 24.75% | 24.75% | 24.75% | 24.75% | 24.75% | 22.25% | 22.25% | 22.25% | 36.37% | 36.37% | 36.37% | 36.37% | 36.37% | 18.84% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 29.8% | 29.8% | 29.8% | 29.8% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | -0.303% | 18.73%
| P75 | 75% | 37.74% | 37.74% | 37.74% | 37.74% | 37.74% | 37.74% | 37.74% | 37.74% | 37.74% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 32.24% | 32.24% | 32.24% | 32.24% | 32.24% | 73.59% | 32.24% | 32.24% | 32.24% | 32.24% | 32.24% | 67.65% | 67.65% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 60.93% | 67.65% | 67.65% | 64.29% | 60.93% | 67.65% | 67.65% | 32.24% | 73.59% | 0.9167% | 0.9167% | 43.65% | 43.65% | 39.28% | 39.28% | 39.28% | 43.65% | 52.38% | 43.65% | 52.38% | 61.2% | 61.2% | 60.09% | 43.65% | 43.65% | 52.38% | 52.38% | 65.29% | 59% | 59% | 33.65% | 43.65% | 37.67% | 23.09% | 23.09% | 23.09% | 23.09% | 23.09% | 23.09% | 49.58% | 49.58% | 49.58% | 49.58% | 49.58% | 49.58% | 49.58% | 40.34% | 40.34% | 40.34% | 40.34% | 40.34% | 40.34% | 40.34% | 37.67% | 37.67% | 37.67% | 51.23% | 51.23% | 51.23% | 51.23% | 51.23% | 33.65% | 67.65% | 67.65% | 67.65% | 67.65% | 67.65% | 67.65% | 67.65% | 67.65% | 67.65% | 67.65% | 67.65% | 67.65% | 43.65% | 43.65% | 43.65% | 43.65% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 0.9167% | 35.47%
| P80 | 80% | 62.07% | 62.07% | 62.07% | 62.07% | 62.07% | 62.07% | 62.07% | 62.07% | 62.07% | 2.2% | 2.2% | 2.2% | 2.2% | 48.72% | 48.72% | 48.72% | 48.72% | 48.72% | 85.34% | 48.72% | 48.72% | 48.72% | 48.72% | 48.72% | 100.5% | 100.5% | 2.2% | 2.2% | 2.2% | 2.2% | 70.51% | 100.5% | 100.5% | 85.53% | 70.51% | 100.5% | 100.5% | 48.72% | 85.34% | 2.2% | 2.2% | 53.6% | 53.6% | 48.24% | 48.24% | 48.24% | 53.6% | 64.32% | 53.6% | 64.32% | 73.53% | 73.53% | 76.62% | 53.6% | 53.6% | 64.32% | 64.32% | 81.73% | 78.69% | 78.69% | 44.6% | 53.6% | 48.38% | 31.91% | 31.91% | 31.91% | 31.91% | 31.91% | 31.91% | 61.63% | 61.63% | 61.63% | 61.63% | 61.63% | 61.63% | 61.63% | 51.61% | 51.61% | 51.61% | 51.61% | 51.61% | 51.61% | 51.61% | 48.38% | 48.38% | 48.38% | 61.32% | 61.32% | 61.32% | 61.32% | 61.32% | 44.6% | 100.5% | 100.5% | 100.5% | 100.5% | 100.5% | 100.5% | 100.5% | 100.5% | 100.5% | 100.5% | 100.5% | 100.5% | 53.6% | 53.6% | 53.6% | 53.6% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 2.2% | 53.59%
| P85 | 85% | 72.34% | 72.34% | 72.34% | 72.34% | 72.34% | 72.34% | 72.34% | 72.34% | 72.34% | 3.483% | 3.483% | 3.483% | 3.483% | 78.14% | 78.14% | 78.14% | 78.14% | 78.14% | 90.33% | 78.14% | 78.14% | 78.14% | 78.14% | 78.14% | 144.1% | 144.1% | 3.483% | 3.483% | 3.483% | 3.483% | 74.1% | 144.1% | 144.1% | 109.1% | 74.1% | 144.1% | 144.1% | 78.14% | 90.33% | 3.483% | 3.483% | 57.78% | 57.78% | 52% | 52% | 52% | 57.78% | 69.34% | 57.78% | 69.34% | 84.63% | 84.63% | 101.9% | 57.78% | 57.78% | 69.34% | 69.34% | 96.52% | 88.19% | 88.19% | 54.97% | 57.78% | 60.74% | 34.32% | 34.32% | 34.32% | 34.32% | 34.32% | 34.32% | 84.86% | 84.86% | 84.86% | 84.86% | 84.86% | 84.86% | 84.86% | 63.03% | 63.03% | 63.03% | 63.03% | 63.03% | 63.03% | 63.03% | 60.74% | 60.74% | 60.74% | 68.25% | 68.25% | 68.25% | 68.25% | 68.25% | 54.97% | 144.1% | 144.1% | 144.1% | 144.1% | 144.1% | 144.1% | 144.1% | 144.1% | 144.1% | 144.1% | 144.1% | 144.1% | 57.78% | 57.78% | 57.78% | 57.78% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 3.483% | 85.95%
| P90 | 90% | 132.6% | 132.6% | 132.6% | 132.6% | 132.6% | 132.6% | 132.6% | 132.6% | 132.6% | 24.11% | 24.11% | 24.11% | 24.11% | 124.8% | 124.8% | 124.8% | 124.8% | 124.8% | 116.8% | 124.8% | 124.8% | 124.8% | 124.8% | 124.8% | 219.2% | 219.2% | 24.11% | 24.11% | 24.11% | 24.11% | 98.31% | 219.2% | 219.2% | 158.7% | 98.31% | 219.2% | 219.2% | 124.8% | 116.8% | 24.11% | 24.11% | 69.98% | 69.98% | 62.98% | 62.98% | 62.98% | 69.98% | 83.98% | 69.98% | 83.98% | 102.2% | 102.2% | 149.1% | 69.98% | 69.98% | 83.98% | 83.98% | 131.3% | 119.8% | 119.8% | 75.4% | 69.98% | 71.22% | 43.28% | 43.28% | 43.28% | 43.28% | 43.28% | 43.28% | 95.56% | 95.56% | 95.56% | 95.56% | 95.56% | 95.56% | 95.56% | 74.81% | 74.81% | 74.81% | 74.81% | 74.81% | 74.81% | 74.81% | 71.22% | 71.22% | 71.22% | 73.73% | 73.73% | 73.73% | 73.73% | 73.73% | 75.4% | 219.2% | 219.2% | 219.2% | 219.2% | 219.2% | 219.2% | 219.2% | 219.2% | 219.2% | 219.2% | 219.2% | 219.2% | 69.98% | 69.98% | 69.98% | 69.98% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 24.11% | 137.3%
| P95 | 95% | 174.6% | 174.6% | 174.6% | 174.6% | 174.6% | 174.6% | 174.6% | 174.6% | 174.6% | 47.95% | 47.95% | 47.95% | 47.95% | 227.5% | 227.5% | 227.5% | 227.5% | 227.5% | 167.1% | 227.5% | 227.5% | 227.5% | 227.5% | 227.5% | 290.4% | 290.4% | 47.95% | 47.95% | 47.95% | 47.95% | 125.2% | 290.4% | 290.4% | 207.8% | 125.2% | 290.4% | 290.4% | 227.5% | 167.1% | 47.95% | 47.95% | 86.1% | 86.1% | 77.49% | 77.49% | 77.49% | 86.1% | 103.3% | 86.1% | 103.3% | 134.3% | 134.3% | 204.5% | 86.1% | 86.1% | 103.3% | 103.3% | 267.6% | 163.8% | 163.8% | 101.8% | 86.1% | 97.51% | 52.19% | 52.19% | 52.19% | 52.19% | 52.19% | 52.19% | 142.8% | 142.8% | 142.8% | 142.8% | 142.8% | 142.8% | 142.8% | 97.52% | 97.52% | 97.52% | 97.52% | 97.52% | 97.52% | 97.52% | 97.51% | 97.51% | 97.51% | 89.01% | 89.01% | 89.01% | 89.01% | 89.01% | 101.8% | 290.4% | 290.4% | 290.4% | 290.4% | 290.4% | 290.4% | 290.4% | 290.4% | 290.4% | 290.4% | 290.4% | 290.4% | 86.1% | 86.1% | 86.1% | 86.1% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 47.95% | 250.2%
| P100 | 100%
Schedule RCF
| Notes |  | L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | MB added | Same | Same | Same | Bldg | Same | Same | Bldg | Same | Bld 0-5y | Same | Same | Same | Same | Same | EW | EW | MB added | Same | Same | Same | Demolition | EW | EW | (EW+Facil W)/2 | Facil Works | EW x | EW x | Bldg | Bld 0-5y | Design | Design | roads | Roads | Roads x | Roads x | Roads x | Urban roads std | Urban roads cx | Rural std | Rural cx | As Rail | 0 | 0 | Roads | Spine roads | Roads | Junctions | Civils | Bridges | Tunnels | Earthworks | Roads | Gen Utilities | Elec | Elec x | Elec x | Elec x | Elec x | Elec x | Gas | Gas x | Gas x | Gas x | Gas x | Gas x | Gas x | Water | Water x | Water x | Water x | Water x | Water x | Water x | Gen x | Gen x | Gen x | Drng | Drng x | Drng x | Drng x | Drng x | Landraising | Enab W x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Roads x | Roads x | Roads x | Roads x | Mngt | Fees x | Fees x | Fees x | Fees x | Fees x | Fees x | As mngt | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Mngt x | Mngt x | Mngt | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | Bldg
|  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 0 | 0 | 0 |  |  | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.9 | 0.9 | 0.9 | 1 | 1.2 | 1 | 1.2 | 1 | 0 | 0 | 1 | 1 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1
| P0 | 0%
| P5 | 5% | -7.397% | -7.397% | -7.397% | -7.397% | -7.397% | -7.397% | -7.397% | -7.397% | -7.397% | -30% | -30% | -30% | -30% | -8.044% | -8.044% | -8.044% | -8.044% | -8.044% | -2% | -8.044% | -8.044% | -8.044% | -8.044% | -8.044% | -2% | -2% | -30% | -30% | -30% | -30% | -1.2% | -2% | -2% | -1.6% | -1.2% | -2% | -2% | -8.044% | -2% | -30% | -30% | -31.12% | -31.12% | -28.01% | -28.01% | -28.01% | -31.12% | -37.34% | -31.12% | -37.34% | -30.59% | -30.59% | -13.86% | -31.12% | -31.12% | -37.34% | -37.34% | -7.188% | -15% | -15% | -30.18% | -31.12% | -4.854% | -2% | -2% | -2% | -2% | -2% | -2% | -2.277% | -2.277% | -2.277% | -2.277% | -2.277% | -2.277% | -2.277% | -10.29% | -10.29% | -10.29% | -10.29% | -10.29% | -10.29% | -10.29% | -4.854% | -4.854% | -4.854% | -10.29% | -10.29% | -10.29% | -10.29% | -10.29% | -30.18% | -2% | -2% | -2% | -2% | -2% | -2% | -2% | -2% | -2% | -2% | -2% | -2% | -31.12% | -31.12% | -31.12% | -31.12% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -30% | -8.848%
| P10 | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -19% | -19% | -19% | -19% | -7.938% | -7.938% | -7.938% | -7.938% | -7.938% | 0% | -7.938% | -7.938% | -7.938% | -7.938% | -7.938% | 0% | 0% | -19% | -19% | -19% | -19% | -1.4% | 0% | 0% | -0.7% | -1.4% | 0% | 0% | -7.938% | 0% | -19% | -19% | -23% | -23% | -20.7% | -20.7% | -20.7% | -23% | -27.6% | -23% | -27.6% | -22.9% | -22.9% | -11.1% | -23% | -23% | -27.6% | -27.6% | -2.818% | -14.11% | -14.11% | -22% | -23% | -1.461% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -7.383% | -7.383% | -7.383% | -7.383% | -7.383% | -7.383% | -7.383% | -1.461% | -1.461% | -1.461% | -7.383% | -7.383% | -7.383% | -7.383% | -7.383% | -22% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -23% | -23% | -23% | -23% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -8.732%
| P15 | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -11.91% | -11.91% | -11.91% | -11.91% | -0.7781% | -0.7781% | -0.7781% | -0.7781% | -0.7781% | 0% | -0.7781% | -0.7781% | -0.7781% | -0.7781% | -0.7781% | 0% | 0% | -11.91% | -11.91% | -11.91% | -11.91% | 3.459% | 0% | 0% | 1.729% | 3.459% | 0% | 0% | -0.7781% | 0% | -11.91% | -11.91% | -14.72% | -14.72% | -13.25% | -13.25% | -13.25% | -14.72% | -17.66% | -14.72% | -17.66% | -12.04% | -12.04% | 1.309% | -14.72% | -14.72% | -17.66% | -17.66% | 0% | -4.683% | -4.683% | -13.48% | -14.72% | -0.4804% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -0.141% | -1.582% | -1.582% | -1.582% | -1.582% | -1.582% | -1.582% | -1.582% | -0.4804% | -0.4804% | -0.4804% | -1.582% | -1.582% | -1.582% | -1.582% | -1.582% | -13.48% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -14.72% | -14.72% | -14.72% | -14.72% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -0.8559%
| P20 | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6% | -6% | -6% | -6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6% | -6% | -6% | -6% | 6.8% | 0% | 0% | 3.4% | 6.8% | 0% | 0% | 0% | 0% | -6% | -6% | -10.18% | -10.18% | -9.162% | -9.162% | -9.162% | -10.18% | -12.22% | -10.18% | -12.22% | -6.8% | -6.8% | 7.2% | -10.18% | -10.18% | -12.22% | -12.22% | 0% | -2.371% | -2.371% | -9.26% | -10.18% | 1.409% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 1.409% | 1.409% | 1.409% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | -9.26% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -10.18% | -10.18% | -10.18% | -10.18% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | 0%
| P25 | 25% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -3% | -4.443% | -4.443% | -4.443% | -4.443% | 0% | 0% | 0% | 0% | 0% | -3% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -4.443% | -4.443% | -4.443% | -4.443% | 10% | 0% | 0% | 5% | 10% | 0% | 0% | 0% | -3% | -4.443% | -4.443% | -3.541% | -3.541% | -3.187% | -3.187% | -3.187% | -3.541% | -4.249% | -3.541% | -4.249% | -0.9424% | -0.9424% | 9.289% | -3.541% | -3.541% | -4.249% | -4.249% | 0% | 0% | 0% | -3.061% | -3.541% | 0.2923% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 0.2923% | 0.2923% | 0.2923% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | -3.061% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -3.541% | -3.541% | -3.541% | -3.541% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | -4.443% | 0%
| P30 | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.67% | 0% | 0% | 6.333% | 12.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.65% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.139% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 6.139% | 6.139% | 6.139% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| P35 | 35% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15.33% | 0% | 0% | 7.667% | 15.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.089% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 7.089% | 7.089% | 7.089% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| P40 | 40% | 1.557% | 1.557% | 1.557% | 1.557% | 1.557% | 1.557% | 1.557% | 1.557% | 1.557% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | 0% | 0% | 0% | 0% | 0% | -0.03761% | 0% | 0% | 0% | 0% | 0% | -1% | -1% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | 18.93% | -1% | -1% | 8.967% | 18.93% | -1% | -1% | 0% | -0.03761% | -0.6427% | -0.6427% | 3.259% | 3.259% | 2.933% | 2.933% | 2.933% | 3.259% | 3.911% | 3.259% | 3.911% | 7.397% | 7.397% | 15% | 3.259% | 3.259% | 3.911% | 3.911% | 0% | 0% | 0% | 2% | 3.259% | 6.822% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 6.822% | 6.822% | 6.822% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 2% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | -1% | 3.259% | 3.259% | 3.259% | 3.259% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | -0.6427% | 0%
| P45 | 45% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 6.013% | 6.013% | 6.013% | 6.013% | 0% | 0% | 0% | 0% | 0% | 3.08% | 0% | 0% | 0% | 0% | 0% | 0.9632% | 0.9632% | 6.013% | 6.013% | 6.013% | 6.013% | 23.47% | 0.9632% | 0.9632% | 12.21% | 23.47% | 0.9632% | 0.9632% | 0% | 3.08% | 6.013% | 6.013% | 8.063% | 8.063% | 7.257% | 7.257% | 7.257% | 8.063% | 9.676% | 8.063% | 9.676% | 14.1% | 14.1% | 18.9% | 8.063% | 8.063% | 9.676% | 9.676% | 0% | 1.829% | 1.829% | 7.183% | 8.063% | 10.02% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 10.02% | 10.02% | 10.02% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 7.183% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 8.063% | 8.063% | 8.063% | 8.063% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 0%
| P50 | 50% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 12.27% | 12.27% | 12.27% | 12.27% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 17.5% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 4.692% | 4.692% | 12.27% | 12.27% | 12.27% | 12.27% | 28% | 4.692% | 4.692% | 16.35% | 28% | 4.692% | 4.692% | 0.2635% | 17.5% | 12.27% | 12.27% | 13% | 13% | 11.7% | 11.7% | 11.7% | 13% | 15.6% | 13% | 15.6% | 19.09% | 19.09% | 26% | 13% | 13% | 15.6% | 15.6% | 1.658% | 3.449% | 3.449% | 11.65% | 13% | 10.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 10.97% | 10.97% | 10.97% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 11.65% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 13% | 13% | 13% | 13% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 0.2899%
| P55 | 55% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 16% | 16% | 16% | 16% | 2.652% | 2.652% | 2.652% | 2.652% | 2.652% | 26% | 2.652% | 2.652% | 2.652% | 2.652% | 2.652% | 14.05% | 14.05% | 16% | 16% | 16% | 16% | 28.8% | 14.05% | 14.05% | 21.42% | 28.8% | 14.05% | 14.05% | 2.652% | 26% | 16% | 16% | 16.67% | 16.67% | 15% | 15% | 15% | 16.67% | 20% | 16.67% | 20% | 26.27% | 26.27% | 29.72% | 16.67% | 16.67% | 20% | 20% | 4% | 7.169% | 7.169% | 15.76% | 16.67% | 17.24% | 0% | 0% | 0% | 0% | 0% | 0% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 17.24% | 17.24% | 17.24% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 15.76% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 16.67% | 16.67% | 16.67% | 16.67% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 2.918%
| P60 | 60% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 21.87% | 21.87% | 21.87% | 21.87% | 3.263% | 3.263% | 3.263% | 3.263% | 3.263% | 32.95% | 3.263% | 3.263% | 3.263% | 3.263% | 3.263% | 18.57% | 18.57% | 21.87% | 21.87% | 21.87% | 21.87% | 29.6% | 18.57% | 18.57% | 24.08% | 29.6% | 18.57% | 18.57% | 3.263% | 32.95% | 21.87% | 21.87% | 22.63% | 22.63% | 20.37% | 20.37% | 20.37% | 22.63% | 27.16% | 22.63% | 27.16% | 30.6% | 30.6% | 44.3% | 22.63% | 22.63% | 27.16% | 27.16% | 14% | 12% | 12% | 21.47% | 22.63% | 21.44% | 0% | 0% | 0% | 0% | 0% | 0% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 21.44% | 21.44% | 21.44% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 21.47% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 22.63% | 22.63% | 22.63% | 22.63% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 3.589%
| P65 | 65% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 27% | 27% | 27% | 27% | 4.324% | 4.324% | 4.324% | 4.324% | 4.324% | 48.71% | 4.324% | 4.324% | 4.324% | 4.324% | 4.324% | 29.81% | 29.81% | 27% | 27% | 27% | 27% | 39.2% | 29.81% | 29.81% | 34.51% | 39.2% | 29.81% | 29.81% | 4.324% | 48.71% | 27% | 27% | 27.36% | 27.36% | 24.62% | 24.62% | 24.62% | 27.36% | 32.83% | 27.36% | 32.83% | 36.7% | 36.7% | 49.65% | 27.36% | 27.36% | 32.83% | 32.83% | 19.87% | 16% | 16% | 27% | 27.36% | 24.41% | 0% | 0% | 0% | 0% | 0% | 0% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 24.41% | 24.41% | 24.41% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 27% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 27.36% | 27.36% | 27.36% | 27.36% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 4.756%
| P70 | 70% | 31.75% | 31.75% | 31.75% | 31.75% | 31.75% | 31.75% | 31.75% | 31.75% | 31.75% | 43.97% | 43.97% | 43.97% | 43.97% | 12.8% | 12.8% | 12.8% | 12.8% | 12.8% | 58% | 12.8% | 12.8% | 12.8% | 12.8% | 12.8% | 55.61% | 55.61% | 43.97% | 43.97% | 43.97% | 43.97% | 60.6% | 55.61% | 55.61% | 58.1% | 60.6% | 55.61% | 55.61% | 12.8% | 58% | 43.97% | 43.97% | 38.93% | 38.93% | 35.04% | 35.04% | 35.04% | 38.93% | 46.72% | 38.93% | 46.72% | 43% | 43% | 53% | 38.93% | 38.93% | 46.72% | 46.72% | 33.56% | 25% | 25% | 38.1% | 38.93% | 35.39% | 3% | 3% | 3% | 3% | 3% | 3% | 35.17% | 35.17% | 35.17% | 35.17% | 35.17% | 35.17% | 35.17% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 35.39% | 35.39% | 35.39% | 53% | 53% | 53% | 53% | 53% | 38.1% | 55.61% | 55.61% | 55.61% | 55.61% | 55.61% | 55.61% | 55.61% | 55.61% | 55.61% | 55.61% | 55.61% | 55.61% | 38.93% | 38.93% | 38.93% | 38.93% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 43.97% | 14.08%
| P75 | 75% | 40.61% | 40.61% | 40.61% | 40.61% | 40.61% | 40.61% | 40.61% | 40.61% | 40.61% | 58.71% | 58.71% | 58.71% | 58.71% | 35.64% | 35.64% | 35.64% | 35.64% | 35.64% | 80% | 35.64% | 35.64% | 35.64% | 35.64% | 35.64% | 70.5% | 70.5% | 58.71% | 58.71% | 58.71% | 58.71% | 89% | 70.5% | 70.5% | 79.75% | 89% | 70.5% | 70.5% | 35.64% | 80% | 58.71% | 58.71% | 63% | 63% | 56.7% | 56.7% | 56.7% | 63% | 75.6% | 63% | 75.6% | 59% | 59% | 63% | 63% | 63% | 75.6% | 75.6% | 47.16% | 48% | 48% | 61% | 63% | 44.31% | 13% | 13% | 13% | 13% | 13% | 13% | 48% | 48% | 48% | 48% | 48% | 48% | 48% | 71.92% | 71.92% | 71.92% | 71.92% | 71.92% | 71.92% | 71.92% | 44.31% | 44.31% | 44.31% | 71.92% | 71.92% | 71.92% | 71.92% | 71.92% | 61% | 70.5% | 70.5% | 70.5% | 70.5% | 70.5% | 70.5% | 70.5% | 70.5% | 70.5% | 70.5% | 70.5% | 70.5% | 63% | 63% | 63% | 63% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 58.71% | 39.21%
| P80 | 80% | 49.22% | 49.22% | 49.22% | 49.22% | 49.22% | 49.22% | 49.22% | 49.22% | 49.22% | 76.4% | 76.4% | 76.4% | 76.4% | 45.99% | 45.99% | 45.99% | 45.99% | 45.99% | 104.2% | 45.99% | 45.99% | 45.99% | 45.99% | 45.99% | 84.8% | 84.8% | 76.4% | 76.4% | 76.4% | 76.4% | 97.8% | 84.8% | 84.8% | 91.3% | 97.8% | 84.8% | 84.8% | 45.99% | 104.2% | 76.4% | 76.4% | 80.4% | 80.4% | 72.36% | 72.36% | 72.36% | 80.4% | 96.48% | 80.4% | 96.48% | 67% | 67% | 82% | 80.4% | 80.4% | 96.48% | 96.48% | 66.28% | 55% | 55% | 79.2% | 80.4% | 56.96% | 17% | 17% | 17% | 17% | 17% | 17% | 73% | 73% | 73% | 73% | 73% | 73% | 73% | 80.87% | 80.87% | 80.87% | 80.87% | 80.87% | 80.87% | 80.87% | 56.96% | 56.96% | 56.96% | 80.87% | 80.87% | 80.87% | 80.87% | 80.87% | 79.2% | 84.8% | 84.8% | 84.8% | 84.8% | 84.8% | 84.8% | 84.8% | 84.8% | 84.8% | 84.8% | 84.8% | 84.8% | 80.4% | 80.4% | 80.4% | 80.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 76.4% | 50.59%
| P85 | 85% | 59.47% | 59.47% | 59.47% | 59.47% | 59.47% | 59.47% | 59.47% | 59.47% | 59.47% | 89% | 89% | 89% | 89% | 56.97% | 56.97% | 56.97% | 56.97% | 56.97% | 114% | 56.97% | 56.97% | 56.97% | 56.97% | 56.97% | 114% | 114% | 89% | 89% | 89% | 89% | 104.6% | 114% | 114% | 109.3% | 104.6% | 114% | 114% | 56.97% | 114% | 89% | 89% | 99.96% | 99.96% | 89.96% | 89.96% | 89.96% | 99.96% | 119.9% | 99.96% | 119.9% | 84.9% | 84.9% | 105.3% | 99.96% | 99.96% | 119.9% | 119.9% | 82.69% | 70.5% | 70.5% | 94.86% | 99.96% | 57.77% | 19% | 19% | 19% | 19% | 19% | 19% | 85.67% | 85.67% | 85.67% | 85.67% | 85.67% | 85.67% | 85.67% | 83.66% | 83.66% | 83.66% | 83.66% | 83.66% | 83.66% | 83.66% | 57.77% | 57.77% | 57.77% | 83.66% | 83.66% | 83.66% | 83.66% | 83.66% | 94.86% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 114% | 99.96% | 99.96% | 99.96% | 99.96% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 89% | 62.67%
| P90 | 90% | 79.96% | 79.96% | 79.96% | 79.96% | 79.96% | 79.96% | 79.96% | 79.96% | 79.96% | 125% | 125% | 125% | 125% | 94.76% | 94.76% | 94.76% | 94.76% | 94.76% | 163% | 94.76% | 94.76% | 94.76% | 94.76% | 94.76% | 158.3% | 158.3% | 125% | 125% | 125% | 125% | 121.6% | 158.3% | 158.3% | 139.9% | 121.6% | 158.3% | 158.3% | 94.76% | 163% | 125% | 125% | 138% | 138% | 124.2% | 124.2% | 124.2% | 138% | 165.6% | 138% | 165.6% | 125% | 125% | 113.9% | 138% | 138% | 165.6% | 165.6% | 107.5% | 100.5% | 100.5% | 130.4% | 138% | 83.15% | 37.32% | 37.32% | 37.32% | 37.32% | 37.32% | 37.32% | 105% | 105% | 105% | 105% | 105% | 105% | 105% | 107.1% | 107.1% | 107.1% | 107.1% | 107.1% | 107.1% | 107.1% | 83.15% | 83.15% | 83.15% | 107.1% | 107.1% | 107.1% | 107.1% | 107.1% | 130.4% | 158.3% | 158.3% | 158.3% | 158.3% | 158.3% | 158.3% | 158.3% | 158.3% | 158.3% | 158.3% | 158.3% | 158.3% | 138% | 138% | 138% | 138% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 104.2%
| P95 | 95% | 113.5% | 113.5% | 113.5% | 113.5% | 113.5% | 113.5% | 113.5% | 113.5% | 113.5% | 176.1% | 176.1% | 176.1% | 176.1% | 169% | 169% | 169% | 169% | 169% | 222.3% | 169% | 169% | 169% | 169% | 169% | 200.6% | 200.6% | 176.1% | 176.1% | 176.1% | 176.1% | 143.7% | 200.6% | 200.6% | 172.1% | 143.7% | 200.6% | 200.6% | 169% | 222.3% | 176.1% | 176.1% | 182.8% | 182.8% | 164.5% | 164.5% | 164.5% | 182.8% | 219.4% | 182.8% | 219.4% | 162% | 162% | 121.8% | 182.8% | 182.8% | 219.4% | 219.4% | 160.9% | 116% | 116% | 175.3% | 182.8% | 107.9% | 73.32% | 73.32% | 73.32% | 73.32% | 73.32% | 73.32% | 127.1% | 127.1% | 127.1% | 127.1% | 127.1% | 127.1% | 127.1% | 123.2% | 123.2% | 123.2% | 123.2% | 123.2% | 123.2% | 123.2% | 107.9% | 107.9% | 107.9% | 123.2% | 123.2% | 123.2% | 123.2% | 123.2% | 175.3% | 200.6% | 200.6% | 200.6% | 200.6% | 200.6% | 200.6% | 200.6% | 200.6% | 200.6% | 200.6% | 200.6% | 200.6% | 182.8% | 182.8% | 182.8% | 182.8% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 176.1% | 185.9%
| P100 | 100%
Note on AB2: Site preparation works, Roads, paths, paving’s and surfacing, Soft landscaping, planting and irrigation systems, fencing, external drainage and utilities and minor building works and ancillary building works
Note on E3: Purchase price including Planning Risk discounts (Actual price to be paid)
Note on F3: Purchasers Agent and Legal fees
Note on G3: SDLT rates as appropriate
Note on H3: Easements, Wayleaves
Note on M3: Costs for securing Outline Planning Permission
Note on N3: Costs for securing Outline Planning Permission
Note on O3: Costs for securing Reserved Matters planning
Note on P3: Pre-app, allocation promotion, SPD/planning brief, design incl B4Life, Listed Buildings surveys, fees associated with S278,38 or 104, highway, noise, and desk top archaeology surveys.
Note on AH3: includes demolition to slab and or below ground, substructures. Planning costs for demolition should be included in planning fees.
Note on AI3: Including cut and fill and ground stabilisation, preparing sub-surfaces, site clearance, including all works to existing trees and TPOs etc.
Note on AJ3: Remediation and decontamination including monitoring costs
Note on AM3: Incl site investigations, topo survey, noise surveys, UXO, building condition survey
Note on AQ3: Including Transport and Highway Assessments
Note on AS3: Means works undertaken by developer
Note on AT3: incl. contribution to strategic infrastructure; works undertaken by others
Note on BB3: Works to be carried out by the developer on Public Transport not included in S106 Costs
Note on BF3: Infrastructure not serving individual plots directly i.e. not local infrastructure included under externals. Including standard sewers. Will include fees, contingencies and prelims
Note on BH3: Additional junctions or junctions works over and above standard
Note on BM3: compensation for depreciation in the value of an interest in land which is attributable to the use of public works i.e construction of a highway
Note on CK4: (likely to be removed in due course as costs become standard and are reflected within base build costs)
Note on D5: From EW Rail "L&P"
Note on M5: From BusConnects "Prelims"
Note on Q5: From BusConnects "Building"
Note on T5: From BusConnects "Building"
Note on AB5: From EW Rail "civils"
Note on AD5: From Busconnects "Management"
Note on AH5: EW Rail "Temp Works"
Note on AQ5: Mr Bartlett: BusConnects Design - change to SW Design?
Note on AR5: Mr Bartlett: BusConnects Design - change to SW Design?
Note on AT5: BusConnects roads
Note on BB5: As rail
Note on BC5: EW Rail "Track"
Note on BD5: EW Rail "Stations"
Note on BI5: EW Rail "Civils"
Note on BJ5: EW Rail "Bridges"
Note on BK5: EW Rail "Tunnels"
Note on CM5: Data from Sydney Water
Note on DO5: Use margin from SW work?
Note on M33: From EW Rail "Prelims etc"
Note on AD33: From EW Rail "Prelims etc"

## RCF FBC data (hidden)
FBC
| Primary RCF Data |  | Land Costs | [8 empty] | Planning |  |  |  | Build Cost (Base build total cost) |  |  | Building | [7 empty] | External Works |  | Management costs |  |  |  | Site Preparation | [6 empty] | Foundations |  | Infrastructure and highways | [22 empty] | Utilities | [23 empty] | Drainage | [5 empty] | Ecology | [11 empty] | Landscaping/ Public Realm |  |  |  | Surveys and Fees |  |  |  |  | Sales and Marketing |  | Profit (inclusive of any developer Overheads, aftercare and sales incentives) | [7 empty] | Community Infrastructure Levy (CIL) |  | Section 106 Obligations | [12 empty] | Other Abnormal Costs
|  |  | General L&P | Acquisition Cost | Agent and Legal fees | SDLT | Access Rights | Ransom Payments | Option Fees | Overage | Additional Land Acquisition | Planning general | Outline Planning | Reserved Matters Planning | Other Planning Costs | Standard construction and foundations | Preliminaries apportioned | Contractors' overheads and profits (not developers’) | General: unspecified | Residential | Custom build properties | Building affordable housing | Commercial (shop units/ offices space | Light industrial (warehousing/ distribution) | Film studios/ creative space | Community/ public buildings | Associated with houses | Associated with apartments | General | Maintenance & protection of a heritage asset | Other holding costs/ estate management | Professional Fees: General | Demolition | Enabling works | Remediation and Decontamination |  |  | Due Diligence (survey works) | Archaeology/Heritage surveys | Standard foundations | Abnormal Foundations | Highway and Transport Design Works | Noise and Vibration Design Works | S278 works | Offsite Highways works (breakdown by type of works as feasible) | [7 empty] | Public Transport |  |  |  | Spine Road | Roundabouts | Junctions | Other civil works |  |  |  | Part 1 Claims | Unspecified or mixed | Electricity | [5 empty] | Gas | [6 empty] | Water | [6 empty] | District Heating | Telecoms | Renewable Energy | General | Pumping Station | SUDS/Swales/Tanks/Attenuation |  | Sewers | Flood Risk | General | Ecology Design Work | Arboriculture | Mitigation | Nitrogen neutrality | Water Neutrality | Biodiversity Net Gain (BNG) | Invasive Species | Birds and Bats | SANGS | Invertebrates/vertebrates | Mammals | Public Realm / Public Open Space | Play areas / Outdoor sports | Endowment | Public Art | Valuation and Appraisal Advice | Legal Advice | Development Management / Master Developer Fees | Health and Safety Advice | Communications Fees | Agent Fees | Legal Fees | Profit on Market Sale | Profit on Affordable | Profit on Commercial | Profit on PRS | Total Blended Profit | Internal Rate of Return (IRR) | Development Management Fee | Return On Capital Employed (ROCE) | CIL Residential | CIL Commercial | General | Roof Tax | Affordable Housing Offsite Payment | Community Facilities | Employment and Skills | Healthcare | Highways / Transport | Education (primary and secondary) | Libraries | Public Realm/Open Space | Monitoring Fee | Play areas | Sports Fields
| RCF Values | [33 empty] | Simple | complex/ brownfield | heavily contaminated | [7 empty] | Unspecified or mixed | Footpaths | Cycle paths | Parking (surface) | Urban roads - standard | Urban roads - complex | Rural roads - standard | Rural roads - complex | Unspecified or mixed | Rail | Stations | Buslanes |  |  |  | Unspecified or mixed | Bridges/ other structures | Tunnels | Earthworks |  |  | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs legal fees for wayleaves, licences, supply agreements, compensation claims | Easement costs | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, Compensation claims | Easement costs | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, compensation claims | Easement Costs | Capital cost, plot costs, legals and heat charger | Upgrading cables | CHP, non plot specific EV charging or solar |  |  | Includes landscaping features associated with attenuation ponds | Beyond plot specific measures included in externals (such as permeable drives) | Includes Surface and Foul beyond standard included in Externals and/or spine road | Includes land raising/barriers/defence |  |  | Covers tree surgery and/or tree protection works | i.e. offsite contribution, Habitat Regulation Assessment, | [6 empty] | Newts – including fencing and ladders | Dormice, badgers | Estate costs/shared areas not included in external works including landscaping wildflower meadows. | in addition to any S. 106 requirements | for long term management | in addition to any S. 106 requirements | (beyond standard house building Professional fees and not included in specialist categories above) | state aid advice, specific questions on ransoms etc. | These include fees paid to development managers/ Master Developers of the site or collaboration costs. | e.g. highways, reservoirs | Fees for example related to any PR on the site but not planning related costs.
| Notes |  | L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | Design | Same | Same | Same | Bldg | Same | Same | Bldg | Same | Bld 0-5 y | Same | Same | Same | Same | Same | EW | EW | Mngt | Same | Same | Same | Demolition | EW | EW | (EW+Facil W)/2 | Facil Works | EW x | EW x | Bldg | Bld 0-5 y | Design | Design | Roads | Roads | Roads x | Roads x | Roads x | Urban roads std | Urban roads cx | Rural std | Rural cx | As Rail | Rail | Stations | Roads | Spine roads | Roads | Junctions | Civils | Bridges | Tunnels | Earthworks | Roads | Gen Utilities | Elec | Elec x | Elec x | Elec x | Elec x | Elec x | Gas | Gas x | Gas x | Gas x | Gas x | Gas x | Gas x | Water | Water x | Water x | Water x | Water x | Water x | Water x | Gen x | Gen x | Gen x | Drng | Drng x | Drng x | Drng x | Drng x | Landraising | Enab W x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Roads x | Roads x | Roads x | Roads x | Mngt | Fees x | Fees x | Fees x | Fees x | Fees x | Fees x | As mngt | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Mngt x | Mngt x | Mngt | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | Bldg
| Factor |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 |  | 1 |  |  | 1 | 1 |  |  | 0 | 0 | 1 | 0 | 0.9 | 0.9 | 0.9 | 1 | 1.2 | 1 | 1.2 | 1 | 0 | 0 | 1 | 1 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1
Cost RCF
| P0 | 0%
| P5 | 5% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -95.6% | -63.35% | -63.35% | -63.35% | -63.35% | -23.43% | -23.43% | -23.43% | -23.43% | -23.43% | -18.86% | -23.43% | -23.43% | -23.43% | -23.43% | -23.43% | -17.83% | -17.83% | -63.35% | -63.35% | -63.35% | -63.35% | -15% | -17.83% | -17.83% | -16.41% | -15% | -17.83% | -17.83% | -23.43% | -18.86% | -63.35% | -63.35% | -7% | -7% | -6.3% | -6.3% | -6.3% | -7% | -8.4% | -7% | -8.4% | -19.65% | -19.65% | -11.3% | -7% | -7% | -8.4% | -8.4% | -18.21% | -21% | -21% | -19.8% | -7% | -24.74% | -28.69% | -28.69% | -28.69% | -28.69% | -28.69% | -28.69% | -13.34% | -13.34% | -13.34% | -13.34% | -13.34% | -13.34% | -13.34% | -32.2% | -32.2% | -32.2% | -32.2% | -32.2% | -32.2% | -32.2% | -24.74% | -24.74% | -24.74% | -32.26% | -32.26% | -32.26% | -32.26% | -32.26% | -19.8% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -17.83% | -7% | -7% | -7% | -7% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -63.35% | -25.78%
| P10 | 10% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -89.64% | -40.56% | -40.56% | -40.56% | -40.56% | -17.18% | -17.18% | -17.18% | -17.18% | -17.18% | -13.82% | -17.18% | -17.18% | -17.18% | -17.18% | -17.18% | -10.6% | -10.6% | -40.56% | -40.56% | -40.56% | -40.56% | -10.15% | -10.6% | -10.6% | -10.37% | -10.15% | -10.6% | -10.6% | -17.18% | -13.82% | -40.56% | -40.56% | 1% | 1% | 0.9% | 0.9% | 0.9% | 1% | 1.2% | 1% | 1.2% | -11.44% | -11.44% | -6.614% | 1% | 1% | 1.2% | 1.2% | -11.27% | -15.35% | -15.35% | -11% | 1% | -16.1% | -16.09% | -16.09% | -16.09% | -16.09% | -16.09% | -16.09% | -7.47% | -7.47% | -7.47% | -7.47% | -7.47% | -7.47% | -7.47% | -24.75% | -24.75% | -24.75% | -24.75% | -24.75% | -24.75% | -24.75% | -16.1% | -16.1% | -16.1% | -28.91% | -28.91% | -28.91% | -28.91% | -28.91% | -11% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | -10.6% | 1% | 1% | 1% | 1% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -40.56% | -18.89%
| P15 | 15% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -71.46% | -27.64% | -27.64% | -27.64% | -27.64% | -13.62% | -13.62% | -13.62% | -13.62% | -13.62% | -5.617% | -13.62% | -13.62% | -13.62% | -13.62% | -13.62% | -4.291% | -4.291% | -27.64% | -27.64% | -27.64% | -27.64% | -7.956% | -4.291% | -4.291% | -6.123% | -7.956% | -4.291% | -4.291% | -13.62% | -5.617% | -27.64% | -27.64% | 3% | 3% | 2.7% | 2.7% | 2.7% | 3% | 3.6% | 3% | 3.6% | -7.431% | -7.431% | -4.436% | 3% | 3% | 3.6% | 3.6% | -6.468% | -10% | -10% | -6.319% | 3% | -7.949% | -7.42% | -7.42% | -7.42% | -7.42% | -7.42% | -7.42% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -0.3954% | -16.03% | -16.03% | -16.03% | -16.03% | -16.03% | -16.03% | -16.03% | -7.949% | -7.949% | -7.949% | -23.13% | -23.13% | -23.13% | -23.13% | -23.13% | -6.319% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | -4.291% | 3% | 3% | 3% | 3% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -27.64% | -14.99%
| P20 | 20% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -39.51% | -17.43% | -17.43% | -17.43% | -17.43% | -8.995% | -8.995% | -8.995% | -8.995% | -8.995% | 0% | -8.995% | -8.995% | -8.995% | -8.995% | -8.995% | -0.3492% | -0.3492% | -17.43% | -17.43% | -17.43% | -17.43% | -5.307% | -0.3492% | -0.3492% | -2.828% | -5.307% | -0.3492% | -0.3492% | -8.995% | 0% | -17.43% | -17.43% | 5.105% | 5.105% | 4.594% | 4.594% | 4.594% | 5.105% | 6.126% | 5.105% | 6.126% | -2.946% | -2.946% | -2.435% | 5.105% | 5.105% | 6.126% | 6.126% | -2.733% | -5.281% | -5.281% | -2.807% | 5.105% | -4.198% | -4.568% | -4.568% | -4.568% | -4.568% | -4.568% | -4.568% | 4.09% | 4.09% | 4.09% | 4.09% | 4.09% | 4.09% | 4.09% | -12.11% | -12.11% | -12.11% | -12.11% | -12.11% | -12.11% | -12.11% | -4.198% | -4.198% | -4.198% | -16.92% | -16.92% | -16.92% | -16.92% | -16.92% | -2.807% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | -0.3492% | 5.105% | 5.105% | 5.105% | 5.105% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -17.43% | -9.894%
| P25 | 25% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -18.6% | -10.51% | -10.51% | -10.51% | -10.51% | -3.161% | -3.161% | -3.161% | -3.161% | -3.161% | 0% | -3.161% | -3.161% | -3.161% | -3.161% | -3.161% | 0% | 0% | -10.51% | -10.51% | -10.51% | -10.51% | 13.12% | 0% | 0% | 6.561% | 13.12% | 0% | 0% | -3.161% | 0% | -10.51% | -10.51% | 7% | 7% | 6.3% | 6.3% | 6.3% | 7% | 8.4% | 7% | 8.4% | -0.001784% | -0.001784% | -1.861% | 7% | 7% | 8.4% | 8.4% | 0% | -1.713% | -1.713% | -0.3264% | 7% | -1.51% | -2.84% | -2.84% | -2.84% | -2.84% | -2.84% | -2.84% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | 5.673% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -7.363% | -1.51% | -1.51% | -1.51% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -0.3264% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7% | 7% | 7% | 7% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -10.51% | -3.477%
| P30 | 30% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -17.35% | -9.25% | -9.25% | -9.25% | -9.25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.4% | 1.4% | -9.25% | -9.25% | -9.25% | -9.25% | 21.77% | 1.4% | 1.4% | 11.59% | 21.77% | 1.4% | 1.4% | 0% | 0% | -9.25% | -9.25% | 9% | 9% | 8.1% | 8.1% | 8.1% | 9% | 10.8% | 9% | 10.8% | 0.9166% | 0.9166% | 0.2737% | 9% | 9% | 10.8% | 10.8% | 0.0396% | 0% | 0% | 0% | 9% | 2.097% | -0.756% | -0.756% | -0.756% | -0.756% | -0.756% | -0.756% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | 9.491% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | -2.443% | 2.097% | 2.097% | 2.097% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 0% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 9% | 9% | 9% | 9% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | -9.25% | 0%
| P35 | 35% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -9.913% | -8.076% | -8.076% | -8.076% | -8.076% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.6314% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 0.3062% | 3.966% | 3.966% | -8.076% | -8.076% | -8.076% | -8.076% | 24.46% | 3.966% | 3.966% | 14.21% | 24.46% | 3.966% | 3.966% | 0.3062% | 0.6314% | -8.076% | -8.076% | 11% | 11% | 9.9% | 9.9% | 9.9% | 11% | 13.2% | 11% | 13.2% | 4% | 4% | 4.16% | 11% | 11% | 13.2% | 13.2% | 3.361% | 2.492% | 2.492% | 0% | 11% | 4.1% | 0% | 0% | 0% | 0% | 0% | 0% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | 12.31% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | -0.01414% | 4.1% | 4.1% | 4.1% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 0% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 11% | 11% | 11% | 11% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | -8.076% | 0.3368%
| P40 | 40% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -5.88% | -6.941% | -6.941% | -6.941% | -6.941% | 1.544% | 1.544% | 1.544% | 1.544% | 1.544% | 2.686% | 1.544% | 1.544% | 1.544% | 1.544% | 1.544% | 9% | 9% | -6.941% | -6.941% | -6.941% | -6.941% | 25% | 9% | 9% | 17% | 25% | 9% | 9% | 1.544% | 2.686% | -6.941% | -6.941% | 13.4% | 13.4% | 12.06% | 12.06% | 12.06% | 13.4% | 16.08% | 13.4% | 16.08% | 8% | 8% | 9.418% | 13.4% | 13.4% | 16.08% | 16.08% | 7.32% | 7.636% | 7.636% | 0% | 13.4% | 5.944% | 0% | 0% | 0% | 0% | 0% | 0% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 15.15% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 2.685% | 5.944% | 5.944% | 5.944% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 0% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 13.4% | 13.4% | 13.4% | 13.4% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | -6.941% | 1.699%
| P45 | 45% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.59% | -4.392% | -4.392% | -4.392% | -4.392% | 2.788% | 2.788% | 2.788% | 2.788% | 2.788% | 5.25% | 2.788% | 2.788% | 2.788% | 2.788% | 2.788% | 12% | 12% | -4.392% | -4.392% | -4.392% | -4.392% | 25.72% | 12% | 12% | 18.86% | 25.72% | 12% | 12% | 2.788% | 5.25% | -4.392% | -4.392% | 16% | 16% | 14.4% | 14.4% | 14.4% | 16% | 19.2% | 16% | 19.2% | 11.75% | 11.75% | 11.03% | 16% | 16% | 19.2% | 19.2% | 11.16% | 15% | 15% | 2% | 16% | 7.509% | 0% | 0% | 0% | 0% | 0% | 0% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 17.05% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 5.481% | 7.509% | 7.509% | 7.509% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 2% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 16% | 16% | 16% | 16% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | -4.392% | 3.067%
| P50 | 50% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -3.503% | -2.156% | -2.156% | -2.156% | -2.156% | 4.197% | 4.197% | 4.197% | 4.197% | 4.197% | 8.941% | 4.197% | 4.197% | 4.197% | 4.197% | 4.197% | 13.33% | 13.33% | -2.156% | -2.156% | -2.156% | -2.156% | 31.5% | 13.33% | 13.33% | 22.42% | 31.5% | 13.33% | 13.33% | 4.197% | 8.941% | -2.156% | -2.156% | 18% | 18% | 16.2% | 16.2% | 16.2% | 18% | 21.6% | 18% | 21.6% | 15.14% | 15.14% | 15.88% | 18% | 18% | 21.6% | 21.6% | 15% | 20.15% | 20.15% | 4.836% | 18% | 10.35% | 0% | 0% | 0% | 0% | 0% | 0% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 22.44% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 8.599% | 10.35% | 10.35% | 10.35% | 10.82% | 10.82% | 10.82% | 10.82% | 10.82% | 4.836% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 18% | 18% | 18% | 18% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | -2.156% | 4.616%
| P55 | 55% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | -1.816% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 7.413% | 7.413% | 7.413% | 7.413% | 7.413% | 14.43% | 7.413% | 7.413% | 7.413% | 7.413% | 7.413% | 18.38% | 18.38% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 37.41% | 18.38% | 18.38% | 27.89% | 37.41% | 18.38% | 18.38% | 7.413% | 14.43% | 0.6532% | 0.6532% | 20.55% | 20.55% | 18.5% | 18.5% | 18.5% | 20.55% | 24.66% | 20.55% | 24.66% | 20% | 20% | 20.96% | 20.55% | 20.55% | 24.66% | 24.66% | 20% | 23% | 23% | 8% | 20.55% | 12.29% | 0% | 0% | 0% | 0% | 0% | 0% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 25.52% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 11.36% | 12.29% | 12.29% | 12.29% | 15.51% | 15.51% | 15.51% | 15.51% | 15.51% | 8% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 20.55% | 20.55% | 20.55% | 20.55% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 0.6532% | 8.155%
| P60 | 60% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | -0.2796% | 3.111% | 3.111% | 3.111% | 3.111% | 11.31% | 11.31% | 11.31% | 11.31% | 11.31% | 18.04% | 11.31% | 11.31% | 11.31% | 11.31% | 11.31% | 22% | 22% | 3.111% | 3.111% | 3.111% | 3.111% | 38.53% | 22% | 22% | 30.27% | 38.53% | 22% | 22% | 11.31% | 18.04% | 3.111% | 3.111% | 23% | 23% | 20.7% | 20.7% | 20.7% | 23% | 27.6% | 23% | 27.6% | 28.12% | 28.12% | 26.15% | 23% | 23% | 27.6% | 27.6% | 26% | 26% | 26% | 11.32% | 23% | 14.85% | 0.952% | 0.952% | 0.952% | 0.952% | 0.952% | 0.952% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 28.26% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 15.34% | 14.85% | 14.85% | 14.85% | 17.3% | 17.3% | 17.3% | 17.3% | 17.3% | 11.32% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 23% | 23% | 23% | 23% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 3.111% | 12.45%
| P65 | 65% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 0.8104% | 4.563% | 4.563% | 4.563% | 4.563% | 12.52% | 12.52% | 12.52% | 12.52% | 12.52% | 30.36% | 12.52% | 12.52% | 12.52% | 12.52% | 12.52% | 34.89% | 34.89% | 4.563% | 4.563% | 4.563% | 4.563% | 40.31% | 34.89% | 34.89% | 37.6% | 40.31% | 34.89% | 34.89% | 12.52% | 30.36% | 4.563% | 4.563% | 25.65% | 25.65% | 23.09% | 23.09% | 23.09% | 25.65% | 30.78% | 25.65% | 30.78% | 33.05% | 33.05% | 34.63% | 25.65% | 25.65% | 30.78% | 30.78% | 33% | 31.7% | 31.7% | 14.94% | 25.65% | 18.83% | 5.757% | 5.757% | 5.757% | 5.757% | 5.757% | 5.757% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 30.17% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 20.58% | 18.83% | 18.83% | 18.83% | 30.04% | 30.04% | 30.04% | 30.04% | 30.04% | 14.94% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 25.65% | 25.65% | 25.65% | 25.65% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 4.563% | 13.78%
| P70 | 70% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 3.025% | 5.862% | 5.862% | 5.862% | 5.862% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 38.57% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 44.74% | 44.74% | 5.862% | 5.862% | 5.862% | 5.862% | 44.99% | 44.74% | 44.74% | 44.87% | 44.99% | 44.74% | 44.74% | 16.23% | 38.57% | 5.862% | 5.862% | 29% | 29% | 26.1% | 26.1% | 26.1% | 29% | 34.8% | 29% | 34.8% | 43% | 43% | 41.67% | 29% | 29% | 34.8% | 34.8% | 42.86% | 33.6% | 33.6% | 18.04% | 29% | 21.45% | 8.737% | 8.737% | 8.737% | 8.737% | 8.737% | 8.737% | 31.66% | 31.66% | 31.66% | 31.66% | 31.66% | 31.66% | 31.66% | 23.95% | 23.95% | 23.95% | 23.95% | 23.95% | 23.95% | 23.95% | 21.45% | 21.45% | 21.45% | 35.57% | 35.57% | 35.57% | 35.57% | 35.57% | 18.04% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 44.74% | 29% | 29% | 29% | 29% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 5.862% | 17.85%
| P75 | 75% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 5.646% | 16.23% | 16.23% | 16.23% | 16.23% | 21.6% | 21.6% | 21.6% | 21.6% | 21.6% | 62.94% | 21.6% | 21.6% | 21.6% | 21.6% | 21.6% | 57% | 57% | 16.23% | 16.23% | 16.23% | 16.23% | 50.28% | 57% | 57% | 53.64% | 50.28% | 57% | 57% | 21.6% | 62.94% | 16.23% | 16.23% | 33% | 33% | 29.7% | 29.7% | 29.7% | 33% | 39.6% | 33% | 39.6% | 50.56% | 50.56% | 49.44% | 33% | 33% | 39.6% | 39.6% | 51% | 48.35% | 48.35% | 23% | 33% | 27.02% | 12.44% | 12.44% | 12.44% | 12.44% | 12.44% | 12.44% | 38.93% | 38.93% | 38.93% | 38.93% | 38.93% | 38.93% | 38.93% | 29.69% | 29.69% | 29.69% | 29.69% | 29.69% | 29.69% | 29.69% | 27.02% | 27.02% | 27.02% | 40.59% | 40.59% | 40.59% | 40.59% | 40.59% | 23% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 57% | 33% | 33% | 33% | 33% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 16.23% | 23.76%
| P80 | 80% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 11.08% | 18.2% | 18.2% | 18.2% | 18.2% | 32.12% | 32.12% | 32.12% | 32.12% | 32.12% | 68.74% | 32.12% | 32.12% | 32.12% | 32.12% | 32.12% | 83.95% | 83.95% | 18.2% | 18.2% | 18.2% | 18.2% | 53.92% | 83.95% | 83.95% | 68.93% | 53.92% | 83.95% | 83.95% | 32.12% | 68.74% | 18.2% | 18.2% | 37% | 37% | 33.3% | 33.3% | 33.3% | 37% | 44.4% | 37% | 44.4% | 56.93% | 56.93% | 60.02% | 37% | 37% | 44.4% | 44.4% | 60.4% | 62.09% | 62.09% | 28% | 37% | 31.78% | 15.31% | 15.31% | 15.31% | 15.31% | 15.31% | 15.31% | 45.03% | 45.03% | 45.03% | 45.03% | 45.03% | 45.03% | 45.03% | 35.01% | 35.01% | 35.01% | 35.01% | 35.01% | 35.01% | 35.01% | 31.78% | 31.78% | 31.78% | 44.73% | 44.73% | 44.73% | 44.73% | 44.73% | 28% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 83.95% | 37% | 37% | 37% | 37% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 18.2% | 35.34%
| P85 | 85% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 23.87% | 21.48% | 21.48% | 21.48% | 21.48% | 61.21% | 61.21% | 61.21% | 61.21% | 61.21% | 73.4% | 61.21% | 61.21% | 61.21% | 61.21% | 61.21% | 127.2% | 127.2% | 21.48% | 21.48% | 21.48% | 21.48% | 57.17% | 127.2% | 127.2% | 92.16% | 57.17% | 127.2% | 127.2% | 61.21% | 73.4% | 21.48% | 21.48% | 40.85% | 40.85% | 36.76% | 36.76% | 36.76% | 40.85% | 49.02% | 40.85% | 49.02% | 67.7% | 67.7% | 85% | 40.85% | 40.85% | 49.02% | 49.02% | 75% | 71.26% | 71.26% | 38.04% | 40.85% | 43.81% | 17.39% | 17.39% | 17.39% | 17.39% | 17.39% | 17.39% | 67.93% | 67.93% | 67.93% | 67.93% | 67.93% | 67.93% | 67.93% | 46.1% | 46.1% | 46.1% | 46.1% | 46.1% | 46.1% | 46.1% | 43.81% | 43.81% | 43.81% | 51.32% | 51.32% | 51.32% | 51.32% | 51.32% | 38.04% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 127.2% | 40.85% | 40.85% | 40.85% | 40.85% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 21.48% | 67.33%
| P90 | 90% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 25.98% | 23.77% | 23.77% | 23.77% | 23.77% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 97.61% | 105.6% | 105.6% | 105.6% | 105.6% | 105.6% | 200% | 200% | 23.77% | 23.77% | 23.77% | 23.77% | 79.12% | 200% | 200% | 139.6% | 79.12% | 200% | 200% | 105.6% | 97.61% | 23.77% | 23.77% | 50.8% | 50.8% | 45.72% | 45.72% | 45.72% | 50.8% | 60.96% | 50.8% | 60.96% | 83% | 83% | 129.9% | 50.8% | 50.8% | 60.96% | 60.96% | 102.8% | 100.6% | 100.6% | 56.21% | 50.8% | 52.04% | 24.1% | 24.1% | 24.1% | 24.1% | 24.1% | 24.1% | 76.38% | 76.38% | 76.38% | 76.38% | 76.38% | 76.38% | 76.38% | 55.63% | 55.63% | 55.63% | 55.63% | 55.63% | 55.63% | 55.63% | 52.04% | 52.04% | 52.04% | 54.55% | 54.55% | 54.55% | 54.55% | 54.55% | 56.21% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 200% | 50.8% | 50.8% | 50.8% | 50.8% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 23.77% | 116.2%
| P95 | 95% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 38.86% | 79.21% | 79.21% | 79.21% | 79.21% | 208.3% | 208.3% | 208.3% | 208.3% | 208.3% | 147.9% | 208.3% | 208.3% | 208.3% | 208.3% | 208.3% | 271.2% | 271.2% | 79.21% | 79.21% | 79.21% | 79.21% | 106% | 271.2% | 271.2% | 188.6% | 106% | 271.2% | 271.2% | 208.3% | 147.9% | 79.21% | 79.21% | 66.92% | 66.92% | 60.23% | 60.23% | 60.23% | 66.92% | 80.3% | 66.92% | 80.3% | 115.1% | 115.1% | 185.4% | 66.92% | 66.92% | 80.3% | 80.3% | 187.2% | 144.6% | 144.6% | 82.6% | 66.92% | 78.33% | 33.01% | 33.01% | 33.01% | 33.01% | 33.01% | 33.01% | 123.6% | 123.6% | 123.6% | 123.6% | 123.6% | 123.6% | 123.6% | 78.34% | 78.34% | 78.34% | 78.34% | 78.34% | 78.34% | 78.34% | 78.33% | 78.33% | 78.33% | 69.82% | 69.82% | 69.82% | 69.82% | 69.82% | 82.6% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 271.2% | 66.92% | 66.92% | 66.92% | 66.92% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 79.21% | 229.1%
| P100 | 100%
Schedule RCF
| Notes |  | L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | MB added | Same | Same | Same | Bldg | Same | Same | Bldg | Same | Bld 0-5 y | Same | Same | Same | Same | Same | EW | EW | Mngt | Same | Same | Same | Demolition | EW | EW | (EW+Facil W)/2 | Facil Works | EW x | EW x | Bldg | Bld 0-5 y | Design | Design | Roads | Roads | Roads x | Roads x | Roads x | Urban roads std | Urban roads cx | Rural std | Rural cx | As Rail | Rail | Stations | Roads | Spine roads | Roads | Junctions | Civils | Bridges | Tunnels | Earthworks | Roads | Gen Utilities | Elec | Elec x | Elec x | Elec x | Elec x | Elec x | Gas | Gas x | Gas x | Gas x | Gas x | Gas x | Gas x | Water | Water x | Water x | Water x | Water x | Water x | Water x | Gen x | Gen x | Gen x | Drng | Drng x | Drng x | Drng x | Drng x | Landraising | Enab W x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Roads x | Roads x | Roads x | Roads x | Mngt | Fees x | Fees x | Fees x | Fees x | Fees x | Fees x | As mngt | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Mngt x | Mngt x | Mngt | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | Bldg
|  |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 1 |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0.9 | 0.9 | 0.9 | 1 | 1.2 | 1 | 1.2 | 1 | 0 | 0 | 1 | 1 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1
| P0 | 0%
| P5 | 5% | -5.397% | -5.397% | -5.397% | -5.397% | -5.397% | -5.397% | -5.397% | -5.397% | -5.397% | -28% | -28% | -28% | -28% | -6.044% | -6.044% | -6.044% | -6.044% | -6.044% | 0% | -6.044% | -6.044% | -6.044% | -6.044% | -6.044% | 0% | 0% | -28% | -28% | -28% | -28% | 0.8% | 0% | 0% | 0.4% | 0.8% | 0% | 0% | -6.044% | 0% | -28% | -28% | -29.12% | -29.12% | -26.21% | -26.21% | -26.21% | -29.12% | -34.94% | -29.12% | -34.94% | -28.59% | -28.59% | -11.86% | -29.12% | -29.12% | -34.94% | -34.94% | -6.737% | -13% | -13% | -28.18% | -29.12% | -2.854% | 0% | 0% | 0% | 0% | 0% | 0% | -0.2766% | -0.2766% | -0.2766% | -0.2766% | -0.2766% | -0.2766% | -0.2766% | -8.285% | -8.285% | -8.285% | -8.285% | -8.285% | -8.285% | -8.285% | -2.854% | -2.854% | -2.854% | -8.285% | -8.285% | -8.285% | -8.285% | -8.285% | -28.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -29.12% | -29.12% | -29.12% | -29.12% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -28% | -6.648%
| P10 | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -19% | -19% | -19% | -19% | -4.938% | -4.938% | -4.938% | -4.938% | -4.938% | 0% | -4.938% | -4.938% | -4.938% | -4.938% | -4.938% | 0% | 0% | -19% | -19% | -19% | -19% | 1.6% | 0% | 0% | 0.8% | 1.6% | 0% | 0% | -4.938% | 0% | -19% | -19% | -20% | -20% | -18% | -18% | -18% | -20% | -24% | -20% | -24% | -19.9% | -19.9% | -8.1% | -20% | -20% | -24% | -24% | -2.818% | -11.11% | -11.11% | -19% | -20% | -1.461% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -4.383% | -4.383% | -4.383% | -4.383% | -4.383% | -4.383% | -4.383% | -1.461% | -1.461% | -1.461% | -4.383% | -4.383% | -4.383% | -4.383% | -4.383% | -19% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -20% | -20% | -20% | -20% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -19% | -5.432%
| P15 | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -11.91% | -11.91% | -11.91% | -11.91% | -0.6371% | -0.6371% | -0.6371% | -0.6371% | -0.6371% | 0% | -0.6371% | -0.6371% | -0.6371% | -0.6371% | -0.6371% | 0% | 0% | -11.91% | -11.91% | -11.91% | -11.91% | 3.6% | 0% | 0% | 1.8% | 3.6% | 0% | 0% | -0.6371% | 0% | -11.91% | -11.91% | -14.58% | -14.58% | -13.12% | -13.12% | -13.12% | -14.58% | -17.49% | -14.58% | -17.49% | -11.9% | -11.9% | 1.45% | -14.58% | -14.58% | -17.49% | -17.49% | 0% | -4.542% | -4.542% | -13.34% | -14.58% | -0.4804% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -1.441% | -1.441% | -1.441% | -1.441% | -1.441% | -1.441% | -1.441% | -0.4804% | -0.4804% | -0.4804% | -1.441% | -1.441% | -1.441% | -1.441% | -1.441% | -13.34% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -14.58% | -14.58% | -14.58% | -14.58% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -11.91% | -0.7008%
| P20 | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6% | -6% | -6% | -6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -6% | -6% | -6% | -6% | 6.8% | 0% | 0% | 3.4% | 6.8% | 0% | 0% | 0% | 0% | -6% | -6% | -10.18% | -10.18% | -9.162% | -9.162% | -9.162% | -10.18% | -12.22% | -10.18% | -12.22% | -6.8% | -6.8% | 7.2% | -10.18% | -10.18% | -12.22% | -12.22% | 0% | -2.371% | -2.371% | -9.26% | -10.18% | 1.409% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | 1.409% | 1.409% | 1.409% | 4.228% | 4.228% | 4.228% | 4.228% | 4.228% | -9.26% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -10.18% | -10.18% | -10.18% | -10.18% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | -6% | 0%
| P25 | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -1.443% | -1.443% | -1.443% | -1.443% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -1.443% | -1.443% | -1.443% | -1.443% | 10% | 0% | 0% | 5% | 10% | 0% | 0% | 0% | 0% | -1.443% | -1.443% | -3.541% | -3.541% | -3.187% | -3.187% | -3.187% | -3.541% | -4.249% | -3.541% | -4.249% | -0.9424% | -0.9424% | 9.289% | -3.541% | -3.541% | -4.249% | -4.249% | 0% | 0% | 0% | -3.061% | -3.541% | 3.292% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | 3.292% | 3.292% | 3.292% | 9.877% | 9.877% | 9.877% | 9.877% | 9.877% | -3.061% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -3.541% | -3.541% | -3.541% | -3.541% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | -1.443% | 0%
| P30 | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.67% | 0% | 0% | 6.333% | 12.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.65% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.139% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 6.139% | 6.139% | 6.139% | 18.42% | 18.42% | 18.42% | 18.42% | 18.42% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| P35 | 35% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 1.169% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15.33% | 0% | 0% | 7.667% | 15.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 14% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 7.089% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 7.089% | 7.089% | 7.089% | 21.27% | 21.27% | 21.27% | 21.27% | 21.27% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| P40 | 40% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 2.557% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0% | 0% | 0% | 0% | 0% | 0.9624% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 18.93% | 0% | 0% | 9.467% | 18.93% | 0% | 0% | 0% | 0.9624% | 0.3573% | 0.3573% | 3.259% | 3.259% | 2.933% | 2.933% | 2.933% | 3.259% | 3.911% | 3.259% | 3.911% | 7.397% | 7.397% | 15% | 3.259% | 3.259% | 3.911% | 3.911% | 0% | 0% | 0% | 2% | 3.259% | 7.822% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 7.822% | 7.822% | 7.822% | 23.46% | 23.46% | 23.46% | 23.46% | 23.46% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.259% | 3.259% | 3.259% | 3.259% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0.3573% | 0%
| P45 | 45% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 4.645% | 6.013% | 6.013% | 6.013% | 6.013% | 0% | 0% | 0% | 0% | 0% | 3.08% | 0% | 0% | 0% | 0% | 0% | 0.9632% | 0.9632% | 6.013% | 6.013% | 6.013% | 6.013% | 23.47% | 0.9632% | 0.9632% | 12.21% | 23.47% | 0.9632% | 0.9632% | 0% | 3.08% | 6.013% | 6.013% | 8.063% | 8.063% | 7.257% | 7.257% | 7.257% | 8.063% | 9.676% | 8.063% | 9.676% | 14.1% | 14.1% | 18.9% | 8.063% | 8.063% | 9.676% | 9.676% | 0% | 1.829% | 1.829% | 7.183% | 8.063% | 10.02% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 10.02% | 10.02% | 10.02% | 30.06% | 30.06% | 30.06% | 30.06% | 30.06% | 7.183% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 0.9632% | 8.063% | 8.063% | 8.063% | 8.063% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 6.013% | 0%
| P50 | 50% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 7.288% | 12.27% | 12.27% | 12.27% | 12.27% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 17.5% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 0.2635% | 4.692% | 4.692% | 12.27% | 12.27% | 12.27% | 12.27% | 28% | 4.692% | 4.692% | 16.35% | 28% | 4.692% | 4.692% | 0.2635% | 17.5% | 12.27% | 12.27% | 13% | 13% | 11.7% | 11.7% | 11.7% | 13% | 15.6% | 13% | 15.6% | 19.09% | 19.09% | 26% | 13% | 13% | 15.6% | 15.6% | 1.658% | 3.449% | 3.449% | 11.65% | 13% | 10.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 0.7774% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 10.97% | 10.97% | 10.97% | 32.15% | 32.15% | 32.15% | 32.15% | 32.15% | 11.65% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 4.692% | 13% | 13% | 13% | 13% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 12.27% | 0.2899%
| P55 | 55% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 10.05% | 16% | 16% | 16% | 16% | 2.652% | 2.652% | 2.652% | 2.652% | 2.652% | 26% | 2.652% | 2.652% | 2.652% | 2.652% | 2.652% | 14.05% | 14.05% | 16% | 16% | 16% | 16% | 28.8% | 14.05% | 14.05% | 21.42% | 28.8% | 14.05% | 14.05% | 2.652% | 26% | 16% | 16% | 16.67% | 16.67% | 15% | 15% | 15% | 16.67% | 20% | 16.67% | 20% | 26.27% | 26.27% | 29.72% | 16.67% | 16.67% | 20% | 20% | 4% | 7.169% | 7.169% | 15.76% | 16.67% | 17.24% | 0% | 0% | 0% | 0% | 0% | 0% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 7.829% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 17.24% | 17.24% | 17.24% | 43.88% | 43.88% | 43.88% | 43.88% | 43.88% | 15.76% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 14.05% | 16.67% | 16.67% | 16.67% | 16.67% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 16% | 2.918%
| P60 | 60% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 14.5% | 21.87% | 21.87% | 21.87% | 21.87% | 3.263% | 3.263% | 3.263% | 3.263% | 3.263% | 32.95% | 3.263% | 3.263% | 3.263% | 3.263% | 3.263% | 18.57% | 18.57% | 21.87% | 21.87% | 21.87% | 21.87% | 29.6% | 18.57% | 18.57% | 24.08% | 29.6% | 18.57% | 18.57% | 3.263% | 32.95% | 21.87% | 21.87% | 22.63% | 22.63% | 20.37% | 20.37% | 20.37% | 22.63% | 27.16% | 22.63% | 27.16% | 30.6% | 30.6% | 44.3% | 22.63% | 22.63% | 27.16% | 27.16% | 14% | 12% | 12% | 21.47% | 22.63% | 21.44% | 0% | 0% | 0% | 0% | 0% | 0% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 18.49% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 21.44% | 21.44% | 21.44% | 45.83% | 45.83% | 45.83% | 45.83% | 45.83% | 21.47% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 18.57% | 22.63% | 22.63% | 22.63% | 22.63% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 21.87% | 3.589%
| P65 | 65% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 16.99% | 27% | 27% | 27% | 27% | 4.324% | 4.324% | 4.324% | 4.324% | 4.324% | 48.71% | 4.324% | 4.324% | 4.324% | 4.324% | 4.324% | 29.81% | 29.81% | 27% | 27% | 27% | 27% | 39.2% | 29.81% | 29.81% | 34.51% | 39.2% | 29.81% | 29.81% | 4.324% | 48.71% | 27% | 27% | 27.36% | 27.36% | 24.62% | 24.62% | 24.62% | 27.36% | 32.83% | 27.36% | 32.83% | 36.7% | 36.7% | 49.65% | 27.36% | 27.36% | 32.83% | 32.83% | 19.87% | 16% | 16% | 27% | 27.36% | 24.41% | 0% | 0% | 0% | 0% | 0% | 0% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 23.93% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 24.41% | 24.41% | 24.41% | 49.29% | 49.29% | 49.29% | 49.29% | 49.29% | 27% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 29.81% | 27.36% | 27.36% | 27.36% | 27.36% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 27% | 4.756%
| P70 | 70% | 23.75% | 23.75% | 23.75% | 23.75% | 23.75% | 23.75% | 23.75% | 23.75% | 23.75% | 35.97% | 35.97% | 35.97% | 35.97% | 9.8% | 9.8% | 9.8% | 9.8% | 9.8% | 50% | 9.8% | 9.8% | 9.8% | 9.8% | 9.8% | 47.61% | 47.61% | 35.97% | 35.97% | 35.97% | 35.97% | 57.6% | 47.61% | 47.61% | 52.6% | 57.6% | 47.61% | 47.61% | 9.8% | 50% | 35.97% | 35.97% | 35.93% | 35.93% | 32.34% | 32.34% | 32.34% | 35.93% | 43.12% | 35.93% | 43.12% | 40% | 40% | 50% | 35.93% | 35.93% | 43.12% | 43.12% | 25.96% | 22% | 22% | 35.1% | 35.93% | 27.39% | 0% | 0% | 0% | 0% | 0% | 0% | 32.17% | 32.17% | 32.17% | 32.17% | 32.17% | 32.17% | 32.17% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 27.39% | 27.39% | 27.39% | 50% | 50% | 50% | 50% | 50% | 35.1% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 47.61% | 35.93% | 35.93% | 35.93% | 35.93% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 35.97% | 10.78%
| P75 | 75% | 27.61% | 27.61% | 27.61% | 27.61% | 27.61% | 27.61% | 27.61% | 27.61% | 27.61% | 45.71% | 45.71% | 45.71% | 45.71% | 22.64% | 22.64% | 22.64% | 22.64% | 22.64% | 67% | 22.64% | 22.64% | 22.64% | 22.64% | 22.64% | 57.5% | 57.5% | 45.71% | 45.71% | 45.71% | 45.71% | 76% | 57.5% | 57.5% | 66.75% | 76% | 57.5% | 57.5% | 22.64% | 67% | 45.71% | 45.71% | 50% | 50% | 45% | 45% | 45% | 50% | 60% | 50% | 60% | 46% | 46% | 50% | 50% | 50% | 60% | 60% | 35.75% | 35% | 35% | 48% | 50% | 31.31% | 0% | 0% | 0% | 0% | 0% | 0% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 58.92% | 58.92% | 58.92% | 58.92% | 58.92% | 58.92% | 58.92% | 31.31% | 31.31% | 31.31% | 58.92% | 58.92% | 58.92% | 58.92% | 58.92% | 48% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 57.5% | 50% | 50% | 50% | 50% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 45.71% | 24.91%
| P80 | 80% | 32.22% | 32.22% | 32.22% | 32.22% | 32.22% | 32.22% | 32.22% | 32.22% | 32.22% | 59.4% | 59.4% | 59.4% | 59.4% | 28.99% | 28.99% | 28.99% | 28.99% | 28.99% | 87.2% | 28.99% | 28.99% | 28.99% | 28.99% | 28.99% | 67.8% | 67.8% | 59.4% | 59.4% | 59.4% | 59.4% | 80.8% | 67.8% | 67.8% | 74.3% | 80.8% | 67.8% | 67.8% | 28.99% | 87.2% | 59.4% | 59.4% | 63.4% | 63.4% | 57.06% | 57.06% | 57.06% | 63.4% | 76.08% | 63.4% | 76.08% | 50% | 50% | 65% | 63.4% | 63.4% | 76.08% | 76.08% | 51.1% | 38% | 38% | 62.2% | 63.4% | 39.96% | 0% | 0% | 0% | 0% | 0% | 0% | 56% | 56% | 56% | 56% | 56% | 56% | 56% | 63.87% | 63.87% | 63.87% | 63.87% | 63.87% | 63.87% | 63.87% | 39.96% | 39.96% | 39.96% | 63.87% | 63.87% | 63.87% | 63.87% | 63.87% | 62.2% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 67.8% | 63.4% | 63.4% | 63.4% | 63.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 59.4% | 31.89%
| P85 | 85% | 45.47% | 45.47% | 45.47% | 45.47% | 45.47% | 45.47% | 45.47% | 45.47% | 45.47% | 75% | 75% | 75% | 75% | 37.97% | 37.97% | 37.97% | 37.97% | 37.97% | 100% | 37.97% | 37.97% | 37.97% | 37.97% | 37.97% | 100% | 100% | 75% | 75% | 75% | 75% | 85.6% | 100% | 100% | 92.81% | 85.6% | 100% | 100% | 37.97% | 100% | 75% | 75% | 80.96% | 80.96% | 72.86% | 72.86% | 72.86% | 80.96% | 97.15% | 80.96% | 97.15% | 65.9% | 65.9% | 86.27% | 80.96% | 80.96% | 97.15% | 97.15% | 68.75% | 51.5% | 51.5% | 75.86% | 80.96% | 43.77% | 0% | 0% | 0% | 0% | 0% | 0% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 64.66% | 64.66% | 64.66% | 64.66% | 64.66% | 64.66% | 64.66% | 43.77% | 43.77% | 43.77% | 64.66% | 64.66% | 64.66% | 64.66% | 64.66% | 75.86% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80.96% | 80.96% | 80.96% | 80.96% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 41.77%
| P90 | 90% | 54.96% | 54.96% | 54.96% | 54.96% | 54.96% | 54.96% | 54.96% | 54.96% | 54.96% | 100% | 100% | 100% | 100% | 69.76% | 69.76% | 69.76% | 69.76% | 69.76% | 138% | 69.76% | 69.76% | 69.76% | 69.76% | 69.76% | 133.3% | 133.3% | 100% | 100% | 100% | 100% | 96.55% | 133.3% | 133.3% | 114.9% | 96.55% | 133.3% | 133.3% | 69.76% | 138% | 100% | 100% | 113% | 113% | 101.7% | 101.7% | 101.7% | 113% | 135.6% | 113% | 135.6% | 100% | 100% | 88.89% | 113% | 113% | 135.6% | 135.6% | 86% | 75.5% | 75.5% | 105.4% | 113% | 58.15% | 12.32% | 12.32% | 12.32% | 12.32% | 12.32% | 12.32% | 80.04% | 80.04% | 80.04% | 80.04% | 80.04% | 80.04% | 80.04% | 82.09% | 82.09% | 82.09% | 82.09% | 82.09% | 82.09% | 82.09% | 58.15% | 58.15% | 58.15% | 82.09% | 82.09% | 82.09% | 82.09% | 82.09% | 105.4% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 133.3% | 113% | 113% | 113% | 113% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 76.73%
| P95 | 95% | 83.53% | 83.53% | 83.53% | 83.53% | 83.53% | 83.53% | 83.53% | 83.53% | 83.53% | 146.1% | 146.1% | 146.1% | 146.1% | 139% | 139% | 139% | 139% | 139% | 192.3% | 139% | 139% | 139% | 139% | 139% | 170.6% | 170.6% | 146.1% | 146.1% | 146.1% | 146.1% | 113.7% | 170.6% | 170.6% | 142.1% | 113.7% | 170.6% | 170.6% | 139% | 192.3% | 146.1% | 146.1% | 152.8% | 152.8% | 137.5% | 137.5% | 137.5% | 152.8% | 183.4% | 152.8% | 183.4% | 132% | 132% | 91.84% | 152.8% | 152.8% | 183.4% | 183.4% | 129.8% | 86% | 86% | 145.3% | 152.8% | 77.88% | 43.32% | 43.32% | 43.32% | 43.32% | 43.32% | 43.32% | 97.13% | 97.13% | 97.13% | 97.13% | 97.13% | 97.13% | 97.13% | 93.19% | 93.19% | 93.19% | 93.19% | 93.19% | 93.19% | 93.19% | 77.88% | 77.88% | 77.88% | 93.19% | 93.19% | 93.19% | 93.19% | 93.19% | 145.3% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 170.6% | 152.8% | 152.8% | 152.8% | 152.8% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 146.1% | 152.9%
| P100 | 100%
Note on AB2: Site preparation works, Roads, paths, paving’s and surfacing, Soft landscaping, planting and irrigation systems, fencing, external drainage and utilities and minor building works and ancillary building works
Note on E3: Purchase price including Planning Risk discounts (Actual price to be paid)
Note on F3: Purchasers Agent and Legal fees
Note on G3: SDLT rates as appropriate
Note on H3: Easements, Wayleaves
Note on M3: Costs for securing Outline Planning Permission
Note on N3: Costs for securing Outline Planning Permission
Note on O3: Costs for securing Reserved Matters planning
Note on P3: Pre-app, allocation promotion, SPD/planning brief, design incl B4Life, Listed Buildings surveys, fees associated with S278,38 or 104, highway, noise, and desk top archaeology surveys.
Note on AH3: includes demolition to slab and or below ground, substructures. Planning costs for demolition should be included in planning fees.
Note on AI3: Including cut and fill and ground stabilisation, preparing sub-surfaces, site clearance, including all works to existing trees and TPOs etc.
Note on AJ3: Remediation and decontamination including monitoring costs
Note on AM3: Incl site investigations, topo survey, noise surveys, UXO, building condition survey
Note on AQ3: Including Transport and Highway Assessments
Note on AS3: Means works undertaken by developer
Note on AT3: incl. contribution to strategic infrastructure; works undertaken by others
Note on BB3: Works to be carried out by the developer on Public Transport not included in S106 Costs
Note on BF3: Infrastructure not serving individual plots directly i.e. not local infrastructure included under externals. Including standard sewers. Will include fees, contingencies and prelims
Note on BH3: Additional junctions or junctions works over and above standard
Note on BM3: compensation for depreciation in the value of an interest in land which is attributable to the use of public works i.e construction of a highway
Note on CK4: (likely to be removed in due course as costs become standard and are reflected within base build costs)
Note on D5: From EW Rail "L&P"
Note on M5: From BusConnects "Prelims"
Note on Q5: From BusConnects "Building"
Note on T5: From BusConnects "Building"
Note on AB5: From EW Rail "civils"
Note on AD5: From Busconnects "Management"
Note on AH5: EW Rail "Temp Works"
Note on AQ5: Mr Bartlett: BusConnects Design - change to SW Design?
Note on AR5: Mr Bartlett: BusConnects Design - change to SW Design?
Note on AT5: BusConnects roads
Note on BB5: As rail
Note on BC5: EW Rail "Track"
Note on BD5: EW Rail "Stations"
Note on BI5: EW Rail "Civils"
Note on BJ5: EW Rail "Bridges"
Note on BK5: EW Rail "Tunnels"
Note on CM5: Data from Sydney Water
Note on DO5: Use margin from SW work?
Note on M33: From EW Rail "Prelims etc"

## RCF CCT data (hidden)
SOBC
| Primary RCF Data |  | Land Costs | [8 empty] | Planning |  |  |  | Build Cost (Base build total cost) |  |  | Building | [7 empty] | External Works |  | Management costs |  |  |  | Site Preparation | [6 empty] | Foundations |  | Infrastructure and highways | [22 empty] | Utilities | [23 empty] | Drainage | [5 empty] | Ecology | [11 empty] | Landscaping/ Public Realm |  |  |  | Surveys and Fees |  |  |  |  | Sales and Marketing |  | Profit (inclusive of any developer Overheads, aftercare and sales incentives) | [7 empty] | Community Infrastructure Levy (CIL) |  | Section 106 Obligations | [12 empty] | Other Abnormal Costs
|  |  | General L&P | Acquisition Cost | Agent and Legal fees | SDLT | Access Rights | Ransom Payments | Option Fees | Overage | Additional Land Acquisition | Planning general | Outline Planning | Reserved Matters Planning | Other Planning Costs | Standard construction and foundations | Preliminaries apportioned | Contractors' overheads and profits (not developers’) | General: unspecified | Residential | Custom build properties | Building affordable housing | Commercial (shop units/ offices space | Light industrial (warehousing/ distribution) | Film studios/ creative space | Community/ public buildings | Associated with houses | Associated with apartments | General | Maintenance & protection of a heritage asset | Other holding costs/ estate management | Professional Fees: General | Demolition | Enabling works | Remediation and Decontamination |  |  | Due Diligence (survey works) | Archaeology/Heritage surveys | Standard foundations | Abnormal Foundations | Highway and Transport Design Works | Noise and Vibration Design Works | S278 works | Offsite Highways works (breakdown by type of works as feasible) | [7 empty] | Public Transport |  |  |  | Spine Road | Roundabouts | Junctions | Other civil works |  |  |  | Part 1 Claims | Unspecified | Electricity | [5 empty] | Gas | [6 empty] | Water | [6 empty] | District Heating | Telecoms | Renewable Energy | General | Pumping Station | SUDS/Swales/Tanks/Attenuation |  | Sewers | Flood Risk | General | Ecology Design Work | Arboriculture | Mitigation | Nitrogen neutrality | Water Neutrality | Biodiversity Net Gain (BNG) | Invasive Species | Birds and Bats | SANGS | Invertebrates/vertebrates | Mammals | Public Realm / Public Open Space | Play areas / Outdoor sports | Endowment | Public Art | Valuation and Appraisal Advice | Legal Advice | Development Management / Master Developer Fees | Health and Safety Advice | Communications Fees | Agent Fees | Legal Fees | Profit on Market Sale | Profit on Affordable | Profit on Commercial | Profit on PRS | Total Blended Profit | Internal Rate of Return (IRR) | Development Management Fee | Return On Capital Employed (ROCE) | CIL Residential | CIL Commercial | General | Roof Tax | Affordable Housing Offsite Payment | Community Facilities | Employment and Skills | Healthcare | Highways / Transport | Education (primary and secondary) | Libraries | Public Realm/Open Space | Monitoring Fee | Play areas | Sports Fields
| RCF Values | [33 empty] | Simple | complex/ brownfield | heavily contaminated | [7 empty] | Unspecified or mixed | Footpaths | Cycle paths | Parking (surface) | Urban roads - standard | Urban roads - complex | Rural roads - standard | Rural roads - complex | Unspecified or mixed | Rail | Stations | Buslanes |  |  |  | Unspecified or mixed | Bridges/ other structures | Tunnels | Earthworks |  |  | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs legal fees for wayleaves, licences, supply agreements, compensation claims | Easement costs | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, Compensation claims | Easement costs | Unspecified | Disconnection and abandonment cost | Diversion cost | New supplies which includes substations, reinforcement, etc. | Services and connection costs | Legal fees for wayleaves, licences, supply agreements, compensation claims | Easement Costs | Capital cost, plot costs, legals and heat charger | Upgrading cables | CHP, non plot specific EV charging or solar |  |  | Includes landscaping features associated with attenuation ponds | Beyond plot specific measures included in externals (such as permeable drives) | Includes Surface and Foul beyond standard included in Externals and/or spine road | Includes land raising/barriers/defence |  |  | Covers tree surgery and/or tree protection works | i.e. offsite contribution, Habitat Regulation Assessment, | [6 empty] | Newts – including fencing and ladders | Dormice, badgers | Estate costs/shared areas not included in external works including landscaping wildflower meadows. | in addition to any S. 106 requirements | for long term management | in addition to any S. 106 requirements | (beyond standard house building Professional fees and not included in specialist categories above) | state aid advice, specific questions on ransoms etc. | These include fees paid to development managers/ Master Developers of the site or collaboration costs. | e.g. highways, reservoirs | Fees for example related to any PR on the site but not planning related costs.
| Notes |  | L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | As Gen L&P | Design | Same | Same | Same | Bldg | Same | Same | Bldg | Same | Bld 0-5 y | Same | Same | Same | Same | Same | EW | EW | Mngt | Same | Same | Same | Demolition | EW | EW | (EW+Facil W)/2 | Facil Works | EW x | EW x | Bldg x | Bld 0-5 y | Design | Design | Roads | Roads | Roads x | Roads x | Roads x | Urban roads std | Urban roads cx | Rural std | Rural cx | As Rail | Rail | Stations | Roads | Spine roads | Roads | Junctions | Civils | Bridges | Tunnels | Earthworks | Roads | Gen Utilities | Elec | Elec x | Elec x | Elec x | Elec x | Elec x | Gas | Gas x | Gas x | Gas x | Gas x | Gas x | Gas x | Water | Water x | Water x | Water x | Water x | Water x | Water x | Gen x | Gen x | Gen x | Drng | Drng x | Drng x | Drng x | Drng x | Landraising | Enab W x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Eco x | Roads x | Roads x | Roads x | Roads x | Mngt | Fees x | Fees x | Fees x | Fees x | Fees x | Fees x | As mngt | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Margin x | Mngt x | Mngt x | Mngt | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | 106 x | Bldg
| Factor |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0.9 | 0.9 | 0.9 | 1 | 1.2 | 1 | 1.2 | 1 | 0 | 0 | 1 | 1 | 1.2 | 1.2 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.1
Cost RCF
| P0 | 0%
| P5 | 5% | -92.48% | -92.48% | -92.48% | -92.48% | -92.48% | -92.48% | -92.48% | -92.48% | -92.48% | -83.97% | -83.97% | -83.97% | -83.97% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | 0% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -83.97% | -83.97% | -83.97% | -83.97% | -27.65% | -27.65% | -27.65% | 0% | 0% | -27.65% | -27.65% | -27.65% | 0% | -83.97% | -83.97% | -27.65% | -32.93% | -29.63% | -29.63% | -29.63% | -32.93% | -39.51% | -32.93% | -39.51% | -29.15% | -29.15% | -17.2% | -32.93% | -32.93% | -39.51% | -39.51% | -31.82% | -27.68% | -30.82% | -31.82% | -32.93% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -42.09% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -27.65% | -32.93% | -32.93% | -32.93% | -32.93% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -30.82% | -30.82% | -30.82% | -30.82% | -30.82% | -30.82% | -30.82% | -30.82% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -83.97% | -30.42%
| P10 | 10% | -86.95% | -86.95% | -86.95% | -86.95% | -86.95% | -86.95% | -86.95% | -86.95% | -86.95% | -68.84% | -68.84% | -68.84% | -68.84% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | 0% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -68.84% | -68.84% | -68.84% | -68.84% | -20.42% | -20.42% | -20.42% | 0% | 0% | -20.42% | -20.42% | -20.42% | 0% | -68.84% | -68.84% | -20.42% | -23.82% | -21.44% | -21.44% | -21.44% | -23.82% | -28.59% | -23.82% | -28.59% | -19.54% | -19.54% | -16.35% | -23.82% | -23.82% | -28.59% | -28.59% | -22.26% | -21.98% | -21.82% | -22.26% | -23.82% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -38.74% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -20.42% | -23.82% | -23.82% | -23.82% | -23.82% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -20.82% | -20.82% | -20.82% | -20.82% | -20.82% | -20.82% | -20.82% | -20.82% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -68.84% | -22.47%
| P15 | 15% | -72.36% | -72.36% | -72.36% | -72.36% | -72.36% | -72.36% | -72.36% | -72.36% | -72.36% | -48.36% | -48.36% | -48.36% | -48.36% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | 0% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -48.36% | -48.36% | -48.36% | -48.36% | -10.12% | -10.12% | -10.12% | 0% | 0% | -10.12% | -10.12% | -10.12% | 0% | -48.36% | -48.36% | -10.12% | -12.83% | -11.54% | -11.54% | -11.54% | -12.83% | -15.39% | -12.83% | -15.39% | -10.77% | -10.77% | -10.49% | -12.83% | -12.83% | -15.39% | -15.39% | -12.63% | -15.83% | -13.43% | -12.63% | -12.83% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -28.95% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -10.12% | -12.83% | -12.83% | -12.83% | -12.83% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -11.83% | -11.83% | -11.83% | -11.83% | -11.83% | -11.83% | -11.83% | -11.83% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -48.36% | -11.13%
| P20 | 20% | -60.84% | -60.84% | -60.84% | -60.84% | -60.84% | -60.84% | -60.84% | -60.84% | -60.84% | -40.39% | -40.39% | -40.39% | -40.39% | -3.305% | -3.305% | -3.305% | -3.305% | -3.305% | 0% | -3.305% | -3.305% | -3.305% | -3.305% | -3.305% | -7.094% | -7.094% | -40.39% | -40.39% | -40.39% | -40.39% | -7.094% | -7.094% | -7.094% | 0% | 0% | -7.094% | -7.094% | -3.305% | 0% | -40.39% | -40.39% | -3.305% | -5.797% | -5.217% | -5.217% | -5.217% | -5.797% | -6.956% | -5.797% | -6.956% | -7.745% | -7.745% | -8.659% | -5.797% | -5.797% | -6.956% | -6.956% | -8.745% | -12.74% | -7.745% | -8.745% | -5.797% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -19.87% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -7.094% | -5.797% | -5.797% | -5.797% | -5.797% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -7.745% | -7.745% | -7.745% | -7.745% | -7.745% | -7.745% | -7.745% | -7.745% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -40.39% | -3.635%
| P25 | 25% | -43.73% | -43.73% | -43.73% | -43.73% | -43.73% | -43.73% | -43.73% | -43.73% | -43.73% | -32.1% | -32.1% | -32.1% | -32.1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | -2.73% | -2.73% | -32.1% | -32.1% | -32.1% | -32.1% | -2.73% | -2.73% | -2.73% | 0% | 0% | -2.73% | -2.73% | 0% | 0% | -32.1% | -32.1% | 0% | 1% | 0.9% | 0.9% | 0.9% | 1% | 1.2% | 1% | 1.2% | -2.73% | -2.73% | -1.207% | 1% | 1% | 1.2% | 1.2% | -2.73% | -5.98% | -1.73% | -2.73% | 1% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -3.414% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | -2.73% | 1% | 1% | 1% | 1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -1.73% | -1.73% | -1.73% | -1.73% | -1.73% | -1.73% | -1.73% | -1.73% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | -32.1% | 0%
| P30 | 30% | -39.84% | -39.84% | -39.84% | -39.84% | -39.84% | -39.84% | -39.84% | -39.84% | -39.84% | -24.56% | -24.56% | -24.56% | -24.56% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 0% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | -24.56% | -24.56% | -24.56% | -24.56% | 1.4% | 1.4% | 1.4% | 0% | 0% | 1.4% | 1.4% | 1.4% | 0% | -24.56% | -24.56% | 1.4% | 3.356% | 3.02% | 3.02% | 3.02% | 3.356% | 4.027% | 3.356% | 4.027% | 3.04% | 3.04% | 6.25% | 3.356% | 3.356% | 4.027% | 4.027% | 3% | -1% | 7.091% | 3% | 3.356% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.305% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 1.4% | 3.356% | 3.356% | 3.356% | 3.356% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | -24.56% | 1.54%
| P35 | 35% | -24.74% | -24.74% | -24.74% | -24.74% | -24.74% | -24.74% | -24.74% | -24.74% | -24.74% | -17.92% | -17.92% | -17.92% | -17.92% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 0% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | -17.92% | -17.92% | -17.92% | -17.92% | 3.966% | 3.966% | 3.966% | 0% | 0% | 3.966% | 3.966% | 3.966% | 0% | -17.92% | -17.92% | 3.966% | 6.954% | 6.259% | 6.259% | 6.259% | 6.954% | 8.345% | 6.954% | 8.345% | 6% | 6% | 11% | 6.954% | 6.954% | 8.345% | 8.345% | 6% | 0% | 11.78% | 6% | 6.954% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 1.439% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 3.966% | 6.954% | 6.954% | 6.954% | 6.954% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | 7.07% | 7.07% | 7.07% | 7.07% | 7.07% | 7.07% | 7.07% | 7.07% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | -17.92% | 4.362%
| P40 | 40% | -15.52% | -15.52% | -15.52% | -15.52% | -15.52% | -15.52% | -15.52% | -15.52% | -15.52% | -11.29% | -11.29% | -11.29% | -11.29% | 9% | 9% | 9% | 9% | 9% | 0% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | -11.29% | -11.29% | -11.29% | -11.29% | 9% | 9% | 9% | 0% | 0% | 9% | 9% | 9% | 0% | -11.29% | -11.29% | 9% | 9% | 8.1% | 8.1% | 8.1% | 9% | 10.8% | 9% | 10.8% | 9.01% | 9.01% | 18% | 9% | 9% | 10.8% | 10.8% | 9% | 1.626% | 18% | 9% | 9% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 3.035% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | 9% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | 11% | 11% | 11% | 11% | 11% | 11% | 11% | 11% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | -11.29% | 9.9%
| P45 | 45% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -10.09% | -6.168% | -6.168% | -6.168% | -6.168% | 12% | 12% | 12% | 12% | 12% | 0% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | -6.168% | -6.168% | -6.168% | -6.168% | 12% | 12% | 12% | 0% | 0% | 12% | 12% | 12% | 0% | -6.168% | -6.168% | 12% | 13% | 11.7% | 11.7% | 11.7% | 13% | 15.6% | 13% | 15.6% | 13.07% | 13.07% | 25.72% | 13% | 13% | 15.6% | 15.6% | 13% | 6% | 23% | 13% | 13% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 5.995% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 13% | 13% | 13% | 13% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | 14% | 14% | 14% | 14% | 14% | 14% | 14% | 14% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | -6.168% | 13.2%
| P50 | 50% | 3.423% | 3.423% | 3.423% | 3.423% | 3.423% | 3.423% | 3.423% | 3.423% | 3.423% | -0.308% | -0.308% | -0.308% | -0.308% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 0% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | -0.308% | -0.308% | -0.308% | -0.308% | 13.33% | 13.33% | 13.33% | 0% | 0% | 13.33% | 13.33% | 13.33% | 0% | -0.308% | -0.308% | 13.33% | 16% | 14.4% | 14.4% | 14.4% | 16% | 19.2% | 16% | 19.2% | 19% | 19% | 29.34% | 16% | 16% | 19.2% | 19.2% | 16% | 12% | 25.36% | 16% | 16% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 8.082% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 13.33% | 16% | 16% | 16% | 16% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | -0.308% | 14.67%
| P55 | 55% | 5.623% | 5.623% | 5.623% | 5.623% | 5.623% | 5.623% | 5.623% | 5.623% | 5.623% | 1.331% | 1.331% | 1.331% | 1.331% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 0% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 1.331% | 1.331% | 1.331% | 1.331% | 18.38% | 18.38% | 18.38% | 0% | 0% | 18.38% | 18.38% | 18.38% | 0% | 1.331% | 1.331% | 18.38% | 19% | 17.1% | 17.1% | 17.1% | 19% | 22.8% | 19% | 22.8% | 24% | 24% | 29.82% | 19% | 19% | 22.8% | 22.8% | 20% | 19.25% | 27% | 20% | 19% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 13.55% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 18.38% | 19% | 19% | 19% | 19% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 1.331% | 20.21%
| P60 | 60% | 8.066% | 8.066% | 8.066% | 8.066% | 8.066% | 8.066% | 8.066% | 8.066% | 8.066% | 3.873% | 3.873% | 3.873% | 3.873% | 22% | 22% | 22% | 22% | 22% | 0% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 3.873% | 3.873% | 3.873% | 3.873% | 22% | 22% | 22% | 0% | 0% | 22% | 22% | 22% | 0% | 3.873% | 3.873% | 22% | 22% | 19.8% | 19.8% | 19.8% | 22% | 26.4% | 22% | 26.4% | 32.61% | 32.61% | 31.4% | 22% | 22% | 26.4% | 26.4% | 24% | 22% | 32% | 24% | 22% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 15.52% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 26% | 26% | 26% | 26% | 26% | 26% | 26% | 26% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 3.873% | 24.2%
| P65 | 65% | 22.01% | 22.01% | 22.01% | 22.01% | 22.01% | 22.01% | 22.01% | 22.01% | 22.01% | 10.29% | 10.29% | 10.29% | 10.29% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 0% | 34.89% | 34.89% | 34.89% | 34.89% | 34.89% | 48.43% | 48.43% | 10.29% | 10.29% | 10.29% | 10.29% | 48.43% | 48.43% | 48.43% | 0% | 0% | 48.43% | 48.43% | 34.89% | 0% | 10.29% | 10.29% | 34.89% | 26.51% | 23.86% | 23.86% | 23.86% | 26.51% | 31.81% | 26.51% | 31.81% | 51.73% | 51.73% | 57.54% | 26.51% | 26.51% | 31.81% | 31.81% | 42.57% | 38.04% | 59.94% | 42.57% | 26.51% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 17.63% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 48.43% | 26.51% | 26.51% | 26.51% | 26.51% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 10.29% | 38.37%
| P70 | 70% | 52.77% | 52.77% | 52.77% | 52.77% | 52.77% | 52.77% | 52.77% | 52.77% | 52.77% | 18.37% | 18.37% | 18.37% | 18.37% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 0% | 45.54% | 45.54% | 45.54% | 45.54% | 45.54% | 57.25% | 57.25% | 18.37% | 18.37% | 18.37% | 18.37% | 57.25% | 57.25% | 57.25% | 0% | 0% | 57.25% | 57.25% | 45.54% | 0% | 18.37% | 18.37% | 45.54% | 31.8% | 28.62% | 28.62% | 28.62% | 31.8% | 38.16% | 31.8% | 38.16% | 58.51% | 58.51% | 66.33% | 31.8% | 31.8% | 38.16% | 38.16% | 47.51% | 40.51% | 62.51% | 47.51% | 31.8% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 31.93% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 57.25% | 31.8% | 31.8% | 31.8% | 31.8% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 51.51% | 51.51% | 51.51% | 51.51% | 51.51% | 51.51% | 51.51% | 51.51% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 18.37% | 50.1%
| P75 | 75% | 69.84% | 69.84% | 69.84% | 69.84% | 69.84% | 69.84% | 69.84% | 69.84% | 69.84% | 23.7% | 23.7% | 23.7% | 23.7% | 67.65% | 67.65% | 67.65% | 67.65% | 67.65% | 0% | 67.65% | 67.65% | 67.65% | 67.65% | 67.65% | 100.9% | 100.9% | 23.7% | 23.7% | 23.7% | 23.7% | 100.9% | 100.9% | 100.9% | 0% | 0% | 100.9% | 100.9% | 67.65% | 0% | 23.7% | 23.7% | 67.65% | 48.65% | 43.78% | 43.78% | 43.78% | 48.65% | 58.38% | 48.65% | 58.38% | 98.53% | 98.53% | 108.3% | 48.65% | 48.65% | 58.38% | 58.38% | 87.88% | 76.63% | 103.9% | 87.88% | 48.65% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 46.95% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 100.9% | 48.65% | 48.65% | 48.65% | 48.65% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 92.88% | 92.88% | 92.88% | 92.88% | 92.88% | 92.88% | 92.88% | 92.88% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 23.7% | 74.41%
| P80 | 80% | 113.1% | 113.1% | 113.1% | 113.1% | 113.1% | 113.1% | 113.1% | 113.1% | 113.1% | 41.99% | 41.99% | 41.99% | 41.99% | 100.5% | 100.5% | 100.5% | 100.5% | 100.5% | 0% | 100.5% | 100.5% | 100.5% | 100.5% | 100.5% | 145.1% | 145.1% | 41.99% | 41.99% | 41.99% | 41.99% | 145.1% | 145.1% | 145.1% | 0% | 0% | 145.1% | 145.1% | 100.5% | 0% | 41.99% | 41.99% | 100.5% | 63.6% | 57.24% | 57.24% | 57.24% | 63.6% | 76.32% | 63.6% | 76.32% | 121.1% | 121.1% | 126.9% | 63.6% | 63.6% | 76.32% | 76.32% | 116.1% | 106.1% | 129.1% | 116.1% | 63.6% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 57.57% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 145.1% | 63.6% | 63.6% | 63.6% | 63.6% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 120.1% | 120.1% | 120.1% | 120.1% | 120.1% | 120.1% | 120.1% | 120.1% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 41.99% | 110.6%
| P85 | 85% | 120.8% | 120.8% | 120.8% | 120.8% | 120.8% | 120.8% | 120.8% | 120.8% | 120.8% | 49.38% | 49.38% | 49.38% | 49.38% | 144.1% | 144.1% | 144.1% | 144.1% | 144.1% | 0% | 144.1% | 144.1% | 144.1% | 144.1% | 144.1% | 190.2% | 190.2% | 49.38% | 49.38% | 49.38% | 49.38% | 190.2% | 190.2% | 190.2% | 0% | 0% | 190.2% | 190.2% | 144.1% | 0% | 49.38% | 49.38% | 144.1% | 75.93% | 68.34% | 68.34% | 68.34% | 75.93% | 91.12% | 75.93% | 91.12% | 138% | 138% | 146% | 75.93% | 75.93% | 91.12% | 91.12% | 127% | 129.5% | 135% | 127% | 75.93% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 62.49% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 190.2% | 75.93% | 75.93% | 75.93% | 75.93% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 134.2% | 134.2% | 134.2% | 134.2% | 134.2% | 134.2% | 134.2% | 134.2% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 49.38% | 158.5%
| P90 | 90% | 239.2% | 239.2% | 239.2% | 239.2% | 239.2% | 239.2% | 239.2% | 239.2% | 239.2% | 82.03% | 82.03% | 82.03% | 82.03% | 219.2% | 219.2% | 219.2% | 219.2% | 219.2% | 0% | 219.2% | 219.2% | 219.2% | 219.2% | 219.2% | 376.5% | 376.5% | 82.03% | 82.03% | 82.03% | 82.03% | 376.5% | 376.5% | 376.5% | 0% | 0% | 376.5% | 376.5% | 219.2% | 0% | 82.03% | 82.03% | 219.2% | 89.02% | 80.12% | 80.12% | 80.12% | 89.02% | 106.8% | 89.02% | 106.8% | 267.1% | 267.1% | 267.5% | 89.02% | 89.02% | 106.8% | 106.8% | 259.5% | 262.5% | 283.5% | 259.5% | 89.02% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 71.4% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 376.5% | 89.02% | 89.02% | 89.02% | 89.02% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 272.9% | 272.9% | 272.9% | 272.9% | 272.9% | 272.9% | 272.9% | 272.9% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 82.03% | 241.1%
| P95 | 95% | 310.4% | 310.4% | 310.4% | 310.4% | 310.4% | 310.4% | 310.4% | 310.4% | 310.4% | 118.5% | 118.5% | 118.5% | 118.5% | 290.4% | 290.4% | 290.4% | 290.4% | 290.4% | 0% | 290.4% | 290.4% | 290.4% | 290.4% | 290.4% | 447.6% | 447.6% | 118.5% | 118.5% | 118.5% | 118.5% | 447.6% | 447.6% | 447.6% | 0% | 0% | 447.6% | 447.6% | 290.4% | 0% | 118.5% | 118.5% | 290.4% | 120.8% | 108.7% | 108.7% | 108.7% | 120.8% | 144.9% | 120.8% | 144.9% | 319.2% | 319.2% | 271.1% | 120.8% | 120.8% | 144.9% | 144.9% | 309.4% | 295.2% | 328.2% | 309.4% | 120.8% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 88.89% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 447.6% | 120.8% | 120.8% | 120.8% | 120.8% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 341.3% | 341.3% | 341.3% | 341.3% | 341.3% | 341.3% | 341.3% | 341.3% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 118.5% | 319.4%
| P100 | 100%
Schedule RCF
Notes
| P0 | 0%
| P5 | 5% | NA
| P10 | 10% | NA
| P15 | 15% | NA
| P20 | 20% | NA
| P25 | 25% | NA
| P30 | 30% | NA
| P35 | 35% | NA
| P40 | 40% | NA
| P45 | 45% | NA
| P50 | 50% | NA
| P55 | 55% | NA
| P60 | 60% | NA
| P65 | 65% | NA
| P70 | 70% | NA
| P75 | 75% | NA
| P80 | 80% | NA
| P85 | 85% | NA
| P90 | 90% | NA
| P95 | 95% | NA
| P100 | 100%
Note on AB2: Site preparation works, Roads, paths, paving’s and surfacing, Soft landscaping, planting and irrigation systems, fencing, external drainage and utilities and minor building works and ancillary building works
Note on E3: Purchase price including Planning Risk discounts (Actual price to be paid)
Note on F3: Purchasers Agent and Legal fees
Note on G3: SDLT rates as appropriate
Note on H3: Easements, Wayleaves
Note on M3: Costs for securing Outline Planning Permission
Note on N3: Costs for securing Outline Planning Permission
Note on O3: Costs for securing Reserved Matters planning
Note on P3: Pre-app, allocation promotion, SPD/planning brief, design incl B4Life, Listed Buildings surveys, fees associated with S278,38 or 104, highway, noise, and desk top archaeology surveys.
Note on AH3: includes demolition to slab and or below ground, substructures. Planning costs for demolition should be included in planning fees.
Note on AI3: Including cut and fill and ground stabilisation, preparing sub-surfaces, site clearance, including all works to existing trees and TPOs etc.
Note on AJ3: Remediation and decontamination including monitoring costs
Note on AM3: Incl site investigations, topo survey, noise surveys, UXO, building condition survey
Note on AQ3: Including Transport and Highway Assessments
Note on AS3: Means works undertaken by developer
Note on AT3: incl. contribution to strategic infrastructure; works undertaken by others
Note on BB3: Works to be carried out by the developer on Public Transport not included in S106 Costs
Note on BF3: Infrastructure not serving individual plots directly i.e. not local infrastructure included under externals. Including standard sewers. Will include fees, contingencies and prelims
Note on BH3: Additional junctions or junctions works over and above standard
Note on BM3: compensation for depreciation in the value of an interest in land which is attributable to the use of public works i.e construction of a highway
Note on CK4: (likely to be removed in due course as costs become standard and are reflected within base build costs)
Note on D5: From EW Rail "L&P"
Note on M5: From BusConnects "Prelims"
Note on Q5: From BusConnects "Building"
Note on T5: From BusConnects "Building"
Note on AB5: From EW Rail "civils"
Note on AD5: From Busconnects "Management"
Note on AH5: EW Rail "Temp Works"
Note on AQ5: Mr Bartlett: BusConnects Design - change to SW Design?
Note on AR5: Mr Bartlett: BusConnects Design - change to SW Design?
Note on AT5: BusConnects roads
Note on BB5: As rail
Note on BC5: EW Rail "Track"
Note on BD5: EW Rail "Stations"
Note on BI5: EW Rail "Civils"
Note on BJ5: EW Rail "Bridges"
Note on BK5: EW Rail "Tunnels"
Note on CM5: Data from Sydney Water
Note on DO5: Use margin from SW work?

## Selectors (hidden)
RCF Linkage |  |  | Phasing | HE Stages |  | Notes | Choices
Cost heading | RCF | SOBC | Scope and Pre-appraisal | Project Concept | SOBC | Proposal for early sighting meeting | SOBC
Acquisition (including from public sector) | Land & Property | SOBC | Concept and feasibility | SOC | SOBC | Early VfM assessment based on ready reckoner. Cost to be agreed to complete the Business Case | OBC
Safeguarding heritage assets | Buildings (public) | OBC | Option selection | Business Case | OBC | Agreement to proceed with project | FBC
Enabling works |  | FBC | Design and Environmental Evaluation | Point of Contract | FBC | Further internal approvals at the point of contract. | CCT
Geotechnical engineering to enable platforms for build | Enabling works | FBC | Statutory Processes | Delivery phase | FBC | Post procurement
Demolition of buildings | Demolition | CCT | Enabling and Procurement |  | CCT
Site remediation - general | Enabling works | CCT | Construction and Implementation |  | CCT
Heavily contaminated/ old coalfields | Enabling works - factored |  | Close out and review
Complex/ brownfield sites | Enabling works - factored
Infrastructure:
Highways | Roads - general urban/ rural | MMC Factoring |  | Factor for analysis:
Other transport | Rail - conventional track | MMC (Quantum of above costs using MMC methods) | Cat 1 - Pre-manufacturing 3D Structural Systems
Utilities | Utilities |  | Cat 2 - Pre-manufacturing 2D Structural Systems - open and closed panel
Green space | Civils |  | Cat 3 - Pre-manufacturing Structural Assemblies and Sub-Assemblies
Flood defences | Civils |  | Cat 4 - Additive Manufacturing - Structural and non-structural
Building |  |  | Cat 5 - Pre-manufacturing non structural pods and sub-assemblies
Residential | Buildings (residential) |  | Cat 6 – Traditional Building Product Led Site Labour reduction/ productivity improvements
Focus on Modern Methods of Construction (MMC) | Develop factor for inclusion? |  | Cat 7 – Sitr Process Led Site Labour reduction/ productivity/ assurance improvements
Custom build properties | Buildings (complex) |  | Total: | Every 10% of MMC reduces affected RCFs by x 5%:
Building affordable housing | Buildings (affordable) |  |  | Reduction Factor: | 2
Commercial (all types) | Buildings (commercial)
Industrial | Buildings (industrial)
Film studios/ creative space | Buildings (arts)
Community buildings | Buildings (community)
Public buildings | Buildings (public)
Indirect costs
Planning, masterplanning, design, costs (capitalised) | Indirects
Development Management costs | Indirects
S106 Obligations – including Biodiversity net gain | Indirects
Holding costs/estate management | Indirects
Finance
Finance – rental | Finance rental??
Finance – house purchase | Finance house purchasing??
Land disposal | Land disposal??
Delivery mechanism
Note on G13: A systemised approach based on volumetric construction involving the production of three-dimensional units in controlled factory conditions prior to final installation. Volumetric units can be brought to final site in a variety of forms ranging from a basic structure only to one with all internal and external finishes and services installed, all ready for installation.
Note on G14: A systemised approach using flat panel units used for basic floor, wall and roof structures of varying materials which are produced in a factory environment and assembled at the final workface to produce a three-dimensional structure. The most common approach is to use open panels, or frames, which consist of a skeletal structure only, with services, insulation, external cladding and internal finishing being installed on-site. More complex panels - typically referred to as closed panels - involve more factory-based fabrication and include lining materials and insulation. These may also include services, windows, doors, internal wall finishes and external claddings. The system includes structural performance for primary walls and all floors(note-this excludes unitised or composite external walling systems that are not load bearing included in category 5)
Note on G15: Use of pre-manufactured structural members made of framed or mass engineered timber, cold rolled or hot rolled steel or pre-caste concrete. Members to include load bearing beams, columns, walls, core structures
Note on G16: The remote, site based or final workface based on printing of parts of buildings through various materials based on digital design and manufacturing techniques.
Note on B17: (noting some of the above may vary by type of building involved and that HE may be more involved in some building types directly whereas others may be enabled)
Note on G17: A series of different pre-manufacturing approaches that includes unitised non-structural walling systems, roofing finish cassettes or assemblies (where not part of a wider structural building system), non-load bearing mini-volumetric units (sometimes referred to as 'pods') utility cupboards, risers, plant rooms as well as pre-formed wiring looms, mechanical engineering composites, would fall into this category.
Note on G18: Includes traditional single building products manufactured in large format, pre-cut configurations or with easy jointing features to reduce extent of site labour required to install.
Note on G19: This category is intended to encompass approaches utilising innovative site-based construction techniques that harness site process improvements falling outside the five main pre-manufacturing categories 1-5 or materials innovation in Category 6. This category would also include factory standard workface encapsulation measures, lean construction techniques, physical and digital worker augmentation, workface robotics, exoskeletons and other wearables, drones, verification tools and adoption of new technology led plant and machinery.

## Asset classes - discussed (hidden)
Homes England cost heading | Homes England Programme | [8 empty] | Suggested RCF dataset | OGP Query | Discussion 26 Sept 22
| Single Land Programme | Land Assembly Fund | Infrastructure grant | Local Authority Accelerated Construction | Home Building Fund: Long term fund | Home Building Fund: Short Term Fund | PRS Guarantees | Help to Buy | Affordable Housing Programme |  |  |  | Clarification of costs
Acquisition (including from public sector) | Yes | Yes | [7 empty] | Land & Property | Ok
Safeguarding heritage assets | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Heritage buildings | Filter from Westminster work (SF) |  | Maintenance & protection of a heritage asset
Enabling works
Surveys | [9 empty] | Surveys | Ok |  | Mostly non-intrusive or minor boreholes/ trial pits
Geotechnical engineering to enable platforms for build | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Enabling works | Ok |  | Stripping surface to reveal good quality substrata
Demolition of buildings | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Demolition | Ok
Site remediation - general | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Enabling works | "facilitating works" |  | Guidance required
Complex/ brownfield sites |  |  |  | Often | Often |  |  |  |  | Enabling works - complex | Factor based on brownfield v greenfield differentials from road studies? |  | Guidance required
Heavily contaminated/ old Coalfield sites | [9 empty] | Enabling works - severe | Even worse than complex |  | Guidance required
Infrastructure:
Highways | Yes | Yes | Yes | Yes | Yes | [5 empty] | Ok | Could be more refined - rural/ urban/ greenfield/ Mways an exception; separate out junctions??
Road - general | [9 empty] | Road - general
Urban roads - standard | [9 empty] | Urban roads - standard
Urban roads - complex | [9 empty] | Urban roads - complex
Rural roads - standard | [9 empty] | Rural roads - standard
Rural roads - complex | [9 empty] | Rural roads - complex
Other transport | Yes | Yes | Yes | Yes | Yes | [5 empty] | Ok | Possibly sustainable works: footpaths/ cyclepaths
Rail | [9 empty] | Rail - conventional track |  |  | Rapid transport or rail conventiona;
Footpaths | [9 empty] | Roads
Cyclepaths | [9 empty] | Roads
Buslanes | [9 empty] | Roads
Pavements | [9 empty] | Roads
Parking - surface only | [9 empty] | Roads
Stations | [9 empty] | Stations - standard | Ok
Utilities | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Utilities | Ok | Clarify what's included - probably not broken down. Check out different profiles. Inc Telecoms? Could be influential | Define inc renewables?
Mixed | [9 empty] | SF
Gas | [9 empty] | SF
Water/ drainage/ sewerage | [9 empty] | SF
Energy transmission | [9 empty] | SF
Telecoms infrastructure | [9 empty] | SF
Green space | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Civils | Ok
Other civils | [9 empty] | Civils
Bridges/ other structures | [9 empty] | Bridges
Tunnels | [9 empty] | Tunnels
Flood defences | Yes | Yes | Yes | Yes | Yes | [5 empty] | Ok
Standard drainage | [9 empty] | SF
Waterways/ canals - bypass channels | [9 empty] | SF
Earthworks | [9 empty] | Sf
Building | [11 empty] | Concentrate more on enablng infrastructure not the buildings | urban areas v greenfield treated as ratio
Residential | Yes | Yes | Yes | Yes | Yes | Yes |  |  |  | Buildings (standard) | Can we divide buildings into this?
Custom build properties | [5 empty] | Yes |  |  |  | Buildings (complex) | Ratchet on standard unless o/w | Other buildings - eg tower blocks
Building affordable housing | [8 empty] | Yes | Buildings (affordable) | Use standard housing until evidence illustrates o/w
Commercial (shop units/ offices space | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Buildings (commercial) | Use custom housing until evidence illustrates o/w
Light industrial (warehousing/ distribution) | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Buildings (industrial) | As commercial unless o/w
Film studios/ creative space | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Buildings (arts)
Community/ public buildings | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Buildings (community) | As commercial unless o/w
Indirect costs
Planning/ masterplanning | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Indirects
Design | [9 empty] | Design
Development Management costs | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Indirects
S106 Obligations – including Biodiversity net gain | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Enabling works |  | Approvals/ petitions for schedule
Holding costs/estate management | Yes | Yes | Yes | Yes | Yes |  |  |  |  | Indirects
Other indirects | [9 empty] | Indirects
Finance | [11 empty] | Variance on income - ignore for now
Finance – rental | [6 empty] | Yes |  |  | For future consideration if HE data available | Use HE data when available | Economic assumptions - ranging
Finance – house purchase | [7 empty] | Yes |  |  | Use HE data when available
Land disposal | Yes | [9 empty] | Use HE data when available | Market value variance- develop this
Factors
Delivery mechanism | Tender for works, site remediation, demolition, infra etc; disposal freehold/ leasehold, JVs, acquisition | Acquisition, derisking and disposal of land | Grants to Las | Grants to Las | Finance to developers | Devt loans; equity investments | Long term loans | Loans | Grant funding | Assumed that this will be considered in the extent of works - there is no intrinsic difference in actuals versus early estimates for differing delivery mechanism
Focus on Modern Methods of Construction (MMC) | Yes if poss |  |  |  | Yes | Yes |  |  | Yes | SF |  | What data would be useful to collate as factors? Generally perceived as an extra cost at the moment. 7 categories
Urban/ rural | [9 empty] | SF
Note on A41: (noting some of the above may vary by type of building involved and that HE may be more involved in some building types directly whereas others may be enabled)