Public Service Delivery Review Board minutes of meeting

Meeting date: 13 June 2023, hosted remotely via Microsoft Teams.
Attendees: Sue Bateman (CDDO), Heather Neate (CDDO), Sulaiman Saeed (CDDO), Ebru Yilmaz (CDDO), Mark Brewin (HMRC), Stephen Mak (DLUHC), Louise Bennett (PCAG), Glyn Jones (Welsh Government), Louise Greenrod (NHSX/DHSC), Jack Ramsden (DESNZ), Debra Heaton (ICO), Jenny McEneaney (LGA)

Observers: Alison Dewar (Scottish Government), Rhian Jones (CDDO)
Speakers: Hannah Wall (DESNZ), Harry Williams (DESNZ)
Apologies: Alessia Morris (Scottish Government), Emma Wharram (DfE), Edgar Whitley (PCAG), Helen Walker (DWP), Ross Young (UKSA), Darrell McCullough (Northern Ireland Government), Andy Gregory (Home Office)

1	Welcome and introduction from the Chair
1.1	The Chair welcomed Members to the meeting and introduced Jenny McEneaney from Local Government Association and Louise Greenrod from (NHSX/Department of Health and Social Care)
2	Conflicts of interest, action points and minutes from the last meeting
2.1	Minutes from the last meeting on 13 December 2022 were approved. / Action point 66: secretariat to publish minutes from 13 December 2022 on GOV.UK
2.2	HMRC logged a potential conflict of interest in relation to the Home Upgrade Grants agenda item.
2.3	The following action points were closed: / Action point 56: Secretariat to arrange a separate meeting for members to review the ICO report in due course. / Action point 62: The secretariat requests that members put forward views on how we can introduce measures to support the public, for example, supporting citizens with the cost of living crisis. / Action point 65: Secretariat to make amendments to the Terms of Reference to address feedback from the Board and publish in due course / Further to the closure of action point 62, members were informed that they will have an opportunity to put forward views on how we can introduce new measures at the end of each meeting.
3	Work programme update
3.1	We continue to liaise with the Scottish Government to finalise the first register entry for the register of data sharing agreements. / Action point 67: secretariat to arrange a meeting with the Scottish Government to finalise the register entry by 20 June.
3.2	The government response to the Identity Verification Services consultation was published on 23 May 2023. The secretariat continues to work with the Government Digital Service to progress work to take forward the Identity Verification Services objective proposal when Parliamentary time allows.
3.3	The secretariat informed members that work on objectives to enable data sharing for emergency planning and recovery and early help and prevention has been temporarily paused.
3.4	Members were briefed on work that is being undertaken with DCMS to develop a new objective focussed on reuniting individuals with their dormant assets.
3.5	Following the presentation in December, the secretariat is liaising with the Scottish Government to look at ways which a data sharing objective could support the Scottish Free School Meals (FSM) scheme. / The secretariat continues to support the Scottish Government with a view to return to the board with a formal proposal in the coming months.
3.6	Members are updated on progress with work to extend the territorial application of the Digital Economy Act 2017 to include Northern Ireland. The secretariat informed members that work was continuing with Northern Ireland on the policy background.
3.7	Members are informed that the Data Protection and Digital Information Bill No 2 has completed committee stages and will progress in due course. Parallel to this, the secretariat continues to explore potential objective proposals which may deliver benefits to businesses.
4	Presentation: public register analysis and quality review
4.1	The secretariat gave an update on the use of the public service delivery, civil registration, debt and fraud powers since the last update in December. Members were briefed on the 44 new register entries this quarter.
5	Home Upgrade Grants (HUG)
5.1	Speakers from DESNZ gave an update on progress of work since their initial presentation in September 2022. Members were informed that DESNZ may look to use an existing power and will liaise with the secretariat to progress work.
6	ICO audit review and workplan
6.1	The chair briefed members on the key messages in the ICO audit report, which demonstrate that the right safeguards are in place in the Digital Economy Act 2017, its Schedules and Code of Practice to protect people's personal data. The public can be reassured that the powers are being used responsibly as seen through the public register. / Members were given an opportunity to discuss the recommendations. It was agreed that the secretariat will update the PSD, Debt and Fraud Code of Practice in line with the ICO’s recommendations, noting that the PSD Review Board has a different role than the Debt and Fraud Review Board. The secretariat will return to the Board with a work plan in due course.
7	Terms of Reference (ToR)
7.1	Members approved of the latest version of the ToR, updated to address feedback given at the last meeting 13 December 2022, subject to changing one reference to a ‘pilot data share’. / Action point 68: secretariat to upload the Terms of Reference (ToR) on GOV.UK in due course.
8	Risk Register
8.1	Members reviewed the risk register and no changes were proposed.
9	AOB
9.1	A member informed the board that policy responsibility for the supporting families programme has been moved to the Department for Education (DfE)
DONM 19 September 2023, 2 - 4pm