Oman Campaign Goal 3 – Evaluation Terms of Reference

Introduction

The UK and Oman share a historic relationship spanning over two centuries. Today we are strategic partners on a range of political, economic and security matters.

The UK is committed to supporting Oman in its ongoing political economic and social reforms. Oman faced significant financial problems towards the end of Sultan Qaboos’ reign in 2020 and subsequent youth protests around a lack of economic opportunity. The UK-Oman Strategic Advisory Group was set up in response to Oman’s economic situation as a forum for crucial knowledge-exchange and support for financial reforms. Oman’s recovery has required an economic focus from Sultan Haitham. The introduction of Oman Vision 2040 set out Oman’s long-term plan to achieve economic sustainability and social reform.

As Oman’s biggest foreign investor, the UK is helping to grow the Omani economy and create jobs. The UK is responsible for over half of all foreign investment into Oman. In January 2022, the UK and Oman signed a Sovereign Investment Partnership to increase high value investment into both countries. Through this partnership, although Omani state-led investment in the UK is relatively small, the UK is prioritising Omani investment into the UK's green energy ecosystem, to help encourage Oman’s own economic and energy diversification ambition, and to support unlocking their huge renewables potential based on their unique geography.

Background
The Oman Country Plan and associated Theory of Change is the primary mechanism for collating strategic alignment and steering British Embassy Muscat’s daily diplomatic, policy, and programmatic engagement in Oman. Oman is a priority country in the FCDO MENA Strategy. The Sultanate is a strategic defence and security partner, championed by the Secretary of State for Defence. Oman’s challenging social and gender equality context offers opportunities to deliver against the International Women and Girls Strategy.

Campaign Goal 3 is the focus of this evaluation:

Oman’s economy is stronger and more resilient. Increased resilience by enacting inclusive economic and structural reforms; continued progress on managing fiscal balance and deepening the financial sector including greater commercial ties with The City; credible efforts on diversification, gender and climate.

Campaign Goal 3 is the most cross-cutting Goal of the Country Plan, pertaining to inclusive social and economic reform, development (including UK-Oman commercial ties), gender, climate, and ultimately supporting resilience. The UK is strategically invested in the stability and resilience of Oman.

Of the Goals in the Oman Country Plan, Campaign Goal 3 is the most future-focussed. This makes it of particular strategic relevance considering Oman’s Vision 2040, which will require significant reforms and changes to the Sultanate’s social contract. There is also the potential for Royal Succession and/or ‘peak oil’ to occur in this timeframe. British Embassy Muscat recognises the need to evaluate and future-proof our approach.

The following Sections at Post are the most engaged with the delivery of Campaign Goal 3:
- Programmes (managing a non-ODA GSF and CSSF portfolio, co-leading on economic, gender and climate policy)
- Trade and Investment (co-leading on climate policy)
- Chancery (including Press and Public Affairs, leading on diplomatic policy, co-leading on economic and gender policy).

Objective
The overarching objective of this evaluation is to support the British Embassy in understanding how well it is performing with regards to Campaign Goal 3, how said performance can be improved across the Embassy, but also whether there is a need to adjust Campaign Goal 3 itself. For example:
- Effectiveness – is the Embassy achieving its objectives with regards to Campaign Goal 3?
- Coherence – how well do the Embassy’s interventions fit together?
- Relevance – is the Embassy doing the right things? Does the Campaign Goal need adjusting?

The evaluation should make recommendations for both refinement of the Campaign Goal and the Embassy’s methods of delivery to achieve the Campaign Goal.

We are planning to use the evaluation to evaluate cross-Embassy ways of working and delivery against Oman Country Plan Campaign Goal 3, to better understand how we most effectively use programmatic, policy, commercial and diplomatic levers to deliver strong sustainable economic growth and resilience in Oman. The intention is that the evaluation will be useful both to understand progress in Oman, but also to improve understanding of how to evaluate cross-embassy working toward strategic goals more generally. It is expected that the evaluation will also be relevant across the other Gulf Strategy Fund countries.

The evaluation may involve making suggestions on the design and implementation of the non-ODA programme portfolio, deployment of other Embassy levers, and/or the Oman Country Plan. The evaluation may advise on other relevant aspects (e.g., policy-programme cohesion, communications, gender and climate mainstreaming) if relevant and/or possible.

The Recipient
The primary recipient will be the British Embassy Muscat, represented by the Ambassador as the accountable owner of the Oman Country Plan and Chair of the Oman Country Board. The evaluation will be relevant to all Embassy Heads of Section but particularly Chancery, Programmes, and Trade as those who engage most with Campaign Goal 3.
Secondary recipients will include HMG teams engaged in the Gulf, such as other British Embassies, the management team of the Gulf Strategy Fund / GSF Oversight Board, and teams managing CSSF interventions in the Gulf. Broader FCDO departments may draw on findings and recommendations concerning coherence.

Scope
Evaluability Assessment
The core purpose of the evaluability assessment is to advise on the design and methodology for the evaluation, including evaluation questions, timing, resources, expertise and methods. The evaluability assessment may benefit from following DFID Working Paper 40. The evaluability assessment should propose a design which is effective and value for money to answer the following evaluability questions:
How could the proposed Oman Country Plan Campaign Goal 3 evaluation be designed to provide the most useful information on how effectively the UK has used its programmatic, policy, commercial and diplomatic levers to support strong, sustainable economic growth and resilience in Oman?

What methods and approaches would help BE Muscat best understand the relative benefits and risks of the different levers in delivering outcomes and impact, and the effectiveness of current planning, coordination and delivery mechanisms?

Are the currently proposed evaluation questions most appropriate and feasible?

What timing, expertise and design would be most appropriate, taking into account the funding already approved?

We expect the evaluability assessment will involve:
- Reviewing key documentation (Oman Country Plan, relevant programme and other strategy documents).
- Interviewing key internal stakeholders on expectations and thoughts around the evaluation. To include: Head of Programmes (Hannah Woodley), DHM (Simon Smart), the Ambassador (Dr Liane Saunders), and HQ lead on the Gulf Strategy Fund (Dave Wells).
- Possibly conducting a group brainstorming on priorities within the Campaign Goal and most useful evaluation questions.

We expect the evaluability assessment report will include:
  - Summary of no more than 1 page, suitable for senior managers
  - Background
  - Methods
  - Feasibility of an evaluation
  - Recommendations, including proposed evaluation questions
  - Summary of any other reflections which would support the design, monitoring and evaluation of the Oman Country Plan Campaign Goal 3.

There will be a break point in the contract, following the delivery of the evaluability assessment. This will give both the supplier and the FCDO the opportunity to reflect on the findings and recommendations before making a decision on whether to go forward.
Evaluation Inception Phase
If the decision is taken to proceed with the evaluation, an inception report will be required. This is expected to include:
  - Summary of no more than 1 page, suitable for senior managers
  - Evaluation methods / evaluation options
  - Agreed evaluation questions
  - Schedule of evaluation inputs and resources required.

Delivery Phase and Evaluation Report
While the precise methods and approaches appropriate will be determined by the evaluability assessment, it’s likely the most appropriate methods would be theory-based. We expect the evaluation to draw on HMG documentation, along with qualitative interviews with key internal and select external stakeholders. Rather than a draft evaluation report, we expect the supplier to deliver an ‘Emerging Findings’ report and accompanying presentation prior to delivery of the Final Report. The Emerging Findings report will focus on initial findings on priority evaluation questions – with exact scope agreed in the inception report stage. The evaluation report should include a Use and Influence Plan as well as an Evaluation Digest, per FCDO’s template for publication.

Administrative arrangement
The study would be supported through The Evidence Fund, an FCDO programme intended to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2022, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects, conduct due diligence assessments on prospective sub- contracted Research Pool providers, where relevant, and ​​​​manage research and evaluation contracting.

The Requirements
Deliverable	Estimated Timing / (Assuming contract commencement on 1st April 2024)	Payment Milestone
Brief evaluability assessment plan setting out how the work will be carried out and timings.	Within one week of contract commencement.
Evaluability assessment report	By end of April	20%
Inception report with accompanying briefing for key stakeholders.	Within two weeks of evaluability decision.	20%
Interviews and workshops with key informants	May and June
Emerging findings report and accompanying briefing for key stakeholders.	By end of June, for discussion at FY24/25 Q1 Country Board	20%
Final evaluation report, including EQUALS review	By end of July, for initial implementation ahead of the FY24/25 Q2 Country Board.	40%
Monthly narrative and financial updates	Throughout the contract period

The main staffing requirement is for an individual or team with expertise in portfolio/complex programme evaluation design and with experience in applying innovative/creative evaluation methods, who understands and can advise on both standard and innovative methods to evaluate this broad and diverse Campaign Goal. As we anticipate the use of stakeholder interviews, we anticipate the successful Supplier to provide evidence previous extensive successful use of qualitative interviews and qualitative analysis, as well as document review. Experience in conducting evaluations in the MENA region would be beneficial. Due to the sensitivities, it will be necessary for at least one member of the Supplier team to hold DV clearance.

Constraints and dependencies
Key data sources:
  - Relevant HMG and FCDO strategy documents (e.g. MENA strategy, Integrated Review Refresh, draft BE Muscat strategy etc.).
  - British Embassy Muscat Country Business Plan and Country Board documentation.
  - Programmes project documentation (e.g., proposals, quarterly reports, light-touch reviews, financials, Programme Board minutes etc.).
  - Trade project documentation and policy reporting.
  - Chancery policy analysis and reporting.
  - Perspectives of current and former staff (particularly considering the new HMA, DHM and Head of Chancery) as well as regional thematic leads (e.g., gender, climate, trade).
  - British Embassy Muscat thematic strategies on gender equality and social inclusion (GESI, commencing imminently) and climate (scheduled for FY24/25).
  - Insights from advisors and partners (e.g., economic cadre, programme suppliers, potentially Omani counterparts – if explored sensitively).

Constraints:
British Embassy Muscat is a small Post, which therefore does not benefit from dedicated HMG Advisers regarding MEL / Evaluation, Climate, or Gender and Social Development. Therefore, Post lacks the capacity and capability to undertake such evaluation exercises internally.

There is some M&E undertaken on the Programmes portfolio. However, this is specific to individual projects and utilises central/external CSSF and GSF resource on a drawdown basis. This limits the scope for holistic, strategic and/or ‘deep-dive’ evaluations.

There are regular strategic and policy discussions held at Post, including the Country Board.

The risks include:

Securing stakeholders’ time (minimised as we work closely with the main people so will ensure they are aware and that the meeting times work for them).

Difficulty identifying a meaningful methodology given the broad scope of the Campaign Goal (minimised by allowing a focus on selected parts if needed, and conducting the evaluability assessment to ensure we properly consider all appropriate methods).

Performance Requirements

The Final Evaluation Report must be quality-assured using the EQUALS2 service before final sign-off and payment.

Reporting
Communication between the consultant and FCDO leads is expected to involve: an initial briefing call, agreement of evaluability assessment plan (virtual), early ideas call, and final document feedback (call or virtual).

Use and Influence
The findings will be used to improve and enhance the Oman Country Business Plan, the programme portfolio, policy and diplomatic engagement, and cross-Embassy ways of working.
An evaluation at this juncture would be particularly timely given Post’s management turnover; a new Country Director for Trade (February 2022), Head of Programmes (March 2023), Ambassador (July 2023), Deputy Head of Mission (September 2023) and Head of Chancery (November 2023). It is important to capture and collate the institutional knowledge within the team.
Given that British Embassy Muscat utilises both non-ODA Gulf Strategy Fund and CSSF programme funding, the learning would also be shared across those portfolios. This would be particularly pertinent to other GSF country portfolios as many of the Gulf Posts share similar strategic objectives and challenges (e.g., on gender, climate, policy-programme cohesion).
Depending on timings, this evaluation could also be used to inform a high-side strategic review of the British Embassy’s engagement in Oman.

Break points (if applicable)
If the Evaluability Assessment should suggest that the information available is not sufficient to conduct this evaluation, a Break Point may be invoked.

Timeframe
We expect the evaluability assessment to take up to 10 person days. It should be finalised by late April to allow time for the evaluation to be completed in Q1 on FY24/25.
For the evaluation itself, travel to Oman will be necessary. It will be important to engage remotely with the previous DHM and Head of Chancery (departed September and November 2023 respectively). It will be important to engage with the new Ambassador, DHM and Head of Chancery. Initial outputs would be beneficial by end of May 2024 in order to steer programming in FY24/25. Final deliverables and onward initial implementation will be discussed at the Q2 Oman Country Board.

Budget
The total budget for the study should not exceed £270,000.00 excluding taxes. Costs of workshops should be explicitly built into the budget.

FCDO Coordination
The Head of Programmes would act as the focal point for supporting this evaluation regarding e.g., administration, connections to stakeholders, provision of existing data sources etc.
All policy leads and Heads of Section across British Embassy Muscat who are relevant to Campaign Goal 3 would be engaged to support this evaluation. Heads of Section would cascade messaging to their teams and opportunities for input into design and implementation.
The Oman Country Board would be used as the forum to endorse, instigate and monitor uptake. This would provide certainty regarding the sustainability of the evaluation.

Bidding process
Technical and financial proposals should be sent as two separate files to uk_evidence_fund_administration@pwc.com by April 5th, 2024 (23:59 GMT). Since these will be assessed independently of each other, they should, in no case, be combined or cross-referenced.
The instructions for submitting the tender and details on scoring methodology and evaluation criteria are detailed in ITT Volume 1. The application forms for submitting the technical proposal (sent as a clearly titled PDF file) are detailed in ITT Volume 3 and ITT Volume 4 provides the Pro Formas for the commercial proposal.

Duty of care
The Supplier is responsible for the safety and well-being of their personnel and relevant third parties affected by their activities under this assignment, including appropriate security arrangements where needed.
General Data Protection Regulation (GDPR)
Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Annex 1, and the standard clause 30 in section 2 of the contract.

Delivery Chain Mapping
In advance of any release of funds, the Supplier will be required to produce a ‘delivery chain risk map’ which should, where possible, identify all partners (funding and non-funding e.g. legal/contributions in kind) involved in the delivery of this study.  This is applicable only if the lead organisation engages downstream partners.

Safeguarding
FCDO places utmost importance on all potential partners’ ability to safeguard children, young people and vulnerable adults they work with from sexual exploitation and abuse, and their ability to protect staff and volunteers. The Supplier Code of Conduct will be included in the terms and conditions of the Contract. New compliance checking mechanisms are now in place to review supplier documentation, their approaches to legal compliance and demonstration of good practice in meeting international principles on labour and ethical employment and to provide assurance that whistleblowing systems are accessible across delivery chains. FCDO will monitor risk and mitigation plans throughout the project cycle. The commitments made by all organisations in receipt of FCDO funding need to provide spending teams with concrete assurance that the new enhanced safeguarding standards are being applied.  The approach will help to promote the adoption of new standards for all organisations in the aid sector.

Ethical principles and standards
Suppliers are required to refer to ethical guidelines available at  https://www.gov.uk/government/publications/dfid-ethical-guidance-for-research-evaluation-and-monitoring-activities.  Bidders should include a statement in their proposals, confirming that the study will comply with ethical guidelines as mentioned above. This is a mandatory requirement.

Research for Development outputs (R4D)
FCDO requires that all final research output(s) from this funding are uploaded to Research for Development Outputs (R4D) on GOV.UK. By law documents published on GOV.UK must comply with the  Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.  This is so they can be used by as many people as possible, including those with disabilities. Further information on open document formats and content accessibility on GOV.UK can be accessed here  https://www.gov.uk/guidance/content-design/planning-content.  Uploading final output(s) to Research for Development Outputs on GOV.UK does not exclude these outputs from being uploaded to other websites or platforms and repositories.

Annex 1
Schedule of Processing, Personal Data and Data Subjects
This schedule must be completed by the Parties in collaboration with each-other before the processing of Personal Data under the Contract.
The completed schedule must be agreed formally as part of the contract with FCDO and any changes to the content of this schedule must be agreed formally with FCDO under a Contract Variation.
Description	Details
Identity of the Controller and Processor for each Category of Data Subject	The Parties acknowledge that for the purposes of the Data Protection Legislation, the following status will apply to personal data under this contract: / The Parties acknowledge that Clause 30.2 Protection of Personal Data and 30.4 (Section 2 of the Below Threshold contract) shall not apply for the purposes of the Data Protection Legislation as the Parties are independent Controllers in accordance with Clause 30.3 in respect of Personal Data necessary for the administration and/or fulfilment of this contract”.

Annex 2
Business & Country Planning (BCP): Strategy and Delivery Overview Template (extract February 2024)
 2023-2025 Business and Country Plans
	Mission Statement:
UK recognised as a trusted and reliable partner, resulting in high level of engagement on key issues in support of an economically and politically resilient Oman which in turn increases mutual security, stability and prosperity.

	Strategic Context 1: Country / Policy / Corporate role in the Global Context:
Oman maintains a ‘friends to all’, neutral and non-interference foreign policy. Its policy thinking is influenced by pragmatism and shaped by what is in its national interest. Despite our differing foreign policy positions in some areas, there is still common ground and shared concerns. Oman’s strategic location means it is a useful partner for our Indo-Pacific tilt.

	Strategic Context 2: Current UK partnership or thematic/corporate interests:
Oman is a priority country for UK security and defence with mutual benefit. A large element of our engagement and partnerships are in the economic opportunity and regional resilience spheres. In effect, our wider support for Oman’s economic / social reforms and new commercial opportunities that result in job creation and workforce upskilling, help provide the environment for defence and security engagement. / The defence partnership is critical for ensuring that our objectives, through the Global Strategic Hub Oman, Joint Logistics Support Base and Ras Madrakah Range, are maintained in Duqm. All provide considerable defence and commercial opportunities, for the UK and Oman, but there is a vulnerability to our shared ambition if resources and/or political commitment on either side are scaled back or withdrawn. / HMG/UK’s strength is the ability to provide targeted technical assistance and credible strategic advice to Oman to support the Sultan’s priorities and vision. Our scale/ range of partnership is a strategic risk as our ability to support is heavily reliant on continued programme funding. / The embassy workforce is distributed appropriately to support our goals and priorities, drawing from programme M&E tools to measure wider impact and success. Sustainability of our outreach in the economic and resilience pillars, and by association continued high level and wider relationships, are linked to future programme allocations and a forward-leaning trade policy.

What are your Goals?
Goal number	Goal description
Goal 1:	Sustained political relationship in support of de-escalating the conflict in Yemen and appreciation of Iran’s regional motivations and intent.
Goal 2:	Sustained engagement to ensure that the UK remains Oman’s preferred defence and security partner.
Goal 3:	Increased resilience by supporting inclusive economic and structural reforms; continued progress on managing fiscal balance and deepening the financial sector including greater ties with London; credible efforts on diversification, gender and climate.
Goal 4:	UK-Oman commercial ties strengthened beyond traditional hydrocarbons and defence sectors into the growth areas that matter most for the UK economy, increasing UK exports and inward investment, supporting UK-GCC FTA negotiations and resolving market access barriers.

	What will you do to achieve these goals, delivering FCDO and HMG objectives?
Key activities in support of Goal 1 include regular engagement at both senior and working level, supplemented by a X-WH senior official and ministerial engagement plan. / Goal 2 will be achieved through the delivery of high-quality military and security assistance at all levels, MOD support of the Oman Defence Review, regular defence engagement and greater interoperability supports the wider prosperity agenda. Through our programming, we will support Oman’s strategic approach to cybersecurity and international governance. / The success of Goal 3 will rely on continuing technical assistance and advisory support to Oman Vision 2040 programmes. A workplan will be co-authored between UK and Oman outlining opportunities to increase linkages and investment between the UK and Oman, particularly across banking, insurance and capital markets. Economic empowerment of women is also key, the programme will expand its current mentoring programme to provide women with targeted support to transition from education to the workplace, and then progress to more senior levels. Greater focus will be on climate initiatives given COP28 is in the Gulf this year, supporting Oman with an inward visit to the UK to share expertise in carbon capture, the creation of a sustainability centre and hydrogen. / We will deliver Goal 4 through G2G engagements and focus on doing the things that industry cannot. With UK industry buy-in, these will link UK technical support to development of Omani market regulations; support on developing industrial ecosystems; and UK Export Finance support. The initial focus is on green energy and defence, with strategies planned for vocational training and digital. Extensive stakeholder/relationship management at all levels will be essential if we are to do the things industry cannot. / Delivery of all 4 goals is also reliant on regular engagement with key senior interlocutors and cultivating new relationships, especially with the next generation of leaders/ influencers, whilst maintain existing ones, to demonstrate the mutual value of the relationship as a whole.