Terms of Reference: Ghana Portfolio Evaluation
Introduction
Ghana is a British Investment Partnerships (BIP) priority country and a key middle-income country identified in the UK’s International Development Strategy. Having shown years of progress and great potential, in recent years Ghana has undergone significant challenges.
The British High Commission (BHC) in Accra employs approximately 45 UK-based and 150 locally employed staff. These cover multiple UK Departments including the Foreign, Commonwealth & Development Office (FCDO), the Department for Business & Trade, the Ministry of Defence and the National Crime Agency, among others.
The objectives of BHC Accra are set out within its Country Business Plan (CBP) and cover a wide range of thematic areas including defence, governance, and mutual prosperity. Over the last four years, BHC Accra has also undergone several structural changes which include the creation of FCDO, a significant reduction in bilateral official development assistance (ODA), and a greater focus on using additional tools beyond ODA to deliver our objectives.
This terms of reference (ToR) is for an evaluation of BHC Accra’s portfolio to review whether the BHC’s vision and corresponding objectives could be refined to better reflect the significant changes undergone by both Ghana and BHC Accra in recent years, as well as new UK strategies such as the White Paper for International Development. It will also look at how we are delivering against our stated objectives in terms of development impact and provide learning on how we might deliver more within our resource envelope.
An evaluability assessment for the review has been completed to help refine the evaluation questions and is attached as an annex (annex B) to the ToR. The cost of the evaluation study should not exceed £200,000.
Background
Ghana, often hailed as a development success story, now faces significant economic challenges. After years of growth and progress in poverty reduction, education, health, and energy access, the country has recently experienced a downturn, culminating in debt default and reliance on a $3bn IMF bailout to somewhat stabilise the economy in 2023. These internal challenges are compounded by external factors, including the lingering effects of the COVID-19 pandemic and the ongoing war in Ukraine. Board papers from the IMF’s ongoing $3bn Extended Credit Facility and the World Bank’s recently approved Development Policy Financing operation provide further useful background on Ghana’s current challenges.
Despite these setbacks, Ghana's past achievements should not be overlooked. The country has halved extreme poverty, a rare feat in Africa, and made notable advancements in education, health services, social safety nets, and energy access. These successes earned Ghana the title of "development poster child." However, the current crisis has made it clear that President Akufo-Addo’s “Ghana beyond aid" strategy is likely to be a long-term goal, requiring a continuing nuanced approach to development partnerships.
The UK, Ghana's long-standing partner, has also faced its own challenges, resulting in a significant reduction in bilateral ODA to Ghana. This has forced BHC Accra to adapt its approach, cutting its portfolio in some areas and spreading support across remaining areas in anticipation of potential funding increases in future years. This has often led to a focus on smaller, short-term projects rather than long-term strategic investments. In financial year 2023/24, the UK had nine operational bilateral programmes in Ghana with an annual budget of £5.5m.
The recent publication of the UK's White Paper for International Development and a planned increase in bilateral spending from financial year 2024/25 presents an opportunity to reassess the UK-Ghana partnership and our overarching strategic approach. A key decision for the BHC is whether to continue to try to cover a broad range of areas & interventions with a limited budget for each, or if it would be more effective to prioritise fewer, deeper interventions with greater resources. This will allow the BHC to assess its strategic direction, allocate resources more efficiently, and ensure its focus is on interventions that address Ghana's most pressing needs, whilst also supporting UK interests.
Navigating this complex landscape effectively is crucial for both Ghana and the UK. Through a strong partnership, we can overcome current challenges and build a sustainable path towards shared prosperity and long-term development success. This will require adapting to the new reality of more limited funding, demonstrating effective resource utilization, and fostering continued collaboration with Ghanaian partners.
Objective
The main focus of the portfolio evaluation is on learning, with a view to informing key future strategic decisions for BHC Accra, including country business planning and funding allocations for the next Spending Review.
The evaluation should provide learning on how the BHC’s overarching strategy, as expressed in the Country Business Plan, could be refined to better reflect:
1. The resources and tools available to the BHC.
2. Ghana’s recent development trajectory and changing needs.
3. Recent UK strategies covering international objectives & development.
The evaluation should also recommend how we might be able to deliver greater development impact by maximising available BHC programme and human resources.
The evaluation should provide a strategic and forward looking assessment to support the shaping of BHC's aid portfolio in a changing context in Ghana. This will allow BHC Accra to refresh our overarching strategy so that it appropriately reflects our available resources, the diverse tools available to us, the current development context in Ghana, relevant UK strategies, and the work of other development partners. Where possible, learnings should also allow BHC Accra to enhance its development impact, providing evidence to support decision making and portfolio design by developing an understanding of what works, for whom and when. The primary audience for the evaluation will be BHC Accra and its senior leadership team. Relevant learnings may also be disseminated more widely to provide useful guidance to other UK country offices who have undergone similar changes. Strategies developed in future by BHC Accra should remain relevant even in the face of potential changes in external context posed by UK and Ghanaian elections.
Priority Areas:
BHC Plans & Objectives. Reviewing the BHC CBP, available staff and resources to meet objectives, the relevance and applicability of the vision, and the BHC’s approach for building a ‘post-aid partnership’ with Ghana considering available resources, local context and UK strategies. Providing learning for staff to inform a strategic refresh of BHC activities. This could be done through the co-creation of an overarching theory of change for the BHC’s activities.

Cross-mission processes and coherence. Providing learning on the coordination and coherence of the UK’s programme and non-programme activities in line with the CBP, Government of Ghana priorities, and wider development partners. Suggesting how cross-cutting issues such as climate, gender and stability could be better integrated across BHC activities in the future. Recommendations are also sought on how best the BHC can deploy its diverse toolbox and improve joint working across the mission to deliver shared objectives.

Development Impact & VfM. Assessing the impact achieved through a sample of BHC development initiatives, including a consideration of how exogenous factors (such as the creation of the FCDO, budget restrictions and others) have affected this impact. Learning and advice is sought on how the UK can offer comparative advantage considering other development partners/multilaterals and GoG priorities. Recommendations are also sought on how the allocation of BHC resources (financial and people) could be adjusted to drive greater development impact and VfM. Given the available resources for the review and the challenges identified in the Evaluability Assessment regarding the measuring of programme results, we expect VfM & impact analysis to be done through case studies on a sample of BHC programmes, rather than in-depth analysis of every programme.

A further objective of this work is that BHC Accra is better able to conduct thorough business planning processes independently in the long term, not just through the evaluation’s recommendations but also through the skills BHC Accra staff build during the process of this evaluation. Therefore, the supplier should, through this evaluation, help build the capability of BHC staff so that they can carry out similar, lighter-touch processes to this end, including for future country business plans beyond the next financial year. Given the absence of an overarching theory of change for the BHC’s work, the supplier could consider the co-creation of this with BHC staff as one possible way to achieve this.
The recipient
The recipient of the portfolio evaluation will be BHC Accra. This will include:
- The High Commissioner, Development Director, and wider senior leadership team.
- Technical advisers.
- Programme and policy teams.
Effective dissemination and discussion of the evaluation’s findings and recommendations is critical to ensure all key stakeholders at BHC Accra understand the learnings and the actions that can be taken to address the learnings. As mentioned above, it is also expected that the supplier will, through their work, help build the capability of key BHC officials to carry out similar, but less extensive reviews independently in the future. This could be through knowledge transfer and transparent accounts of the approaches taken throughout the evaluation.
Scope
The scope for the review should be limited to BHC activities over the last five years, with a view to drawing useful lessons for this and future financial years. We expect the focus will be on the last two years, with the previous three years providing more of a baseline and context for comparison. ICAI’s 2020 report on “The Changing Nature of Aid in Ghana” provides a useful baseline for UK development activities at that time. The supplier will have unlimited access to the material required for the evaluation unless there are confidentiality restrictions.
BHC Plans & Objectives: All BHC teams and activities within scope.
Cross-mission processes and coherence: All BHC teams and activities within scope.
Development Impact & VfM: Only development activities within scope, including programme and non-programme development activities. Whilst the BHC is interested in the question of the impact and VfM of non-development activities, this is not within the scope of this evaluation. Given the breadth of the BHC’s ODA programmes and activities in Ghana, as well as the measurement & attribution challenges identified in the evaluability assessment, we expect only a sample of development activities will be assessed. Learnings should then be used to inform the BHC’s strategic refresh and guide future development work.
The final scope of the review will be agreed through discussion between the BHC Accra and the supplier, with a view to focussing on areas most relevant to the stated objectives. The evaluator may choose to adopt a sampling methodology, given the complexity and breadth of the portfolio. For the BHC’s strategic refresh and cross-mission coherence, sample selection is likely to be driven by the relevance of teams and activities in terms of delivering the country business plan. For development impact & VfM, sampling is likely to be based on the scale of investment and the availability of relevant evidence.
Requirements
The supplier is required to design and implement an approach to the portfolio evaluation, including developing a methodology for sampling, data collection, research, evidence gathering, analysis (including an approach to assessing development impact) and the presentation of findings. The supplier is required to draft a set of evaluation questions to be agreed with the recipient during the inception phase, drawing on the requirements set out in this ToR and the evidence provided by the Evaluability Assessment
The supplier is required to assess all relevant strategies, plans, documents[1] and carry out consultations with BHC staff, Government of Ghana, and other key local stakeholders such as Civil Society Organisations and development partners(access to development partners will be facilitated by the BHC), to inform the portfolio evaluation. An in-depth analysis, synthesising information from a diverse range of sources within (and across) specific areas is required, as well as a holistic approach to identify strengths and weaknesses across programmes/activities to support learning and improvement.
[1] These will be specified during inception, but will include: the White Paper for International Development 2023, BHC Accra Business Country Plan, Programme Documentation, 2020 ICAI Report on aid in Ghana and other relevant strategies.
In addition to secondary data sources, the supplier should gather primary data to inform process, impact and VfM assessments, drawing on BHC and wider stakeholders.
The methodology should employ an appropriate level of quantitative and qualitative techniques to analyse the data, aligned to the nature of programmes agreed within scope of the evaluation.
The supplier must ensure full transparency of the end-to-end approach and is required to share all raw materials and analysis with the recipient in the form of appendices to the final report. FCDO will have unlimited access to all materials produced or used by the supplier for this evaluation
The supplier should effectively quality assure all products before they are shared with FCDO. Draft reports will be reviewed by BHC Accra staff as well as an independent evaluator, with comments then collated and returned to the supplier so the report can be finalised.
The recipient will provide the supplier access to the relevant internal documentation and contacts required for the evaluation.
6.1 Outputs[2]
[2] Details in the outputs table are suggestive and will be agreed with the supplier on contract initiation.
The supplier is required to deliver the following outputs on completion of the portfolio evaluation:
Phase 1: Research Design	Phase 2: Data Collection, analysis and early findings	Phase 3: Final Report and Dissemination
Outputs: / Inception report, outlining research design and methodology (max 10 pages) / Verification workshop with BHC team to ensure agreement on proposed approach	Outputs: / ‘Early Findings’ report covering findings on BHC Plans & objectives, process & coherence.	Outputs: / Final report covering all evaluation components (BHC plans & objectives, processes, coherence, development impact and VfM and recommendations. (including a framework for tracking implementation) / Two report presentations (at least one presented in country)
Main Tasks: / Identification of stakeholders / Initial consultations / Finalise evaluation questions / Identification of data needs and collection methodology / Developing methodology / Designing analysis framework / Verification workshop with recipient to discuss proposed approach	Main Tasks: / Primary and secondary data collection & analysis / Stakeholder consultations / Country visit / Please refer to the processes/effectiveness/impact and value for money framework / Data analysis / Presentation of early findings and facilitated discussion	Main Tasks: / Impact and VfM assessments / Initial drafting and opening for comments / Finalising the report / Internal QA. / Preparation of the presentation and dissemination sessions / Country visit
Timeframe – 8 weeks / 4 weeks to deliver Draft Inception Report / 4 weeks to Finalise Inception Report incorporating BHC feedback	Timeframe – 10 weeks / 10 weeks to deliver Early Findings Report	Timeframe – 12 weeks / 6 weeks to deliver draft final report / 4 weeks to finalise report incorporating BHC feedback / 2 weeks to deliver dissemination workshops

6.2 Evaluation Components
The supplier is required to agree and finalise high level evaluation questions during the inception phase. Reference should be paid to the requirements set out below as well as the high level questions suggested in the Evaluability Assessment. The supplier is required to include the following components in the portfolio evaluation applying OECD Evaluation Criteria highlighted in each section below:
Process Assessments[3] (BHC Plans & Objectives & Cross-mission processes and coherence: All BHC teams and activities within scope). The supplier should apply OECD criteria on ‘Relevance’ and Coherence’ to this assessment.
[3] HMG Magenta Book
Relevance: The extent to which the intervention objectives and design respond to beneficiaries, global, country, and partner/institution needs, policies, and priorities, and continue to do so if circumstances change.
Coherence: The compatibility of the intervention with other interventions in a country, sector or institution[4].
[4] OECD Evaluation Criteria
- An assessment of whether key strategies (country business plans, and others of relevance) are well-aligned with the socio-economic context of Ghana, available BHC resources and wider development partner activities Learnings on how future strategies and activities could be better aligned.
- An assessment of whether interventions are being implemented as intended, including learning on what is working more or less well, and why.
- Learning on how well cross-cutting considerations, including gender, climate and stability, have been incorporated across BHC activities and how this could be done better in future.
- An assessment of the extent to which BHC Accra objectives and design respond to beneficiaries and partner needs and priorities (relevance[5]), with recommendations for how the overarching strategy might be refreshed to improve this.
  [5] OECD Evaluation Criteria
- An assessment of the efficiency of the allocation of BHC staff resources in terms of time and technical capability, as well as advice on how this could be better allocated in the future.
Key Question: how could BHC Accra’s strategy and resource allocation be improved to best deliver its overarching goals?
Effectiveness Assessments[6] (Development Impact & VfM: Only development activities within scope). The supplier should apply OECD criteria on ‘Effectiveness’ and ‘Efficiency’ to this assessment.
[6] OECD Evaluation Criteria
Effectiveness: The extent to which the intervention achieved, or is expected to achieve, its objectives, and its results, including any differential results across groups
Efficiency: The extent to which the intervention delivers, or is likely to deliver, results in an economic and timely way.
- An assessment of the extent to which selected BHC development activities are achieving or expected to achieve their objectives, including, where possible, analysis of the results of UK interventions in terms of development impact.
- Learning and recommendations on how resources could be allocated and prioritised to drive greater development effectiveness.
Impact Assessments[7] (Development Impact & VfM: Only development activities within scope): The supplier should apply OECD criteria on ‘Impact’ and ‘Sustainability’ to this assessment.
[7] HMG Magenta Book
Impact: The extent to which the intervention has generated or is expected to generate significant positive or negative, intended or unintended, higher-level effects.
Sustainability: The extent to which the net benefits of the intervention continue, or are likely to continue.
- An assessment of some of the targeted development outcomes that have or have not been delivered or what changes have occurred following BHC Accra interventions (both programme and non-programme).
- Learnings on how positive development impacts can be driven by BHC Accra within its resource envelope
Value for money (Development Impact & VfM: Only development activities within scope). The supplier should apply UK Government Guidance on Value for Money Assessments, from the Magenta Book and Green Book.
- An assessment of whether the allocation of financial and staff resources offers ‘value for money’ in terms of development outcomes.
- Key Question: How has the BHC portfolio (or a relevant sample) delivered value for time and money, including through the prioritisation of allocations, and how could it be further adjusted to deliver more results with less effort and resources?
6.3 Requirements for the supplier team
The supplier is expected to propose the core team with required evaluation experience and expertise to deliver the scope of work. The proposed team should have the right mix (and level) of skills, including understanding of FCDO strategic goals (White Paper, SDGs) and processes (Programme cycle).
Specifically, the team should have the following skills and experience:
  1. Strong and proven expertise implementing a wide range of mixed-method evaluations, including quantitative experimental and non-experimental methods, realist and behavioural methods;
  2. Strong expertise in the dissemination of evaluation findings;
  3. Strong understanding of and experience in primary data collection;
  4. Strong expertise in international development, covering a range of fields;
  5. Strong understanding of UK ODA programming and wider UK policy and processes.
  6. An equitable gender balance within the team.
The evaluation should focus on learning, providing useful, actionable insights and clear recommendations for improvement. It should provide clear and concise findings and propose appropriate timeframes for the implementation.
6.4 Risks
The following risks have been identified due to their potential to affect delivery. The supplier is invited to present a mitigation strategy for each risk:
1. Limited internal data to inform impact assessments
2. Availability of and access to key stakeholders
3. Capacity within BHC to understand and apply evaluation learnings
4. Retention of findings and insights among recipient and stakeholders

Performance requirements
KPIs
Reports	Assessment
Reports are received on or before agreed deadlines. / Reports are concise (do not exceed page limits), well-written, cover all areas specified and need no more than 1 round of FCDO comments. / Reports are prefaced by an executive summary of no more than two pages in length. / Robust methodological and analytical approach applied and explained in all reports. / All requirements set out in ToR met	FCDO review of and comments on reports covering content/ quality and timeliness. / The inception and final reports will be quality assured independently by FCDO’s Evaluation Quality Assurance and Learning Services (EQuALS).
Dissemination
Presentations are clear and set out recommendations and framework for their implementation. / Are well delivered and scheduled with sufficient advance notice to ensure key stakeholders can attend.	FCDO review and comments on delivery.

The evaluator should stay objective in their reporting, using evidence to support arguments and recommendations.
Delays in the completion of deliverables must be flagged by the supplier as far in advance as possible.
Constraints and dependencies
Access to documentation, data or experts at BHC Accra may be constrained by classifications and availability of key stakeholders. Capacity at post to support the review is assessed as adequate, although this could change on account of unexpected changes in the Ghana context that require a reallocation of staff resource.
Reporting
A full set of reporting deliverables is outlined in Section 6.1. In addition, the supplier is required to provide the following reporting updates:
1. Monthly progress updates to recipients: via email to the contract management team setting out work competed, planned work, challenges and risks.
2. Early findings report: brief descriptive report setting out initial findings from the study.
3. Final report and presentations: as set out in Section 6.1.

Use and influence
The findings from this evaluation will be used to inform approaches to strategy and delivery across BHC Accra. The supplier is required to produce a dissemination plan setting out how the findings will be shared with the recipients and an approach for the recipient to implement the recommendations identified through the study.
Administrative arrangement
The study would be supported through The Evidence Fund, an FCDO programme intended to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2022, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects, conduct due diligence assessments on prospective sub- contracted Research Pool providers, where relevant, and ​​​​manage research and evaluation contracting.
Timeframe, deliverables, and budget
The supplier’s work is expected to be finalised within 7 months. The indicative timeline for activities is set out below:
Milestone	Task	Estimated Timeframe
Output 1	Draft Inception Report, including research methodology	6 weeks following award
Output 2	Final Inception Report	8 weeks following award
Output 3	Early Findings Report	18 weeks following award
Output 4	Draft Final Report	24 weeks following award
Output 5	Final Report	28 weeks following award
Output 6	Dissemination workshops	30 weeks following award

The total budget for the study should not exceed £200,000.00 excluding taxes. Costs of workshops should be explicitly built into the budget.
Bidding Process:
Technical and financial proposals should be sent as two separate files to uk_evidence_fund_administration@pwc.com by April 12th (17:00 GMT). Since these will be assessed independently of each other, they should, in no case, be combined or cross-referenced.
The instructions for submitting the tender and details on scoring methodology and evaluation criteria are detailed in ITT Volume 1. The application forms for submitting the technical proposal (sent as a clearly titled PDF file) are detailed in ITT Volume 3 and ITT Volume 4 provides the Pro Formas for the commercial proposal.
Assessment criteria:
FCDO will assess all bids using the following criteria, designed to ensure a fair review process.
Criteria	Weighting
Relevant team skills and experience	30%
Proposed approach to meeting ToR and applying HMG/OECD best practices, including: / Approach to meeting overall objectives / Initial approach to meeting evaluation requirements (methodological and analytical approaches) / Approach to dissemination and learning.	55%
Risk mitigation approaches	15%

Bids will be scored using the following ratings:
Rating	Description	Explanation
4	Excellent	The criterion was fully met (or exceeded) and there were no shortcomings
3	Good	The criterion was met with only minor shortcomings
2	Fair	The criterion was partially met with some shortcomings
1	Unsatisfactory	There were major shortcomings in meeting requirements

FCDO Coordination – consultations across BHC Accra
This work will be jointly led by Infrastructure & Climate Finance Advisor, Magdalena Leisten Johansson, and Economic Advisor, Harry Fisher, with technical support from Results Advisor, Hinnd Mohamed. They will oversee the management of the evaluation and ensure delivery is aligned to the TORs. The lead coordinator for the evaluation will be Theophilus Amoah, who will support with logistics and coordination between counterparts across the supplier and BHC Accra. Focal points will also be identified within BHC teams for whom most engagement is needed so that an overall working group for the evaluation can be agreed from the outset.
In-country and remote consultations are expected and will be facilitated through the evaluation leads, lead coordinator, and relevant technical experts. To ensure everyone has sufficient time to prepare, the supplier should aim to request meetings at least 5 working days in advance. A clear agenda and key discussion questions should also be shared in advance to facilitate productive discussions. If questions relate to any specific document, those should be shared beforehand to facilitate informed discussion. The supplier is expected to have read all relevant documentation in advance of stakeholder consultations.
Duty of care
The Supplier is responsible for the safety and well-being of their personnel and relevant third parties affected by their activities under this assignment, including appropriate security arrangements where needed.
General Data Protection Regulation (GDPR)
Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Annex 1, and the standard clause 30 in section 2 of the contract.
Delivery Chain Mapping
In advance of any release of funds, the Supplier will be required to produce a ‘delivery chain risk map’ which should, where possible, identify all partners (funding and non-funding e.g. legal/contributions in kind) involved in the delivery of this study.  This is applicable only if the lead organisation engages downstream partners.
Safeguarding
FCDO places utmost importance on all potential partners’ ability to safeguard children, young people and vulnerable adults they work with from sexual exploitation and abuse, and their ability to protect staff and volunteers. The Supplier Code of Conduct will be included in the terms and conditions of the Contract. New compliance checking mechanisms are now in place to review supplier documentation, their approaches to legal compliance and demonstration of good practice in meeting international principles on labour and ethical employment and to provide assurance that whistleblowing systems are accessible across delivery chains. FCDO will monitor risk and mitigation plans throughout the project cycle. The commitments made by all organisations in receipt of FCDO funding need to provide spending teams with concrete assurance that the new enhanced safeguarding standards are being applied.  The approach will help to promote the adoption of new standards for all organisations in the aid sector.
Ethical principles and standards
Suppliers are required to refer to ethical guidelines available at  https://www.gov.uk/government/publications/dfid-ethical-guidance-for-research-evaluation-and-monitoring-activities.  Bidders should include a statement in their proposals, confirming that the study will comply with ethical guidelines as mentioned above. This is a mandatory requirement.
Research for Development outputs (R4D)
FCDO requires that all final research output(s) from this funding are uploaded to Research for Development Outputs (R4D) on GOV.UK. By law documents published on GOV.UK must comply with the  Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.  This is so they can be used by as many people as possible, including those with disabilities. Further information on open document formats and content accessibility on GOV.UK can be accessed here  https://www.gov.uk/guidance/content-design/planning-content.  Uploading final output(s) to Research for Development Outputs on GOV.UK does not exclude these outputs from being uploaded to other websites or platforms and repositories.

Annex A
Schedule of Processing, Personal Data and Data Subjects
This schedule must be completed by the Parties in collaboration with each-other before the processing of Personal Data under the Contract.
The completed schedule must be agreed formally as part of the contract with FCDO and any changes to the content of this schedule must be agreed formally with FCDO under a Contract Variation.
Description	Details
Identity of the Controller and Processor for each Category of Data Subject	The Parties acknowledge that for the purposes of the Data Protection Legislation, the following status will apply to personal data under this contract: / The Parties acknowledge that Clause 30.2 Protection of Personal Data and 30.4 (Section 2 of the Below Threshold contract) shall not apply for the purposes of the Data Protection Legislation as the Parties are independent Controllers in accordance with Clause 30.3 in respect of Personal Data necessary for the administration and/or fulfilment of this contract”.

​ ANNEX B:
​
​
​
​
​
​
​Evaluability Assessment
​Ghana Portfolio Evaluation
​

​
​
​
​
​
​
​
​
​
​
​​

​​Table of Contents
​
​
​
​
​
​
​
​
​
​
​
​
​
​​

Introduction
The objective of the evaluability assessment was to “assess whether the proposed evaluation questions can be effectively evaluated within the proposed budgets (£200k) and timelines (6 months)”, according to the terms of reference (ToR), with a view to preparing the ToR for the actual portfolio review. The purpose of the portfolio review was to assess if the portfolio was effectively delivering against the BHC Country Business Plan (CBP) and if it could be improved 1) to reflect new UK strategies or 2) enhance its impact within the limited available staff and financial resources. This should include also an assessment in relation to the soon to be published White Paper on International Development. Ultimately, the portfolio review should contribute lessons on how best the BHC could structure its work from FY 24/25 and beyond.
The evaluability assessment addressed specifically the following areas:
Clarity of the Ghana Business Plan objectives
Coherence of the portfolio logic, as presented in theories of change/logic models
Availability and quality of data across pillars, tools and selected bilateral programmes
Capacity of BHC Ghana to commission and oversee the portfolio evaluation
Time and budget allocation for the portfolio evaluation
The scope was limited to the past three years, notably the financial years 22/23 and 23/24, with a view to drawing useful lessons for the CBP 24/25 and following cycles of support.
The evaluability assessment findings are presented in the following sections, based on the structure of a standard FCDO ToR, to facilitate the subsequent use of the information for the drafting of the actual portfolio review ToR. Additional, purple text boxes are used to highlight any additional actions or things to keep in mind when drafting the evaluation ToR.

Context
Ghana is a British Investment Partnerships (BIP) priority country and a key middle-income country identified in the International Development Strategy. Having shown years of progress and great potential, Ghana has recently undergone significant challenges following a year overshadowed by economic crisis, culminating in debt default and a $3bn IMF bailout. Further external challenges include hang-over effects of the Covid-19 pandemic and the on-going war in Ukraine.
The government of the United Kingdom (HMG) has faced its own changes and challenges, including the creation of FCDO and a reduction in Ghana’s bilateral ODA budget by almost 90%, from ~£40m four years ago to £4.5m in 2023/24. Based on the desk review, the budget cuts in particular have had a major impact, notably on programming, as well as the resources of the British High Commission (BHC) in Ghana. According to the terms of reference of this evaluability assessment,  “BHC Ghana has worked hard to align its work to the International Development Strategy in the face of resulting resource limitations, notably through deepening the existing partnership with Ghana leveraging particularly UK expertise across HMG, whilst retaining a broad programming footprint in country despite limited funds”.

Ghana portfolio description

Clarity of objectives
Through the merger and inadvertently also the reduction of budget, the overall objectives of the BHC in Ghana have evolved over time. In 2021/22 there was still a distinguishable, intended impact sought in Ghana:

“A safer, healthier Ghana (and Togo, Benin and Burkina Faso), which is the first democratic African country to move beyond aid and is engaging with the UK as a valued partner of choice for security, trade and sustainable economic development. Ghana and the diaspora use their regional and international influence to further our shared values and priorities including through establishment of the African Continental Free Trade Area”.

This impact statement highlighted the post-aid status of Ghana and the mutual benefits of the relationship between Ghana and the UK, which was now on a more equal footing. This was no longer the case in 2022/23. The Ghana Delivery Plan 2023 only referred to five distinct pillars of support, as well as the One HMG toolbox; there was no more overall impact or shared objective statement. According to interviews, the introduction to the Ghana Delivery Plan 2023 could serve this function:

“Ghana’s leadership in West Africa, across the continent and on the global stage continues and is strengthened, influencing others in line with the UK interests and values. Ghana overcomes its current economic crisis and moves towards a stable, prosperous and climate-resilient future, including moving beyond aid over the medium to longer term. The UK remains a valued partner for security, democracy, trade, economic and human development, climate, science and innovation, with Ghana as an active partner in a relationship that supports the UK national interests. The British-Ghanaian diaspora uses their regional and international influence to further our shared values and priorities”.
There is a greater focus on listing the numerous “means to an end” including fostering the relationship and promoting UK interests.  Based on the desk review and discussions, potential ingredients for a common vision can be found in the phrase highlighted in bold “a stable, prosperous and climate-resilient future”  including references to the aim of a “modern “, “post-aid” Ghana, as well as green growth. Notably, there is no reference to poverty alleviation or more marginalised and vulnerable groups.
Two of the nine reviewed bilateral programmes also no longer had impact or outcome statements, purportedly to remain proportional and align with their curtailed resources.
There were fewer references to poverty alleviation, women and girls and other more marginalised and vulnerable groups, in the latest strategic documentation (e.g. CBP 2021/22, 2023), with the exception of the climate pillar and women and girls pillar, respectively. Among the reviewed programmes, only Financial Sector Deepening Africa continued the strong focus on gender equality, but here the annual review and logframe were both dated to 2020.
There was substantially greater emphasis on the promotion of UK national interests. In 2023 Ghana was termed “an active partner in a relationship that supports the UK national interests”. However, only two of the reviewed programmes included UK interests in their logframes, UK-Ghana Jobs for Economic Transformation and Tackling Serious Organised Crime in Ghana.

CBP Pillars
Instead of a singular vision, mission, objective and sought impact, the latest BHC Accra’s 2023 Country Business Plan (CBP) is divided into five pillars:
- Strengthening Economic Ties
- Delivering a Cleaner, Greener Planet
- Building Defence & Security Partnerships
- Promoting Freedom & Democracy
- Empowering Women & Girls
The CBP toolbox covers: “Consular, Soft Power, Programming, Influence, Advocacy, Expertise, Analysis, Diaspora, Diplomacy, Comms”.

Bilateral programmes
With the “programming” tool from this kit, according to the ToR, BHC Ghana currently delivers nine1 bilateral programmes and is supported to differing degrees by several other centrally managed programmes. BHC Ghana provided the following list of nine active bilateral projects for the review:

Jobs & economic transformation
Ghana revenue programme
Leave no one behind programme
Education beyond aid Ghana
Partnerships beyond aid
Tackling serious organised crime in Ghana
Agriculture transformation in Ghana
Financial sector deepening Africa (CMP that we also fund bilaterally)
Cities & infrastructure for growth (also CMP).
Programming covers a wide breadth of themes including, private sector development, human development, governance, serious organised crime, and public financial management, among others.
Notably, at least two of the reviewed programme annual reviews argued that there had been no need to adjust the degree of ambition in their objectives, despite the substantial budget cuts. Many recognized that with the waves of reductions, cutting back on these ambitions would eventually be required. As not all of the annual reviews and log frames had been updated recently (at least 3/7 reviewed programmes), it is also not completely clear if they still provide an accurate description of their programme objectives and targets.
The evaluation should also cover distinct initiatives, such as the work of the United Kingdom Ghana Business Council.

Logic models & theories of change

CBP theory of change
The CBP does not have an overall, shared theory of change among its pillars to orient its tools. Based on limited consultations and input from management and some key staff2 at the BHC Ghana, the headline of the Ghana Delivery Plan 2023 is what should guide joint efforts:
“Ghana’s leadership in West Africa, across the continent and on the global stage continues and is strengthened, influencing others in line with the UK interests and values. Ghana overcomes its current economic crisis and moves towards a stable, prosperous and climate-resilient future, including moving beyond aid over the medium to longer term. The UK remains a valued partner for security, democracy, trade, economic and human development, climate, science and innovation, with Ghana as an active partner in a relationship that supports the UK national interests. The British-Ghanaian diaspora uses their regional and international influence to further our shared values and priorities”.
Attention is drawn to the multiple objectives and themes covered, whether in security, democracy, trade, economic and human development, climate, science and innovation. The CBP may benefit from a review and co-creation of a shared objective that is more specific and measurable across these themes and HMG departments.

Pillar theories of change
Each of the pillars has developed pillar-specific theories of change. Nevertheless, the TOC approach across pillars has not been completely harmonized.

While each has its own objective, the individual TOCs do not refer to a  shared objective across the portfolio, for example, in the way that poverty alleviation has for programming work, at least in the past (see above). Poverty alleviation is reflected only in the objective of the Delivering a cleaner, greener planet pillar, and as one of the outcomes of the Empowering women and girls pillar. Jobs appear only in the Delivering a cleaner, greener planet TOC, but not prominently in Resilient and productive economies nor Empowering women and girls. UK interests are represented across four of the pillars and are no longer designated as “secondary benefits”.  Only “Providing insight and analysis” is identified as a shared outcome (or rather an activity) in the Resilient and productive economies pillar, but it is then not reflected among the other pillar logics.

The pillar TOCs have also not been harmonized in their development process and presentation. There is limited shared understanding of different levels of impacts/objectives/outcomes and outputs. At the lowest level of the logic, there is a mix of activities, outputs, partnership fora, and funded programmes among all the TOCs. Some TOCs simply “stack” objectives, stating very similar objectives repeatedly at different levels of the logic (e.g. Girls’ education) Some have more coherent causal logics between short term and long-term results (e.g. Promoting freedom and democracy) than others (e.g. Delivering a cleaner, greener planet). The expectation is not that the logics are linear but that shorter term outcomes lead to longer term ones or that interdependencies are clearly demonstrated.

It is also not clear how the different pillar logics will support each other, among each other, between different HMG agencies or with other donors. Considering the limited resources, a division of labour with other donors could have and should have been factored, especially when the degree of ambition in overall objectives was not adjusted. This could be represented through the assumptions or otherwise.

None refer sufficiently and specifically to the people being influenced by the interventions; “who needs to change and how?” Gender and inclusion are strongly represented in the Empowering women and girls pillar TOC, but not in any of the others.

None of the TOCs have outlined assumptions underlying the causal logic, though one pillar, Delivering a cleaner, greener planet, outline risks.

Despite the fact that financial resources have been reduced by 90% over four years, this is not reflected in any adjustment to the variety of objectives and outcomes demonstrated across the pillar TOCs nor the degree of ambition in the expected outcomes and objectives. The degree of attribution is also not referenced or adjusted downward as a result of the budget cuts.

If value for money was to be obtained through the use of central or UK expertise, this is also not represented in the TOCs, though the connected results frameworks do indicate staff time commitments (%). While the shift from direct service delivery to advice and advocacy should entail a substantial alteration in the pathways of change, this new logic is little apparent among the TOCs, except the Building defence & security partnerships pillar, where the logic may be made more explicit for the first time.
The weaknesses identified among all five TOCs may speak to the MEL capacity or simply staff time at the BHC Ghana.

Evaluation purpose, scope and objectives
The main focus of the portfolio evaluation is on learning, with a view to informing the BHC’s upcoming programme and portfolio refresh. BHC Ghana is planning to consolidate the programme portfolio, also as the ODA budget is due to increase significantly, according to the evaluability assessment ToR. Therefore, the evaluation and related evidence can contribute to determining how the portfolio could be adapted and scaled-up to better deliver BHC Ghana and wider HMG objectives.
Based on engagement and discussions with various staff at the BHC, to be useful, the evaluation should deliver the following; 1) good advice and standards to meet on the overall clarity and quality of the strategy, its objectives and achieved results, as well as the alignment of both CMP and CBP activities and tools; 2) their sufficient representation in the TOC(s), as well as their measurement and assessment through rigorous results management; and  3)  advice on making better related “value for money” decisions, to achieve better results for the resources allocated.
A key decision for the BHC is whether to continue to try to cover a broad range of areas & interventions with a limited budget for each intervention, or if it would be more effective to prioritise fewer, deeper interventions with greater resources. Both the value delivered through results, as well as the money and the time commitment required from staff should be reviewed. According to the ToR, “with a reduced bilateral budget, BHC Ghana has tried to use flexible financing to provide time-critical technical support as and when opportunities have emerged. The evaluation could helpfully assess whether such interventions have had the desired diplomatic and development impacts, with findings used to inform the BHC Ghana approach to allocating flexible funding throughout the year. The evaluation could also usefully assess how BHC Ghana is leveraging UK expertise and CMPs, providing evidence on how these can better be harnessed to deliver UK objectives”.  There is a real need to translate what worked and did not work so well, for future planning and programming.

The portfolio evaluation therefore has the following, more specific objectives:

Outcome objectives

- Inform an improved CBP and other related, key processes
- Consider how the BHC Accra is fostering the sought post-aid relationship with Ghana and how this is perceived by the government and key partners
- Assess and facilitate the definition of a cross-HMG vision of a shared mission and objectives of the BHC Accra portfolio (through the review and further elaboration of a shared TOC across the portfolio)
- Consider the coherence of the portfolio with new UK strategies, including the soon to be published White Paper on International Development and assess the results and performance of the various CBP pillars and CBP tools
- Assess if and how the BHC portfolio is delivering value for money, where measurable results can be demonstrated, through efficient decision-making and other processes

Process objectives

- To evaluate the efficiency, including both value for money and “value for time” of the BHC portfolio by considering efficiency of both budget and staff allocation
- Determine whether a wide range of thematic focus areas and interventions with less human and financial resources or a narrower, but better resourced approach is more effective

Evaluation approach and questions

Contribution vs. attribution
In light of the substantial shifts in approach and cuts in resources, the evaluation approach will face difficulties in attributing results to given GBP tools and specific interventions. An emphasis on their contribution, for example, through theory-based approaches is more amenable to these circumstances. Strengthening the overall basis of the portfolio evaluation through a facilitated review of the CBP TOC, along with its pillars would also be useful for BHC Ghana, including inter-agency coordination. There is no expectation of an experimental/quasi-experimental approach to any of the data collection.

Prioritisation of evaluation criteria

The evaluation should place particular emphasis on understanding the relevance of the BHC for the post-aid partnership with Ghana, as well as its coherence with the substantially adjusted strategies of the UK government, including the centralization of support, coordination across UK agencies and substantially reduced budget and staff resources. The assessment of coherence should also include the perception of Ghana and its key partners of these adjusted strategies. Lessons should particularly be drawn on the value for money of the work of the BHC, including all four E’s3, including effectiveness and results achieved. The BHC is particularly interested in understanding and improving the process of decision-making, with a view to the effectiveness of the portfolio; the results and value generated with the available time and prioritisation of allocations, including the tension between the breadth and depth within the portfolio.
Less attention should be given to the impact of the portfolio, namely due to substantial changes in approach, limited resources and challenges to it evaluability. While the ownership by the government of Ghana is critical for the relevance of support to its own objectives, the sustainability criteria is also less central than relevance, coherence, effectiveness and efficiency, notably of the BHC decision-making process.

Draft evaluation questions
The draft evaluation questions in the evaluability assessment ToR were reviewed extensively, in a participatory manner with BHC Ghana during the evaluability assessment. There are three main evaluation questions (see below). The evaluators should be encouraged to review and further specify these questions, including the potential definition of related sub-questions with a view to fully understanding and addressing the information needs of the BHC. For example, sub-questions should be developed around the post-aid, sustainable partnership, external perceptions of the adjusted UK strategies and to further integrate cross-cutting issues, such as gender, the focus on the more vulnerable Northern Ghana, climate change, as well as conflict-sensitivity.
How has the BHC Accra developed and deepened a long-term, post-aid sustainable partnership with Ghana and how could this relationship be further improved?
How does UK engagement in Ghana, including the CBP, represent a shared, cross-HMG vision and sought impact, including attention to more vulnerable groups (e.g.women and girls) that uses all of the tools in the CBP tool box and reflects new UK strategies, such as the International Development Strategy, Integrated Review and soon to be published White Paper on International Development? How could internal coherence and coordination be further improved?
How has the BHC portfolio delivered value for time and money, including through the prioritisation of allocations, and how could it be further adjusted to deliver more results with less effort and resources?
These evaluation questions and a draft evaluation framework can be found in appendix 1.

Evaluability assessment
An independent, external evaluability assessment was commissioned through EQUALS to facilitate the participatory review of the evaluation purpose, objectives, evaluation questions, as well as the existing TOC  and results framework, including the availability and quality of data down to the level of the individual programmes in the Ghana BHC portfolio. The results of the review of the overall evaluation framework, including the evaluation questions and the TOC were presented above. The remainder of this report will hone in on the data availability and data quality, including its reliability and validity, across the portfolio, including at the level of the main pillars and individual projects.
Overall, while the programming modality remains very evaluable, especially in relation to output performance, greater challenges relate to tracing the effect of individual programmes and projects at the outcome level and understanding aggregate performance beyond overly simple metrics, such as the number of beneficiaries reached. More effort will be required in ensuring the evaluability of other pillars and tools, where greater effort will be required for establishing the related TOC/pathways of change, KPIs, as well as in primary data collection (e.g. survey, interviews).
Data availability and quality across programmes
Based on data availability across the CBP, programming remains the most evaluable among the pillars, though there are concerns around the deterioration in the quality of log frames, including the definition of key performance metrics, as well as the availability of relevant, quality data. Here, also the assessment of performance against outputs is the easiest to reliably assess and aggregate, due to the use of the standardised annual review methodology and availability of output data.
The availability and quality of documentation was the highest at the level of individual programmes. The assessment of output performance remains straight-forward, even at the aggregate portfolio-wide level through the comprehensive application of the standardised annual review methodology and related availability of output data.
It will be more challenging to assess results at the outcome and impact level. Here there is very limited monitoring data available, often restricted to the number of beneficiaries reached, disaggregated by sex. According to the ToR, very few evaluations have been conducted that would have attempted measurement at these levels, also due to limited resources. Any evaluation findings would be mentioned also in Project Completion Reports, where projects are already concluded.
As a part of the evaluability assessment, a desk review of existing documents at the strategic, pillar/portfolio and individual programme (nine bilateral programmes in total) was conducted, with a view to assessing their availability and quality for the portfolio evaluation. Strategic and portfolio wide documents included CBPs, partnership plans, cross-HMG plans and financial management data, including budget and spend from 2019 – 2023. Pillar documentation included the detailed review of the individual TOCs and delivery monitoring plans.
Programme documentation included business cases, contracts, memoranda of understanding, related addenda, log-frames/results frameworks and annual reviews. Additional progress reports may also be available from contractors, in the few cases they are still used, but are not uploaded onto Devtracker. These were not reviewed for any of the bilateral programmes as a part of the evaluability assessment. For the programmes, the main focus was on the review of the latest log frame (and changes made), as well as the annual reviews, as a comprehensive source of output data and assessment of related performance.
Overall, the degree of evaluability of individual programmes is the highest, among the CBP tools. The availability and quality of documentation and data was the highest at the level of individual programmes, presumably due to the strength of the FCDO programming modality, including the availability of expected, standards, established procedures, related guidance and templates (e.g. business plan and log frame templates, annual reviews). More recent log frames were sparce on detail, with weaker KPIs and related data collection. The presentation of up-to-date actual data in the log frame itself was an exception, with only the Education Beyond Aid Ghana programme doing so. Data on output indicators was more readily available in annual reviews.
Three programmes4 did not have the latest annual review and two programmes did not have a recent update to their log frame uploaded to Devtracker. This information may nevertheless be available with project teams. Outcome indicators were designated for all the reviewed programmes with the exception of Agriculture transformation in Ghana, where it appears all related work was halted due to the substantial budget reduction from a total budget of £32m to £2.47m and spending freeze. The Agriculture transformation in Ghana log frame was particularly affected, basically with no data entry at all on the results logic, indicators, nor targets. Only two programmes5 had outcome values in the log frame and reported actual (not only planned targets) data in the log frame itself. The availability of baseline data was less of an issue, as only two programmes were missing this data.6
KPIs, where used, generally reflected sector standards (e.g. Donor Committee for Enterprise Development (DCED) standards on private sector development indicators, education metrics). Nevertheless, there appears to be a somewhat worrying trend to reduce reliance of robust KPIs, replacing them with qualitative description of, for example, activity progress7. At times, the same KPI was used at different levels of the programme logic.8
The overall quality of the log frame of the Cities & infrastructure for growth was particularly high, potentially attributable to the role of the independent MEL contractor.
The composite annual review score provides a useful aggregate indicator of output-related performance. Five programmes scored an overall “A”, meaning that they met expectations and only two programmes an “A+”, moderately exceeding expectations, with no recent annual review data available for Partnerships beyond aid.
All of the reviewed programmes were affected by the spending cuts, with the exception of Education beyond aid Ghana, presumably as it was coming to an end. Design repercussions ranged from reductions in thematic scope, major pivot from service delivery to technical assistance, cancelled procurements for contractors and postponed MEL work (e.g. baseline data collection, TOC and log frame development). Further adjustments to programme scope, with expected repercussions on TOCs and performance targets are expected. Already two programmes do not have any impact or outcome statements, as support is so minimal that change cannot be expected at these levels.

Data availability and quality across pillars
Data availability and quality differs across the five CBP pillars, being the strongest in the pillars with established programming (e.g. Strengthening economic ties, Empowering women and girls) than in areas such as security and defence with a shorter tradition of results measurement. Reliance on KPIs from programming remained high though notable efforts have been made to generate metrics also around advocacy, governance reforms, as well as peace and security. A wide attribution gap between planned activities and high-level outcome KPIs remained an issue across most pillars.

Table 1 Evaluability of the Ghana CBP Pillars
Pillar	Quality of KPIs	Data availability	Data quality reliability/validity	Comment
Strengthening Economic Ties	Green	Green	Reliable secondary data sources	Well established, high standard KPIs
Delivering a Cleaner, Greener Planet	Yellow	n/a	Standard ICF measurement methodology increases data quality, but less present in 2023.	ICF indicators used in 2021/22 but not in 2023. but data could not be verified. A mix of outcome and output/activity indicators.
Building Defence and Security Partnerships	Red	Yellow	n/a	Limited to no KPIs, though effective activity and output monitoring.
Promoting freedom and democracy	Yellow	Yellow	Attribution gap to global indices is extremely wide. CPI cannot be monitored over time.	Data availability from secondary sources can be presumed, but could not be verified.
Empowering women and girls	Green	Green	Attribution gap can be very wide between resourced activities and very high level outcomes.	Well established KPIs (see attribution). Data availability beyond the specific programmes could not be verified.

Proposed evaluation methods, data collection and analysis
The data collection and analysis methods should be as rigorous and robust as possible within the resource framework. They should be identified and tailored to answer the agreed evaluation questions and to collect data at the different, relevant levels: strategic (e.g. UK), BHC portfolio/pillar and tool-wide, as well as at the individual programme and initiative (e.g. UK-Ghana Business Council) level.
In light of the complexity of the portfolio and the variety of available tools, it will be critical to also expect a sound sampling methodology, with rigorous selection criteria, at the level of the strategy, portfolio, pillars, programmes, any survey population and interviews with different types of stakeholders. Due to the breadth of the portfolio and tools available, selecting the sample population will inevitably entail that not all pillars, tools and programmes can be reviewed to the same extent.
Mixed-methods, including both quantitative and qualitative tools should be employed, with a view to ensuring the reliability and validity of triangulated findings, as well as capturing learning. Quantitative data can be derived from the existing monitoring system in place, including aggregated data on key performance indicators at the portfolio level, as well as additional indicators at the level of selected programmes. Primary data collection, for example, a survey of HMG and BHC Ghana staff may strengthen the rigour of evaluative findings through a wider net of responses. Considering the emphasis on learning, qualitative primary data collection tools are nevertheless expected to generate the greatest added-value. No large-n, statistically representative survey work with final beneficiaries is expected, as the portfolio has shifted to support technical assistance over service delivery.
Enough interviews should also be conducted with different groups to reach data saturation, as well as to sufficiently represent the views, including of women and also of more marginalized groups.
The scope over time should allow for longitudinal comparison, but still also generate a reasonable amount of information for analysis. While there has been evolution over the past three years, a single comparison point further back in time, where quantitative data is still available and recollection by interviewees is feasible, could be considered (e.g. 2018) .
The evaluation team should summarise the approach, evaluation criteria, questions and methods in a detailed evaluation matrix, as a part of the inception report.

Workplan and outputs
The table below provides a tentative estimate of the man-days required for the standard evaluation and phases required for a portfolio evaluation. The more substantial allocation of resources during the inception phase relates to the required work around the further review and participatory elaboration of the overall TOC and related pathways.
Input from the BHC will entail the dedication of a focal person, as well as engagement, notably from management, during the kick-off meeting, as well as broader engagement for the review of the TOC(s) and specific pathways of change. The sharing of relevant documentation and the identification of interviewees, as well as support around site visits also entails some additional level of effort from BHC. It would be critical that relevant staff take part in the discussion around preliminary findings. With a view to the utility of the process and products of the evaluation, the co-creation of overall conclusions and recommendations is strongly encouraged. The main evaluation deliverables, such as the inception report and the final evaluation report will also require review, also from management.
Table 2 Draft Work Plan
Activity/phase	Days estimated	Output
Inception phase	68 days 6 weeks
Kick-off meeting	5
Initial desk review	15
Initial interviews	5
Participatory TOC review of pillars (ideally in person)	15	Revised Pillar TOCs
Participatory TOC review of CBP (ideally in person)	3	Overall CBP TOC
Evaluation Design	5
Sampling strategy for pillars/tools/programmes	3
Communication and learning plan	1
Inception report	15	Inception report
Implementation phase	68 days 8 weeks
Desk review of portfolio data, including HR and financial data	25
Detailed desk review of a sample of the 9 programmes	15
Interviews of BHC staff, government, private sector, civil society, donors and key programme stakeholders (of a sample of the 9 programmes), including final beneficiaries, where relevant (ideally in person)	20
Site visits (2-3 projects, ideally in person)	6
Facilitated discussion of preliminary findings	1	Powerpoint presentation
Reporting and learning sessions	64 days 4 weeks
Data analysis	20
Draft report	15	Draft evaluation report
Comments on draft report	10 (BHC)
Final report	15
Learning sessions (online)	15	Final evaluation report
TOTAL	Approximately 200 days over 18 weeks

Management

Evaluation team composition and competencies
The evaluation team would ideally consist of a team leader, with substantial experience in the monitoring, evaluation and learning of complex portfolios of programmes, but also experts on different instruments, such as diplomacy, trade & investment, conflict management, and immigration. Ideally, the team should have familiarity across the five pillars. The team should also have strong expertise in portfolio and financial analysis, including VfM analysis. In the spirit of the post-aid partnership, all efforts should be made to identify local expertise to fill these roles. A gender balance should also be sought on the team.

Sufficient flexibility should be given to bidders to determine the seniority and number of staff committed to the assignment.

Embassy resources and capacity to commission and manage the evaluation

The responsible staff for the evaluation at BHC Ghana are highly committed and enthusiastic about the value of the evaluation but also conscious of their limited experience in commissioning evaluations, certainly of this scope and complexity. External support was sought from EQUALS to assess the evaluability of the ambitious portfolio and notably the numerous instruments in the CBP toolbox.

One of the greatest risks of the evaluation is the substantial time constraints of BHC Ghana staff. In order for the evaluation to be truly useful and meaningful in the portfolio refresh process, especially considering the novelty of the joined-up approach there is a need to operate within the prevailing staff and budget constraints. The full commitment, notably from management, but also from staff to the portfolio evaluation terms of reference, the evaluation process itself, the review of key deliverables and most importantly, the implementation of its recommendations is critical.

A more formal governance structure, for example an evaluation reference group that also includes representation from management, may increase the required buy-in and ownership and also ensure accountability of staff to participate in the evaluation.

The evaluation team should also value and prepare a communication and learning plan, ensuring that it is also implemented and regularly monitored and adjusted, if required.

Evaluation budget

An indicative budget maximum of GBP 200,000, inclusive of all expenses, VAT if applicable and that bidders are responsible for all local taxes.

See EQUALS TOR review form for further guidance on the evaluation ToR sections.