## Annual Review Template

Title: ASEAN Economic Reform Programme (AERP)
Programme Value £ (full life): £19,629,802		Review date: June 2023
Programme Code: GB-GOV-50-PF-18-ASEANER	AMP start date: April 2018	AMP end date: June 2023

Summary of Programme Performance
Year	04/2018-08/2019	08/2019-10/2020	09/2020-09/2021	10/2021-03/2023
Overall Output Score	B	A	A	A
Risk Rating	Moderate/Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/810873/Business_case_for_ASEAN_Economic_Reform_PF_Programme.odt
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW

Description of programme
The ASEAN Economic Reform Programme (AERP) aims to achieve inclusive economic growth and poverty reduction in ASEAN, particularly focused on Indonesia, Malaysia, Myanmar, the Philippines, Thailand and Vietnam, by enabling a fairer business environment and deepening financial markets. The programme includes programme-level components on financial services, financial technology (fintech), intellectual property (IP), competition and business regulation, business integrity and anti-corruption.
This is the fourth and the last annual review of the AERP, covering the period October 2021 to March 2023. Originally due to complete in March 2022, a business case extension was approved in May 2022, which allowed the programme to run until 30 June 2023, with all activity finalising by March 2023. The extension increased the value of the business case to £21.4m and extended the programme scope to all 10 ASEAN Member States, adding Cambodia, Laos, Singapore and Brunei (the latter two countries being covered by non-ODA funding).

Summary supporting narrative for the overall score in this review
In the last year of its implementation, AERP achieved significant milestones as most of the output targets were achieved. In addition, the programme also received recognition for its contributions. For example, the ASEAN Secretariat expressed gratitude for the AERP's work on the IP project, which resulted in successful initiatives such as the IP E-commerce Code of Conduct and collaboration with the ASEAN Network of IP Enforcement Experts (ANIEE). AERP was also commended by the Ministry of Finance in Indonesia for its support in strengthening financial sector policies, which facilitated the delivery of outputs aligned with the G20 Financial Inclusion Framework and improvements to the Omnibus Law in the finance sector.
There were some delays to budget allocations during this reporting period, which meant that final budgets were not fully confirmed until Quarter 2. Despite the challenges posed by these budget uncertainties, AERP managed to continue its operations and programme delivery. However, to ensure viability within the shortened timeframe, some activities had to be scaled down and cancelled, compromising the achievement of some intended outputs. The overall success of the programme was reliant on continuous adaptation to the evolving budgetary landscape and effective management of project timelines and resources.

Major lessons and recommendations for the year ahead
AERP officially closed in June 2023, with the majority of activity being completed by March 2023. Therefore, these lessons and recommendations place particular emphasis on actions that could help inform the design of any future economic programming in the ASEAN region.
Stakeholder engagement:
- The FairBiz Project noted that implementation during this reporting period has highlighted the importance of a ‘collective action’ approach – i.e., engagement and collaboration with a range of stakeholders on key areas/issues – for greater impact. The collective action approach has elevated the results and created a momentum that is more likely to sustain the results after the end of the project.
- Government-to-Government cooperation is highly valued by government counterparts. For instance, the British Embassy in Manila was presented with a Plaque of Recognition by the Anti-Red Tape Authority (ARTA) for the UK Government’s continued support on regulatory reform in the Philippines through AERP. Regulatory reform in ASEAN member states (AMS) is often a crowded space with several other international donors operating. However, the UK Government, has been recognised for its thought leadership, expertise and experience on regulatory reform and is one of the only donors to combine knowledge and funding in this way, which is a strong, niche position valued by partner governments.
Recommendation: Future programmes should continue to prioritise Government-to-Government cooperation where the UK can offer specialised support and expertise. In terms of stakeholder engagement, programme design should be cognisant of the benefits of a ‘collective action’ approach, involving government, civil society and the private sector in support of programme objectives.

Monitoring, Evaluation and Learning (MEL):
There appeared to be a lack of detailed understanding regarding the programme MEL expectations amongst some delivery partners, as some delivery partners were not adequately reporting on progress at the outcome level or on the link between output and outcome. This issue was prominent for multiple projects introduced during the current review year. Due to the time constraints of the programme and the urgency to initiate the activities this year, the development of a comprehensive logframe prior the start some projects was delayed. Thus, reporting on the contribution that each project made to the programme’s outcomes has proved to be more challenging than it could have been.
Recommendation: At the outset of any future project delivery, it may be helpful to hold a workshop with all programme managers and delivery partners, to outline FCDO expectations regarding programme management requirements. This could include: an overview of the programme Theory of Change; how to develop log frames and to agree the indicators/targets and how these will be reported; narrative and financial reporting (the importance of reporting and analysing progress against outcomes rather than just output level); expectations of delivery partners regarding gender and inclusion; and FCDO expectations regarding the quality of reporting. Best practice case studies may be helpful in this regard.
Programme Delivery:
Throughout the final year of AERP implementation several smaller new projects were added to the programme. Some of these smaller, short-term projects presented a few challenges for programme delivery, such as setting up each individual project work plan and managing the quality of multiple deliverables. Due to constrained time frames some of these projects struggled to develop MEL tools that seamlessly connected to the AERP portfolio-level logframe, there was room for improvement in risk assessment and mitigation, and there could have been a clearer understanding of stakeholder expectations to maintain the quality of reporting. Whilst the projects were satisfactorily completed, they placed pressure on the capacity of programme managers to meet the end-of-year deadlines.
Recommendation: In planning for future programme, it is essential to exercise caution and deliberation when introducing additional activities during the implementation phase, particularly for short-term projects. Several factors warrant careful consideration, such as assessing the potential contribution of these activities towards achieving the programme-level logframe, managing stakeholders’ expectation, and ensuring that an adequate time frame is allocated for their successful implementation.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
During the review period, no modifications were implemented at the outcomes and impact level of the programme. The intended impact of this programme is to generate more ‘inclusive economic growth and poverty reduction by enabling a fairer business environment and broadening and deepening financial markets’. The programme seeks to do that by delivering three outcomes. These outcomes are then subdivided into a series of more specific ‘intermediary outcomes’ (IO), as summarised below:
Outcome 1: Strengthened and harmonised business environment frameworks.
- Regulators implement Intellectual Property legal, regulatory or policy changes.
- Improved policy and regulatory frameworks to streamline business processes.
- Actions identified to make logistics sector regulations more pro-competitive.
Outcome 2: Improved business practices adopted and corruption risks minimised.
- Improved transparency and integrity policies and practices by government and businesses.
- Strengthened legislation and application of judicial mechanisms to decrease corruption.
Outcome 3: More inclusive, efficient and diversified financial markets.
- Regulators implement improved capital market policies, regulations and development plans.
- Improved regulatory environment to expand the fintech sector and access to financial services.
- Enhanced ability of Myanmar government to tackle financial crime (cancelled post-coup 2021)

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme's progress towards planned intermediate outcomes and outcomes has continued despite a temporary halt in activity at the start of the financial year due to budget uncertainties. However, assessing the concrete achievement of these objectives during this review period presents challenges. Regulatory programmes working with policy, roadmaps, mandates, amendment and/or establishment of laws and procedures take time to realise concrete changes to policies, mandates, and rules/laws. Furthermore, some intermediate outcome and outcome level indicators in AERP exhibit a high-level perspective, which may have been better suited to measuring the longer-term impacts of the programme rather than providing a realistic assessment of outcomes within the designated timeframe. A further evaluation in two or more years after programme closure could capture any changes more comprehensively.
This review is able to capture early signs of progress towards intermediate outcome level changes which have been used to produce the progress analysis. The data obtained in this period shows clear progress on several intermediate outcome indicators, such as number of laws/proposals implemented to streamline business processes, number of policy recommendations on business environment developed and/or revised as a result of public-private dialogue, and number of measures following international standards and good practices adopted to mitigate and remedy corruption risks at national, sub-national, and sectoral level as the results of output level products and services. The interviews with the programme beneficiaries also indicate a possibility of contribution to changes happening in the long run.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
As the programme closed in June 2023, it is important to reflect upon the assessments and recommendations made during this review period, which will serve as valuable insights for any future programming with similar objectives. Throughout this period, the project has successfully delivered the intended outputs, garnering positive feedback from the beneficiaries. This feedback serves as evidence that the project has effectively addressed the pertinent issues and challenges in the region and also helped to build deeper and stronger relationship with key government, business, and civil society stakeholders.
The success of the programme is partly evidenced by the on-going design of a similar new programme, the ASEAN Economic Integration Programme. Regional diagnostics, and a review of mutual priorities in ASEAN, have confirmed that the areas that AERP was addressing remain important and relevant. The new programme will build on the success of AERP, particularly for the work on regulatory reform and financial services. The new programme design has already used the experience and lessons learned from AERP to ensure that best practice is maintained, whilst learning lessons from the challenges AERP has faced and how these have been addressed.

## C. DETAILED OUTPUT SCORING

Output Title	FSIP: Inclusive Intellectual Property (IP) capacity building through knowledge sharing and technical assistance to improve IP and related legal/policy frameworks, regulation and practices
Output number:		1A	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
No. of new or improved IP policies, standards and regulations including targets, mandates, incentives and roadmaps that have benefitted from FSIP’s support	2022 Planned: 11	2022 Achieved: 11

Briefly describe the output’s activities and provide supporting narrative for the score.
This output aims to promote and improve the protection of Intellectual Property Rights (IPR) and strengthen the legal basis for IP protection as well as enforcement of these regulations across five ASEAN countries: Cambodia, Indonesia, Myanmar, the Philippines, and Vietnam, through the provision of technical advice, capacity building and knowledge sharing assistance. The output was completed in March 2022, with the following notable milestones:

In Indonesia: A working paper on ‘Elements for an SME IP Finance System’ in Indonesia covering key IP policies to drive renewable energy technologies was submitted to the Ministry of Law and Human Rights and a report on ‘E-commerce IP enforcement regulatory regime’ in Indonesia was submitted to the Ministry of Law and Human Rights, Ministry of Communication and Informatics, and Ministry of Trade, with suggestions for the ministries to take this discussion forward after the FSIP closure.
- In Cambodia: An IP enforcement manual with business related advice/commentary was published and launched in cooperation with the British Chamber of Commerce. In addition, an IP Q&A guide on IP enforcement was produced and handed over to the lead stakeholder. A webinar was organised to promote the manual, and it has been uploaded on the website and shared to individuals electronically.
- In the Philippines: The project provided technical assistance to support a study and recommendations report on the e-commerce regulatory regime. A Memorandum of Understanding (MoU) was signed between an e-commerce platform and relevant IP owners to cooperate on tackling counterfeit items online with the support of the Intellectual Property Office of the Philippines (IPOPHL). In addition, a research and recommendation report on the e-commerce regulatory regime was published and support for implementing the recommendations was provided. The output also supported technical assistance to support a consultation, research and a report on the IP customs system and submitted a best practice report to the lead stakeholder. Using these recommendations, the stakeholder will be able to compare custom seizures, which can help to improve the overall custom enforcement system.
- In Vietnam: The project supported the government with consultations, workshops, research, and recommendations to strengthen the policy environment and IP ecosystem in Vietnam. The deliverables included: recommendations to build an effective IP finance ecosystem which analyses the obstacles of local Small and Medium Enterprises (SMEs) in accessing debt financing due to the lack of tangible collateral, a recommendation on IP enforcement coordination which was then shared with the Deputy Prime Minister of Vietnam and support to strengthen the IP function within the creative economy sector.

Assess the Value for Money (VfM) of this output compared to the proposition in the Business Case, based on performance over the past year.
During this review period, the COVID-19 pandemic continues to persist in ASEAN. The delivery partner was still required to employ virtual methods to deliver their activities. The virtual delivery has enabled AERP to reach an increased number of participants, without additional costs, enabling greater reach of the activities. In addition, virtual delivery has led to a reduction of travel costs and led to overall cost savings. However, virtual delivery also created challenges around level of engagement, participation, and feedback. Interaction with the stakeholders indicated that some of them would have preferred to have in-person sessions.

The output’s target of 11 new or improved IP policies, standards, and regulations, including targets, mandates, incentives, and roadmaps, that have benefited from FSIP’s support, has been fully accomplished prior to the official conclusion of AERP. Sufficient time has been invested in building strong relationships with beneficiaries and ensuring their buy-in for the success of this output. A future programme could be developed based on these achievements.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes to this output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
No specific recommendations were made about this output in the previous AR.

Output Title	In-House IP: Inclusive IP capacity building through knowledge sharing and technical assistance to improve IP and related legal/policy frameworks, regulation and practices
Output number:		1B	Output Score:	A+
Impact weighting (%):		3	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1b-a. Number of delegates reporting having used learning from the capacity building activities after 6 months	Planned (2021): 45 / Planned (2022): 40	2021 Achieved: 2 / 2022 Exceeded (Achieved: 65)
2b-a. Number of non-PF funded industry speakers delivering sessions at each capacity building seminar	Planned (2021): 2 / Planned (2022): 10	2021 Exceeded (Achieved: 90) / 2022 Exceeded (Achieved: 15)

Briefly describe the output’s activities and provide supporting narrative for the score.
The In-house IP Project is delivered by FCDO in collaboration with the UK Intellectual Property Office (IPO). The majority of activity is capacity building through training across two strands: IP enforcement and IP innovation. The indicators data were primarily obtained from the following sessions:

- The UK-ASEAN IP Innovation Webinar on 8 November 2021. The theme of the seminar was ‘Build Back Better: IP innovation for Micro-, Small and Medium-Sized Enterprises (MSMEs)’. The sessions focussed on understanding IP and digital, and the tools which governments can enact to encourage innovation to support MSMEs. The seminar also identified the IP challenges faced by MSMEs and how government policies / programmes can be more tailored to address these challenges.
- On 26-27 September 2022, the UK-ASEAN Intellectual Property Enforcement Seminar 2022 and ANIEE meeting was held in Manila, Philippines. The seminar discussed selected topics related to e-commerce, customs, and free trade zones. It was organised by the UK IPO in partnership with the ASEAN Secretariat and the Intellectual Property Office of the Philippines. The seminar also served as an avenue to inspire other ASEAN Member States to replicate the FSIP-supported work in the Philippines which aims to curb counterfeiting and online piracy.
Assess the Value for Money (VfM) of this output compared to the proposition in the Business Case, based on performance over the past year.
The Business Case set out the objective to ‘progress implementing an ASEAN IP action plan, especially on enforcement, including online trademark infringement and engaging regional online intermediary platforms on their IP policy.’ Through this activity, there has been an indication that the delivered activities will demonstrate progress in achieving the targets at the intermediate outcome level as the delivery partner reported participants have actively used the learning and knowledge gained from the training activities in their work. This output added further secondary benefits by highlighting the UK’s expertise and assistance on IP enforcement and innovation, thereby improving relationships and consolidating the UK’s position as a strong ASEAN partner on IP enforcement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There are no changes to this output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
There are no recommendations from the previous AR.

Output Title	ROUSE: New or improved policies, standards, and regulations.
Output number:		1C	Output Score:	A
Impact weighting (%):		3	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
1c-a. No. of new or improved IP policies, standards and regulations including targets, mandates, incentives and roadmaps that have benefitted from the project's support.	2023 Planned: 2	2023 Achieved: 2

Briefly describe the output’s activities and provide supporting narrative for the score.
This output aims to simplify and strengthen IP enforcement for e-commerce in ASEAN so that local and international businesses, including UK businesses, can leverage e-commerce channels to safely conduct business with effective solutions against piracy and counterfeits, and consumers will not be harmed by dangerous or sub-standard counterfeit products sold online. Over this period, Rouse planned to deliver two stages of deliverables under two separate contracts. The first included three distinct activities:

- Indonesia IP e-commerce: Coordination and consultation meetings were held between Rouse, UK IPO, and the relevant ministries to discuss issues relating to e-commerce IP enforcement and to develop an MoU to overcome the sale of counterfeit goods in e-commerce platforms. In addition, technical assistance was provided to support the Government of Indonesia to understand the overlap between the different government rules on e-commerce and to address the issue through an MoU, aligned with the approach taken in the Philippines and Thailand. A Focused Group Discussion (FGD) was conducted and brought together over 90 attendees, including IP owners, government representatives, e-commerce platforms, and supporting organisations aiming to collect inputs on the draft of MoU. A draft MoU is now in place, which serves as code of conduct among e-commerce industry players, including online platforms and IP owners to prevent counterfeit product sold online.
- Cambodia e-commerce: Support was provided to identify the impact of Cambodia’s new e-commerce law for IP enforcement of infringing goods on e-commerce platforms. The technical assistance supported the Government to understand the issues relating to e-commerce IP enforcement and strengthen the ability to address it with long term solutions (regulatory changes) or medium-term solutions (code of conduct).
- Gap Analysis on ASEAN IP E-Commerce Landscape: A region-wide comparative analysis was conducted to provide the ASEAN Working Group on Intellectual Property Cooperation (AWGIPC) and its IP offices with an understanding of the regulatory gaps that exist at a national level and to provide recommendations to help to address them. In addition, the project deliverables will inform the roadmap for ASEAN to move towards a harmonised IP regime that will enable better trade facilitation. The Gap Analysis report was launched with the ASEAN Secretariat on 5 March 2023. The report supports a number of ASEAN Economic Community roadmaps and priorities (e.g., ASEAN IPR Action Plan, ASEAN Agreement on E-commerce, ASEAN Digital Integration Index) and was given ASEAN Annual Priority Status by the AWGIPC.
A second contract was then agreed with Rouse (April – June 2023) to allow for the completion of the work on the Indonesian draft e-commerce MoU. Two outputs included the negotiation and agreement of a draft MoU and the organisation of a signing ceremony and agreeing next steps. The final AERP Programme Completion Review (PCR) will provide updates on the delivery of these outputs.

Assess the Value for Money (VfM) of this output compared to the proposition in the Business Case, based on performance over the past year.
The delivery partner successfully established cooperation with the relevant government stakeholders through extensive engagement, leading to strong working relationships. This has opened up possibilities for long-term cooperation on IP in the region. The output also led to significant benefits, including engagement with various IP owners, and e-commerce platforms, generating wider interest and support for the programme from the private sector. The engagement with ASEAN has set the stage for future action on e-commerce IP issues, driving growth in this area and, as a secondary benefit, providing additional value to international companies, including UK companies, by promoting a transparent and lawful e-commerce economic landscape, freer from the challenges posed by counterfeit products.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This output was introduced in 22/23 as part of the programme extension to cover IP topics relating to e-commerce.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
No recommendations from the previous AR since the output was introduced at the end of Year 3 for implementation in Year 4. For any future similar projects, the time frame should be carefully considered. Sufficient time is required to design, implement, and assess the project’s achievements. This is due to the substantial scope of the project, involving extensive collaboration between governments, e-commerce platforms, and IP owners. Ensuring effective coordination and understanding of issues, approach, roles, and responsibilities across government agencies who often have different priorities is important.

Output Title	Increased capacity building and collaboration for government stakeholders to improve regulatory practices
Output number:		2	Output Score:	A
Impact weighting (%):		18%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
RDI/BEIS: 2a. Number of recommendations proposed for adoption by GoPh, GoV or GoI to implement/revise laws, regulations, rules and/or administrative practices to improve business environment (cumulative)	2023 Planned: 9 (cumulative)	2023 Exceeded (Achieved: 15)
RDI/BEIS: 2b. Number of officials trained (cumulative)	2023 Planned: 700 (cumulative)	2023 Not achieved (Achieved: 670)
RDI/BEIS: 2c. % of positive feedback from selected domestic and international business organisations on reform plans and processes and views about future improvement	Planned: 80%	N/A (See narrative below.)
ICC: 2d. Number of delegates participating in the workshops who increased their knowledge and understanding of the development and implementation of electronic transferable records	2023 Planned: 150	2023 Exceeded (Achieved: 211)
OCP: 2e. Delivery of an action plan containing options for open contracting implementation and next steps for Bangkok Metropolitan Administration’s procurement system that promotes open contracting in Thailand	2023 Planned: 1	2023 Achieved: 1
ODI: 2f. Delivery of an action plan containing a roadmap and recommendations for Bangkok Metropolitan Administration to become an open city that promotes the use of open data in Thailand	2023 Planned: 1	2023 Achieved: 1
ASLIP: 2g. Number of delegates from ASEAN Member States who participated in the ASEAN Sustainable Leadership in Infrastructure Programme (ASLIP)	2023 Planned: 10	2023 Achieved: 16
ASLIP: 2h. Development of an executive leadership programme on sustainable infrastructure agreed by ASEAN and accredited by Cambridge University	2023 Planned: 1	2023 Achieved: 1
DFAS: 2i. Delivery of the G20 High Level Digital Financial Inclusion Principles Framework publication	2023 Planned: 1	2023 Achieved: 1

Briefly describe the output’s activities and provide supporting narrative for the score.
This output focused on developing the capacity of government officials on good regulatory practices, supporting the development and harmonisation of new laws and policies, improving the delivery (enforcement) of regulations and the development of better government/business/citizen consultations and engagement. The output will also help to increase confidence for domestic and international (including UK) businesses to invest in ASEAN by reducing the uncertainty, risks, and costs of doing business, contributing to a more level playing field for business. Improved regulatory frameworks and the adoption of good regulatory practices across the region, will create more export opportunities as ASEAN business can more actively participate in global supply chains.
In the final year of AERP, the output has been expanded to include additional activities:
- Workshops on the development and implementation of electronic transferable records (Thailand).
- Delivery of an action plan for open contracting implementation for Bangkok Metropolitan Administration’s procurement system that promotes open contracting in Thailand.
- Delivery of an action plan containing a roadmap and recommendations for Bangkok Metropolitan Administration to become an open city that promotes the use of open data.
- The ASEAN Sustainable Leadership in Infrastructure Project (ASLIP) has developed and delivered a 16-week executive programme designed for infrastructure practitioners from across ASEAN. It aimed to equip the course participants with the knowledge and skills to evaluate, prioritise, and procure sustainable infrastructure projects. Sixteen infrastructure professionals participated in the course representing the 10 AMS.
- Support for the Government of Indonesia in delivery of the G20 working group focused on financial inclusion namely the Global Partnership in Financial Inclusion (GPFI) by delivering consultative support and technical assistance to develop a roadmap, toolkit, and framework related to financial inclusion.
Overall, the output has met its objectives. For Output 2b, the programme did not quite meet the target fully due to the delay in the approval for FY22/23 budget leading to one activity being cancelled which was a training course for government officials on the Whole of Government (WoG) Scrutiny Manual in the Philippines. For Output 2c, it was unable to present the results precisely in a quantitative measure as stated in the indicator because sufficiently detailed quantitative data was not available. However, the delivery partner provided an alternative qualitative assessment. They identified that the engagement with businesses has shown a general increase in optimism about progress on business environment reforms across all partner countries, with concerns over external factors, such as COVID-19, uncertain global economic outlook, and election cycles, having also impacted business confidence and therefore producing mixed results.
Although, the target for Output 2b was not fully achieved, and Output 2c was not able to be determined, the work on improving regulatory reform through consultative meetings, workshops, trainings, and policy recommendations has effectively delivered its objectives as evidenced by commendable feedback from beneficiaries. For instance, on 7 December 2022, the British Embassy Manila was conferred a Plaque of Recognition by ARTA, an award in appreciation of the UK government’s continued support to the ARTA’s capacity building initiatives around regulatory management systems and regulatory impact assessment in the Philippines. In addition, during the Closing of Cooperation event in February 2023, the Government of Indonesia expressed its appreciation and requested that the UK continue to share international best practice, particularly to improve the investment ecosystem and ease of doing business. The event evidenced the value placed on UK technical assistance by the Indonesian Government, noting the achievements of the project to date and the desire for the relationship to continue.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.
The output showed a degree of agility and flexibility to adjust resources and activities in response to evolving priorities and needs to capitalise on new opportunities and challenges. Furthermore, this output has effectively and efficiently utilised HMG’s internal delivery team and external partners. This helped to maximise the impact of programme interventions and drive better VFM. The hybrid delivery model, which is cost-effective, has increased inclusivity and greater participation through virtual platforms. However, face-to-face engagement remains important in certain countries, especially during high-level meetings and when building relationships with key officials.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
In this review period, several indicators have been added to this output as part of expanding the output to accommodate various additional activities.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
The recommendations from the previous AR are still relevant for use in future programming, such as considering continuing and expanding topics on regulatory reform, understanding the importance of regulatory diplomacy, and strengthening cross-government coordination. Additionally, similar programming in the future should be flexible and responsive to any changes or dynamics in each ASEAN country with regard to improving regulatory practices.

Output Title	UNDP Fairbiz Project: Strengthened partnerships between civil society and public and private sectors to implement and monitor integrity policy, opening participation for women and underrepresented groups.
Output number:		3A	Output Score:	A+
Impact weighting (%):		7	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3a-a. Number of learning & knowledge platforms for Government – private sector and civil society policy dialogue	2022 Planned: 6 (cumulative)	2022 Achieved: 6
3a-b. % of involved stakeholders reporting feeling more comfortable on dialogue on integrity and transparency with counterparts following participation in the platforms (disaggregated by gender) - referring to the ability of understand and trust each other and work for common goals	2021 Planned: 80% / 2022 Planned: 98%	2021 Exceeded (Achieved: 97.66%) 2022 Exceeded (Achieved: 99%)
3a-c. # stakeholders engaged through the regional platforms (sex- disaggregated and sector-disaggregated: public sector, private sector, CSO...)	2022 Planned: 4200 (cumulative)	2022 Exceeded (Achieved: 4456)

Output Title	UNDP Fairbiz Project: Improved transparency in government contracts and increased compliance with international procedures and trade standards
Output number:		3B	Output Score:	A+
Impact weighting (%):		7	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3b-a. # of countries that have established open and innovative service delivery mechanisms	2022 Planned: 6 (cumulative)	2022 Achieved: 6
3b-b. # of new infrastructure projects where data is disclosed by governments of Thailand and Indonesia following CoST methodology	2022 Planned: 1500 (cumulative)	2022 Exceeded (Achieved: 2425)
3b-c. CoST West Lombok and CoST Thailand uses the guidance developed by the CoST IS to promote and increase the participation of women	2022 Planned: 3 (cumulative)	2022 Achieved: 3

Output Title	UNDP Fairbiz Project: Adoption of responsible business practices & good corporate governance including gender and diversity by private companies & SOEs
Output number:		3C	Output Score:	A+
Impact weighting (%):		7	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3c-a. # of business integrity instruments adopted (trainings and/or tools on code of conduct, internal control mechanisms or whistleblowing mechanisms developed for business sector)	2022 Planned: 44 (cumulative)	2022 Exceeded (Achieved: 48)
3c-b. # of companies in ASEAN that have joined responsible business conduct initiatives by project	2022 Planned: 100 (cumulative)	2022 Exceeded (Achieved: 242)

Output Title	UNDP/UNODC: Anti-corruption policies and redress mechanisms improved in target countries
Output number:		4	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
UNDP: 4a. # countries supported to develop or update preventive anti-corruption policies, plans or strategies	2022 Planned: 4 (cumulative)	2022 Achieved: 4
UNDP: 4b. # of new in-country judicial initiatives initiated following regional peer to peer exchanges (targeted countries)	2022 Planned: 3 (cumulative)	2022 Achieved: 3
UNODC: 4c. # of people (NGOs, independent media outlets, schools) trained on anti-corruption investigation techniques, approaches and technology	2022 Planned: 30	2022 Achieved: 30

Briefly describe the output’s activities and provide supporting narrative for the score.
All UNDP-led indicators come under the FairBiz project. The project works both regionally and in the six target countries to improve business practices and minimise corruption risks, creating a fairer business environment.
- Output 3a.
  - This output focused on the collective action of the FairBiz project to engage a variety of stakeholders from the government, private sector, and civil society, in meaningful dialogue and action for a fair business environment by reducing corruption and fostering integrity. During the review period, UNDP delivered various activities at the regional and country level. For example, UNDP co-organised a workshop with UNODC, Indonesian Government and CSOs called “Public-Private Dialogue on Beneficial Ownership and Transparency” in the margins of the B20 Summit. In addition, as part of the project’s efforts to transform the business environment into a more diverse, inclusive, and fair business ecosystem, the project conducted a series of studies on: (i) understanding the barriers of public procurement; (ii) correlation between disability and business integrity; (iii) and women entrepreneurs as drivers of business integrity. All were published and are available on the UNDP Fairbiz website.
  - The programme delivered six thematic platforms to improve government, private sector, and civil society dialogue. The feedback from participants in the evaluation surveys demonstrated a steady improvement in feeling more comfortable in dialogue on integrity and transparency with counterparts. The number of stakeholders engaged through the regional platforms was increased considerably, mainly due to the use of virtual teleconferencing.

- Output 3b.
  - This output focused on strengthening the transparency, accountability, and accessibility of public procurement systems. During the review period, UNDP delivered various activities at the regional and country level. For example, UNDP developed guidance on mainstreaming gender equality to promote inclusive and transparent public infrastructure, supporting the capacity development of national and subnational institutions on anti-corruption and ethics in public procurement and working with the ASEAN Secretariat in advancing sustainable public procurement by organising an online workshop titled “Leveraging Sustainable Public Procurement for Blue and Green Economy Development in ASEAN”.

- Output 3c.
  - This output promotes the adoption of business integrity and sustainable practices for private companies and state-owned enterprises. Indicator 3c-a identified that 48 business integrity instruments (cumulatively) were adopted or developed in the partner countries. The main activities implemented were trainings on business integrity, code of conduct and whistleblowing, advanced trainings for young entrepreneurs, and south-south exchange of best practices. For example, training workshops for young entrepreneurs on business integrity in Vietnam, training for women-led enterprises on business integrity in Thailand and Indonesia, and the development of an online Integrity Self-Assessment Tool ISAT in the Philippines.

- Output 4.
  - Output 4a and 4b pertain to the UNDP work strand under the Fairbiz project which provided technical assistance and capacity building for the government and anti-corruption agencies to strengthen their capacity to combat corruption. The project supported the development or improvement of preventive anti-corruption policies, plans, or strategies and promoting judicial initiatives in Laos. This output also promoted the regional approach of AERP by producing a regional guidance note - “Strategic Programming for Anti-Corruption Agencies” which provided a structured approach for Anti-Corruption Agencies (ACA) in the ASEAN member states to measure, monitor, and evaluate their success. Intended for practitioners, the document summarises the experience gained during a prior project supporting the National Anti-Corruption Commission (NACC) of Thailand. The Guidance Note, which is available on the UNDP website, aims to provide direction to address the core issues to strengthen ACAs in the region.
  - Output 4c pertains to the UNODC work strand, to support Malaysian civil society organisations tackling corruption to contribute to a more accountable, transparent, and inclusive economy and society. Activities included four seminars by experts on anti-corruption investigation techniques, training more than 30 representatives of NGOs, independent media outlets and students.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.
Implementation of these activities has demonstrated a satisfactory blend of efficiency and effectiveness. This is observable in the project’s consistent ability to not only meet but also exceed output targets within the confines of the allocated timeframe and budget. This is signifying a commendable level of proficiency in managing resources, time, and costs. In some cases, a collective action approach – i.e., engagement and collaboration with a range of stakeholders on key areas/issues has elevated the results for greater impact. The outputs also have contributed meaningfully to the advancement of women, youth, and marginalised group in the economy, aligning with the AERP’s broader outcomes. For example, Fairbiz has impacted many women entrepreneurs in Thailand and Indonesia as a result of the training that was conducted which positively changed the business organisations by strengthening their internal policies and regulations to introduce more ethical and responsible principles in their companies.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
There are no changes to this output during the past year.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
There are no recommendations from the previous AR to be followed up. The following recommendations were drawn from this review period:
- These outputs contributed to the gender and social inclusion (GESI) narrative of the AERP by providing interventions that engaged women business leaders. Specifically, FairBiz interventions in Thailand and Indonesia have produced evidence of how practical training can have impact on individual companies, and with the support of local grassroots organisations, how it can create the beginnings of a social movement led by women entrepreneurs for women entrepreneurs. This approach on GESI could be replicated by future programmes.
- UNDP noted that momentum for promoting business integrity at all levels exists in the region and should be sustained. In its PCR, UNDP gathered testimonials that demonstrate the strong appetite of stakeholders to participate in similar activities in the future. For example, the success of the SHE-BID initiative has called for scaling up the impact, supporting advocacy with public institutions to collect disaggregated data in procurement and adopting a preferential quota for women and marginalised groups. Future programmes could build on these achievements.
Output Title	UKABC: A fairer business environment for UK businesses in ASEAN is enabled
Output number:		5	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5a. No of strategic recommendations reports developed	2023 Planned: 60	2023 Exceeded (Achieved: 67)

Briefly describe the output’s activities and provide supporting narrative for the score.
Managed entirely using non-ODA AERP funds, this project aims to advance commercial diplomacy and demonstrate UK’s private sector expertise, to deliver secondary benefits. The project deliverables were ASEAN-facing diplomatic activities such as the ASEAN Business Investment Summit in November 2022 and the UK-ASEAN Business Forum in March 2023. It also leveraged UK-ASEAN Business Council’s strong relations across the region and expert insights to feed into the market access work of the UK Government.
The UK-ASEAN Business Forum, which was the focus of the logframe assessment, was a convention of over 400 participants from the public and private sectors, both online and in-person in London. 67 of them represented UK companies and UK officials, who discussed existing trade relationships with counterparts from ASEAN and AMS and explored future partnerships given Indonesia’s ASEAN chairmanship in 2023. Sustainable infrastructure and green finance were also discussed in the panel discussions.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year.
The output of this initiative aligns with its stated objectives fulfils the effectiveness proposition outlined in the business case. In the context of creating a stronger business environment, the output will contribute to promoting new opportunities in the region. For example, following the success of ABIS 2022, it inspired a UK multi-national company to organise a roadshow for ASEAN companies across the UK to explore partnerships. The output resulted in added value creation by maintaining relationships with key stakeholders in ASEAN leading to strengthened alignment with stakeholder interests and a shared sense of ownership and commitment.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The output was recently introduced in this review period to cover the programme’s expansion.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
No recommendations were made in the previous AR. It is suggested for the future programme to ensure that any UKABC projects fully interlocks with FCDO regional strategy and ensure strong relationships and communication between FCDO, UKABC, and DBT.

Output Title	PwC: Positive influence on market regulation through ASEAN Capital Markets Forum (ACMF) and promotion of international standards in FS / (Logframe: Capital markets’ development plans, policies and regulations developed or improved)
Output number:		6	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
6 No of strategic recommendations reports developed	2021 Planned: 3 / 2022 Planned: 3	2021 Not Achieved: 1 / 2022 Achieved: 3

Output Title	Policies and regulatory issuances updated or developed, and industry provided the platform to develop or enhance responsible Fintech products or services
Output number:		7	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
PWC: 7a. No. of new frameworks or systems developed	2021 Planned: 2	2021 Achieved: 2
PWC: 7b. No of strategic recommendations reports developed	2021 Planned: 6 / 2022: Planned: 2	2021 Exceeded (Achieved: 7) / 2022 Achieved: 2
Surecert: 7c. Number of sub-projects delivered to provide study results and recommendations focusing on priority areas and key principles that drive digital authentication services in Thailand identified by Electric Transactions Development Agency (ETDA)	2022 Planned: 3	2022 Achieved: 3
FSE: 7d. Number of consultation sessions between the Bank of Thailand (BoT) and other jurisdictions that implemented Open Banking using voluntary approach	2022 Planned: 5	2022 Not Achieved: 2

Briefly describe the output’s activities and provide supporting narrative for the score.
- Output 6.
  - This output aimed to strengthen regulatory frameworks and capacity for financial regulators in policies and legislation in order to develop and enhance capital markets in the Philippines and Vietnam. During the review period, the project focused on strengthening the Philippines Security and Exchange Commission (SEC)’s efforts for inspections of Risk Based Capital Requirement (RBCA) supervision, by supporting SEC in drafting a framework for inspections, proposing profiling metrics to focus SEC’s attention on Trading Participants (TPs) with the highest risk, assisting SEC to set up a review process to further develop monitoring, giving SEC access to new analytical tools, and addressing current and future strategic market developments which are expected to affect capital needs and risk of TPs.
  - The workstream supported the scope extension of RBCA monitoring by SEC to cover a wide range of market intermediaries starting with Investment Houses (IHs). After completion of the programme, the SEC agreed to draft Implementation Regulations giving force to the IH reporting requirements, to present them to the Commission for approval, to undertake industry consultation and to institute the working group in conjunction with the Bangko Sentral ng Pilipinas (Central Bank of the Philippines) for implementation during the first half of 2022.

- Output 7.
  - This output aimed to assess the readiness and impact of FinTech adoption by providing regulatory advice, training and capacity building. Activities during the reporting period have made a substantial contribution towards the attainment of the output. During the review period, the activities were as follows:

    - Financial Regulation
    - In Thailand, the project delivered a webinar on Decentralised Finance (DeFI) and Global Financial Innovation Network (GFIN) to the Bank of Thailand (BoT), Securities and Exchange Commission (SEC), Office of Insurance Commission (OIC), and Electronic Transactions Development Agency (ETDA). The webinar addressed the challenges of regulating a parallel financial system under DeFi and reviewed the steps necessary to become members of GFIN.
    - In Vietnam, a report on Global P2P Lending for the Ministry of Finance was produced that provided broader understanding of the emerging international P2P lending regulatory frameworks and practices in the UK and AMS including Indonesia, Malaysia, Philippines, and Thailand. The knowledge product also presented an opportunity for lesson learning with peers in ASEAN.
    - In Indonesia, the Ministry of Finance (MoF) produced a report with recommendations for the FinTech cluster under the Omnibus Law in the Financial Sector. The report includes recommendations on three key issues: regulatory sandboxes, licensing and registration, and consumer protection. During the G20 Presidency, the MoF was tasked with leading the development of the G20 Global Policy for Financial Inclusion. As part of this work package, the MoF team also requested the delivery partner to provide inputs on MSME digitalisation. When FSIP contract finished in March 2022, there was still strong demand from the Indonesian Government to continue the work. To cater to this momentum, the work was continued in the form of a small bilateral project – see earlier discussion for Output 2i. The appointed delivery partner completed the work package and managed to facilitate the delivery and publishing of the Digital Financial Inclusion Principles Framework, amongst other technical assistance products related to updating the Omnibus Law.
    - Digital Verification
    - The project aimed to assist ETDA to achieve a broader understanding of the opportunities and challenges in advancing the digital verification landscape in Thailand. It delivered a report on inclusive digital identification (ID) in the country that provided analysis on (i) Thailand’s approach vis-à-vis digital ID global practice; (ii) user experience of current platforms; and (iii) development of digital ID for corporate use. A workshop was held to deep dive into the findings.
    - Open Banking
    - The project aimed to share UK and international experiences and provide technical assistance to support BoT towards its future implementation of an open banking policy in Thailand.
    - The project initially struggled to meet stakeholder requirements. Open banking is a very niche topic, so it proved challenging to identify the right expertise, and this was exacerbated by the short time frame. Therefore, a decision was made to scale down the scope of the project. The delivery partner produced a report on alternative credit decisioning for BoT and delivered two webinars that presented the findings of the report.
Assess the VfM of these outputs compared to the proposition in the Business Case, based on performance over the past year
Overall, the output performed well and almost all of the indicators’ targets were met. The delivery of this output faced challenges such as identifying the right expertise on open banking. However, the programme managed to maintain engagement and communication with the stakeholders which allowed the programme to understand more about government priorities, in turn maintaining the stakeholders’ satisfaction level. In some cases, the project also resulted in great buy-in from the stakeholder’s high-level executives to continue working with the UK government on these issues.
Describe any changes to these outputs during the past year, and any planned changes as a result of this review.
The activities on digital verification and open banking were added to the outputs during the review period.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The previous AR identified several recommendations which should be considered by future programming, such as suggesting that an adaptive programme approach could be used to test and scale innovative interventions alongside the completed work, maintain relationships with stakeholders, and explore new work streams aligned with the country’s priorities.
The main lessons drawn from this review period relate to the tight project timeline for additional activities. This presented challenges for the project to achieve the objectives with the implementing partners. It is crucial to have sufficient time to ensure effective understanding of the needs of the stakeholders.
Output Title	CCU/GDS: Increased capacity building and collaboration for government stakeholders to improve digital and cybersecurity processes
Output number:		8	Output Score:	A+
Impact weighting (%):		10	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
8a. % of stakeholders that indicate that they have increased knowledge regarding improving security awareness and reducing fraud/ regulators	2022 Planned: 24	2022 Exceeded (Achieved: 34)
8b. Number of stakeholders trained on digital and international standards	2022 Planned: 8	2022 Exceeded (Achieved: 18)

Briefly describe the output’s activities and provide supporting narrative for the score.
The objective of this output was to enhance capacity and foster collaboration amongst government stakeholders, with the goal of strengthening digital and cybersecurity regulatory frameworks in Thailand. By focusing on capacity building, the initiative aimed to equip government officials with the necessary knowledge, skills, and tools to effectively address the challenges posed by the rapidly evolving digital landscape and the increasing threats to cybersecurity. Additionally, by encouraging collaboration amongst government stakeholders, the initiative sought to create a platform for sharing insights, experiences, and resources, thereby enabling a collective and coordinated response to digital and cybersecurity issues.

During the review period, several noteworthy activities took place:
- The Cyber Capacity Unit (CCU) delivered a series of workshops on cyber exercising, countering fraud and technical approaches to countering money laundering; a training course for cyber defence practitioners covering threat intelligence, vulnerability management, incident response and shared the UK approaches in these areas; and produced a paper outlining different options for reducing the cyber security regulatory compliance overhead for SMEs.
- The Government Digital Service (GDS) organised workshops on digital ID for business and data interoperability. The workshops focused on digital ID for business looking at developments in the UK and describing developments to date on the UK Trust Framework and identifying the components for drafting a standard for digital ID for business and looking at the needs for Thailand and how these might vary to the UK for cultural, language and regulatory reasons. GDS also hosted an in-person workshop for Thailand’s Comptroller General's Department (CGD), Ministry of Finance, covering 3 areas: procurement policy, user research, and technical architecture.
Assess the VfM of this output compared to the proposition in the Business Case, based on performance over the past year
The interventions that have been implemented support the proposition put forth in the business case to enhance the business environment. It is expected that the government stakeholders acquired the necessary skills and knowledge to more effectively tackle digital threats and cyber risks, which is important in the business environment. This will lead to heightened awareness of security protocols and a proactive approach towards safeguarding sensitive information and systems. Over time, the level of confidence in the digital realm of the business environment among customers, partners, and stakeholders will be increased.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
The output was introduced during this review period.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There are no recommendations from the previous AR to be followed up. The following lessons were derived from the implementation:
- The two projects showcased the importance of flexibility in achieving their objectives and managing risks within a tight timeframe. This was demonstrated during stakeholder consultations and when delivering workshops. As the projects were delivered at the height of the COVID-19 pandemic, remote/virtual delivery became the common delivery model. However, whilst it saved travel costs and reached wider audience, it was noted that it was harder to engage workshop attendees. Acknowledging this, the delivery partners employed various presentation techniques and styles to ensure engagement and establish connection with the stakeholders.
- The success of this output also helped to establish effective relationships with stakeholders given the short timeframe of the project through taking a tailored approach. This is crucial to secure trust and get buy-in from the stakeholders.
## D: VALUE FOR MONEY

Economic
The economic assessment of the project reveals several positive aspects. There is evidence of efforts being made to minimise costs and maximise economy. The transition to virtual delivery has proven to be a cost-effective measure, resulting in reduced expenses and increased reach. By embracing virtual platforms, the project has been able to overcome geographical constraints and extend its impact to a wider audience.

Efficiency
The efficiency assessment of the project reveals several commendable practices that have contributed to its effective utilisation of resources. Firstly, the programme team and delivery partners successfully delivered efficient financial planning and allocation. This minimised the risk of budgetary deviations and allowed for better resource management. Secondly, the programme’s swift adaptation during the COVID-19 pandemic and budget uncertainties demonstrates its agility in responding to unforeseen circumstances. This ability to pivot quickly and effectively ensured that resources were directed towards the most relevant and impactful activities, optimising the project's efficiency in achieving its objectives.

Effectiveness
The effectiveness assessment of the project highlights key elements that contribute to its ability to achieve its intended goals. During this review period, all intended outputs have been delivered. This achievement was supported by the regular review and update of the programme’s progress in response to changes in work streams and scope to ensure that the programme remained aligned with evolving circumstances. This adaptive approach enabled the programme to effectively address emerging challenges and seize new opportunities while staying focused on its objectives.

Equity
The equity assessment of the project highlights efforts made towards promoting fairness and inclusivity. AERP demonstrated commitment to addressing equity considerations, even under challenging circumstances. Despite constraints, the programme proactively worked towards promoting equitable outcomes within the given framework. In addition, several outputs were intended to provide direct intervention to support women entrepreneurs. This targeted approach acknowledges the importance of gender equity and seeks to empower and uplift women within the financial sector. By providing support, resources, and opportunities to women entrepreneurs, the project aims to reduce gender-based disparities and promote inclusivity.

E: RISK

Overview of risk management
Risk management was reported through quarterly reports and the AERP Dashboard for the Programme Board. Risks and issues were grouped at the project level or as cross-cutting risks (e.g. COVID-19). The risk profile is reducing as the programme moves towards completion. The main risk during this review period was the delivery risk regarding the possibility that projects were unable to complete within the remaining programme time frame. This has been managed through careful risk management and effective communication between programme team and the implementing partners.

There were risks related to the staffing/programme capacity as regional programme management will transition from Singapore to Jakarta in 2023. There is also a risk related to any gap in programming between the closure of AERP and the initiation of a new programme, which could damage stakeholder relationships if FCDO wants to continue working on similar issues in future. This will need to be mitigated as far as possible through good communication with key stakeholders and beneficiaries whilst the new programme is designed.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

FCDO
The programme is managed by a regional programme team based out of Singapore, with the support of programme staff at British Embassies and High Commissions in the region. A Programme Working Group (PWG) met monthly for the first 12 months of this review, with meetings reducing as activities were completed. The meetings served to exchange information about progress and challenges, provide capacity building training and updates from the regional and central levels. In compliance with governance arrangements, all delivery partners provided regular quarterly narrative and financial reports, which were then compiled into a portfolio level quarterly report, submitted to the Programme Board for scrutiny and approval. Programme Boards occurred every quarter during the period in question, with full minutes distributed and approved by the following meeting.

The Regional Team held monthly meetings with all delivery partners, and meet more often if necessary. For example, when setting up new projects in Thailand during this period, the regional team were meeting Post every week to facilitate this work. There were also challenges when delivering the programme with multiple implementing partners. These challenges primarily revolved around aligning programme expectations and effectively managing the diverse set of partners involved. However, these obstacles were overcome through the coordination efforts exhibited by the FCDO programme managers in the region, the regional programme team, and delivery partners. Extensive modes of communication were employed to ensure that programme expectations were properly managed, enabling a smoother implementation process.

Implementing Partners
Overall, the implementing partners demonstrated good proficiency in effectively delivering the outputs and making a contribution towards outcomes. There is an indication that significant majority of the outputs — training for capacity building; knowledge and policy products; and a variety of consultative support — have increased the likelihood of outcome level changes happening in future. For instance, the Fairbiz Project supporting the inclusion of women entrepreneurs in public procurement and in the development of anti-corruption policies will contribute to improved business practices and minimised corruption risks to create a fairer business environment in ASEAN. Furthermore, the programme’s success is evident through the positive feedback received from beneficiaries. Notably, during this review period, the ASEAN Secretariat expressed their gratitude with a letter of thanks in response to the AERP IP Programme and the closure of FSIP project highlighted the delivery of significant primary and secondary benefits. This accomplishment also strengthened relationships with key ministries and agencies in ASEAN countries.

Partners did provide feedback to FCDO regarding the added difficulty of delivering projects during this reporting period due to the uncertainties that arose around funding allocations at the start of the financial year. Scenario planning multiple times with different timeframes and allocations caused a heavy burden for programme management and made delivery of high quality activities more challenging. The robustness and quality of reporting at the outcome level has been challenging for all delivery partners during this period. This has been noted throughout this report, with the recommendation to ensure that delivery partners have the necessary capacity to design effective logframes, with realistic targets and indicators, and to ensure that the logframes are agreed and in place prior to delivery.

Commercial
This reporting period saw the closure of the FSIP contract with PwC in March 2022. The regional programme team, working with commercial advisors in London, oversaw the exit procedures ensuring that the contractual arrangements were met including the submission of an independent audit report by the commercial firm within six months of the closure. Apart from FSIP, the regional programme team and programme managers ensured that commercial and audit requirements were upheld in all grant and commercial agreements signed with delivery partners, both not-for-profit organisations and commercial companies.

Financial
The programme actual cost reached £1,645,915 or 98% against forecast at the end of FY 2022-2023. It spent £726,453 in Q4 (FY22-23), meeting the target forecast whilst ensuring satisfactory delivery of programme outputs. The 98% spend against forecast is a significant achievement, particularly regarding the funding challenges over this period. It has been achieved through regular and thorough budget management, working very closely with delivery partners to monitor spend and make adjustments as necessary. The AERP maximum business case value stands at £21.4m following the approval of a business case addendum in May 2022. At the end of March 2023, £19.63m has been spent.

Date of last narrative financial report	31 March 2023	Date of last audited annual statement	N/A