Programme Completion Review

Title: ASEAN Economic Reform Programme
Final Programme Spend £ (full life): £19,661,564	Review Date:	June 2023
Programme Code: GB-GOV-50-PF-18-ASEANER	Start Date: April 2018	End Date: June 2023

Summary of Programme Performance

Year	2018-19	2019-20	2020-21	2021-23	PCR
Programme Score	B	A	A	A	A
Residual Risk Exposure Rating	Moderate/ / Major	Moderate	Moderate	Moderate

DevTracker Link to Business Case	https://assets.publishing.service.gov.uk/government/uploads/system/uploads/attachment_data/file/810873/Business_case_for_ASEAN_Economic_Reform_PF_Programme.odt

A. Summary and Overview

The ASEAN Economic Reform Programme (AERP) was designed to improve the business environment and a set of public financial and business services critical to well-functioning firms and markets in the six countries of Indonesia, Thailand, Vietnam, Philippines, Malaysia, and Myanmar, to ultimately improve the development of the private sector in these economies. This was later expanded to cover all 10 ASEAN Member States (AMS).

To achieve this objective, the programme worked to improve the conditions for the development and successful operation of private entrepreneurship through regulatory reform and government capacity building, focused on improvements to the business environment and public financial and business services. These included intellectual property rights frameworks, transparency and accountability in public procurement systems, access to and inclusiveness of capital markets, financial technology, accounting standards, anti-money laundering regulation, Islamic finance, business licencing regulation, market competition, and digitalisation of government platforms related to trade and governance.

The nature and quality of regulation in these areas, plus the government capacity to provide a range of services related to them, can directly influence the start-up of new firms, encourage innovation and entrepreneurship, improve equality of opportunity among market participants, and thereby strengthen the general sustainability of economic growth in the long run. AERP’s long-term objective was to contribute to the elimination of poverty and to promote inclusive economic growth and shared prosperity in the ASEAN region. The programme spent a total of £19,661,564 over its lifetime, from April 2018 to June 2023.

For achieving its objectives, AERP adopted a relatively complicated delivery model that included nearly a dozen sub-thematic focus areas, eighteen implementing partners, and a wide geographic focus. This approach to delivery, while creating multiple programme management challenges, has also been a strength, allowing it to respond to both country-level and regional ambitions as well as giving it the flexibility to meet a wide range of identified priorities and needs across such a diverse region, in support of the overarching programme objectives.

Despite facing a number of challenges beyond its control, including the COVID-19 pandemic, the programme delivered a range of achievements that directly contributed to the UK’s long-term ambition of building prosperity and sustainable development in ASEAN, as reaffirmed in the March 2021 Integrated Review. Despite being designed and started before the UK became an ASEAN Dialogue Partner in 2021, the programme has also supported the priorities in the Economic Cooperation Pillar of the ASEAN-UK Plan of Action in recent years, suggesting the continued relevance of the programme priorities.

Some of the key achievements, challenges and lessons learned from the programme are summarised below.

Achievements

Moving toward a more enabling and inclusive business environment in ASEAN:

Development of the private sector is critically affected by a range of public policies and regulations that create a conducive business environment, defined as an environment that incentivises the start-up of new firms, helps existing businesses operate effectively and successfully, leads to the creation of jobs, and accelerates the transition from informal to formal firms. Furthermore, a range of government systems—particularly the availability and access to information—directly determines the inclusiveness of the business environment or the extent to which it provides equal opportunity to individuals from all sections of society, and across the gender divide, to start and maintain businesses. Over its lifetime, AERP aimed not only to improve regulations and institutional capacity for a more enabling and inclusive business environment but also to strengthen the capacity of women and Small and Medium-Sized Enterprises (SMEs) to participate in successful private entrepreneurship. The following are some of AERP’s top achievements which this review concludes increase the likelihood of an enabling and inclusive business environment in ASEAN:

Making participation in public procurement easier for SMEs: Under AERP’s Promoting a Fair Business Environment in ASEAN (FairBiz) component, delivered by the United Nations Development Programme (UNDP), a comprehensive online platform was co-developed with Indonesia’s National Public Procurement Agency (NPPA), including an online e-learning course, providing an easily accessible space for the country’s SMEs to learn about the government’s public procurement systems, with an objective of improving their capacity to participate in and win government contacts. AERP’s support not only helped develop the course but was also key to help integrate it into the Agency’s online interface where SME’s can access it from anywhere in the country. In a meeting with NPPA officials, the PCR team was able to see first-hand both the quality and ease of access to the platform and how SMEs are likely to benefit from this service, contributing to the programme’s larger objective of making an AMS’s business environment not just more enabling for entrepreneurship but also more inclusive. Between August 2021, when the course was launched, and December 2022, more than 800 SMEs registered for the e-learning course. 488 passed the assessment, which increases their likelihood of winning government contracts. The continuing availability of the course is an example of AERP’s sustainable impact—the online course is permanently part of NPPA’s Massive Online Platform, and the Agency continues to admit multiple batches of SMEs into the course every year.

Enabling women to become successful entrepreneurs: AERP’s FairBiz component worked with small women business owners in Indonesia to improve their skills and capacity for successfully bidding for government contracts. The PCR team met with beneficiaries of this support who confirmed that the training significantly helped them increase their awareness and understanding of the public procurement system, providing them with an improved opportunity to bid for government contracts. The training helped participants to successfully register as suppliers in the government’s e-catalogue. The direct beneficiaries have continued to meet with a community of other women entrepreneurs, helping them address shared issues and concerns. About 100 women-led businesses were trained, out of which 68 successfully opened an account on the government’s procurement system, 33 took part in bids, and four participants won a tender with the Government of Indonesia.

Filling key knowledge and information gaps for effective Intellectual Property Rights (IPR) regimes: Efficient and effective IPR systems are fundamental to ensure innovation, an activity critical to economic change. Weak enforcement of IPR reduces incentives for entrepreneurs, both domestic and foreign, to invest in innovation. Better, more effective enforcement strengthens these incentives, directly contributing to building a more enabling business environment. Various work strands of AERP with multiple delivery partners were aimed at improving the standard of IPR systems and strengthening their enforcement in selected AMS. The programme has done so by developing comprehensive knowledge products that fill critical information gaps required for effective IP enforcement by the regulators, while also providing necessary information to both domestic and foreign investors (including UK businesses) who look to invest in the region. For example, IP Enforcement Manuals developed for Indonesia, Philippines and Vietnam provide all IP owners in these countries, and other interested parties in the region, with a clear explanation of IP enforcement procedures. The manuals provide detailed country specific information on IP enforcement systems, criminal IP enforcement, civil IP enforcement, digital IP infringements of trademarks and copyrights, and administrative procedures related to IP enforcement. The manuals were launched in cooperation with the British Chamber of Commerce, with an objective of directly helping businesses, including UK businesses, improve their understanding of IP regulations in ASEAN. Apart from the technical outputs, the support for the IP policy agenda was also complemented by a series of working-level capacity building fora for specialist IP agencies across ASEAN, with strong engagement from the ASEAN Secretariat through the ASEAN Network of Intellectual Property Enforcement Experts (ANNIEE).

Improving financial Inclusion; expanding access to digital financial services: A range of policy products and services—reports, workshops, trainings, targeted advisory support—delivered under AERP’s FSIP component have increased the likelihood of better financial inclusion of individuals and businesses in targeted AMS, through improving access to useful and affordable financial products and services, including transactions, payments, savings, and credit. In Indonesia, AERP, both through FSIP and the work of the Digital Finance Advisory Team, supported the framing of the Financial Technology chapter during the drafting of the country’s Omnibus law on Financial Sector Development and Reinforcement. This support helped Indonesia’s Ministry of Finance to strengthen the case for FinTech reform in the country. The law, which was passed by the Government of Indonesia in January 2023, provides a stronger legal basis for financial tech firms to make more innovations for better financial inclusion and financial services. Officials from the Policy Analysis division of the Ministry confirmed the importance of this support to the PCR team. In the Philippines, FSIP’s support helped the Central Bank of Philippines (BSP) to pilot a Fintech Industry Sandbox that invited Financial Tech firms to show how they will promote mobile banking, credit scoring and digital customer verification systems in the country, all part of the Government’s roadmap to creating an open and inclusive financial sector.

Improving transparency in public procurement; fostering competition; easing access to business licensing; and developing regulation for better public service delivery:

Improved standards for transparent and fair public procurement: Building on the work done by the British Embassy Bangkok to improve transparency and accountability in public infrastructure procurement in Thailand through engagement of CoST – the Infrastructure Transparency Initiative, AERP’s support has further helped the government to apply CoST’s transparency and open contracting tools at the provincial level. Officials from the Thai government’s Comptroller General’s Department confirmed in an interview that this support contributed to the Chachoengsao provincial government’s potential cost savings of up to USD 73 million as a result of the deterrent effect of the CoST approach. Similar support has been provided to three other provinces, with expectations for equally significant cost savings. The new procurement standards are now permanently part of the government’s system. Similarly in Indonesia, AERP support has helped promote the use of CoST standards in public infrastructure procurement at local level in the West Lombok administrative area.

Fostering better competition in AMS: Under AERP’s Fostering Competition in ASEAN component, OECD, the component’s implementing partner, produced comprehensive policy reports with recommendations for all ten AMS, assessing existing laws and regulations in these countries that directly affect competition in the logistics sector and providing recommendations for reform to improve competition. In addition, two ASEAN-wide reports built on the country reports and identified 30 non-binding recommendations across AMS where changes could be made to mitigate harm to competition from regulatory barriers. It is important to note that the desired impact sought under this component is longer-term because reforming competition environments at country level can take time and depends on many factors. However, OECD’s initial assessment has already identified some notable country developments that are in line with the recommendations made. This work has also contributed to strengthening the UK’s relationship with the ASEAN Secretariat and AMS on these issues, with two ASEAN-wide competition reports launched at the ASEAN Economic Ministers Meeting in September 2021, alongside a UK Minister, the ASEAN Secretary-General, and the OECD Secretary-General. The event served as good evidence of the importance that the ASEAN Secretariat and AMS accorded to the work.

Improving government capacity for faster and easier business licensing: In Indonesia, AERP responded to the government’s priority of removing licensing and inspection related delays for new businesses by supporting the development and implementation of a new risk-based approach to all licensing, representing a step change from ex-ante licensing for all business activities, followed by inspections which mostly checked the licence paperwork, to a risk-based, “trust but verify” approach. This will have a transformational impact on business licensing in Indonesia, with a graded scale of licensing requirements from simple registration, through self or 3rd party certification of compliance with an ‘operational standard’ to a government-issued ex-ante licence. The importance of AERP’s support in this process, delivered under the programme’s ASEAN Regulatory Reform component, was discussed during the project’s closure ceremony co-organised with the key stakeholder, Coordinating Ministry for Economic Affairs (CMEA), and further confirmed by a high-level official from the Ministry in an interview with FCDO’s PCR team.

Improving delivery of public services: In the Philippines, AERP, through the Regulatory Reform Project, supported the design and implementation of a Whole-of-Government (WOG) approach for streamlining government systems and procedures to deliver public services. The approach and methodology developed will help to eliminate outdated, unnecessary, and duplicative processes, and support the harmonisation, integration, and coordination of remaining processes. This will make government processes faster and more efficient, making it less burdensome for businesses and saving government resources.

The launching of the Philippine Good Regulatory Practice (PGRP) Guidelines: The PGRP guidelines which were developed with AERP support are the first of their kind in the country and will serve as a guiding document for regulatory agencies on the development, implementation and monitoring of policies, procedures, organizational values, behavioural and service standards. This work provides a good example of UK expertise and best practice directly supporting Government policy and guidelines, ensuring a sustainable longer-term impact for the project.

Resolution 68 - In May 2020 the Vietnamese Prime Minister signed Resolution 68 on the simplification and streamlining of regulations relating to business activities. This is a major success for the AERP’s Regulatory Reform project, which had been working with the Government since 2019, building capacity and sharing experiences of the UK’s One-In, Two Out (OITO) initiative and the Administrative Burdens Reduction Programme. In just 10 months, a legal document on regulatory reform in Vietnam, informed by the UK engagement, with the highest level of political endorsement and a clear implementation plan, is now in effect.

Strengthening Accounting Standards and Anti Money Laundering frameworks: In the Philippines, Thailand, Vietnam, and Central Bank of Myanmar (before 2021) about 1750 regulators received training through AERP on how to align accounting standards in their countries with international standards and best practices, specifically with International Financial Reporting Standards (IFRS). Following the support, Vietnam issued a draft IFRS implementation roadmap that sees gradual IFRS implementation between 2025 and 2030. If the beneficiaries apply the training to improve their organisational outcomes, there is a good likelihood that accounting standards in the targeted countries will improve over time. Myanmar proposed adopting IFRS for public corporations by 2022/23. However, following the coup in February 2021 these dates have now shifted. The Accountancy Council postponed the compulsory adoption of the IFRS 2018 report standards (which public interest entities were supposed to have adopted by the 2022-2023 financial year) to the 2027-2028 financial year.

Deeper and stronger relationships with key stakeholders in ASEAN Member States:

Overall, this PCR concludes that AERP has also helped the UK missions in the original six target countries and wider ASEAN region to build deeper and stronger relationships with key government, business, and civil society stakeholders. The relationships will play a key role in helping the UK take forward its wider partnership with ASEAN, assisting the ASEAN Secretariat and AMS in achieving their own development objectives in those areas where the UK can offer specialist advice and expertise. In Indonesia, for example, AERP support has led to stronger relationships with national stakeholders such as Ministry of Finance, CMEA, and National Public Procurement Agency (NPPA). In Thailand, multiple targeted projects have enabled the UK to maintain key relationships and build stronger relationships with nationally influential stakeholders such as the Bank of Thailand, Bangkok Metropolitan Authority, and the Comptroller General’s Department (Ministry of Finance). Similarly, in the Philippines, the support has led to a stronger relationship with the Central Bank of Philippines. High level officials from all these organisations confirmed in interviews the value and importance they place in the UK’s support, and its importance in maintaining strong relationships. Moreover, UK’s engagements with the ASEAN Secretariat became stronger as a result of regionally led projects including the work on IP. In March 2023, an ASEAN Secretariat Director sent a Letter of Appreciation to FCDO recognising the partnership and support the UK provided through AERP’s policy products and capacity-building activities on IP.

Challenges

Transitioning from Prosperity Fund to FCDO programming framework: AERP started in 2018 as a Prosperity Fund programme under the name of Southeast Asia Economic Reform Programme. The programme was transferred to the Foreign, Commonwealth and Development Office (FCDO) after the merger of ex-FCO and ex-DFID in 2020. The transition meant the application of FCDO’s new Programme Operating Framework (ProF) rules to the programme, including new rules governing programme delivery, compliance requirements, and new tools and methodologies for programme monitoring and evaluation. For AERP, whilst the Business Case outlined a high-level Theory of Change, some aspects were not as detailed as would be expected in a Business Case developed under the ProF. The Business Case was reviewed, and logical frameworks developed at both the project and portfolio levels, after the programme had gone into delivery. As a result, the programme had to stretch its limited programme-management capacity to match the new demands, while not having the same leverage over implementing partners to ensure full compliance. Even though the programme managed to ensure a quality delivery overall, the transition did create challenges for effective oversight and management across multiple countries and almost a dozen thematic focus areas.

COVID-19: Due the COVID-19 pandemic, all delivery channels of AERP had to transition to an online model. For a programme designed to deliver targeted, specialised Technical Assistance (TA) to a wide range of government stakeholders, who sometimes have limited technological capacity for effective online interactions, transitioning to online delivery created challenges for AERP. Furthermore, the pandemic also prevented any sustained engagement among AERP’s various implementing partners, which could have helped implementers to navigate shared challenges better and share lessons and learning.

Budget Uncertainties: Changes to the Official Development Assistance (ODA) budget of FCDO for 2021/22 also led to changes in AERP allocation. This required scenario planning for each aspect of the programme and ultimately a reduction to the Financial Services & Intellectual Property (FSIP) pillar. Overall, and based on interviews with a range of internal and external stakeholders, including implementing partners and beneficiaries of AERP, this PCR concludes that budget uncertainties, in the form of unpredictability around the timing of both the amount and availability of funds each financial year, created challenges for implementing partners to effectively plan workstreams before implementing them. The late availability of funds also created pressure on delivery. The programme flexed to meet this demand, working closely with Posts and partners to design shorter term projects which, while still delivering against AERP objectives, could be implemented in a shorter windows within a given financial year. This was achieved, but it was necessary to adopt a proportionate approach to programme management, given the burden on programme management resources that this created, both regionally and at Posts.

Political Context: The 2021 military coup in Myanmar led to the suspension of all programme activity in the country. As a result, significant progress made in the Anti-Money Laundering (AML) workstream was lost.

Lessons learned, evidence generated and recommendations.

Proportionality between programme scope and programme resources: AERP’s business case set the programme up for creating change across three very broad areas, which, combined with eighteen implementing partners, about a dozen sub-thematic areas, and a regional geographic focus, ultimately led to a fragmentation of the programme’s financial resources and management capacity, and also may have reduced focus on converting output level results into outcome level change. Strengthening the business environment; improving transparency of firms and related government structures; and making financial markets more inclusive and open are big focus areas, involving both macro and microeconomic variables. For example, the business environment covers a very large number of conditions, ranging from macroeconomic stability to a number of microeconomic regulations that affect firms’ behaviour and performance. Similarly, transparency in the business environment relies on a complex system of supporting institutions that promote more transparent governance of firms. Particularly, AERP’s financial markets pillar became diversified into six sub-thematic areas,[1] which created pressures on programme management and led to a thin spread of the programme’s quality assurance capacity. Overall, a key learning from this review is that in order to increase the likelihood of output level results leading to outcome level change, it is critical to ensure complementarity between programme scope or ambition and programme resources, including the resources dedicated to programme management. This could mean reducing the number of thematic focus areas in future programming, or increasing the programme management resources available.
[1] Intellectual Property Rights; Capital Market Access; Accounting Standards; Anti-Money Laundering; FinTech; and Islamic Finance.

Develop a more robust Theory of Change: A high-quality programme Theory of Change (ToC) is more than just a high-level description of programme’s intended impact, outcome, and output level change. ToC are in effect a prediction of how delivery will take place in the real world, and a team will make a number of assumptions when forming this prediction. The greater the confidence the team has in these assumptions, the greater the chances of success. In other words, a ToC explains what makes us confident that if we do X (output level activity) we will achieve Y (outcome) by outlining best evidence in support of our predictions; assumptions with high significance for delivery; evidence in support of the assumptions, while also clearly identifying those with weak evidence as key risks for the programme. Furthermore, a ToC must provide absolute definitional clarity of the broad conceptual areas where it seeks to achieve real world change. This helps to provide a clear direction, particularly to implementing partners and programme teams regarding what the programme is set up to achieve. This PCR recommends that all future ASEAN development programmes develop more rigorous ToC, which can clearly and simply set the direction for programme activity (without increasing programme management complexity). Any future programmes should also take steps to ensure that the TOC is consistently used throughout implementation to guide all aspects of programme governance and delivery. This will ensure a better direction for programmes throughout their lifetime to stay focused on their outcomes, keep implementing partners and programme teams aware of the risks, improve quality of monitoring, and overall, a higher likelihood of ensuring outcome level change.

Ensuring that all Implementing Partners have the right expertise and networks: For a multi-country programme, aiming to deliver change across three broad pillars and a dozen sub-thematic areas, it can be difficult to find delivery partners who fulfil all the requirements—a region-wide presence, expertise in all thematic areas, plus a strong country-level presence with established relationships and networks. There were some cases in AERP where implementing partners were potentially asked to cover too much (either geographically or thematically). Fewer implementing partners can make programme management simpler and help to focus programme activity on a narrower range of priority outcomes, but it may also provide less deep, niche expertise compared to working with multiple specialist partners. Any future programme should consider these trade-offs carefully from the outset and ensure that implementing partners are carefully selected to match the new programme design – depending on the range of issues being covered, the amount of in-house programme management capacity available and the kind of technical expertise required to deliver the outcomes in the ToC.

Make sure all implementing partners remain focused on delivering against the ToC throughout implementation: For overall programme efficiency and effectiveness it is critical that a programme’s vision, the outcomes it aims to deliver, are unambiguously communicated to all implementing partners at the very beginning. This is critical to ensure alignment between the partners’ interventions and a programme’s overall, portfolio level objectives. Often this is not easy, and more complicated if the number of implementing partners is large, which increases the risk of lack of coordination among them and a lesser focus on the programme’s portfolio level objectives. Any future programmes are recommended to spend enough time and resources in the inception phase on making sure the implementing partners fully understand and can be held accountable for delivery against the programme’s ToC and stay focused on the programme’s overall vision as well as their own specific outputs and deliverables.

Set up Monitoring, Evaluation and Learning (MEL) processes that generate stronger accountability from implementing partners for converting output level results into outcome level change: The bulk of AERP’s activity involved providing Technical Assistance (TA) —capacity building TA through trainings, workshops, and consultations and knowledge TA through delivering various types of knowledge products. Without setting up mechanisms that generate accountability from implementing partners to invest time and effort in increasing the likelihood of TA deliverables leading to longer-term outcome level change, programmes run the risk of focusing too much on output level products rather than outcome level change. This risk is higher in programmes where the volume of output level products and services is very large, such as in AERP. One way of creating these accountability mechanisms would be to include output and outcome level qualitative indicators in programme logframe that push implementing partners to consistently measure the effectiveness of TA. These indicators can be used in addition to quantitative measures, which simply focus on the volume of materials produced.

Limiting the number of logframe indicators: AERP’s Logframe included 37 output-level indicators. Indicators are fundamental tools for generating knowledge about a programme’s performance, requiring strong quality assurance mechanisms in place to ensure the collected data are of high quality. Having a higher number of indicators directly impacts the efficiency of quality assurance, particularly in case of regional programmes where data are collected across multiple countries, with bulk of programme management delivered centrally. A recommendation from this review for FCDO’s future programming is to consider having a smaller number of logframe indicators.

Having a dedicated MEL adviser or an external MEL organisation involved in the programme: For a regional programme of AERP’s size and ambition, particularly if it chooses to focus on as many sub-thematic areas, this PCR recommends that having an independent MEL adviser can help improve the programme’s overall effectiveness and, therefore, its Value for Money (VFM). The programme can use a MEL partner’s services particularly for effective monitoring—ensuring the quality of data provided by implementing partners, applying qualitative indicators and contribution analysis at output level to measure TA effectiveness, and ensure effective coordination among the programme’s various pillars and partners. The focus on monitoring will not require a large MEL budget and can make a big difference in keeping a programme on track toward outcome level change.

More specific outcome indicators: AERP’s Logframe used relatively generic outcome indicators, such as indices developed by outside organisations that publish annual country level rankings on governance, corruption, and other high-level variables.[2] Such indicators are recommended only for impact level, and rarely for programme outcomes. Using trends in annual country rankings is usually too high-level to capture a programme’s outcome level progress. For AERP, having these indicators in the logframe made capturing progress at outcome level accurately more difficult. Programme outcome level indicators should be narrower and more targeted, directly reflecting what is possible to achieve with small-scale knowledge and skills TA within the programme’s lifetime. For any future programming, this PCR highly recommends the use of more specific outcome indicators, developed in consultation with a programme’s implementing partners.
[2] The Indices used in AERP Logframe include, for example, World Economic Forum’s Global Competitiveness Index, Corruption Perception Index by Transparency International, and the Rule of Law Around the World Index.

Ensuring better coordination amongst different implementing partners and programme components: It can be helpful for a programme spread across a big regional geography, with many implementing partners and thematic focus areas, to periodically come together as a whole and take stock of how well the programme is moving forward toward its overall outcomes, ask what the partners and pillars can learn from one another and share learnings and lessons. Prior to COVID-19, there was an annual regional Prosperity Fund Forum which serviced this function. However, for two of the key years of AERP delivery, 2020 and 2021, this was impossible due to the pandemic. It is recommended that any future programme taking a similar approach to delivery should do this more consistently over the programme’s lifetime.

Having a dedicated Gender and Inclusion (G&I) strategy from the beginning, along with permanent G&I advisory support: For future programmes, this PCR recommends developing a programme level Gender and Inclusion (G&I) strategy at the beginning, with measurable indicators and possibly a dedicated social development expert to provide consistent guidance to the programme on this issue. Future programmes should both mainstream G&I into delivery, as well as look to develop targeted G&I workstreams where appropriate and in alignment with objectives. The ambition should be higher than to just secure equality of participation. Expectations on this should be made clear to delivery partners at the outset. It is also recommended to assess the viability of using Service Level Agreements (SLAs) in commercial contracts to encourage constructive development of G&I initiatives.

Provide an improved standard for project closure reporting from partners: It is recommended that future programmes work closely with delivery partners at the outset to agree expectations regarding reporting, and to ensure that they have the necessary capability and capacity to meet this expectation. This is more important in technical assistance interventions that target specialised, technical areas where more clarity may be needed on what was delivered. Reporting templates should guide the provision of clear information, particularly on what a project’s aims and activities were and what it managed to achieve. All achievements should be supported by robust evidence. This standard should be applied equally across all projects, irrespective of the size, for the sake of quality assurance.

This report is based on the information collected from the project closure reports submitted by various delivery partners of AERP and previous FCDO Annual Reviews of the programme. In addition, the PCR team conducted a total of twenty-five interviews, including with programme beneficiaries, key implementing partners, and FCDO personnel associated with the management and delivery of the programme over its lifetime. The assessment of achievements, lessons and recommendations, reported in this review is based on a holistic view of the evidence available, beneficiaries’ account of the support they received through this programme, and an overall assessment of how much the output level TA deliverables converted into outcome level change as described in the AERP logframe and business case.

## B: Theory of Change and Outcome Assessment

	Starting point	Final result
Budget	£19 million (increased to £21.4 million in May 2022)	£19.66 million
Timeframe	October 2018 – March 2022	October 2018 to June 2023

Overall assessment of programme outcomes, sustainability and VfM

A number of AERP’s output level deliverables have supported changes or improvements that are now permanently part of beneficiary systems, serving as examples of AERP’s sustainable impact. For example, the online training and skills building course for SMEs, developed with AERP’s support, is now permanently part of Indonesia’s National Public Procurement Agency’s online interface and continues to be used by Indonesian small businesses to learn more about and improve their capacity to bid for government contracts. Similarly, a strengthened case for FinTech reform in Indonesia for financial inclusion is now part of the Omnibus Law on Financial Inclusion passed in January 2023. The CoST methodology approaches incorporated by multiple provincial governments in Thailand and Indonesia to make infrastructure public procurement more transparent will continue to result in significant cost savings to the respective governments in future. There is also strong evidence that a large number of output level products and services—trainings for capacity building; knowledge and policy products filling the beneficiaries’ knowledge gaps; and a variety of consultative support, building capacity in different ways—have increased the likelihood of outcome level changes happening in future. These achievements—outlined upfront in this PCR—are captured by intermediate outcome indicators in AERP’s logframe.

However, at the time of conducting this PCR, it has been difficult to measure with certainty the extent to which AERP’s output level activity resulted in longer term sustainable outcome level changes, despite the positive indications and evidence noted above. This is largely due to not having enough qualitative indicators in place or robust enough MEL processes that could measure the effectiveness of the AERP TA over the longer term and directly link the output level activity to the intended programme outcomes. This is often the case when trying to measure the long-term impact of TA support, but finding evidence in support of AERP’s outcome level changes was made particularly challenging by the use of very high-level, external indices as outcome indicators and the lack of qualitative TA effectiveness indicators which could have provided more evidence on whether beneficiaries are engaging with the TA material and transferring the skills and knowledge gained to improve intended outcomes.

This PCR assessment shows that AERP scores highly on VfM overall despite the complexity of a programme covering broad thematic focus areas, multiple implementation partners and many countries. The programme’s wide-ranging activities also supported ASEAN economic integration through national level policy advice and technical assistance and there is strong VfM evidence supporting this type of approach for economic development (see section D for detailed VfM assessment).

AERP Logframe Outcomes	Contributing achievements
Strengthened and harmonised Business Environment frameworks for domestic and foreign firms, including UK companies	AERP support to business licensing reform procedures in Indonesia is contributing to an improved—faster and easier—business registration process, particularly for small, low-risk businesses. / In the Philippines and Vietnam reforms are underway following support from AERP, leading to reforms such as Philippine Good Regulatory Principles (PGRPs) and the Whole of Government re-engineering and e-Consultation in the Philippines. The PGRP serves as the Philippines' regulators code, informed by the UK's own regulators code. The reengineering process has helped reduce the process cycle time for availing government services (from a months’ long process to just a week, and in some agencies just a few days or hours, depending on the service), and put a premium on transparency in government operations. The reengineering has also helped to inspire the new administration in 2022 to push for e-governance (through an impending E-governance bill) to further facilitate and improve government services. / In Vietnam, AERP supported the development of Resolution 68 2020, a government resolution which aims to tackle red tape and as a result make the business environment more enabling. / A strengthened, more harmonised business environment also means one that is inclusive and offers equal opportunity to relatively disadvantaged groups to participate in private entrepreneurship. AERP’s support to women business owners in Indonesia and Thailand has improved their ability to bid for government contracts. / AERP’s support is also making the business environment more inclusive for SMEs in AMS, making it easier for them to grow their businesses, removing various information blocks, and providing better platforms to them for connecting to business opportunities. / The IP enforcement manuals developed for Indonesia, the Philippines and Vietnam as well as an ASEAN IP Enforcement manual address the lack of adequate IP enforcement information in ASEAN countries, therefore facilitating IP protection for businesses. / In the Philippines, AERP engaged representatives from the e-commerce industry to sign an MOU with the Intellectual Property Office of the Philippines (IPOPHL) to operationalise the proposed systems and procedures to improve the e-commerce enforcement regulatory regime in the country. / AERP provided critical consultation services and recommendations for making amendments to Indonesia’s copyright law. Once the law is amended it will help protect creators’ rights to benefit from their own work. / Under the OECD delivered component, AERP made 30 recommendations to AMS, outlining where changes could be made to mitigate harm to competition from regulatory barriers and to foster competition.
Improved business practices adopted, and corruption risk minimised to create a fairer Business Environment in ASEAN.	Provincial level support for improving transparency in governments’ infrastructure procurement processes (Indonesia and Thailand) is contributing to reduced corruption and more transparency in government procurement, providing stronger incentive for business to bid for government contracts. / Support for women-led businesses to participate in public procurement (Indonesia) by developing a gender-responsive procurement programme; 60% of the women involved have registered on the governments’ e-procurement platform, and 4 have already won public contracts. / Support for women to improve their business practices to promote business integrity. In Thailand, four out of the sixty companies have integrated integrity policies into their operations by implementing new policies or reviewing existing ones. One of these initiatives was about provision of equal pay for both Myanmar and Thai workers, which resulted in recognition nationally and internationally as a ‘responsible’ organisation, in turn increasing client’s and investors’ interest in the business. / 242 companies in ASEAN joined responsible business conduct initiatives, and 20 companies adopted business integrity instruments within 6 months of receiving training from AERP. / AERP, through the FairBiz project, supported the development of national anti-corruption policies and legislation to improve the fair business environment. In Malaysia the project contributed to the development of the National Anti-Corruption Plan in 2019 and in Vietnam, supported changes to the anti-corruption law to include provisions on business integrity. In Thailand, the project assisted with the amendment of the national Anti-Corruption strategy and in Myanmar (pre 2021), Fairbiz supported the establishment of Corruption Prevention Units (CPUs) in Ministries (2019) and the training of civil servants for the CPUs (2020).
More inclusive, efficient and diversified financial markets to create new financing opportunities for businesses and individuals.	Overall, a large number of output level TA products and services delivered under AERP’s FSIP component, across multiple AMS, should help the targeted beneficiaries practice more innovation; more easily and quickly access credit; and make the financial markets more inclusive, through initiatives like better integration of Financial Technology services into economy. However, there is only limited evidence at this early stage that these output level deliverables will lead to outcome level change over the longer term. / The Central Bank of the Philippines (BSP) has incorporated advice provided on Regulatory Tech tools into Financial Services Regulation. The BSP introduced the Open Finance Framework, which empowers customers by giving them better control over their personal and financial data, catalysing the development of products and services which are responsive to their needs. / In Indonesia, following research on procure to pay (P2P) lending by AERP’s FSIP component, the regulatory framework has been updated to better enable broad access to financing via P2P lending platforms for all individuals, but especially to underbanked communities and SMEs. / Launch of a FinTech Sandbox in the Philippines – the pilot ensured all three initial problem statements focused on financial inclusion. / Nearly 1750 regulators received training on international accounting standards in the Philippines, Thailand, Vietnam, and Myanmar. The training will assist these countries to align to align better with International Financial Reporting Standards (IFRS). / Islamic finance services provide new financing sources to MSMEs, including funding to support vulnerable communities affected by disaster. FSIP provided support to establish an Emergency Waqf-linked investment fund, involving 28 stakeholders including government agencies, asset management companies, CSR arms, State Islamic Religious Council, NGOs and Academia. The programme manged to secure funding from the Ministry of Finance of RM 3.3 million (£556,000) as part of the initial investment launch, evidencing government buy in to the concept and the potential for the fund to grow and be sustainable.

Summarise the programme’s theory of change and results framework, including any changes to outcome indicators.

AERP’s intended impact is to help generate more inclusive economic growth and poverty reduction in ASEAN. The principal pathways the programme used to deliver this included: creating a more enabling business environment and improving a range of public financial and business services (through reform and capacity building) which are critical to well-functioning businesses and markets. The business case identified four outcomes for the programme: business environment integrity improved; ease of doing business improved; efficiency of finance allocation improved; and inclusivity of financial systems improved. However, these could have been defined in greater detail. AERP’s business case included the World Bank’s Ease of Doing Business reports as a metric. In September 2021, the World Bank ended its entire Doing Business project after data irregularities were reported in 2018 and 2020.

The programme’s portfolio level logframe narrowed down the four business case outcomes into three outcome statements. These remained with the programme throughout its lifetime:

Outcome 1: Strengthened and harmonised business environment frameworks for domestic and foreign firms. including UK companies.
- Performance in the Global Competitiveness Index, such as: 7.01 Distortive effect of taxes and subsidies on competition.
- Performance in the Global Competitiveness Index, such as: 7.02 Extent of market dominance.
- Performance in the Global Competitiveness Index, such as: 7.03 Competition in Services.
- Business environment ranking (WB EODB Survey).

Outcome 2: Improved business practices adopted, and corruption risk minimised to create a fairer Business Environment in ASEAN.
- Change in the Rule of Law Around the World. Scores range from 0 to 1, with 1 indicating the strongest adherence to the rule of law.
- Change in the 'Incidence of corruption' rank in the World Economic Forum, Global Competitiveness Report.
- Open Budget Survey (KPI 11).

Outcome 3: More inclusive, efficient and diversified financial markets to create new financing opportunities for businesses and individuals.
- Philippines Capital Adequacy Ratio.
- Vietnam Total Equity % ('Total Equity Market Value/GDP)
- Vietnam CM Equity % (Total Equity Trading/Total Equity Market Value)
- Number of MSMEs supported by new IF services.
- Number of women-led medium and small and medium enterprises supported by financial services.

To realise the above high-level outcomes, AERP used skills-building and knowledge TA pathways across a dozen sub-thematic areas spanning the conceptual categories of business environment, financial services, and business services. Given the multiple pathways, across multiple countries with eighteen implementing partners, the programme delivered a large quantity of output level products and services—reports, studies, policy papers, trainings, workshops, and consultations. A major portion of TA services were delivered online due to the COVID19 outbreak just when the programme was taking off. As already detailed in the lessons and recommendations section, AERP’s ToC could have been more specific. The ToC could have narrowed down the programme’s conceptual or thematic focus areas and set up better definitional clarity on the nature of real world changes the programme sought to achieve.

Results Framework/Logframe
As noted previously in the report, one of the challenges of AERP was that the detailed logframes were not developed and agreed early enough in the process, prior to funding arrangements being signed with delivery partners. This meant that the programme team were in a weaker negotiating position when it came to agreeing milestones and targets, potentially curtailing a higher level of ambition. The programme team and MEL advisers worked closely with delivery partners to finalise their logframes over a number of months and to ensure that they effectively fed into the portfolio framework. The process was challenging, particularly working with a range of delivery partners with differing levels of knowledge and expertise of MEL.

Further challenge was caused by the regular requirement to revise work plans and budgets as a result of the pandemic and the ODA budget changes. This work took priority over updating logframes, which meant that the logframes became further compromised as a useful tool. At the same time, the external MEL resource was withdrawn when the Prosperity Fund closed and the programme transferred to FCDO. As highlighted above, any future programming should ensure that there is sufficient programme management capacity and MEL expertise in place throughout to manage a complex programme like AERP and ensure that the MEL frameworks can be updated efficiently when programme changes are introduced.

## C: Detailed Output Assessment

	FSIP: Inclusive Intellectual Property (IP) capacity building through knowledge sharing and technical assistance to improve IP and related legal/policy frameworks, regulation, and practices
Output Score	A+
Impact weighting (%)	5%		Impact weighting revised since last AR?	NA

Output Indicator		Final Logframe Target	Final Result Achieved
No. of new or improved IP policies, standards and regulations including targets, mandates, incentives and roadmaps that have benefitted from FSIP’s support.		2022: 11 (end of programme target)	18 total achieved

This output covered a total of 30 work packages with 8 being closed throughout the second and third year of the programme. Through the provision of TA, capacity building and knowledge sharing assistance, these work packages sought to improve IP and related legal/policy frameworks (e.g. IP valuation, IP commercialisation, IP creation), as well as enforcement of these regulations. Achievements include development of IP Manuals for Indonesia, the Philippines, and Vietnam to address the lack of adequate IP information in AMS. Across the three countries, the manuals were promoted and published on several channels including the British Chamber websites and the UK-ASEAN Business Council website. The programme also developed an ASEAN-wide IP manual which compiled IP laws and procedures for 10 AMS to assist businesses/investors with IP rights who would like to invest in any of the AMS. In Indonesia, the programme provided continued support to stakeholders for execution of recommendations on the e-commerce regulatory regime and submitted a report on issues with the e-commerce regulatory regime. In the Philippines, the programme delivered a report on the IP Finance ecosystem with recommendations on how to develop a functioning IP financing ecosystem. Another key achievement in the Philippines was the finalisation and signing of an MoU between the e-commerce platform and IP owners to establish an industry code of practice. In addition, the programme delivered a number of IP capacity building webinars and online workshop in Vietnam, the Philippines, and Indonesia, overall exceeding the indicator target.

The programme’s IP workstream design resulted in 30 work packages ranging in size from £7,000 to £80,000. Significant time was invested engaging with beneficiaries for ownership and buy-in, and in the administration of the work packages. This potentially diverted resources from focusing on building on successful outputs to grow impact. A recommendation for future programmes is to build in more time and accountability mechanisms in programme results frameworks for focusing more on converting output level TA into sustainable improvements in IP legal and policy frameworks.

	In-House IP: Inclusive IP capacity building through knowledge sharing and technical assistance to improve IP and related legal/policy frameworks, regulation and practices
Output Score	A+
Impact weighting (%)	3%	Impact weighting revised since last AR?	NA

Output Indicator		Final Logframe Target	Final Result Achieved
Number of delegates reporting having used learning from the capacity building activities after 6 months.		2022: 160 (end of programme target)	Total: 258 achieved.
Number of non-PF funded industry speakers delivering sessions at each capacity building seminar.		2022: 42 (end of programme target)	Total / 44 achieved

This output was delivered in-house by FCDO and overseen by the UK Intellectual Property Office (IPO). The majority of activity involved capacity building through training across two strands: IP enforcement and IP innovation. The training sessions were originally delivered in person but later shifted to online delivery due to travel restrictions. These trainings also increasingly focused on e-commerce IP capacity given the sharp rise in usage of e-commerce platforms due to the pandemic. The main activities included:
- UK-ASEAN IP Enforcement Seminar 2022 + ANIEE (Ecommerce Code of Conducts, Regulations, and Challenges; Data Protection Issues; ISP Liabilities and Customs Challenges; Improving FTZs);
- UK-ASEAN IP Enforcement Webinar Series 2021 Part 1 (Illicit Trade & Substandard Drugs)
- UK-ASEAN IP Enforcement Webinar Series 2021 Part 2 (FTZ, Customs and Environmental Impact of Counterfeits)
- UK-ASEAN IP Ecommerce Webinar 2021 (IP Enforcement & Ecommerce Policies)
- UK-ASEAN IP Innovation Webinar 2021 (IP Innovation Tactics for MSMEs, Manpower Development and Skills; Venture Capitalists)
- UK-ASEAN IP Innovation Webinar 2020 Part 1 (IP & Innovation Policy & Strategy Development)
- UK-ASEAN IP Innovation Webinar 2020 Part 2 (IP & Vaccines, Commercialisation & IP Analytics; Innovation & Entrepreneurship)
- UK-ASEAN IP Enforcement Webinar Series 2020 Part 1 (Digital Piracy)
- UK-ASEAN IP Enforcement Webinar Series 2020 Part 2 (Ecommerce)
- UK-PHL IP Judges Colloquium 2020 (Online IP Infringements, Enforcement Strategies, Prosecution Approaches); Philippines
- UK-Indonesia Copyright Seminar 2019 (Policy Development & Strategies for MSMEs Support); Indonesia
- UK-ASEAN IP Enforcement Seminar 2019 + ANIEE (IP Crimes, Investigation Techniques, Enforcement for Economic Growth); Philippines
- UK-ASEAN IP Enforcement Seminar 2018 + ANIEE (IP Enforcement Coordination); Thailand
The capacity building sessions enabled ASEAN and the UK to build strong policy networks to share experiences and deepen opportunities for regional collaboration. The sessions also partnered ASEAN’s IP enforcement committee – ASEAN Network of IPR Enforcement Experts (ANIEE) – to support ASEAN’s IP Enforcement Action Plan and forged close relations with ASEAN’s IP enforcement co-chairs (Philippines and Thailand). AERP’s business case set out the objective of achieving ‘progress in implementing ASEAN IP action plan, especially on enforcement including online trademark infringement and engage regional online intermediary platforms on their IP policy.’ This output was particularly used to achieve this objective. The delivery partner has reported that participants have actively used the learning and knowledge gained from the training sessions in their work.

	ROUSE: New or improved policies, standards, and regulations.
Output Score	A
Impact weighting (%)	2%		Impact weighting revised since last AR?		NA
Output Indicator		Final Logframe Target		Final Result Achieved
No. of new or improved IP policies, standards and regulations including targets, mandates, incentives and roadmaps that have benefitted from the project's support.		2022: 2 (end of programme)		2

The workstream delivered by ROUSE started late in AERP’s lifetime in August 2022, after the IP work strand under the FSIP project, delivered by PwC, formally ended in March 2022. The activities were an extension of the work delivered by PwC with three objectives: 1) coordination and consultation meetings with key authorities in Indonesia to discuss the e-commerce IP regulatory regime; 2) to identify the impact of Cambodia’s new e-commerce law for IP enforcement of infringing goods on e-commerce platforms; and 3) provide evidence to ASEAN authorities and platforms on the gaps in best practices.

A range of activities were delivered under the Indonesia e-commerce project, Cambodia e-commerce project and e-commerce Gap Analysis. In Indonesia, activities involved consultations with Director General Intellectual Property (DGIP); with the Ministry of Communication and Information Technology and Ministry of Trade to disseminate issues of e-commerce in the country. In Cambodia, activities included consultations with Department of Intellectual Property (DIPR) and Ministry of Commerce. Under the e-commerce gap analysis activities included research on e-commerce regulatory regimes and their implementation in each country; analysis of e-commerce regulations in ASEAN countries and their effectiveness in supporting IP enforcement and reducing IP infringement.

The main achievements include a better understanding and capability within Indonesia’s DGIP and Cambodia’s Ministry of Commerce on ecommerce IP protection than before. The ecommerce gap analysis work strand produced the first comprehensive analysis of all ecommerce IP issues in the ASEAN region – both regulatory and platform IP policies; and the creation of benchmarks which can be used for years into the future. This work strand also created a new level of engagement with ASEC and ASEAN on ecommerce IP issues, setting the stage for longer-term action by ASEAN in this area.

	Multi-delivery strand: Increased capacity building and collaboration with government stakeholders to improve regulatory practices
Output Score	A
Impact weighting (%)	18%	Impact weighting revised since last AR?	NA

Output Indicator (RDI BEIS)		Final Logframe Target	Final Result Achieved
Number of recommendations proposed for adoption to Govt. of Philippines, Govt. of Vietnam, or Govt. of Indonesia for implementation /revision of laws, regulations, rules and/or administrative practices to improve business environment (Cumulative)		2023: 12 (end of programme target)	15
Number of officials trained (gender disaggregated) (Cumulative)		2023: 700 (end of programme target)	670
% of positive feedback from selected domestic and international business organisations on reform plans and processes and views about future improvement		2019: (50% planned) / 2020: (75% planned) / 2021: (80% planned) / 2022: (80% planned) / 2023: (80% planned)	Unquantified; positive qualitative feedback from business organisations

Output Indicator (International Chamber of Commerce) Digital Trade Project, Thailand.	Final Logframe Target	Final Result Achieved
Number of delegates participating in the workshops who increased their knowledge and understanding of the development and implementation of electronic transferable records	2023: 150 (end of programme target)	211 achieved

Output Indicator (Open Contracting Project, BMA, Thailand)	Final Logframe Target	Final Result Achieved
Delivery of an action plan containing options for open contracting implementation and next steps for Bangkok Metropolitan Administration’s procurement system that promotes open contracting in Thailand	2023: 1 (end of programme)	1 achieved

Output Indicator (ODI) Open Data Initiative, BMA, Thailand.	Final Logframe Target	Final Result Achieved
Delivery of an action plan containing a roadmap and recommendations for Bangkok Metropolitan Administration to become an open city that promotes the use of open data in Thailand	2023: 1 planned (end of programme)	1 achieved

Output Indicator (ASEAN Sustainable Leadership in Infrastructure Programme)	Final Logframe Target	Final Result Achieved
Number of delegates from ASEAN Member States who participated in the ASEAN Sustainable Leadership in Infrastructure Programme (ASLIP)	2023: 10 planned (end of programme)	16 achieved

Output Indicator (ASLIP)	Final Logframe Target	Final Result Achieved
Development of an executive leadership programme on sustainable infrastructure agreed by ASEAN and accredited by Cambridge University	2023: 1 planned	1 achieved

Output Indicator (Digital Financial Advisory Services)	Final Logframe Target	Final Result Achieved
Delivery of the G20 High Level Digital Financial Inclusion Principles Framework publication	2023: 1 planned	1 achieved

This output reflects AERP activities delivered by multiple implementing partners, targeting capacity building of government agencies in Indonesia, Vietnam, the Philippines, and Thailand to strengthen selective regulatory practices and frameworks related to all three pillars of AERP—business environment, business services, and financial services. The bulk of activities were delivered under the ASEAN Regulatory Reform component delivered by the Office for Product Safety and Standards (OPSS) in the UK’s Department for Business and Trade (DBT). The activities included delivery of technical assistance to build capacity of government officials on good regulatory practices, supporting the development and harmonisation of new laws and policies in partner countries, and improving the delivery (enforcement) of regulation. This was combined with ongoing support provided by a local regulatory reform attaché, as the country lead for the programme, establishing and maintaining relationships with key stakeholders in the region and supporting and supplementing the delivery of technical and capacity building missions.

Major achievements include the reform in Indonesia to a risk-based business licensing system, as a result of which businesses are now categorised as low, medium-low, medium-high or high risk with a graded scale of requirements from simple registration, through self or third party certification of compliance with an ‘operational standard’ to a government-issued ex-ante licence. The transition to risk-based approach licensing has already delivered significant increases in new formal business registrations. In the Philippines, OPSS supported the design and implementation of a Whole-of-Government (WOG) approach to streamlining government systems and procedures to deliver public services and the development of a Security Manual, setting out an approach to monitoring and evaluation of the reengineering efforts by guiding the assessment of progress made by the agencies to implement the WOG approach. The programme also supported the development of the Philippine Good Regulatory Principles based on the UK’s Regulators’ Code. The principles will help to improve accountability, facilitating an open and constructive relationship and dialogue between regulators and those they regulate.

In Vietnam, OPSS supported the development of Resolution 68 2020, which aimed to tackle the red tape challenge in Vietnam and was modelled on the UK Government’s Administrative Burdens Reduction Programme (ABRP, 2005-2010). Through streamlining regulations, reducing costs for businesses, and freeing up business resources, Resolution 68 is expected to help improve the business environment, boost productivity as well as attract more investment from foreign companies, including those from the UK.

A series of shorter projects (6 months) in Thailand delivered capacity building workshops to government stakeholders, including:
1. Open Contracting project: Support to Bangkok Government to apply Open Contracting practices and data standards to promote more open, efficient, and inclusive public procurement.
2. Open Data project: Promoting Transparent, Open, Inclusive and Efficient Government in Thailand through working with Bangkok government to become an ‘open city’ and adopting the ODI’s approach towards using open data, open standards, open source, open innovation and an open culture.
3. Digital Trade project: Adopting and Implementing Electronic Transferable Records in Thailand to support more Thai and international companies to trade cheaper, faster, simpler, and become more environmentally friendly through digital technologies.
4. Open Banking project: Sharing the UK and international experiences to support the Bank of Thailand’s policy decision towards potential implementation of open banking in Thailand to promote inclusion, competition, and inclusivity of financial sector.
5. Digital Identity project: Supporting the Development of a simple and inclusive Digital Identity Verification in Thailand, in alignment with global best practices.

Key lessons from this output include:
- For in-country regulatory reform work, it is best to use locally based regulatory reform attaches who are subject matter experts and help the programme gain traction with respective governments, accelerating the MoUs, helping a programme move more quickly into implementation.
- For any future regulatory reform work, it is recommended that a flexible approach is taken, which can be responsive to the political context and institutional strengths of individual countries. Taking a standardised approach which is not responsive to these factors could affect government willingness to initiate reform.

5.	OECD: Increased adoption of recommendations on use / misuse of competition assessments and special rights and privileges of SOE’s
Output Score	A
Impact weighting (%)	12%	Impact weighting revised since last AR?	NA

Output Indicator		Final Logframe Target	Final Result Achieved
Number of Competition Authorities reporting increased knowledge and usage of competition assessment (Cumulative)		2021: 10 achieved (6 planned)	10 achieved (6 planned)
Number of recommendations Competition Authorities or other Government regulators say they support for implementation, have implemented or may recommend for implementation. (Cumulative)		2021: 30% achieved (20% planned)	30% achieved (20% planned)
Policymakers reached via stakeholder meetings, launch events and workshops as a % of key stakeholders that attended the launch events		2021: 80% achieved (100% planned)	80% achieved (100% planned)

This output covers AERP’s work to support the implementation of Outcomes 4.1.2 and 4.2.1 of ASEAN Competition Action Plan 2016-2025. Delivered through OECD, the activities mainly involved reviewing regulatory constraints on competition in all ten AMS to identify regulations that hinder the efficient functioning of markets and/or create an un-level playing field for business. The project covered five sub-sectors, including freight transportation, freight forwarding, small package service delivery, warehouse services, and value-added logistics services. The implementing partner reviewed over 700 laws and regulations in AMS and consulted with more than 280 public and private stakeholders.

The achievements included issuing reports for each AMS covering a competition assessment review of the targeted sub-sectors and a competitive neutrality review of small-package delivery services. These reports provided over 660 country-level recommendations. Highlights were also prepared for each report. In addition, OECD also published two regional reports that compiled the key findings at the ASEAN-wide level. These reports provided over 70 regional-level recommendations. The reports and their corresponding highlights were published and made available for download.

The work delivered under this output achieved buy-in at the highest political levels in ASEAN countries. It is the only time a non-ASEAN report has been launched at an ASEAN Ministerial meeting (September 2021, ASEAN Economic Ministers Meeting) indicating its strategic relevance at a political and working level. It was launched with all 10 Economic Ministers of ASEAN, as well as the UK Minister for Trade Policy and the Secretary Generals of ASEAN and of the OECD. In order to increase the likelihood of implementing the recommended policy changes, the OECD has worked closely with all relevant public and private stakeholders, including government and competition authorities, to ensure buy-in for the proposals.

A lesson from this output is that delivery should include clear mechanisms for the implementing partner to focus on ensuring governments actively engage with policy recommendations after they are delivered and possibly consider providing targeted support on recommendation implementation and uptake.

	UNDP: Strengthened partnerships between civil society and public and private sectors to implement and monitor integrity policy, opening participation for women and underrepresented groups.
Output Score	A
Impact weighting (%)	7%	Impact weighting revised since last AR?	NA

Output Indicator		Final Logframe Target	Final Result Achieved
4a (a): Number of learning & knowledge platforms for Government – private sector and civil society policy dialogue (UNDP Output Indicator 1.1) / (Cumulative)		2022: 6 (end of the programme target)	6 achieved
4a (b): % of involved stakeholders reporting feeling more comfortable on dialogue on integrity and transparency with counterparts following participation in the platforms (disaggregated by gender) - referring to the ability of understand and trust each other and work for common goals		2022: 99% end of programme target (98% achieved)	98% achieved
4a (c)# stakeholders engaged through the regional platforms (sex-disaggregated and sector-disaggregated: public sector, private sector, CSO...) (Cumulative) / * This indicator was introduced in March 2020		2022: 4200 end of programme target.	4456 achieved

UNDP delivered AERP’s second largest component, utilising approximately £6.4 million of the programme’s total budget. The component titled, Promoting a Fair Business Environment in ASEAN, partnered with governments, private sector, and civil society in Indonesia, Malaysia, Myanmar, the Philippines, Thailand and Vietnam, focusing on four areas of intervention:
- To foster partnerships between public and private sectors and civil society, including women and under-represented groups.
- To strengthen public procurement systems through transparency and open contracting tools.
- To promote business integrity and sustainable practices for private companies and state-owned enterprises.
- Improve anti-corruption policies and redress mechanisms in target countries.

The first intervention area, represented by this output, included a range of activities focused on bringing together organisations and individuals from private sector, public sector, and civil society to generate open conversations around sensitive issues such as corruption in the business environment and making it more inclusive. The FairBiz component used this as a pathway to reducing corruption, or improving transparency, in the business environment. FairBiz engaged the interest and support of more than 6,000 stakeholders in the private and public sectors, and CSOs, through six thematic regional platforms and working with 400 companies.

Key achievements include training 100 women-led businesses in Indonesia in business integrity and how to access government procurement contracts under the “SHE-BID” initiative. As a result, 68% of the businesses opened an account on the government’s procurement system, 33% took part in bids, and four participants won a tender with the Indonesian Government. In Malaysia, FairBiz trained 21 SMEs in the multinational healthcare company supply chain on how to strengthen their codes of conduct and internal control systems. Within three months of the course, four of the SMEs had adopted business integrity instruments. Also, through south-south exchanges between Malaysia and Vietnam, companies in both countries have restructured their internal policies, developed new employees’ regulations, whistleblowing mechanisms, and a responsible supplier sourcing strategy in line with FairBiz promoted principles. In partnership with the Federation of Business Professional Women of Thailand, FairBiz developed programmes to promote the agency of women in fostering a fair business environment, creating more equitable workplaces, promoting responsible practices and tackling integrity challenges in their organizations.

A lesson from this project is that future programmes could more clearly define what is meant by partnerships. Even though FairBiz used “partnerships” in their output level statement, a specific definition was not given. Activities delivered under this output often seemed focused on bringing stakeholders together to generate conversations rather than necessarily about fostering longer term partnerships. Lack of clarity about intended aims creates barriers to programme effectiveness as it can lead to less focused (less effective) use of programme resources.

	UNDP: Improved transparency in government contracts and increased compliance with international procedures and trade standards
Output Score	A
Impact weighting (%)	7%	Impact weighting revised since last AR?	NA

Output Indicator		Final Logframe Target	Final Result Achieved
4b (a) # of countries that have established open and innovative service delivery mechanisms. / (Cumulative)		2022: 3 (end of programme target)	3 achieved (3 cumulative)
4b (b) # of new infrastructure projects where data is disclosed by governments of Thailand and Indonesia following CoST methodology (Cumulative)		2022: 1500 end of programme target	2425 achieved
4b (c) CoST West Lombok and CoST Thailand uses the guidance developed by the CoST IS to promote and increase the participation of women (Cumulative)		2022: 2 (end of programme target)	3 achieved

This output covered various initiatives delivered by the FairBiz component to improve public procurement transparency in Thailand, Indonesia, and the Philippines. To deliver some activities under this output, UNDP partnered with the Infrastructure Transparency Initiative (CoST). Major activities included training of trainers in Indonesia to enhance the performance of public procurement suppliers; a workshop in Thailand with the Comptroller General’s Department (CGD) to illustrate impediments in the current international tendering system and provide practical and detailed recommendations for its improvement; a workshop delivered to Comptroller General’s Department (CGD), Thailand, engaging the UK Government Digital Service to share knowledge with Thai officials on how they established a comprehensive e-platform to facilitate service providers in public tendering both at the technical level and the regulatory framework; a two day workshop in Thailand with the Office of the Public Sector Development Commission (OPDC), and with the support of the UK Government Digital Service, on achieving digital transformation in Thailand.

Key achievements for the output include application of CoST’s transparency and open contracting tools at the provincial level in Thailand, building transparency into the provincial governments’ infrastructure procurement mechanisms. This contributed to the Chachoengsao provincial government’s cost savings of an estimated US$73 million as result of the deterrent effect of the CoST approach to procurement. Furthermore, the programme delivered a study on a centralised system of public procurement in Indonesia offering recommendations to the Government for mitigating procurement misconduct, including human resource development, amendments to laws and regulations, improvement of the electronic procurement system, environmental procurement conditions and monitoring system. FairBiz also developed an online course in coordination with National Public Procurement Agency of Indonesia to improve the capacity of SMEs to access the e-procurement system, providing practical guidance to participate in government bids.

This output produced a set of knowledge products for government beneficiaries in Indonesia, Thailand, and the Philippines, offering recommendations for and better understanding of improving transparency in public procurement systems. It is recommended that future programmes should also focus significantly on the dissemination of these knowledge products for them to be able to contribute to the desired outcome level change. Building activities into the delivery that focus on going back to the recipients of a workshop or training or report, after a gap of 4 to 6 months, to gauge how well the learners have engaged with the material can increase the likelihood of outcome level change.

	UNDP: Adoption of responsible business practices & good corporate governance including gender and diversity by private companies & state-owned enterprises (SOEs)
Output Score	A
Impact weighting (%)	7%	Impact weighting revised since last AR?	NA

Output Indicator		Final Logframe Target	Final Result Achieved
4c (a): # of business integrity instruments adopted (trainings and/or tools on code of conduct, internal control mechanisms or whistleblowing mechanisms developed for business sector) / (Cumulative)		2022: 44 (end of programme target)	48 achieved
4c (b) # of companies in ASEAN that have joined responsible business conduct initiatives by project. / (Cumulative)		2022: 200 (end of programme target)	242 achieved

This output focused on partnering with major private sector corporations and networks to provide companies with practical tools for raising standards and operating with integrity, especially SMEs operating in multinationals’ supply chains. Activities under this output included:
- Trainings and mentoring to help women business owners strengthen their capacity and knowledge of how to combat corruption in Indonesia and Thailand.
- A pilot initiative on compliance in Malaysia attended by fifty companies, part of the supply chain of two multinational corporations.
- Two trainings for women led companies on Business Integrity in Thailand, reaching fifty-nine companies.
- Two trainings for SMEs on empowering women entrepreneurs to access government contracts in Indonesia, engaging eighty-nine women owned businesses.
- One training in Myanmar on Business Integrity.
- A set of trainings in Vietnam focusing on innovative entrepreneurship and business integrity.

 Key achievements under this output include:
- In Vietnam, securing pledges from 14 business associations to promote anti-corruption legislation to over 6,000 companies; training 800 companies in business conduct and internal control systems; and partnering with the Vietnam National University to incorporate a Handbook on Fundamental Auditing in its training programme. The project also helped private and state-owned companies establish the Vietnam Business Integrity Network to raise awareness of the need to improve corporate governance and the tools to do so.
- Business Integrity Toolkit for Young Entrepreneurs to help start-ups prevent, detect and take action against unfair business practices.
- In Malaysia, the project piloted business integrity training for more than 50 SMEs in the supply chains of two multinational corporations. In addition, an online chatbot that can answer up to 100 questions on business integrity for start-ups was developed in partnership with the Vietnam Chamber of Commerce and Industry.
- An online Integrity Self-Assessment Tool (ISAT) was developed for companies in the Philippines to measure their integrity standards and provide a better understanding of which areas require more attention.

	UNDP & UNODC: Strengthened anti-corruption policies, plans and strategies and improved redress mechanisms
Output Score	A
Impact weighting (%)	4%	Impact weighting revised since last AR?	NA

Output Indicator (UNDP)		Final Logframe Target	Final Result Achieved
5a: # countries supported to develop or update preventive anti-corruption policies, plans or strategies. / (Cumulative)		2022: 4 (end of programme target)	4 achieved
5b: # of new in-country judicial initiatives initiated following regional peer to peer exchanges (targeted countries)		2022: 4 (end of programme target)	4 achieved.

Output Indicator (UNODC)	Final Logframe Target	Final Result Achieved
# of people (NGOs, independent media outlets, schools) trained on anti-corruption investigation techniques, approaches, and technology	2023: 30 achieved (30 planned)	30 achieved (30 planned)

Activities under this output supported the government and anti-corruption agencies in ASEAN countries to strengthen their capacity to combat corruption. Activities were delivered in Malaysia, Thailand, and Vietnam. In Malaysia, FairBiz developed tools to help the country’s Governance, Integrity, and anti-corruption Centre (GIACC). In Thailand, activities supported the National anti-Corruption Commission in developing recommendations to fight corruption more effectively, including improvement in the international indicator’s scoring. In Vietnam, the programme supported the Supreme People’s Court in organizing workshops on sharing relevant international experiences in settling international trade disputes. UNDP also worked with the Court Academy to develop a training module for judges on handling international commercial disputes and the recognition and enforcement of foreign arbitral awards. In July 2019, the Vice Chief Justice of the Supreme People’s Court cum Director-General of the Court Academy approved the training module to be published and incorporated it into the training programme for both students and judges. In November 2019, two pieces of training for trainers were organized in Hanoi and Ho Chi Minh City, using this module as the main course material, with participants from the Supreme People's Court, Court Academy, High courts, and provincial courts of more than 20 cities and provinces across Vietnam.

Businesses can only realise their potential if governments’ laws, policies, and plans treat them all equitably. The support delivered under this output has enabled the development of appropriate “rules of the game” and worked with the judiciary to ensure legislation affecting businesses was fairly and efficiently implemented. Top achievements include:

- Identifying drivers of corruption in Indonesia: Three corruption risk assessments of sectors often associated with corruption helped Indonesia’s newly formed National Agency for the Prevention of Corruption identify drivers of corruption in each sector and the entry points to promote the prevention of corruption.
- Working with Vietnam’s Supreme People’s Court: In Vietnam, the country’s Court Academy for the Supreme People’s Court agreed to integrate a UNDP-developed training module for judges on commercial dispute resolution and foreign arbitral awards into its six-month training programme for judges. Until now, Vietnamese courts have not always recognised foreign arbitral awards. More than 300 judges received training on this issue.
- Gender and Inclusion: Corruption affects women and marginalized groups disproportionately. FairBiz initiatives provided opportunities for women to come together and speak up about corruption regarding their businesses, employees, and management risks. The project has raised awareness, created a platform for peer-to-peer exchange and equipped women entrepreneurs with tools to combat corruption. Furthermore, resources developed by the component such as the study, “Gender and Inclusion for a Fair Business Environment,” provides an analysis of best practices and guidelines for organizations in the region on how to advance inclusion in their companies.

The UNODC project supported Malaysian civil society organisations tackling corruption to contribute to a more accountable, transparent, and inclusive economy and society. Activities included four seminars by experts on anticorruption investigation techniques, training more than 30 representatives of NGOs, independent media outlets and students.

	UK-ASEAN Business Council: A fairer business environment for UK businesses in ASEAN is enabled
Output Score	A
Impact weighting (%)	2%	Impact weighting revised since last AR?	NA

Output Indicator	Final Logframe Target	Final Result Achieved
Number of UK companies and UK senior officials present in the UK-ASEAN Business Forum	2023: 60 (end of programme target)	67 achieved

The UK-ASEAN Business Forum was a key deliverable of the UK-ASEAN Business Council (UKABC). The project with UKABC, which was funded with non-ODA, aimed to support the business organisation in delivering ASEAN-facing diplomatic activities to enable commercial diplomacy and demonstrate UK’s private sector expertise in the region. UKABC also fed insights into DBT and the UK Mission to ASEAN’s market access work with AMS.

Delivered in March 2023 in London and via Zoom, the UK-ASEAN Business Forum attracted over 400 in-person and online delegates from the public and private sectors from the UK and the ASEAN. It included representatives of 67 UK companies and UK senior officials to discuss existing UK-ASEAN partnerships through various regional and bilateral trade partnerships and explore stronger collaboration amidst Indonesia’s new ASEAN chairmanship in 2023. Sustainable infrastructure and green finance were also a focus of the panel discussion.

	PwC: Positive influence on market regulation through ASEAN Capital Markets Forum (ACMF) and promotion of international standards in financial services / (Logframe: Capital markets’ development plans, policies and regulations developed or improved)
Output Score	B
Impact weighting (%)	5%	Impact weighting revised since last AR?	NA

Output Indicator		Final Logframe Target	Final Result Achieved
6(a) No of strategic recommendations reports developed		2021: 1 achieved (3 planned) / 2022: 3 achieved (3 planned)	Total / 4 achieved (6 planned)

Activities under the Capital Market workstream were aimed at providing strategic and targeted implementation support in Vietnam and regulatory technical assistance and capacity building support in the Philippines. In the Philippines, the FSIP team focused on strengthening regulations and supervisory capacity related to the Securities and Exchange Commission’s (SEC) risk-based supervision of capital markets intermediaries. The aim was to diversify the financial sector through better regulations within capital markets, supported by the strengthening of market policies, regulations, and supervision. In Vietnam, the FSIP team aimed to provide a long-term roadmap for Vietnam capital markets, enabling the Ministry of Finance (MoF) and other Vietnamese authorities and stakeholders to develop and implement policies and plans in a coordinated manner. The strategy aimed to connect several strategic initiatives in the midst of implementation and ensure greater representation of stakeholder views and topics at the national level.

In Vietnam, the Capital Markets Master Plan faced significant delays. Across Year 1 of the programme, significant time was invested in engagement with MoF. However, after the kick-off in November 2020, challenges with stakeholder ownership and engagement persisted, impacting progress. As a result of the significant delays, it became increasingly unviable to deliver the work package outputs within the remaining FSIP timeline. The decision was made to close the work package.

In the Philippines, achievements included: a framework developed for the Philippines Securities and Exchange Commission (SEC) to strengthen its risk based supervision of capital market intermediaries; proposed profiling metrics to focus SEC’s attention on Trading Participants (TPs) presenting the highest risk; assisted the SEC in setting up a review process to further develop monitoring; gave the SEC access to analytical tools to investigate time-series and cross-sectional patterns among TPs; addressed current and future strategic market developments which are expected to affect capital needs and the risk of TPs.

A key recommendation from this output is that before designing and implementing workstreams, programmes should thoroughly assess that there is strong appetite among intended beneficiaries for engagement and ownership. Overall, the capital markets workstream was affected by weak stakeholder engagement and ownership, impacting the delivery progress.

	Multi-delivery strand: Improved capacity and frameworks within key financial institutions and markets / (Logframe: Policies and regulatory issuances updated or developed, and industry provided the platform to develop or enhance responsible Fintech products or services)
Output Score	A
Impact weighting (%)	20%	Impact weighting revised since last AR?	NA

Output Indicator (PwC)		Final Logframe Target	Final Result Achieved
7 (a): No. of new frameworks or systems developed		2020: 4 achieved (4 planned) / 2021: 1 achieved (2 planned)	Total / 5 achieved (6 planned)
7 (b): No of strategic recommendations reports developed		2020: 1 achieved (1 planned) / 2021: 7 achieved (6 planned) / 2022: 2 achieved (2 planned)	Total / 10 achieved (8 planned)
Output Indicator (Surecert)		Final Logframe Target	Final Result Achieved
Number of sub-projects delivered to provide study results and recommendations focusing on priority areas and key principles that drive digital authentication services in Thailand identified by Electric Transactions Development Agency (ETDA)		2023: 3 achieved (3 planned)	3 achieved (3 planned)
Output Indicator (FSE)		Final Logframe Target	Final Result Achieved
Number of consultation sessions between the Bank of Thailand (BoT) and other jurisdictions that implemented Open Banking using voluntary approach		2023: 4 achieved (5 planned)	4 achieved (5 planned)

The Fintech workstream under the programme’s FSIP component included a total of twelve work packages with 3 being closed throughout the second year. The activities differed by country depending on the current needs and
focus of the relevant regulatory bodies. Work in Thailand and Vietnam started by developing FinTech Ecosystem catalogues demonstrating the current status of the FinTech landscape within these countries. In all countries technical support was provided as relevant around Peer-to-Peer (P2P) and IT-based lending regulation, Open Finance, Crowdfunding, eKYC and Cyber regulations. Guidance and support were also provided to government bodies around joining or understanding the requirements and benefits of participating in Global Financial Innovation Network (GFIN).

Key achievements include:
- In Indonesia, working with FinTech Lending Association (Asosiasi Fintech Pendanaan Bersama Indonesia; APFI), the programme provided several recommendations and best practices on the regulatory Code of Conduct (CoC) for P2P/IT lending, which were incorporated into the new CoC. This will help increase the speed and transparency of new digital technologies in the financial sector. At the same time the CoC would help prevent over-indebtedness and implement good faith lending principles.
- The programme assisted Indonesia’s Ministry of Finance to draft the Fintech chapter for the Omnibus Finance Review. The programme produced a report with recommendations for the FinTech cluster of the draft Omnibus Law on Financial Inclusion. Government of Indonesia passed the law in January 2023.
- In The Philippines, the programme facilitated the Bangko Sentral ng Pilipinas (BSP) in becoming a member of the UK-based Global Financial Innovation Network (GFIN) in June 2020, where they can leverage the best practices from the FCA and other members. GFIN is a leading platform for national financial services regulators to cooperate with other members and FinTech companies to test innovation in Open Banking and Regulatory Technology.
- A FinTech Catalogue website was launched on 27 January 2022 in collaboration with Bank of Thailand, Thai SEC, and Cambridge Centre for Alternative Finance (CCAF). The Catalogue is an online, one-stop FinTech platform that showcases Thailand’s growing FinTech ecosystem and promises to become an important tool for the promotion and development of FinTech in Thailand.

This output also covers the Accounting Standards (AS) workstream and Islamic Finance (IF) workstream under the FSIP component implemented by PwC. Under the AS workstream, a total of 1450 accounting professionals including regulators (of which 956 were women) were trained and informed about IFRS best practises in Philippines (215/331 female), Thailand (150/197 female) and Vietnam (591/922 female). This training helped the regulators and stakeholders gain awareness and alignment to the international IFRS. Feedback from the KIIs shows that this increased capacity will contribute to improved financial reporting frameworks and solvency standards.

The IF workstream provided research support on solutions for social funding in Malaysia by adopting and promoting ISF instruments, such as Zakat, Waqf, Sadaqah, Takaful, and Sukuk. The scope included research and recommendations for a Pre-emergency Fund based on ISF instruments, a FinTech enabled Waqf solution and Islamic Financing for Social Enterprises (SEs). The Emergency fund structure conceptual framework was socialised with 28 different stakeholders consisting of government agencies, asset management companies, CSR arms, State Islamic Religious Council, NGOs and Academia. The Emergency Waqf Fund Memorandum of Association was signed in November 2021, at which time the programme managed to successfully secure some funding from the Ministry of Finance - approximately RM 3.3 million as part of the initial investment to launch the Waqf product. At this point the Fund was officially handed over to the Programme Custodian, who will manage the fund going forward with support from other stakeholders.

Lessons from this output include:
- Having a single accountable beneficiary owner in place strengthens the pace of delivery. Delivery progress was delayed where there were multiple stakeholders who were identified as potential owners of an initiative, and as a result no single beneficiary or individual could take up the required decision-making role. Delivery momentum was improved in the instances where a single accountable beneficiary was determined as a part of the delivery, and the decision-making authority was clear.
- While AERP delivered a lot of capacity building work under this workstream, it is unclear how much of it has resulted in improving the Fintech environment in the targeted countries over the longer term. This is partly because both indicators used at the outcome level are based on secondary data and there have not been any updates available on them. This lack of information makes it challenging to understand if there is overall progress at the country level and what the FSIP contribution may have been. For future programmes it is strongly recommended to use more specific outcome level indicators that can more meaningfully capture progress toward outcome level change. For example, a proxy outcome level indicator could have been – Number of FinTech related frameworks, systems, or recommendations implemented. This would have enabled to measure something closer to the outcome level change; a step ahead of frameworks and recommendations simply developed.

	PwC: Capacity building and knowledge sharing to tackle financial crime and money laundering. / (Logframe: Training and frameworks delivered across Myanmar’s government agencies to improve institutional standards of anti-money laundering and countering the financing of terrorism)
Output Score	A
Impact weighting (%)	5%	Impact weighting revised since last AR?	NA

Output Indicator		Final Logframe Target	Final Result Achieved
8 (a) No of strategic recommendations reports developed		2020: 6 achieved (6 planned)	6 achieved (6 planned)
8 (b) 'No. of new frameworks or systems developed		2020: 4 achieved (4 planned)	4 achieved (4 planned)

Activities under this output aimed to provide technical assistance to the Myanmar government in implementing a more robust Anti-money Laundering (AML) and Financial Crime (FC) regime in line with international standards. The planned support intended to deliver a set of long-term activities by local and international experts, including drafting recommendations on regulatory frameworks for AML, training on international best practices for supervisors, prosecutors and law enforcement, research on weaknesses in the Anti-Money Laundering/ Combating the Financing of Terrorism (AML/CFT) framework and illicit financial flows to/from Myanmar, and mentoring across the different departments by specialists in areas including Financial Intelligence operations, AML prosecution and Risk-Based Supervision. However, during the 2nd year of programme implementation, Myanmar had a military coup, which led to cancellation of all of the remaining planned activities under this output.

In the first year of implementation, FSIP team organised a week-long virtual training programme for the Union Attorney General’s Office’s (UAGO) staff in August 2020 on AML/CFT prosecution. The training engaged 20 newly recruited prosecutors on AML/CFT prosecution and was well received by all participants. FSIP also delivered training to Myanmar’s Financial Intelligence Unit to improve its capability in analysing and processing financial intelligence in supervision and law enforcement. The FSIP team also successfully delivered a Risk Management Manual (RMM) for the Financial Regulatory Department in July 2020. As already noted, following the military coup in February 2021, all activities were closed.

	CCU & GDS: Increased capacity building and collaboration for government stakeholders to improve digital and cybersecurity processes
Output Score	A+
Impact weighting (%)	3%	Impact weighting revised since last AR?	NA

Output Indicator (CCU)		Final Logframe Target	Final Result Achieved
% of stakeholders that indicate that they have increased knowledge regarding improving security awareness and reducing fraud/ regulators		2022: 34 achieved (24 planned)	34 achieved (24 planned)
Output Indicator (GDS)		Final Logframe Target	Final Result Achieved
Number of stakeholders trained on digital and international standards		2022: 18 achieved (8 planned)	18 achieved (8 planned)

Activities under this output focused on supporting Government of Thailand on two fronts: a) support delivered by the UK’s Cyber Capacity Unit (CCU) on regulatory environment for FinTech to strengthen cybersecurity practices and improve financial inclusion, and b) support to improve Thai government’s capacity for implementing electronic Know Your Customer (KYC) standards, delivered by the UK’s Government Digital Service (GDS).

Activities delivered by CCU included: a workshop on Improving Security Awareness of consumers and reducing fraud; Cyber Security Training on threats, vulnerabilities, threat intelligence, and incident response; a Cyber Security Exercising Workshop and Exercise Support; a workshop on Fraud through SMS phishing and phone calls and detecting and responding to mule accounts used for money laundering. Beneficiaries included the Bank of Thailand, the Securities and Exchange Commission, the Electronic Transaction Development Agency, and the Office of Insurance Commission.

Activities delivered by GDS included:
- A review of current eKYC activities in Thailand and how these aligned with regional (SE Asian) and international developments.
- A mapping exercise to identify key stakeholders for eKYC development in Thailand.
- A workshop on digital ID for businesses looking at developments in the UK and describing development to date on the UK Trust Framework.
- A workshop on digital ID for businesses, looking at how business identity can be developed to ensure data interoperability.

The short-term support provided through these activities was well received by stakeholders in Thailand, as confirmed by high levels of post support satisfaction reported in surveys. For the support delivered by CCU, Bank of Thailand became forward leaning and engaged fully with the project after some initial engagement challenges.

D: Value for Money

Economy focus was on minimising costs despite the programme complexity with a large number of implementing partners, wide range of activities and geographic focus, which ultimately could have led to a less-efficient fragmentation of the programme’s financial resources and management capacity. The programme team ensured VfM during the procurement phase with VfM plans required as part of the contracts. The programme maintained efficiencies by paying all commercial partners such as PWC based on payment by results which allows for cost containment. The system of KPIs ensured VfM across the portfolio, with the programme transitioning from payment by milestone initially, to using an activity-focused incentive system. This incentivised delivery partners to focus on effectiveness of delivery, although this also resulted in the wide number of log frame indicators which resulted in an increased programme management burden. For other delivery partners, such as UNDP and OECD which are governed by pre-agreed multilateral frameworks, payments were made in advance. However, the programme teams both at the regional and bilateral levels were involved in project delivery to ensure that outputs were well-vetted and matched the project and financial criteria agreed with the delivery partners. For some projects COVID19 reduced costs and increased the reach with the transition to virtual delivery.
Efficiency/Effectiveness was achieved on multiple outputs and outcomes by contributing towards policy change with AMS. Although measurement of benefits has been a challenge at the outcome and impact levels, the programme has contributed to policy changes across many areas. In addition, the programme was able to deliver on other benefits such as IP knowledge products filling critical information gaps across AMS, expanding access to digital financial services with a range of policy products and services—reports, workshops, trainings, targeted advisory support and the Fintech Industry Sandbox pilot in the Philippines.
Cost effectiveness is shown by the contribution towards several country-level reforms on regulations and laws, which suggests the programme is likely to be highly cost-effective. There is also evidence of other primary benefits, such as capacity building from UNDP delivering learning & knowledge platforms and the estimated CoST Thailand procurement savings of $73m. Taken together the programme maximised impact and effectiveness by providing AMS with national level policy advice and technical assistance to promote pro-growth policies. This type of support has strong evidence of cost-effectiveness across many contexts. Over time, it may be possible additional benefits accrue from the reforms such as the OECD 30 non-binding recommendations across AMS but it has not been possible to provide evidence for this during the life of the programme.
The business case assumed the project would target a total of 16 reforms across the 6 countries over the 4 years, equivalent to an average of 0.67 successful reforms, per country, per year, mostly from regulation, transparency and IP, with a small number of financial market reforms. The programme achieved over 20 such reforms, for example through supporting business licencing reform and the 2023 financial sector Omnibus law in Indonesia. The business case primary benefits net present value provided around 0.01% additionally to projected GDP growth in the 6 countries. Across these countries between 2019 and 2023, GDP increased by over $1.5 trillion. If there was any contribution towards an impact on growth the benefits are likely to be substantial.
In addition to the primary development benefits for AMS and ASEAN, the programme also provided additional secondary benefits by supporting the growing UK-ASEAN economic and diplomatic relationship. For example, in Vietnam, the work on regulatory reform also helped to support the British Chamber in Vietnam in their application to become a member of the Prime Minister’s Advisory Council on Administrative Procedure Reform (ACAPR) in 2022. Overall, the programme represented strong VfM despite delivery challenges from operating a complex programme with multiple implementation partners, thematic areas and countries. The programme could have further improved VfM through using a more focused design and delivery model.
Equity was a key design consideration in the programme, but there were limited resources and budget allocated to this consideration at the start of the programme, resulting in weaker implementation by delivery partners. In addition, as one of the first Prosperity Fund (PF) programmes to go into implementation, the programme did not benefit from the G&I framework and PF resources which were developed later to guide work on equity. Consequently, G&I indicators were not mainstreamed into delivery partner logframes at the outset. Attempts to integrate equity considerations once the programme was under implementation proved quite challenging as contracts / agreements had already been signed. For indicators, although there were some on G&I (e.g., % of workstreams applying minimum G&I requirements), there was relatively little disaggregation of other indicators by gender. However, the programme also showed strong results in some areas such as UNDP FairBiz helping female entrepreneurs in Thailand and Indonesia by working with small business owners to improve skills and capacity for bidding for government contracts.
E: Risk

Covid-19 was the most significant risk to the programme and when it materialised as an issue, it had significant consequences. This was particularly true during 2020-2021. The pandemic required extensive revision of work plans for all delivery partners. Given the scale and complexity of the programme, this created a significant burden on both programme staff and partners. For example, for PwC and the FSIP project, the entire plan for milestone delivery (involving hundreds of milestones) had to be reviewed, re-negotiated, and agreed through a contract variation. This process was repeated across all delivery partners and work plans.

Some activities were cancelled, others postponed. All activity shifted to a virtual model. Stakeholders reacted quite differently to this shift, with some being amenable to the change and others requesting postponement until in person activity could be resumed. Virtual delivery did present some advantages in terms of increasing reach both geographically and in the levels of participation. There was some assessment that it also promoted inclusivity, as virtual activities can be more accessible. This has resulted in the adoption of hybrid models of delivery post-pandemic, to be able to capitalise on these benefits.

It would be very difficult to measure the impact of Covid-19 on programme delivery in any meaningful way. What we can say with certainty is that the pandemic resulted in a reduced level of ambition with many activities being curtailed. It was a major interruption and disruption in programme delivery, which inevitably will affect the potential impact of the programme over the longer term.

Uncertainty regarding funding allocations was a major risk for the programme. The delay in approving the annual budgets due to changes to the ODA budget in 2021/22, and consequent uncertainty, had a significant impact on delivery. This risk was managed by maintaining close relationships with all delivery partners and stakeholders, ensuring open channels of communication, and keeping everyone apprised of the situation. The programme team adopted a flexible approach in order to be able to adapt to various scenarios as they were confirmed. Inevitably, this situation led to reduced delivery times in some cases, and cancellation of activity in others. It also resulted in an interruption to some engagement with regional stakeholders which may have had an effect on the reputation of FCDO as a donor.

Political uncertainties in the region were constantly monitored. This risk materialised with the coup in Myanmar in February 2021 and resulted on closure of all AERP workstreams in the country.

F: Programme Management: Commercial and Financial Performance, Monitoring and Evaluation

AERP had a Senior Responsible Officer (SRO) in place since the beginning of the programme and was overseen by a Regional Programme Board, which included representatives from British Embassies and High Commissions across the region, representation from FCDO in London and other government departments (OGDs). The Programme Team in Singapore reported to the Board on a quarterly basis, with presentation of a quarterly report, including inputs from all delivery partners, assessing progress against objectives, financial management and risk. The Board was also presented with country summaries for the original six priority countries. Relevant issues were raised for decision (i.e. on budget forecasts, extension of activities, business case extensions) or for information (i.e. annual review recommendations). All meetings were conducted in a timely manner, with Board papers and formal minutes from each meeting. A Programme Responsible Owner (PRO) was appointed in September 2019 along with a Regional Programme Manager based in Singapore. The programme was delivered through a network of regional programme managers based in British Embassies and High Commissions in the region.

Narrative and financial reporting has been efficient. Due to the sheer volume of inputs, the narrative reporting was perhaps too long and detailed. The programme team noted the challenge of delivery partners often mainly reporting at the output level, rather than at the outcome level. Despite attempts to solve this, it remained a challenge throughout delivery. It is recommended for future programmes that at the outset of delivery, it is made clear to partners both how they are contributing to a larger regional programme, and the imperative for them to be able to report against these higher-level objectives by delivering on high level outcomes.

Financial reporting has been timely and accurate, with regular updates provided to the Programme Board on a quarterly basis, and more often to the SRO as needed. Programme forecasts were regularly reviewed and updated, and commissions from central finance teams responded to in a timely manner. The team worked closely with delivery partners and programme managers at Posts to ensure accurate tracking of financial spend. On accountability, delivery partners agreed in the funding agreements to provide financial information (e.g. receipts) when required and submit independently audited financial statements within six months after their project’s closure.

The final AERP business case value stood at £21.4m following the approval of a business case addendum in May 2022. At programme close, £19.66m had been spent. Delivery partners were governed by a range of different funding arrangements including commercial contracts, grant agreements and memorandums of understanding. Terms of reference were drawn up, with delivery partners developing theories of change, log frames and activity-based budgets for each project. For the shorter term, smaller value projects, a light touch and proportionate approach was adopted, with the consequence that logframes were not always as detailed.

The FSIP project was delivered under a commercial contract worth £6,855,430, which was later reduced to £5,991,075 after the FCDO Spending Review in 2021. PwC, the consortium lead, developed a programme operating manual with a set of rules and guidelines, which was revised as needed during implementation. Service Level Agreements (SLAs) were introduced during the second year of the programme and applied over the period Y2Q2 – Y3Q4. For each quarterly report, FSIP was measured against a set of SLAs for which a financial penalty could be incurred for SLAs not met. Six categories of SLAs were agreed: timely reporting; meeting attendance and minutes; financial management, replacement of staff and client relationship management. Over the 2.5-year delivery period, PwC met a total of 126 out of 129 SLAs (98%) and incurred financial penalties of £3,200).

Changes to the FCDO ODA budget in 2021/22 caused delays in budget confirmations, which made it harder for implementing partners to plan and deliver activities effectively, although these challenges were ultimately managed through close consultation and scenario planning with the AERP programme team.

Programme-level approach to monitoring and evaluation
- Field visits were curtailed due to the pandemic. However, the network of programme managers across the region have ensured that activities on the ground are properly monitored and reported.
- The theory of change, portfolio level and project level logframes were developed after the programme went into delivery. This compromised the leverage the programme team had with delivery partners to build detailed logframes and ensure they were fully utilised for project monitoring.
- As noted above, logframes could have been more robust, including by articulating clearer change pathways and agreeing the level of ambition and how to measure success at the outset, including quantitative and qualitative indicators and building in a level of contribution analysis during review points.
- A dedicated MEL advisor would have helped the programme to ensure the necessary collection of data at appropriate points during delivery.
- The evaluation cycle reviews which were conducted by an external contractor under the Prosperity Fund were constructive and helpful. Terminating the contract when the Prosperity Fund ended in 2021 made MEL more difficult for the last two years of AERP.
- The programme team have maintained regular monthly meetings with all delivery partners throughout implementation. The meetings presented an opportunity to assess progress, risks and issues and to review financial management. Through these channels the programme team developed very positive and constructive relationships with delivery partners. Maintaining these communication channels has been vital to manage the reputational and delivery risks caused by the uncertainty of funding and the challenges of the pandemic. These relationships have in no small part been integral to the success of the programme.

Annex

List of Acronyms
AERP	ASEAN Economic Reform Programme
ACMF	ASEAN Capital Markets Forum
AML	Anti-Money Laundering
AML/ CFTA	Anti-Money Laundering/ Combating the Financing of Terrorism
AMS	ASEAN Member States
ANIEE	ASEAN Network of Intellectual Property Enforcement Experts
ASEAN	Association of Southeast Asian Nations
AR	Annual Review
APFI	Asosiasi Fintech Pendanaan Bersama Indonesia
ASLIP	ASEAN Sustainable Leadership in Infrastructure Programme
BMA	Bangkok Metropolitan Administration
BSP	Bangko Sentral ng Pilipinas/ Central Bank of the Philippines
CCU	Cyber Capacity Unit
CGD	Comptroller General’s Department, Thailand
CM	Capital Markets
COC	Code of Conduct
CMEA	Coordinating Ministry for Economic Affairs (CMEA)
CoST	CoST – Infrastructure Initiative
CPU	Crime Prevention Units
CSO	Civil Society Organisations
CSR	Corporate Social Responsibility
DBT	Department for Business and Trade
DFAS	Digital Financial Advisory Services
DFID	Department for International Development
eKYC	electronic Know Your Customer
ETDA	Electronic Transaction Development Agency
FCDO	Foreign, Commonwealth and Development Office
FairBiz	Referring to the project with UNDP, Promoting a Fair Business Environment in ASEAN
FBPW	Federation of Business Professional Women of Thailand
FCA	Financial Conduct Authority
Fintech	Financial technology
FSE	Finserv Experts Limited
FSIP	Financial Services and Intellectual Property Programme, delivered by PwC
G20	Group of Twenty
G&I	Gender and Inclusion
GDS	Government Digital Service
GDP	Gross Domestic Product
GESI	Gender and Social Inclusion
GFIN	Global Financial Innovation Network
GIACC	Governance, Integrity, and Anti-Corruption Centre, Malaysia
HMG	His Majesty’s Government
ICC	International Chamber of Commerce
IFRS	International Financial Reporting Standards
IF	Islamic Finance
IP	Intellectual Property
IPOPHL	Intellectual Property of the Philippines
IPR	Intellectual Property Rights
ISAT	Integrity Self-Assessment Tool
IT	Information technology
KPI	Key performance indicator
Logframe	Logical framework
MEL	Monitoring, Evaluation, and Learning
MoF	Ministry of Finance
MoU	Memorandum of Understanding
MREL	Monitoring, Reporting, Evaluation, and Learning
MSMEs	Micro, Small and Medium Enterprises
NGO	Non-Government Organisations
Non-ODA	Non-Official Development Assistance
NPPA	National Public Procurement Agency, Indonesia
OCP	Open Contracting Partnership
ODA	Official Development Assistance
ODI	Open Data Institute
OECD	Organisation for Economic Co-operation and Development
OPDC	Office of the Public Sector Development Commission
OPSS	Office for Product Safety and Standards
P2P	Peer-to-Peer
PCR	Programme Closure Report
PF6	Prosperity Fund 6, refers to the initial focus countries of AERP – Indonesia, Malaysia, Myanmar, Philippines, Thailand, and Vietnam
PGRP	Philippine Good Regulatory Practice
PRO	Programme Responsible Owner
PwC	PricewaterhouseCoopers
RDI/ BEIS	Regulatory Development International, Department for Business, Energy, and Industrial Strategy
SEC	Securities and Exchange Commission, Philippines
SLA	Service-level Agreements
SME	Small and medium-sized enterprises
SOEs	State-owned enterprises
SRO	Senior Responsible Owner
TA	Technical assistance
ToC	Theory of Change
TP	Trading participants
UAGO	Union Attorney General Office, Myanmar
UKABC	UK-ASEAN Business Council
UNDP	United Nations Development Programme
UKIPO	UK Intellectual Property Office
VfM	Value for Money
WOG	Whole-of-Government, refers to the WOG approach delivered as part of AERP’s regulatory reform component in the Philippines