## Cover
Building Safety Remediation Data Release, England: 31st March 2024
Back to Contents
Background
This publication provides data on 1) the remediation progress across DLUHC’s Building Safety Remediation portfolio, covering buildings in the ACM programme, Building Safety Fund, Cladding Safety Scheme, developer remediation contract and reported by registered providers of social housing, 2) Progress with remediation of high-rise (18 metres and over in height) residential buildings (including student accommodation and hotels) and publicly owned buildings with ACM cladding systems unlikely to meet Building Regulations in the ACM programme, 3) the progress of the Waking Watch Relief Fund and Waking Watch Replacement Fund, 4) progress with remediation of high-rise residential buildings with non-ACM cladding systems assessed as eligible for funding from the Building Safety Fund , 5) Progress with the applications for and remediation of medium-rise (11 – 18 metres in height) residential buildings in England and high-rise residential buildings outside of London with non-ACM cladding systems in the Cladding Safety Scheme, 6) progress of remediation of residential buildings 11 metres and over in height with life-safety defects under the developer remediation contract, 7) progress of remediation of residential buildings 11 metres and over in height with unsafe cladding reported by registered providers of social housing, 8) enforcement action taken by local authorities against high-rise residential buildings with cladding defects under the Housing Act 2004.
Tables on the ACM programme, BSF, CSS, developer remediation contract and social housing surveys include buildings which can be in multiple schemes or data collections so counting across tables can result in double counting. Tab Combined_2 provides an overall summary of all remediation progress, without double counting.
Publication dates
The data tables in this spreadsheet were originally published on 18 April 2024.
The next publication is scheduled for 23 May 2024.
Useful Information
Further information on the data collection, data quality and definitions is available in the Technical Note published alongside these statistics.
Technical Note
Contact details
We are committed to improving and broadening this data release further in the months ahead and would welcome feedback both on the content of this data release and what could be further done in the future.
BuildingSafetyData2@levellingup.gov.uk
NewsDesk@levellingup.gov.uk
Date published: 18 April 2024

## Table_of_Contents
Building Safety Remediation Data Release Contents
Worksheet Name	Worksheet Title
Cover	Background information about the statistics.
Notes	Notes found in the tables.
ACM_1	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 March 2024
ACM_2	Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 March 2024
ACM_3	Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 March 2024
ACM_4	ACM remediation progress by local authority, England, 31 March 2024
ACM_5	ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 March 2024
ACM_6	ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 March 2024
ACM_7	Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 31 March 2024
ACM_8	ACM remediation progress by sources of funding, England, 31 March 2024
ACM_9	Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 March 2024
ACM_10	Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 March 2024
WWRF_1	Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 March 2024
WWRF_2	Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 March 2024
WWRF_3	Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 March 2024
BSF_1	Remediation status of eligible buildings within BSF by tenure, England, 31 March 2024
BSF_2	BSF remediation progress of eligible buildings by region, England, 31 March 2024
BSF_3	BSF number of eligible buildings with funding approved and expenditure amounts by tenure, England, 31 March 2024
BSF_4	BSF remediation progress of eligible buildings by local authority, England, 31 March 2024
Combined_1	Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 March 2024
Combined_2	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 March 2024
CSS_1	Application status of buildings within the CSS, England, 31 March 2024
CSS_2	CSS remediation progress by region, England, 31 March 2024
CSS_3	CSS remediation progress by height, England, 31 March 2024
CSS_4	CSS remediation progress by tenure, England, 31 March 2024
Social_1	Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 30 November 2023
Social_2	Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 November 2023
Social_3	Provider by provider breakdown of buildings, by assessment status, England, 30 November 2023
Social_4	Provider by provider breakdown of buildings, by remediation status, England, 30 November 2023.
Developer_1	Remediation status of buildings covered by the developer remediation contracts by height group, England, 31 March 2024
Developer_2	Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 January 2024
Developer_3	Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 January 2024
Developer_4	Developer by developer breakdown of buildings covered by the developer remediation contract, by assessment status, England, 31 January 2024
Developer_5	Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 January 2024
Developer_6	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 January 2024
Developer_7	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 31 January 2024
Developer_8	Developer by developer breakdown of buildings requiring remediation, which had not started works in the previous quarter England, 31 January 2024
Developer_9	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 31 January 2024
Developer_10	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 31 January 2024
Developer_11	Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 31 January 2024
Enforcement_1	Enforcement action taken by local authorities against high-rise buildings under the Housing Act (2004) by remediation programme status, England, 28 March 2024
Enforcement_2	Building inspections conducted by local authorities, England, 28 March 2024
Enforcement_3	Statutory notices served by local authorities under the Housing Act (2004), England, 28 March 2024
Enforcement_4	Number of building inspections by local authorities supported by the Joint Inspection Team, England, 28 March 2024
JIT_1	Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 March 2024

## Notes
Notes
Back to Contents
Note	Note Explanation	Note Location
[note 1]	Vacant buildings detailed in this table are included in table ACM_1 and ACM_2.	ACM_3
[note 2]	This table excludes local authorities with fewer than 10 high-rise residential buildings, regardless of whether they have unsafe cladding, and groups local authority figures into bands. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	ACM_4, Enforcement_1, Enforcement_2, Enforcement_3, Enforcement_4
[note 3]	Yet to complete remediation includes all dwellings in buildings that are yet to complete remediation works on-site	ACM_7
[note 4]	Social Sector Fund: Payments are made as cash grants, and will be payable in two tranches. The government will pay 80% of eligible costs at stage one. Once building owners confirm that they have tendered for the removal and replacement of cladding systems and work has started on site, we will make the first payment. Then we will pay the remaining 20% of eligible costs once building owners have submitted further evidence and confirmed final costs.	ACM_8
[note 5]	Private Sector Fund: The majority of private sector buildings receiving government funding for ACM remediation are funded through the Private Sector Cladding Remediation Fund. Payments from the Private Sector Cladding Remediation Fund will be made as cash grants and will be made on the basis of monthly valuations of work carried out on site, with an appropriate degree of due diligence, mirroring industry standard practice. Following Practical Completion the government will withhold a final payment which will be made on completion of the defects liability period. Seven private sector buildings are receving government funding from the Building Safety Fund, so do not appear in the totals in table ACM_9, but do in ACM_8.	ACM_8, ACM_9
[note 6]	The approved figure for the Private and Social Sector ACM Cladding Remediation Funds incorporates tendering support for applicants and approved project cost overrun. This figure reflects funding for the costs of remediation of unsafe ACM cladding only.	ACM_10
[note 7]	The Private Sector ACM Cladding Remediation Fund approved funding figure does not yet include any funds that will be reimbursed by developers who have signed the Pledge in relation to buildings they had a role in developing or refurbishing which have received government funding. All eligible applications to the Private Sector ACM Cladding Remediation Fund will be funded.	ACM_10
[note 8]	Expenditure for the Private and Social Sector ACM Cladding Remediation Funds is based on grant payments made by Delivery Partners to the applicant.	ACM_10
[note 9]	Private Sector ACM Cladding Remediation Fund (PSCRF) expenditure includes spend for non-ACM remediation works on buildings with unsafe ACM cladding funded through the PSCRF and therefore can exceed the amount approved which reflects unsafe ACM cladding remediation costs only.	ACM_10
[note 10]	Total figures may not sum due to rounding.	WWRF_1, WWRF_2, WWRF_3, BSF_3, Combined_4
[note 11]	The first tranche of the Waking Watch Relief Fund was administered by eight local/combined authorities alongside DLUHC. Further information on funding allocations by administering authority is available in the Waking Watch Relief Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_2
[note 12]	The Waking Watch Replacement Fund was administered by five local/combined authorities alongside DLUHC. Further information on funding allocations by administering authority is available in the Waking Watch Replacement Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_3
[note 13]	Remediation complete figures in this table include buildings that have completed remediation but are still awaiting building control sign off.	BSF_2
[note 14]	Private sector buildings can receive pre-tender support allocation in addition to their full applications funding, but not all buildings receive this therefore these numbers cannot be added together to directly give a total.	BSF_3
[note 15]	This table includes allocation figures for buildings which have only non-ACM cladding and buildings which have both non-ACM and ACM cladding.	BSF_3
[note 16]	For buildings with both ACM and non-ACM cladding in this table, 'Remediation not Started' is assigned for buildings that have not started works on either type of cladding. 'Remediation Started' is assigned for buildings where work has started on remediating at least one type of cladding. 'Remediation complete: awaiting building control sign off' is assigned for buildings that have completed remediation but sign off is required for work on remediating at least one type of cladding. 'Remediation complete' is assigned for buildings that have completed, and received sign off, on works for the remediation of both types of cladding.	Combined_1, Combined_2
[note 17]	Buildings can be in multiple schemes and data collections. These tables show the unique number of buildings across the schemes without double counting buildings where they are in multiple schemes. The total here will be lower than the summed total number of buildings reported in each scheme.	Combined_1, Combined_2
[note 18]	Where buildings are in multiple schemes or data collections, the remediation stage assigned follows the rules in Note_16 for buildings in both the BSF and ACM programme. For further overlaps, remediation stages are assigned from schemes in this priority order: ACM, BSF, (or combined ACM and BSF), CSS, developer returns, social housing returns	Combined_2
[note 19]	Enforcement action is where an inspection under the Housing Act 2004's Housing Health and Safety Rating System has been organised/undertaken, and includes where a statutory notice has also then been served.	Enforcement_1
[note 20]	The Housing Health and Safety Rating System (HHSRS) is a risk-based assessment evaluation tool to help local authorities identify and protect against potential risks and hazards to health and safety from any deficiencies identified in residential premises. Each hazard has a weighting which will help determine whether the building is rated as having risks which are either category 1 or category 2. Where a risk is deemed to be category 1, a local authority has a duty to take enforcement action; where a risk is deemed to be category 2, an authority has the power to take action.	Enforcement_2
[note 21]	The Government-funded Joint inspection Team, hosted by the Local Government Association, provides expert advice to local authorities on enforcement on buildings with unsafe cladding.	Enforcement_4
[note 22]	The number of training sessions for Wandsworth and Richmond are combined as Merton, Wandsworth and Richmond operate a joint service where Merton officers attend training on behalf of Richmond and Wandsworth.	JIT_1
[note 23]	Buildings confirmed by delivery partners to be transferred to developers have been withdrawn from the Building Safety Fund, this has led to a decrease in the number of eligible buildings in the Fund. The number of eligible buildings may continue to decrease as more buildings are confirmed by developers and transferred out of the fund.	BSF_1, BSF_2
[note 24]	The Building Safety Fund first opened to registrations from June to July 2020 receiving registrations from 3,488 buildings. In July 2022 the Building Safety Fund reopened to new applications, this remains open therefore the number of buildings will continue to increase. Buildings from both application periods are now combined as one Building Safety Fund, so numbers include both application periods.	BSF_1, BSF_2, BSF_3
[note 25]	Some buildings have an unknown remediation status reported by the developer. These have been interpreted as ‘Remediation not started – no plans in place’.	Developer_1
[note 26]	The buildings reported in this table as requiring remediation are estimated by DHLUC using information provided by developers in their data return and other data available within the department. In this table, a building is defined as requiring works under the developer remediation contract if it is either self-reported by the developer as requiring works; is an eligible building in the BSF or ACM and the developer has agreed to re-imburse the funds; has had money paid out by the BSF or ACM; or has a self-reported work status of either: works completed, works started, or works not started but plans in place. / They therefore differ from other published tables which reference only to the number of 'self-reported' buildings requiring works.	Developer_1
[note 27]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which are not being completed through government funds, unless they have Other Non-External Wall systems defects which the developer is remediating directly. The tables shows the number of buildings which have not yet started works; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Plans under Development' or where no status was provided. The table shows the estimated or actual start date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet started remediation work, but have an estimated or actual start date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_6, Developer_7
[note 28]	This table covers only buildings which have been self-reported by the developer as requiring works under the data return field Does this building require works?. This differs from the total figure of buildings requiring remediation in Developer_1, as that number is an estimate and includes the subset of buildings developers have self-reported. Please see [note 26] for further information)	Developer_3, Developer_4
[note 29]	The table holds data for 53 developers who have signed the contract. Data for one developer who signed the contract on the 31 January 2024 and data for a developer who has gone into administration are not included in this release. Data for the recent signatory will be added to future releases. / Some data has been supressed, as seen in the row 'Other (combined total for all developers with 5 or fewer buildings each' summarises information of 12 developers with five or fewer buildings, this includes: Abbey Developments, Allison Homes, Bloor, CG Fry, Courdace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata and William Davis. This data has been supressed due to the number of buildings being fewer than six and is represented in the data with a dash (-) in the data.	Developer_3, Developer_4, Developer_5, Developer_6, Developer_7, Developer_8, Developer_9, Developer_10, Developer_11
[note 30]	A building is interpreted as having an assessment if one or more of the following fields show as 'Yes' in the developer data return: Have you carried out an assessment of whether External Wall System (EWS) works are required on this building?; Have you carried out an assessment of whether non-EWS (other fire safety defects) works are required on this building?; Does the Building have an FSA?; Does the Building have an FRAEW?; or Does this building require works?	Developer_4
[note 31]	This column removes buildings requiring works which are being completed through government funds and reimbursed by the developer, as the developer cannot influence the pace of remediation on these buildings. However, those buildings being completed through government funds but which have Other Non-Externall Wall systems defects are included as the developer is remediating these directly themselves.	Developer_3
[note 32]	The data here is comprised of 'Don't know', 'Don't know - no assessment made' and blanks in response to the field 'Does this building require works?' regardless of whether the building has had an assessment or not.	Developer_3
[note 33]	The total estimated cost of remediation is based on the actual or estimated cost reported by developers, and an assumed average where a cost has not been reported (averages are based on the developer-reported costs, by height).	Developer_2
[note 34]	Data is taken from The Fire Safety Remediation Survey (FRS) for 11 metre plus buildings, which opened to all landlords on 01 December 2023 and closed on 31 December 2023. Data was sought on buildings as at 30 November 2023. / Landlords were asked to respond to the survey for buildings in which they are the responsible entity. A 'Responsible Entity' is the organisation that has the legal obligation or right to carry out the remediation works. The Responsible Entity may be the building’s freeholder or head leaseholder, registered provider of social housing or a management company or Right To Manage (RTM) company that has primary responsibility for the repair of the property. / As a result, buildings within the The Fire Safety Remediation Survey may comprise of mixed tenure dwellings e.g., private leasehold and social rented dwellings, however remedial works will fall under the responsibility of the responding landlord. / Furthermore, landlords were asked to provide information on any life critical fire safety (LCFS) defects, which the survey defined as defects, shrinkages, faults or other failings in a building that give rise to fire safety risks. These are identified by: / 1) a Fire Risk Appraisal of External Wall construction (FRAEW) undertaken in accordance with PAS 9980 that assesses the external wall construction or cladding as not “medium - tolerable” (or better); or / 2) a fire risk assessment (FRA) that assesses the relevant parts of the building as high risk or medium risk or equivalent according to industry standards.	Social_1
[note 35]	A building with EWS 'cladding defects' reported by Registered Providers of social housing' is defined as a building which has at least one Life-critical Fire-safety defect relating to an External Wall System (EWS) cladding defect. These buildings may also include non-cladding associated defects.	Social_1; Social_2; Social_3; Social_4
[note 36]	The number of buildings identified as 'Remediation complete' may not match the number of social buildings being reported and complete under the BSF, ACM, CSS or developer contract due to the following: / 1) Non-responses to The Fire Safety Remediation Survey - a small number or landlords did not respond to the survey, which means some buildings remediated through other remediation schemes may not be captured. / 2) Differences in how buildings are reported in The Fire Safety Remediation Survey - some buildings which have already completed remediation via other schemes have been reported as having no Life-Critical Fire-Safety defects in The Fire Safety Remediation Survey, as the latest fire safety assessment has concluded that the the building is safe. Subsequently, the landlord has reported that no defects are present in the survey and have left the remediation category blank.	Social_1
[note 37]	The data here includes buildings in The Fire Safety Remediation Survey which may have also applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract. These are not excluded from the Management Information tabe (Social_1) but are excluded from 'Overall Remediation' estimates in the Building Safety Remediation Data Release.	Social_1
[note 38]	The total number of social high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 3 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 39]	The total number of social high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 1 building that falls under the developer remediation contract.	ACM_8
[note 40]	The total number of private high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 23 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 41]	The total number of private high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 63 buildings that fall under the developer remediation contract.	ACM_8
[note 42]	The data for the following schemes are up to the 30 November 2023: ACM, BSF, CSS, whilst Developer data is up to the 31 October 2023 and Social Housing data from 31 August 2023. Developer and Social Housing data are based on quaterly data returns, falling in different months, whereas the ACM, BSF and CSS have updated data monthly.	Combined_2
[note 43]	The number of buildings associated with particular expenditures paid out may also include buildings where a full reimbursement of funding has taken place, including those where required under the developer contract.	BSF_3
[note 44]	Buildings receive expenditure funding in stages and therefore these figures should not be used to calculate the average expenditure paid out to each building.	BSF_3
[note 45]	In this table where a local authority has 5 or fewer eligible BSF buildings, the numbers provided are banded. In all other cases the numbers are provided. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	BSF_4
[note 46]	Intelligence gathered from registered providers suggests these are planned demolition.	Social_1
[note 47]	One building with a live application to the CCS are in Northern Ireland, the remainder are in England.	CSS_1
[note 48]	Three eligible buildings in the CSS are in Northern Ireland, the remainder are in England.	CSS_1, CSS_2, CSS_3, CSS_4
[note 50]	The data in this table is derived from a building level survey which has been submitted by registered social housing providers. The survey opened on 1 December 2023 and closed on 31 December 2023, and sought data on buildings as at 30 November 2023. It covers buildings in England over 11m which contain at least 1 unit of social housing for which the social housing provider is the Responsible Entity. / Some buildings in this table may have applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract.	Social_2; Social_3; Social_4
[note 51]	Registered social housing providers who have five or fewer 11m+ buildings (which may or may not require EWS life-critical fire-safety works) have been grouped together in the ‘Other RPs’ row in the data table, in order to avoid inadvertently identifying individual buildings with EWS life-critical fire-safety defects.	Social_2; Social_3; Social_4
[note 52]	A building works assessments should comply with the requirements of the Fire Safety Order, for example a Fire Risk Assessment or Fire Risk Appraisal of External Walls assessment (FRAEW)	Social_2; Social_3
[Note 53]	These providers submitted a return using an outdated survey template which did not include a question on whether an assessment had taken place on each building. For these providers data has been imputed from the aggregate-level Fire Safety Remediation Survey (FRS) for the following metrics: the number of assessments, the number of buildings identified as having EWS life-critical fire-safety defects and the remediation status of buildings identified as having EWS life-critical fire-safety defects. Those providers where data has been imputed from the FRS have been marked with an asterisk by their name (*).	Social_2; Social_3; Social_4
[Note 54]	Buildings reported as having completed remediation in the building level survey may require reassessment to confirm the building is now safe.	Social_1; Social_4
[note 55]	These buildings are the subset of buildings which in the last developer data return (as at 31 October 2023), required remediation works, had not yet started remediation, but had an estimated or actual start date between 1 November 2023 and 31 January 2024. This table displays their current remediation status based on the data as at 31 January 2024.	Developer_8
[note 56]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which are not being completed through government funds, unless they have Other Non-External Wall systems defects the developer is remediating directly. The tables shows the number of buildings which have not yet started completed; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Remediation Started'. The table shows the estimated or actual completion date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet completed remediation work, but have an estimated or actual completion date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_9, Developer_10
[Note 57]	Funding allocations of Full Applications Approved has reduced from previously published figures. This is the result of a data reconciliation exercise, where buildings transferring from the BSF to the Responsible Actors Scheme have had their BSF funding allocation removed.	BSF_3

## ACM_1
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Tenure	Number of buildings this month	Number of buildings last month	Monthly change
Social sector residential	161	161	0
Private sector residential	238	238	0
Student accommodation	58	58	0
Hotels	31	31	0
Publicly-owned buildings	8	8	0
Total buildings	496	496	0

## ACM_2
Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Completed Remediation	132	82%	185	78%	53	91%	24	77%	7	88%	401	81%
Works complete awaiting building control signoff	10	6%	16	7%	2	3%	3	10%	1	13%	32	6%
Remediation started - cladding removed	19	12%	12	5%	0	0%	2	6%	0	0%	33	7%
Remediation started	0	0%	17	7%	2	3%	2	6%	0	0%	21	4%
Remediation plans in place	0	0%	6	3%	1	2%	0	0%	0	0%	7	1%
Reported an intent to remediate	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	161	100%	238	100%	58	100%	31	100%	8	100%	496	100%

## ACM_3
Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 March 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff - Vacant	0	1	0	0	0
Remediation started - cladding removed - Vacant	0	1	0	0	0
Remediation started - Vacant	0	0	0	1	0
Remediation plans in place - Vacant	0	0	0	0	0
Reported an intent to remediate - Vacant	0	1	0	0	0
Remediation plan unclear - Vacant	0	0	0	0	0
Total vacant buildings	0	3	0	1	0

Remediation Category for occupied buildings	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff	10	15	2	3	1
Remediation started - cladding removed	19	11	0	2	0
Remediation started	0	17	2	1	0
Remediation plans in place	0	6	1	0	0
Reported an intent to remediate	0	0	0	0	0
Remediation plan unclear	0	1	0	0	0
Total occupied buildings	29	50	5	6	1

## ACM_4
ACM remediation progress by local authority, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_2]	Number of buildings identified with ACM cladding systems (unlikely to meet Building Regulations)	Number of buildings with ACM cladding systems (unlikely to meet Building Regulations) yet to be remediated	Percentage of buildings with ACM cladding systems completed remediation	Percentage of buildings with ACM cladding systems started or completed remediation
Barking and Dagenham	1 to 5	1 to 5	Between 50% and 99%	100%
Barnet	6 to 10	1 to 5	Less than 50%	100%
Basildon	1 to 5	None	100%	100%
Bedford	1 to 5	None	100%	100%
Birmingham	6 to 10	1 to 5	Between 50% and 99%	100%
Bournemouth, Christchurch and Poole	1 to 5	1 to 5	Less than 50%	100%
Bracknell Forest	1 to 5	None	100%	100%
Bradford	1 to 5	None	100%	100%
Brent	11 to 20	11 to 20	Less than 50%	Between 50% and 99%
Brighton and Hove	1 to 5	None	100%	100%
Bristol, City of	6 to 10	None	100%	100%
Bromley	1 to 5	None	100%	100%
Buckinghamshire	1 to 5	None	100%	100%
Bury	1 to 5	None	100%	100%
Calderdale	1 to 5	None	100%	100%
Camden	6 to 10	6 to 10	Less than 50%	Between 50% and 99%
City of London	1 to 5	None	100%	100%
Croydon	6 to 10	1 to 5	Between 50% and 99%	100%
Dacorum	1 to 5	None	100%	100%
Doncaster	1 to 5	None	100%	100%
Ealing	1 to 5	1 to 5	Between 50% and 99%	100%
Elmbridge	1 to 5	None	100%	100%
Epping Forest	1 to 5	1 to 5	Less than 50%	100%
Gateshead	1 to 5	None	100%	100%
Greenwich	Over 20	1 to 5	Between 50% and 99%	100%
Hackney	11 to 20	1 to 5	Between 50% and 99%	100%
Hammersmith and Fulham	6 to 10	None	100%	100%
Haringey	6 to 10	1 to 5	Between 50% and 99%	100%
Harrow	1 to 5	None	100%	100%
Havering	1 to 5	None	100%	100%
Hillingdon	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Hounslow	1 to 5	None	100%	100%
Islington	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Kensington and Chelsea	1 to 5	None	100%	100%
Kingston upon Thames	1 to 5	None	100%	100%
Kirklees	1 to 5	None	100%	100%
Lambeth	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Leeds	6 to 10	None	100%	100%
Leicester	1 to 5	None	100%	100%
Lewisham	1 to 5	1 to 5	Between 50% and 99%	100%
Lincoln	1 to 5	None	100%	100%
Liverpool	11 to 20	1 to 5	Between 50% and 99%	100%
Luton	1 to 5	1 to 5	Less than 50%	100%
Manchester	Over 20	1 to 5	Between 50% and 99%	100%
Medway	1 to 5	None	100%	100%
Merton	1 to 5	None	100%	100%
Milton Keynes	1 to 5	1 to 5	Less than 50%	100%
Newcastle upon Tyne	6 to 10	None	100%	100%
Newham	Over 20	1 to 5	Between 50% and 99%	100%
Norwich	6 to 10	1 to 5	Between 50% and 99%	100%
Nottingham	6 to 10	None	100%	100%
Oldham	1 to 5	None	100%	100%
Oxford	1 to 5	None	100%	100%
Plymouth	1 to 5	None	100%	100%
Portsmouth	1 to 5	1 to 5	Between 50% and 99%	100%
Reading	1 to 5	1 to 5	Between 50% and 99%	100%
Redbridge	1 to 5	None	100%	100%
Reigate and Banstead	1 to 5	None	100%	100%
Salford	Over 20	6 to 10	Between 50% and 99%	100%
Sandwell	1 to 5	None	100%	100%
Sefton	1 to 5	None	100%	100%
Sheffield	6 to 10	1 to 5	Between 50% and 99%	100%
Slough	1 to 5	1 to 5	Between 50% and 99%	100%
Southwark	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Stockton-on-Tees	1 to 5	None	100%	100%
Sunderland	1 to 5	None	100%	100%
Sutton	1 to 5	1 to 5	Between 50% and 99%	100%
Tower Hamlets	Over 20	6 to 10	Between 50% and 99%	Between 50% and 99%
Trafford	1 to 5	None	100%	100%
Waltham Forest	1 to 5	None	100%	100%
Wandsworth	11 to 20	1 to 5	Between 50% and 99%	100%
Warrington	1 to 5	None	100%	100%
Westminster	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Windsor and Maidenhead	1 to 5	None	100%	100%
Woking	1 to 5	None	100%	100%
Wolverhampton	1 to 5	None	100%	100%

## ACM_5
ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 March 2024
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Manchester	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	38	81%	13	72%	5	100%	1	50%	0	0%	57	79%
Works complete awaiting building control signoff	0	0%	2	11%	0	0%	0	0%	0	0%	2	3%
Remediation started - cladding removed	9	19%	2	11%	0	0%	1	50%	0	0%	12	17%
Remediation started	0	0%	1	6%	0	0%	0	0%	0	0%	1	1%
Plans in place	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	47	100%	18	100%	5	100%	2	100%	0	0%	72	100%

London	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	62	76%	131	79%	11	85%	11	73%	0	0%	215	78%
Works complete awaiting building control signoff	10	12%	6	4%	1	8%	2	13%	1	100%	20	7%
Remediation started - cladding removed	10	12%	8	5%	0	0%	1	7%	0	0%	19	7%
Remediation started	0	0%	13	8%	0	0%	1	7%	0	0%	14	5%
Plans in place	0	0%	6	4%	1	8%	0	0%	0	0%	7	3%
Responded with intent	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Total buildings	82	100%	166	100%	13	100%	15	100%	1	100%	277	100%

Rest of England	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	32	100%	41	76%	37	93%	12	86%	7	100%	129	88%
Works complete awaiting building control signoff	0	0%	8	15%	1	3%	1	7%	0	0%	10	7%
Remediation started - cladding removed	0	0%	2	4%	0	0%	0	0%	0	0%	2	1%
Remediation started	0	0%	3	6%	2	5%	1	7%	0	0%	6	4%
Plans in place	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	32	100%	54	100%	40	100%	14	100%	7	100%	147	100%

## ACM_6
ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 March 2024
Back to Contents
This worksheet contains four tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Identified by 31 December 2019	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	126	82%	164	88%	51	98%	22	81%	7	88%	370	86%
Works complete awaiting building control signoff	9	6%	8	4%	1	2%	2	7%	1	13%	21	5%
Remediation started - cladding removed	19	12%	6	3%	0	0%	2	7%	0	0%	27	6%
Remediation started	0	0%	7	4%	0	0%	1	4%	0	0%	8	2%
Plans in place	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Responded with intent	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	154	100%	187	100%	52	100%	27	100%	8	100%	428	100%

Identified by 31 December 2020	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	127	81%	180	85%	52	96%	23	79%	7	88%	389	85%
Works complete awaiting building control signoff	10	6%	12	6%	2	4%	3	10%	1	13%	28	6%
Remediation started - cladding removed	19	12%	8	4%	0	0%	2	7%	0	0%	29	6%
Remediation started	0	0%	9	4%	0	0%	1	3%	0	0%	10	2%
Plans in place	0	0%	2	1%	0	0%	0	0%	0	0%	2	0%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	156	100%	212	100%	54	100%	29	100%	8	100%	459	100%

Identified by 31 December 2021	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	131	82%	183	81%	53	95%	24	77%	7	88%	398	83%
Works complete awaiting building control signoff	10	6%	14	6%	2	4%	3	10%	1	13%	30	6%
Remediation started - cladding removed	19	12%	11	5%	0	0%	2	6%	0	0%	32	7%
Remediation started	0	0%	14	6%	0	0%	2	6%	0	0%	16	3%
Plans in place	0	0%	3	1%	1	2%	0	0%	0	0%	4	1%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	160	100%	226	100%	56	100%	31	100%	8	100%	481	100%

Identified by 31 December 2022	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	131	82%	185	80%	53	95%	24	77%	7	88%	400	82%
Works complete awaiting building control signoff	10	6%	16	7%	2	4%	3	10%	1	13%	32	7%
Remediation started - cladding removed	19	12%	11	5%	0	0%	2	6%	0	0%	32	7%
Remediation started	0	0%	15	6%	0	0%	2	6%	0	0%	17	3%
Plans in place	0	0%	3	1%	1	2%	0	0%	0	0%	4	1%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	160	100%	232	100%	56	100%	31	100%	8	100%	487	100%

Identified by 31 December 2023	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	132	82%	185	78%	53	91%	24	77%	7	88%	401	81%
Works complete awaiting building control signoff	10	6%	16	7%	2	3%	3	10%	1	13%	32	6%
Remediation started - cladding removed	19	12%	12	5%	0	0%	2	6%	0	0%	33	7%
Remediation started	0	0%	17	7%	2	3%	2	6%	0	0%	21	4%
Plans in place	0	0%	6	3%	1	2%	0	0%	0	0%	7	1%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	161	100%	238	100%	58	100%	31	100%	8	100%	496	100%

All buildings identified	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	132	82%	185	78%	53	91%	24	77%	7	88%	401	81%
Works complete awaiting building control signoff	10	6%	16	7%	2	3%	3	10%	1	13%	32	6%
Remediation started - cladding removed	19	12%	12	5%	0	0%	2	6%	0	0%	33	7%
Remediation started	0	0%	17	7%	2	3%	2	6%	0	0%	21	4%
Plans in place	0	0%	6	3%	1	2%	0	0%	0	0%	7	1%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	161	100%	238	100%	58	100%	31	100%	8	100%	496	100%

## ACM_7
Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 31 March 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed	9,700	14,700	17,600	24,400	27,300
Works complete awaiting building control signoff	400	1,200	1,600	1,600	2,000
Yet to complete remediation [note_3]	1,800	3,500	3,700	5,300	5,500
Occupied and yet to complete remediation	1,800	3,400	3,600	5,200	5,400

Leasehold dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed	2,700	14,700	17,600	17,400	20,300
Works complete awaiting building control signoff	100	1,200	1,600	1,300	1,700
Yet to complete remediation [note_3]	500	3,500	3,700	4,000	4,200
Occupied and yet to complete remediation	500	3,400	3,600	3,900	4,100

## ACM_8
ACM remediation progress by sources of funding, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	In social fund / [note 4]	Not in social fund	Private: government funded / [note 5]	Private: not government funded
Remediation completed	125	7	82	103
Works complete awaiting building control signoff	10	0	9	7
Remediation started - cladding removed	9	10	9	3
Remediation started	0	0	13	4
Plans in place	0	0	5	1
Responded with intent	0	0	0	1
Remediation plan unclear	0	0	0	1
Total	144	17	118	120

## ACM_9
Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Category	Number of buildings inside London	Number of buildings outside London
No contact with delivery partners	0	0
Preparing application	0	0
Eligibility application submitted	0	0
Eligibility approved	3	0
Applications approved: for pre-contract support	2	1
Full cost application submitted	0	0
Applications approved: for full costs	66	39
TOTAL	71	40

## ACM_10
Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Funding	Social Sector / (£ million)	Private Sector / (£ million)
Approved [note_6, note_7]	297	235
Expenditure [note_8, note_9]	271	288

## WWRF_1
Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 March 2024
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Tranche	Applications	Buildings	Approved Applications	Approved Buildings	Leasehold dwellings in approved buildings	Approved Funding / (£ million)	Mean Waking Watch cost per month per dwelling in approved buildings / (£)	Median Waking Watch cost per month per dwelling in approved buildings / (£)	Buildings with alarm installation complete
Waking Watch Relief Fund	329	468	212	320	24,700	27.3	169	104	304
Waking Watch Replacement Fund	38	67	25	47	2,200	2.4	216	210	42
Total [note_10]	367	535	237	367	26,900	29.7	172	106	346

## WWRF_2
Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 March 2024
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_11]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	9	8	1	0	0	11%	89%	9	8	89%	3%	1.6	200,826	180,147
Bristol	3	2	1	0	0	33%	67%	3	2	67%	1%	0.1	46,256	46,256
Greater London Authority	110	65	29	16	0	26%	59%	171	111	65%	35%	8.3	74,911	64,551
Greater Manchester Combined Authority	25	20	5	0	0	20%	80%	38	33	87%	10%	2.5	75,477	76,928
Leeds	10	9	0	1	0	0%	90%	12	11	92%	3%	1.8	162,466	124,500
Liverpool	18	17	1	0	0	6%	94%	19	18	95%	6%	1.7	94,400	63,784
Newcastle	3	3	0	0	0	0%	100%	3	3	100%	1%	0.4	128,496	163,181
Sheffield	6	5	0	1	0	0%	83%	7	6	86%	2%	0.5	88,753	87,828
DLUHC (1st Tranche)	35	21	14	0	0	40%	60%	55	39	71%	12%	2.7	69,807	65,577
DLUHC (2nd Tranche)	60	27	32	1	0	53%	45%	70	34	49%	11%	3.8	112,303	81,624
DLUHC (3rd Tranche)	50	35	14	1	0	28%	70%	81	55	68%	17%	3.9	70,341	57,389
DLUHC Total	145	83	60	2	0	41%	57%	206	128	62%	40%	10.4	81,324	65,486
Total [note_10]	329	212	97	20	0	29%	64%	468	320	68%	100%	27.3	85,371	67,894

## WWRF_3
Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 March 2024
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_12]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	2	2	0	0	0	0%	100%	4	4	100%	9%	0.4	89,328	87,683
DLUHC	25	21	1	3	0	4%	84%	46	40	87%	85%	1.8	45,360	26,643
Greater Manchester Combined Authority	11	2	9	0	0	82%	18%	17	3	18%	6%	0.2	65,206	46,743
Leeds	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Liverpool	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Sheffield	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Total [note_10]	38	25	10	3	0	26%	66%	67	47	70%	100%	2.4	50,369	30,209

## BSF_1
Remediation status of eligible buildings within BSF by tenure, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note 23]	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Total residential Number	Total residential Percentage (%)
Remediation complete	37	22%	121	16%	158	17%
Remediation complete: awaiting building control sign-off	12	7%	94	12%	106	11%
Remediation started	57	33%	190	25%	247	26%
Remediation not yet started	66	38%	357	47%	423	45%
Total buildings [note 10]	172	100%	762	100%	934	100%

## BSF_2
BSF remediation progress of eligible buildings by region, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note 23]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF / Percentage(%)	Not Started Remediation / Number	Not Started Remediation / Percentage(%)	Started Remediation / Number	Started Remediation / Percentage(%)	Completed Remediation [note_13] / Number	Completed Remediation [note_13] / Percentage(%)	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible BSF buildings that have started or completed remediation / Percentage (%)
North West	134	14%	50	12%	45	18%	39	15%	29%	63%
London	550	59%	270	64%	141	57%	139	53%	25%	51%
East of England	29	3%	15	4%	4	2%	10	4%	34%	48%
East Midlands	29	3%	16	4%	9	4%	4	2%	14%	45%
North East	14	1%	10	2%	2	1%	2	1%	14%	29%
South East	67	7%	23	5%	7	3%	37	14%	55%	66%
South West	35	4%	14	3%	15	6%	6	2%	17%	60%
West Midlands	18	2%	7	2%	6	2%	5	2%	28%	61%
Yorkshire and The Humber	58	6%	18	4%	18	7%	22	8%	38%	69%
Total	934	100%	423	100%	247	100%	264	100%	28%	55%

## BSF_3
BSF number of eligible buildings by funding allocations, expenditure and tenure, England, 31 March 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Some cells in this table are empty because data is not available for these variables.
Table BSF_3a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the BSF .
Funding Allocations [note_15][note_57]	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Funding / (£ millions)
Full Applications Approved	449	1,757
Pre-Tender Support Allocations	723	281
Total [note 10]		2,037	107	214	2,251

Table BSF_3b: Amount of expenditure from the BSF by tenure.
Expenditure [note_43][note_44]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	761	1,409	85	171	846	1,580

## BSF_4
BSF remediation progress of eligible buildings by local authority, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_45]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF yet to be remediated / Number	Completed Remediation / Percentage(%)	Started or Completed Remediation / Percentage(%)
Adur	1-5	0	100%	100%
Ashford	1-5	0	100%	100%
Barking and Dagenham	7	7	0%	86%
Barnet	1-5	1-5	Less than 50%	50-99%
Barnsley	1-5	1-5	50-99%	50-99%
Basildon	1-5	1-5	Less than 50%	Less than 50%
Bedford	1-5	1-5	Less than 50%	Less than 50%
Bexley	1-5	1-5	Less than 50%	100%
Birmingham	14	13	7%	71%
Bolton	1-5	1-5	50-99%	100%
Bournemouth, Christchurch and Poole	1-5	1-5	Less than 50%	50-99%
Bradford	1-5	1-5	Less than 50%	50-99%
Brent	21	20	5%	43%
Brighton and Hove	6	5	17%	50%
Bristol, City of	14	12	14%	71%
Bromley	1-5	1-5	50-99%	50-99%
Buckinghamshire	1-5	1-5	50-99%	50-99%
Calderdale	1-5	1-5	Less than 50%	100%
Cambridge	1-5	1-5	50-99%	100%
Camden	14	13	7%	57%
Central Bedfordshire	1-5	1-5	Less than 50%	Less than 50%
Chelmsford	1-5	0	100%	100%
City of London	1-5	1-5	Less than 50%	Less than 50%
Coventry	1-5	1-5	Less than 50%	Less than 50%
Croydon	16	13	19%	44%
Dorset	1-5	1-5	Less than 50%	50-99%
Ealing	9	9	0%	67%
Eastbourne	7	7	0%	86%
Enfield	6	6	0%	50%
Gateshead	1-5	1-5	50-99%	50-99%
Greenwich	16	15	6%	56%
Guildford	1-5	1-5	Less than 50%	Less than 50%
Hackney	41	36	12%	51%
Hammersmith and Fulham	11	11	0%	9%
Haringey	7	6	14%	71%
Harrow	1-5	1-5	Less than 50%	50-99%
Hastings	1-5	1-5	Less than 50%	Less than 50%
Havering	1-5	1-5	Less than 50%	50-99%
High Peak	1-5	1-5	Less than 50%	Less than 50%
Hillingdon	8	8	0%	0%
Hounslow	16	11	31%	56%
Hyndburn	1-5	1-5	Less than 50%	Less than 50%
Ipswich	9	9	0%	44%
Isle of Wight	1-5	1-5	Less than 50%	100%
Islington	27	26	4%	33%
Kensington and Chelsea	11	9	18%	64%
Kingston upon Hull, City of	1-5	1-5	Less than 50%	Less than 50%
Kingston upon Thames	1-5	1-5	Less than 50%	Less than 50%
Kirklees	1-5	0	100%	100%
Knowsley	1-5	1-5	Less than 50%	Less than 50%
Lambeth	21	21	0%	48%
Lancaster	1-5	0	100%	100%
Leeds	36	25	31%	78%
Leicester	9	9	0%	33%
Lewes	1-5	0	100%	100%
Lewisham	8	7	13%	50%
Lincoln	1-5	1-5	Less than 50%	Less than 50%
Liverpool	33	30	9%	42%
Luton	1-5	1-5	Less than 50%	50-99%
Maidstone	1-5	1-5	Less than 50%	Less than 50%
Manchester	65	49	25%	77%
Mansfield	1-5	1-5	Less than 50%	100%
Medway	1-5	1-5	Less than 50%	100%
Merton	8	6	25%	38%
Middlesbrough	1-5	1-5	Less than 50%	Less than 50%
Milton Keynes	1-5	1-5	Less than 50%	50-99%
Mole Valley	1-5	1-5	Less than 50%	Less than 50%
Newcastle upon Tyne	8	7	13%	38%
Newham	75	67	11%	47%
North Somerset	1-5	1-5	Less than 50%	100%
North Yorkshire	1-5	1-5	Less than 50%	100%
Norwich	1-5	1-5	Less than 50%	Less than 50%
Nottingham	16	13	19%	56%
Peterborough	1-5	0	100%	100%
Plymouth	10	9	10%	40%
Portsmouth	1-5	1-5	Less than 50%	100%
Preston	1-5	0	100%	100%
Reading	13	6	54%	92%
Redbridge	6	6	0%	67%
Richmond upon Thames	1-5	0	100%	100%
Rother	1-5	1-5	Less than 50%	100%
Salford	22	13	41%	64%
Sefton	1-5	1-5	Less than 50%	Less than 50%
Sevenoaks	1-5	1-5	Less than 50%	100%
Sheffield	12	11	8%	42%
Slough	6	6	0%	50%
Southampton	6	5	17%	33%
Southend-on-Sea	1-5	0	100%	100%
Southwark	36	31	14%	42%
St Albans	1-5	1-5	Less than 50%	Less than 50%
St. Helens	1-5	1-5	Less than 50%	Less than 50%
Stevenage	1-5	1-5	50-99%	100%
Stockport	1-5	1-5	Less than 50%	100%
Stoke-on-Trent	1-5	1-5	Less than 50%	Less than 50%
Sunderland	1-5	1-5	Less than 50%	Less than 50%
Surrey Heath	1-5	0	100%	100%
Sutton	1-5	1-5	Less than 50%	50-99%
Swindon	1-5	1-5	Less than 50%	Less than 50%
Thanet	1-5	1-5	Less than 50%	Less than 50%
Tower Hamlets	115	89	23%	56%
Trafford	1-5	1-5	Less than 50%	Less than 50%
Wakefield	1-5	0	100%	100%
Waltham Forest	1-5	1-5	Less than 50%	Less than 50%
Wandsworth	12	9	25%	92%
Warrington	1-5	1-5	Less than 50%	Less than 50%
Watford	1-5	1-5	Less than 50%	100%
Westminster	28	22	21%	61%
Worcester	1-5	1-5	Less than 50%	100%

## Combined_1
Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17]	ACM cladding only / Number	ACM cladding only / Percentage (%)	Non-ACM cladding only in the BSF / Number	Non-ACM cladding only in the BSF / Percentage (%)	Both ACM and non-ACM cladding in the BSF / Number	Both ACM and non-ACM cladding in the BSF / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation completed	338	85%	123	15%	35	36%	496	37%
Works complete awaiting building control signoff	26	7%	98	12%	8	8%	132	10%
Remediation started	30	8%	217	26%	50	51%	297	22%
Remediation not started	4	1%	398	48%	5	5%	407	31%
Total	398	100%	836	100%	98	100%	1,332	100%

## Combined_2
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17, note_18, note_42]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	132	8%	844	31%	976	23%
Remediation underway	360	22%	632	23%	992	23%
In programme	1,115	69%	1,246	46%	2,361	55%
Total	1,607	100%	2,722	100%	4,329	100%

## Combined_3
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, by local authority, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_45]	Buildings monitored	In programme / Percentage(%)	Remediation Underway / Percentage(%)	Completed Remediation / Percentage(%)
Barking and Dagenham	11-50	60%	15%	25%
Barnet	51-100	56%	8%	36%
Basingstoke and Deane	11-50	79%	0%	21%
Bexley	11-50	44%	50%	6%
Birmingham	101-200	20%	16%	64%
Bournemouth, Christchurch and Poole	11-50	39%	36%	25%
Bradford	11-50	75%	0%	25%
Brent	51-100	63%	18%	18%
Brighton and Hove	11-50	81%	11%	7%
Bristol, City of	101-200	63%	26%	11%
Bromley	11-50	33%	48%	19%
Cambridge	11-50	73%	14%	14%
Camden	51-100	60%	12%	28%
Chelmsford	11-50	5%	60%	35%
Croydon	51-100	66%	22%	12%
Dacorum	11-50	44%	33%	22%
Dartford	11-50	74%	13%	13%
Ealing	51-100	51%	18%	31%
Eastbourne	11-50	45%	0%	55%
Enfield	11-50	71%	10%	19%
Epping Forest	11-50	17%	75%	8%
Greenwich	101-200	61%	13%	26%
Hackney	101-200	62%	18%	20%
Hammersmith and Fulham	11-50	74%	11%	14%
Haringey	51-100	29%	60%	11%
Harrow	11-50	52%	12%	36%
Havering	11-50	46%	46%	7%
Hertsmere	11-50	63%	31%	6%
Hillingdon	11-50	88%	0%	13%
Hounslow	51-100	46%	25%	28%
Ipswich	11-50	69%	6%	25%
Islington	101-200	72%	19%	9%
Kensington and Chelsea	11-50	45%	45%	10%
Kirklees	11-50	67%	17%	17%
Lambeth	101-200	71%	16%	13%
Leeds	51-100	39%	27%	34%
Leicester	11-50	61%	26%	13%
Lewisham	51-100	48%	32%	20%
Liverpool	51-100	53%	27%	20%
Maidstone	11-50	82%	9%	9%
Manchester	101-200	40%	28%	32%
Medway	11-50	27%	27%	45%
Merton	11-50	64%	7%	29%
Milton Keynes	11-50	82%	5%	14%
Newcastle upon Tyne	11-50	45%	32%	23%
Newham	101-200	59%	24%	17%
North Somerset	11-50	62%	38%	0%
Norwich	11-50	26%	26%	48%
Nottingham	11-50	50%	18%	32%
Plymouth	11-50	52%	29%	19%
Portsmouth	51-100	41%	39%	20%
Reading	11-50	37%	11%	52%
Redbridge	11-50	71%	9%	20%
Richmond upon Thames	11-50	93%	0%	7%
Salford	51-100	24%	32%	44%
Sheffield	11-50	54%	14%	32%
Slough	11-50	48%	26%	26%
Solihull	11-50	75%	25%	0%
Southampton	101-200	31%	65%	4%
Southwark	101-200	72%	11%	18%
Stevenage	11-50	80%	7%	13%
Sunderland	11-50	57%	7%	36%
Sutton	11-50	41%	41%	18%
Tower Hamlets	over 400	63%	14%	22%
Waltham Forest	11-50	82%	10%	8%
Wandsworth	51-100	57%	5%	38%
Watford	11-50	73%	27%	0%
West Northamptonshire	11-50	15%	85%	0%
Westminster	51-100	51%	12%	37%
Woking	11-50	84%	11%	5%
Wolverhampton	11-50	77%	0%	23%

## Combined_4
Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys by remediation status, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings [note_10]	Estimated dwellings in 11-18m buildings	Estimated dwellings in 18m+ buildings	Estimated Total dwellings
Remediation complete (including those awaiting building control signoff)	6,000	58,000	64,000
Remediation underway	10,000	50,000	60,000
In programme	33,000	91,000	125,000
Total	49,000	199,000	248,000

## CSS_1
Application status of buildings within the CSS, England, 31 March 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Application category for pre-eligible buildings [note_47, note_48]	Number
Pre - application	494

Application category for pre-eligbile live applications	Number	Percentage (%)
Initial Application	331	75%
FRAEW	79	18%
Eligibility in review	31	7%
Total pre-eligible live applications	441	100%

Pre - eligible buildings total	Number
Total pre - eligible buildings	935

Application category for eligible buildings	Number	Percentage (%)
Grant Funding Agreement	42	25%
Pre - works package	107	63%
Works package	19	11%
Works started	2	1%
Works completed	0	0%
Total eligible buildings	170	100%

## CSS_2
CSS remediation progress by region, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_48]	Eligible Buildings in the CSS / Number	Not Started Remediation / Number	Started Remediation / Number	Completed Remediation / Number	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible CSS buildings that have started or completed remediation / Percentage (%)
North West	20	20	0	0	0%	0%
London	79	78	1	0	0%	1%
East of England	13	13	0	0	0%	0%
East Midlands	10	10	0	0	0%	0%
North East	4	4	0	0	0%	0%
South East	20	19	1	0	0%	5%
South West	7	7	0	0	0%	0%
West Midlands	2	2	0	0	0%	0%
Yorkshire and The Humber	12	12	0	0	0%	0%
Northern Ireland	3	3	0	0	0%	0%
Total	170	168	2	0	0%	1%

## CSS_3
CSS remediation progress by height, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_48]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)
Remediation complete	0	0%	0	0%
Remediation started	2	1%	0	0%
In programme	147	99%	21	100%
Total buildings	149	100%	21	100%

## CSS_4
CSS remediation progress by tenure, England, 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_48]	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)
Remediation complete	0	0%	0	0%
Remediation started	1	3%	1	1%
In programme	37	97%	131	99%
Total buildings	38	100%	132	100%

## Developer_1
Remediation status of buildings requiring works under the developer remediation contract by height group, England, 31 March 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - All Defect Types [Note_25, Note_26]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	123	20%	184	21%	307	20%
Remediation started	101	16%	216	25%	317	21%
Remediation not Started - Plans in Place	223	35%	289	33%	512	34%
Remediation not Started - No Plans in Place	183	29%	182	21%	365	24%
Total buildings	630	100%	871	100%	1501	100%

Remediation Category - Cladding Defects [Note_25, Note_26]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	103	18%	181	22%	284	20%
Remediation started	96	17%	207	25%	303	22%
Remediation not Started - Plans in Place	201	36%	280	33%	481	34%
Remediation not Started - No Plans in Place	162	29%	174	21%	336	24%
Total buildings	562	100%	842	100%	1404	100%

## Developer_2
Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 January 2024
Back to Contents
This worksheet contains one table. All figures are for estimated cost of buildings identified as requiring works under the Developer Remediation Contract in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Cost Category [Note_33]	11-18m / (£ millions)	18m+ / (£ millions)	Total / (£ millions)
Total estimated cost of works	738	2,284	3,022

## Developer_3
Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 January 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 January 2024
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29]	Number of buildings for which the developer has accepted responsibility under the contract	Number of buildings assessed and found to require remediation [Note_28]	Number of buildings assessed and found to require remediation, and which will be remediated by the developer directly (rather than being remediated through a government fund, with cost re-imbursed by developer) [Note 31]	Number of buildings where it is not known whether remediation is required [Note 32]	Number of buildings where no remediation is required
Total	4614	1324	1205	1607	1683
Abbey Developments Limited(*)	-	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	54	0	0	54	0
Ballymore Limited	85	32	17	1	52
Barratt Developments PLC	709	174	162	263	272
Bellway PLC	503	207	187	234	62
The Berkeley Group Holdings PLC	819	72	61	44	703
Bewley Group Limited	9	3	1	3	3
Bloor Investments Limited(*)	-	-	-	-	-
The British Land Company PLC	16	6	6	10	0
Cala Group (Holdings) Limited	28	1	1	27	0
Canary Wharf Group PLC	13	0	0	13	0
C.G. Fry and Son Limited (*)	-	-	-	-	-
Churchill Retirement PLC	8	0	0	0	8
Crest Nicholson Holdings PLC	290	101	100	166	23
Croudace Homes Group Limited (*)	-	-	-	-	-
Dandara Living Holdings Limited	21	16	10	3	2
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-	-
Fairview Holdings Limited	121	56	53	64	1
Frasers Property (UK) Ltd	23	0	0	10	13
Galliard Group Limited	104	16	16	41	47
MJ Gleeson PLC	17	12	11	5	0
Grosvenor Group Limited	17	2	2	15	0
Hill Holdings Limited	87	8	7	13	66
Hopkins Home Group Limited (*)	-	-	-	-	-
Jelson Holdings Limited	7	2	2	3	2
Keepmoat Limited (*)	-	-	-	-	-
Land Securities Group PLC	43	5	4	26	12
Lendlease Europe Holdings Limited	92	28	27	30	34
Lifestory Holdings Limited (also covers Anthology Group)	18	1	1	17	0
London Square Development (Holdings) Limited	43	29	29	14	0
Miller Homes Limited	32	17	17	15	0
Morris Homes Group Limited	6	2	2	0	4
Morgan Sindall Group PLC (parent company for Lovell and Muse)	119	13	13	16	90
Persimmon Public Limited Company	64	47	45	9	8
Redrow PLC	129	62	48	65	2
Regal Holdco Limited (parent company for Regal London)	15	0	0	0	15
Rowland Group Limited (*)	-	-	-	-	-
Rydon Group Holdings Limited	25	14	11	1	10
Sorbon Group Limited (parent company for Shanly Homes)	26	3	3	23	0
St Modwen Group Holdings Company Limited	13	0	0	8	5
Story Homes Limited (*)	-	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-	-
Taylor Wimpey PLC	383	171	164	209	3
Telford Homes Limited	148	62	55	70	16
Tilia Homes Limited	8	7	7	1	0
Vistry Group PLC	289	109	99	21	159
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-	-
Weston Group PLC	88	21	21	11	56
McCarthy & Stone Limited	61	0	0	61	0
Seven Capital PLC	21	5	5	16	0
Wates Group Limited	25	8	7	12	5
Watkin Jones PLC	14	6	6	8	0
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	21	6	5	5	10

## Developer_4
Developer by developer breakdown of buildings covered by the developer remediation contract, by assessment status, England, 31 January 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 January 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29]	Progress with assessments
	Buildings that…
	…have had an Assessment [Note 30]		…have not had an assessment		…have been assessed and confirmed to require remediation
					out of total buildings [Note_28]	out of total buildings	out of assessed buildings
Total	3613	78%	1001	22%	1324	29%	37%
Abbey Developments Limited(*)	-	-	-	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	10	19%	44	81%	0	0%	0%
Ballymore Limited	84	99%	1	1%	32	38%	38%
Barratt Developments PLC	492	69%	217	31%	174	25%	35%
Bellway PLC	273	54%	230	46%	207	41%	76%
The Berkeley Group Holdings PLC	781	95%	38	5%	72	9%	9%
Bewley Group Limited	9	100%	0	0%	3	33%	33%
Bloor Investments Limited(*)	-	-	-	-	-	-	-
The British Land Company PLC	16	100%	0	0%	6	38%	38%
Cala Group (Holdings) Limited	7	25%	21	75%	1	4%	14%
Canary Wharf Group PLC	13	100%	0	0%	0	0%	0%
C.G. Fry and Son Limited (*)	-	-	-	-	-	-	-
Churchill Retirement PLC	8	100%	0	0%	0	0%	0%
Crest Nicholson Holdings PLC	146	50%	144	50%	101	35%	69%
Croudace Homes Group Limited (*)	-	-	-	-	-	-	-
Dandara Living Holdings Limited	21	100%	0	0%	16	76%	76%
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-	-	-	-
Fairview Holdings Limited	121	100%	0	0%	56	46%	46%
Frasers Property (UK) Ltd	13	57%	10	43%	0	0%	0%
Galliard Group Limited	96	92%	8	8%	16	15%	17%
MJ Gleeson PLC	15	88%	2	12%	12	71%	80%
Grosvenor Group Limited	9	53%	8	47%	2	12%	22%
Hill Holdings Limited	74	85%	13	15%	8	9%	11%
Hopkins Home Group Limited (*)	-	-	-	-	-	-	-
Jelson Holdings Limited	7	100%	0	0%	2	29%	29%
Keepmoat Limited (*)	-	-	-	-	-	-	-
Land Securities Group PLC	20	47%	23	53%	5	12%	25%
Lendlease Europe Holdings Limited	75	82%	17	18%	28	30%	37%
Lifestory Holdings Limited (also covers Anthology Group)	18	100%	0	0%	1	6%	6%
London Square Development (Holdings) Limited	43	100%	0	0%	29	67%	67%
Miller Homes Limited	32	100%	0	0%	17	53%	53%
Morris Homes Group Limited	6	100%	0	0%	2	33%	33%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	112	94%	7	6%	13	11%	12%
Persimmon Public Limited Company	62	97%	2	3%	47	73%	76%
Redrow PLC	129	100%	0	0%	62	48%	48%
Regal Holdco Limited (parent company for Regal London)	15	100%	0	0%	0	0%	0%
Rowland Group Limited (*)	-	-	-	-	-	-	-
Rydon Group Holdings Limited	25	100%	0	0%	14	56%	56%
Sorbon Group Limited (parent company for Shanly Homes)	26	100%	0	0%	3	12%	12%
St Modwen Group Holdings Company Limited	5	38%	8	62%	0	0%	0%
Story Homes Limited (*)	-	-	-	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-	-	-	-
Taylor Wimpey PLC	266	69%	117	31%	171	45%	64%
Telford Homes Limited	124	84%	24	16%	62	42%	50%
Tilia Homes Limited	8	100%	0	0%	7	88%	88%
Vistry Group PLC	273	94%	16	6%	109	38%	40%
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-	-	-	-
Weston Group PLC	78	89%	10	11%	21	24%	27%
McCarthy & Stone Limited	61	100%	0	0%	0	0%	0%
Seven Capital PLC	6	29%	15	71%	5	24%	83%
Wates Group Limited	12	48%	13	52%	8	32%	67%
Watkin Jones PLC	6	43%	8	57%	6	43%	100%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	16	76%	5	24%	6	29%	38%

## Developer_5
Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 January 2024.
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 January 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29]	Remediation Status
	Proportion of buildings being remediated by the developer directly where remediation is...
	…not yet started		... started or complete		... started		...complete
Total	759	63%	446	37%	233	19%	213	18%
Abbey Developments Limited(*)	-	-	-	-	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	-	0	-	0	-	0	-
Ballymore Limited	8	47%	9	53%	0	0%	9	53%
Barratt Developments PLC	94	58%	68	42%	42	26%	26	16%
Bellway PLC	111	59%	76	41%	48	26%	28	15%
The Berkeley Group Holdings PLC	18	30%	43	70%	8	13%	35	57%
Bewley Group Limited	1	100%	0	0%	0	0%	0	0%
Bloor Investments Limited(*)	-	-	-	-	-	-	-	-
The British Land Company PLC	5	83%	1	17%	1	17%	0	0%
Cala Group (Holdings) Limited	1	100%	0	0%	0	0%	0	0%
Canary Wharf Group PLC	0	-	0	-	0	-	0	-
C.G. Fry and Son Limited (*)	-	-	-	-	-	-	-	-
Churchill Retirement PLC	0	-	0	-	0	-	0	-
Crest Nicholson Holdings PLC	44	44%	56	56%	56	56%	0	0%
Croudace Homes Group Limited (*)	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0%	10	100%	10	100%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-	-	-	-	-
Fairview Holdings Limited	29	55%	24	45%	5	9%	19	36%
Frasers Property (UK) Ltd	0	-	0	-	0	-	0	-
Galliard Group Limited	1	6%	15	94%	4	25%	11	69%
MJ Gleeson PLC	11	100%	0	0%	0	0%	0	0%
Grosvenor Group Limited	1	50%	1	50%	1	50%	0	0%
Hill Holdings Limited	1	14%	6	86%	0	0%	6	86%
Hopkins Home Group Limited (*)	-	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0%	2	100%	0	0%	2	100%
Keepmoat Limited (*)	-	-	-	-	-	-	-	-
Land Securities Group PLC	4	100%	0	0%	0	0%	0	0%
Lendlease Europe Holdings Limited	25	93%	2	7%	2	7%	0	0%
Lifestory Holdings Limited (also covers Anthology Group)	1	100%	0	0%	0	0%	0	0%
London Square Development (Holdings) Limited	29	100%	0	0%	0	0%	0	0%
Miller Homes Limited	9	53%	8	47%	2	12%	6	35%
Morris Homes Group Limited	0	0%	2	100%	2	100%	0	0%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	7	54%	6	46%	3	23%	3	23%
Persimmon Public Limited Company	36	80%	9	20%	7	16%	2	4%
Redrow PLC	43	90%	5	10%	5	10%	0	0%
Regal Holdco Limited (parent company for Regal London)	0	-	0	-	0	-	0	-
Rowland Group Limited (*)	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	18%	9	82%	4	36%	5	45%
Sorbon Group Limited (parent company for Shanly Homes)	3	100%	0	0%	0	0%	0	0%
St Modwen Group Holdings Company Limited	0	-	0	-	0	-	0	-
Story Homes Limited (*)	-	-	-	-	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	107	65%	57	35%	15	9%	42	26%
Telford Homes Limited	55	100%	0	0%	0	0%	0	0%
Tilia Homes Limited	7	100%	0	0%	0	0%	0	0%
Vistry Group PLC	69	70%	30	30%	11	11%	19	19%
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-	-	-	-	-
Weston Group PLC	15	71%	6	29%	6	29%	0	0%
McCarthy & Stone Limited	0	-	0	-	0	-	0	-
Seven Capital PLC	5	100%	0	0%	0	0%	0	0%
Wates Group Limited	7	100%	0	0%	0	0%	0	0%
Watkin Jones PLC	6	100%	0	0%	0	0%	0	0%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	4	80%	1	20%	1	20%	0	0%

## Developer_6
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 January 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 January 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_27, Note_29]	Buildings that require remediation by the developer which have not yet started, with a start date…

	...at all		…within the next 12 months
Total	591	78%	346	46%
Abbey Developments Limited(*)	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	-	0	-
Ballymore Limited	2	25%	2	25%
Barratt Developments PLC	94	100%	71	76%
Bellway PLC	86	77%	20	18%
The Berkeley Group Holdings PLC	18	100%	18	100%
Bewley Group Limited	1	100%	0	0%
Bloor Investments Limited(*)	-	-	-	-
The British Land Company PLC	1	20%	1	20%
Cala Group (Holdings) Limited	0	0%	0	0%
Canary Wharf Group PLC	0	-	0	-
C.G. Fry and Son Limited (*)	-	-	-	-
Churchill Retirement PLC	0	-	0	-
Crest Nicholson Holdings PLC	40	91%	37	84%
Croudace Homes Group Limited (*)	-	-	-	-
Dandara Living Holdings Limited	0	-	0	-
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-
Fairview Holdings Limited	29	100%	17	59%
Frasers Property (UK) Ltd	0	-	0	-
Galliard Group Limited	1	100%	1	100%
MJ Gleeson PLC	10	91%	8	73%
Grosvenor Group Limited	0	0%	0	0%
Hill Holdings Limited	0	0%	0	0%
Hopkins Home Group Limited (*)	-	-	-	-
Jelson Holdings Limited	0	-	0	-
Keepmoat Limited (*)	-	-	-	-
Land Securities Group PLC	0	0%	0	0%
Lendlease Europe Holdings Limited	14	56%	12	48%
Lifestory Holdings Limited (also covers Anthology Group)	1	100%	1	100%
London Square Development (Holdings) Limited	0	0%	0	0%
Miller Homes Limited	9	100%	7	78%
Morris Homes Group Limited	0	-	0	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	4	57%	4	57%
Persimmon Public Limited Company	32	89%	6	17%
Redrow PLC	43	100%	18	42%
Regal Holdco Limited (parent company for Regal London)	0	-	0	-
Rowland Group Limited (*)	-	-	-	-
Rydon Group Holdings Limited	0	0%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	2	67%	2	67%
St Modwen Group Holdings Company Limited	0	-	0	-
Story Homes Limited (*)	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-
Taylor Wimpey PLC	96	90%	63	59%
Telford Homes Limited	26	47%	19	35%
Tilia Homes Limited	5	71%	5	71%
Vistry Group PLC	62	90%	34	49%
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-
Weston Group PLC	15	100%	0	0%
McCarthy & Stone Limited	0	-	0	-
Seven Capital PLC	0	0%	0	0%
Wates Group Limited	0	0%	0	0%
Watkin Jones PLC	0	0%	0	0%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	0	-	0	-

## Developer_7
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 31 January 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 January 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_27, Note_29]	For buildings which have not yet started, start profiles by financial year...					Buildings which have not yet started, with...

	2023-2024	2024-2025	2025-2026	2026-2027	2027-2028	2028-2029	.. no start date provided	... start date prior to 2023-2024
Total	136	316	85	41	4	3	168	6
Abbey Developments Limited(*)	-	-	-	-	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0	0	0	0	0	0	0
Ballymore Limited	0	2	0	0	0	0	6	0
Barratt Developments PLC	3	76	15	0	0	0	0	0
Bellway PLC	1	21	34	23	4	3	25	0
The Berkeley Group Holdings PLC	6	12	0	0	0	0	0	0
Bewley Group Limited	0	0	0	0	0	0	0	1
Bloor Investments Limited(*)	-	-	-	-	-	-	-	-
The British Land Company PLC	1	0	0	0	0	0	4	0
Cala Group (Holdings) Limited	0	0	0	0	0	0	1	0
Canary Wharf Group PLC	0	0	0	0	0	0	0	0
C.G. Fry and Son Limited (*)	-	-	-	-	-	-	-	-
Churchill Retirement PLC	0	0	0	0	0	0	0	0
Crest Nicholson Holdings PLC	26	13	0	0	0	0	4	1
Croudace Homes Group Limited (*)	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0	0	0	0	0	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-	-	-	-	-
Fairview Holdings Limited	12	17	0	0	0	0	0	0
Frasers Property (UK) Ltd	0	0	0	0	0	0	0	0
Galliard Group Limited	1	0	0	0	0	0	0	0
MJ Gleeson PLC	5	5	0	0	0	0	1	0
Grosvenor Group Limited	0	0	0	0	0	0	1	0
Hill Holdings Limited	0	0	0	0	0	0	1	0
Hopkins Home Group Limited (*)	-	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0	0	0	0	0	0	0
Keepmoat Limited (*)	-	-	-	-	-	-	-	-
Land Securities Group PLC	0	0	0	0	0	0	4	0
Lendlease Europe Holdings Limited	4	10	0	0	0	0	11	0
Lifestory Holdings Limited (also covers Anthology Group)	1	0	0	0	0	0	0	0
London Square Development (Holdings) Limited	0	0	0	0	0	0	29	0
Miller Homes Limited	0	9	0	0	0	0	0	0
Morris Homes Group Limited	0	0	0	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	1	3	0	0	0	0	3	0
Persimmon Public Limited Company	31	1	0	0	0	0	4	0
Redrow PLC	6	12	10	15	0	0	0	0
Regal Holdco Limited (parent company for Regal London)	0	0	0	0	0	0	0	0
Rowland Group Limited (*)	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	0	0	0	0	0	0	2	0
Sorbon Group Limited (parent company for Shanly Homes)	1	1	0	0	0	0	1	0
St Modwen Group Holdings Company Limited	0	0	0	0	0	0	0	0
Story Homes Limited (*)	-	-	-	-	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	11	75	10	0	0	0	11	0
Telford Homes Limited	2	19	2	3	0	0	29	0
Tilia Homes Limited	5	0	0	0	0	0	2	0
Vistry Group PLC	8	40	14	0	0	0	7	0
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-	-	-	-	-
Weston Group PLC	11	0	0	0	0	0	0	4
McCarthy & Stone Limited	0	0	0	0	0	0	0	0
Seven Capital PLC	0	0	0	0	0	0	5	0
Wates Group Limited	0	0	0	0	0	0	7	0
Watkin Jones PLC	0	0	0	0	0	0	6	0
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	0	0	0	0	0	0	4	0

## Developer_8
Developer by developer breakdown of buildings requiring remediation, which had not started works in the previous quarter England, 31 January 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 January 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29, Note_55]	For buildings which had not started last quarter, but were due to start this quarter, current remediation status...

	... not started	... started	... completed	... total number due to start	% not started, that were due to start
Total	112	51	1	164	68%
Abbey Developments Limited(*)	-	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0	0	0	-
Ballymore Limited	0	0	0	0	-
Barratt Developments PLC	5	1	0	6	83%
Bellway PLC	0	3	0	3	0%
The Berkeley Group Holdings PLC	4	0	1	5	80%
Bewley Group Limited	0	0	0	0	-
Bloor Investments Limited(*)	-	-	-	-	-
The British Land Company PLC	1	1	0	2	50%
Cala Group (Holdings) Limited	0	0	0	0	-
Canary Wharf Group PLC	0	0	0	0	-
C.G. Fry and Son Limited (*)	-	-	-	-	-
Churchill Retirement PLC	0	0	0	0	-
Crest Nicholson Holdings PLC	22	35	0	57	39%
Croudace Homes Group Limited (*)	-	-	-	-	-
Dandara Living Holdings Limited	0	0	0	0	-
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-	-
Fairview Holdings Limited	5	1	0	6	83%
Frasers Property (UK) Ltd	0	0	0	0	-
Galliard Group Limited	1	1	0	2	50%
MJ Gleeson PLC	2	0	0	2	100%
Grosvenor Group Limited	0	0	0	0	-
Hill Holdings Limited	0	0	0	0	-
Hopkins Home Group Limited (*)	-	-	-	-	-
Jelson Holdings Limited	0	0	0	0	-
Keepmoat Limited (*)	-	-	-	-	-
Land Securities Group PLC	0	0	0	0	-
Lendlease Europe Holdings Limited	3	0	0	3	100%
Lifestory Holdings Limited (also covers Anthology Group)	0	0	0	0	-
London Square Development (Holdings) Limited	0	0	0	0	-
Miller Homes Limited	0	0	0	0	-
Morris Homes Group Limited	0	0	0	0	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	1	3	0	4	25%
Persimmon Public Limited Company	23	0	0	23	100%
Redrow PLC	2	0	0	2	100%
Regal Holdco Limited (parent company for Regal London)	0	0	0	0	-
Rowland Group Limited (*)	-	-	-	-	-
Rydon Group Holdings Limited	0	0	0	0	-
Sorbon Group Limited (parent company for Shanly Homes)	0	0	0	0	-
St Modwen Group Holdings Company Limited	0	0	0	0	-
Story Homes Limited (*)	-	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-	-
Taylor Wimpey PLC	20	5	0	25	80%
Telford Homes Limited	1	0	0	1	100%
Tilia Homes Limited	4	0	0	4	100%
Vistry Group PLC	13	1	0	14	93%
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-	-
Weston Group PLC	5	0	0	5	100%
McCarthy & Stone Limited	0	0	0	0	-
Seven Capital PLC	0	0	0	0	-
Wates Group Limited	0	0	0	0	-
Watkin Jones PLC	0	0	0	0	-
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	0	0	0	0	-

## Developer_9
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 31 January 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 January 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29, Note_56]	Buildings that require remediation by the developer which have not yet completed, with a completion date…

	...at all		…within the next 12 months
Total	779	79%	219	22%
Abbey Developments Limited(*)	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	-	0	-
Ballymore Limited	2	25%	0	0%
Barratt Developments PLC	134	99%	27	20%
Bellway PLC	129	81%	12	8%
The Berkeley Group Holdings PLC	22	85%	17	65%
Bewley Group Limited	1	100%	0	0%
Bloor Investments Limited(*)	-	-	-	-
The British Land Company PLC	2	33%	1	17%
Cala Group (Holdings) Limited	0	0%	0	0%
Canary Wharf Group PLC	0	-	0	-
C.G. Fry and Son Limited (*)	-	-	-	-
Churchill Retirement PLC	0	-	0	-
Crest Nicholson Holdings PLC	95	95%	42	42%
Croudace Homes Group Limited (*)	-	-	-	-
Dandara Living Holdings Limited	10	100%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-
Fairview Holdings Limited	34	100%	20	59%
Frasers Property (UK) Ltd	0	-	0	-
Galliard Group Limited	5	100%	4	80%
MJ Gleeson PLC	10	91%	10	91%
Grosvenor Group Limited	1	50%	0	0%
Hill Holdings Limited	0	0%	0	0%
Hopkins Home Group Limited (*)	-	-	-	-
Jelson Holdings Limited	0	-	0	-
Keepmoat Limited (*)	-	-	-	-
Land Securities Group PLC	0	0%	0	0%
Lendlease Europe Holdings Limited	23	85%	6	22%
Lifestory Holdings Limited (also covers Anthology Group)	1	100%	1	100%
London Square Development (Holdings) Limited	0	0%	0	0%
Miller Homes Limited	11	100%	3	27%
Morris Homes Group Limited	2	100%	2	100%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	7	70%	4	40%
Persimmon Public Limited Company	38	88%	14	33%
Redrow PLC	22	46%	8	17%
Regal Holdco Limited (parent company for Regal London)	0	-	0	-
Rowland Group Limited (*)	-	-	-	-
Rydon Group Holdings Limited	4	67%	4	67%
Sorbon Group Limited (parent company for Shanly Homes)	1	33%	1	33%
St Modwen Group Holdings Company Limited	0	-	0	-
Story Homes Limited (*)	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-
Taylor Wimpey PLC	111	91%	16	13%
Telford Homes Limited	26	47%	3	5%
Tilia Homes Limited	4	57%	4	57%
Vistry Group PLC	66	83%	16	20%
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-
Weston Group PLC	17	81%	3	14%
McCarthy & Stone Limited	0	-	0	-
Seven Capital PLC	0	0%	0	0%
Wates Group Limited	0	0%	0	0%
Watkin Jones PLC	0	0%	0	0%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	1	20%	1	20%

## Developer_10
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 31 January 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings for each developer that has signed the developer remediation contract, as of 31 January 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29, Note_56]	For buildings which have not yet completed, completion profiles by financial year...					Buildings which have not yet completed, with...

	2023-2024	2024-2025	2025-2026	2026-2027	2027-2028	2028-2029	2029-2030	.. no completiondate provided	... completion date prior to 2023-2024
Total	79	245	272	93	45	20	3	213	22
Abbey Developments Limited(*)	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0	0	0	0	0	0	0	0
Ballymore Limited	0	0	2	0	0	0	0	6	0
Barratt Developments PLC	23	28	39	18	16	0	0	2	10
Bellway PLC	11	14	32	23	19	20	3	30	7
The Berkeley Group Holdings PLC	2	20	0	0	0	0	0	4	0
Bewley Group Limited	0	0	0	0	0	0	0	0	1
Bloor Investments Limited(*)	-	-	-	-	-	-	-	-	-
The British Land Company PLC	0	1	1	0	0	0	0	4	0
Cala Group (Holdings) Limited	0	0	0	0	0	0	0	1	0
Canary Wharf Group PLC	0	0	0	0	0	0	0	0	0
C.G. Fry and Son Limited (*)	-	-	-	-	-	-	-	-	-
Churchill Retirement PLC	0	0	0	0	0	0	0	0	0
Crest Nicholson Holdings PLC	4	48	43	0	0	0	0	5	0
Croudace Homes Group Limited (*)	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0	2	0	8	0	0	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	6	17	11	0	0	0	0	0	0
Frasers Property (UK) Ltd	0	0	0	0	0	0	0	0	0
Galliard Group Limited	1	4	0	0	0	0	0	0	0
MJ Gleeson PLC	2	8	0	0	0	0	0	1	0
Grosvenor Group Limited	0	0	0	0	0	0	0	1	1
Hill Holdings Limited	0	0	0	0	0	0	0	1	0
Hopkins Home Group Limited (*)	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0	0	0	0	0	0	0	0
Keepmoat Limited (*)	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	0	0	0	0	0	0	0	4	0
Lendlease Europe Holdings Limited	1	7	13	2	0	0	0	4	0
Lifestory Holdings Limited (also covers Anthology Group)	0	1	0	0	0	0	0	0	0
London Square Development (Holdings) Limited	0	0	0	0	0	0	0	29	0
Miller Homes Limited	2	6	3	0	0	0	0	0	0
Morris Homes Group Limited	1	1	0	0	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	0	5	2	0	0	0	0	3	0
Persimmon Public Limited Company	4	20	14	0	0	0	0	5	0
Redrow PLC	2	12	1	7	0	0	0	26	0
Regal Holdco Limited (parent company for Regal London)	0	0	0	0	0	0	0	0	0
Rowland Group Limited (*)	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	4	0	0	0	0	0	0	2	0
Sorbon Group Limited (parent company for Shanly Homes)	0	1	0	0	0	0	0	2	0
St Modwen Group Holdings Company Limited	0	0	0	0	0	0	0	0	0
Story Homes Limited (*)	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	2	23	58	28	0	0	0	11	0
Telford Homes Limited	1	5	16	2	2	0	0	29	0
Tilia Homes Limited	0	4	0	0	0	0	0	3	0
Vistry Group PLC	0	18	35	13	0	0	0	14	0
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-	-	-	-	-	-
Weston Group PLC	13	1	0	0	0	0	0	4	3
McCarthy & Stone Limited	0	0	0	0	0	0	0	0	0
Seven Capital PLC	0	0	0	0	0	0	0	5	0
Wates Group Limited	0	0	0	0	0	0	0	7	0
Watkin Jones PLC	0	0	0	0	0	0	0	6	0
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	0	1	0	0	0	0	0	4	0

## Developer_11
Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 31 January 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 January 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29]	Buildings where the developer or 'responsible entity' has engaged with the leaseholders, freeholders, residents, occupiers and other users regarding works for buildings being remediated directly by the developer, excluding completed buildings, by...					Number of buildings being remediated by the developers, excluding completed buildings	Sum of communication
	... the Responsible Entity		... directly		... directly and by the Responsible Entity		... unconfirmed how
Total	561	57%	19	2%	99	10%	131	13%	992	82%
Abbey Developments Limited(*)	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited(*)	-	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	-	0	-	0	-	0	-	0	-
Ballymore Limited	8	100%	0	0%	0	0%	0	0%	8	100%
Barratt Developments PLC	0	0%	0	0%	0	0%	131	96%	136	96%
Bellway PLC	157	99%	0	0%	0	0%	0	0%	159	99%
The Berkeley Group Holdings PLC	23	88%	1	4%	2	8%	0	0%	26	100%
Bewley Group Limited	1	100%	0	0%	0	0%	0	0%	1	100%
Bloor Investments Limited(*)	-	-	-	-	-	-	-	-	-	-
The British Land Company PLC	2	33%	0	0%	0	0%	0	0%	6	33%
Cala Group (Holdings) Limited	1	100%	0	0%	0	0%	0	0%	1	100%
Canary Wharf Group PLC	0	-	0	-	0	-	0	-	0	-
C.G. Fry and Son Limited (*)	-	-	-	-	-	-	-	-	-	-
Churchill Retirement PLC	0	-	0	-	0	-	0	-	0	-
Crest Nicholson Holdings PLC	94	94%	0	0%	0	0%	0	0%	100	94%
Croudace Homes Group Limited (*)	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0%	0	0%	10	100%	0	0%	10	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes) (*)	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	0	0%	2	6%	32	94%	0	0%	34	100%
Frasers Property (UK) Ltd	0	-	0	-	0	-	0	-	0	-
Galliard Group Limited	1	20%	0	0%	4	80%	0	0%	5	100%
MJ Gleeson PLC	7	64%	2	18%	2	18%	0	0%	11	100%
Grosvenor Group Limited	0	0%	0	0%	1	50%	0	0%	2	50%
Hill Holdings Limited	0	0%	0	0%	1	100%	0	0%	1	100%
Hopkins Home Group Limited (*)	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	0	-	0	-	0	-	0	-	0	-
Keepmoat Limited (*)	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	0	0%	0	0%	0	0%	0	0%	4	0%
Lendlease Europe Holdings Limited	0	0%	0	0%	0	0%	0	0%	27	0%
Lifestory Holdings Limited (also covers Anthology Group)	0	0%	1	100%	0	0%	0	0%	1	100%
London Square Development (Holdings) Limited	0	0%	0	0%	0	0%	0	0%	29	0%
Miller Homes Limited	4	36%	0	0%	5	45%	0	0%	11	82%
Morris Homes Group Limited	1	50%	0	0%	1	50%	0	0%	2	100%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	3	30%	0	0%	7	70%	0	0%	10	100%
Persimmon Public Limited Company	42	98%	0	0%	0	0%	0	0%	43	98%
Redrow PLC	37	77%	11	23%	0	0%	0	0%	48	100%
Regal Holdco Limited (parent company for Regal London)	0	-	0	-	0	-	0	-	0	-
Rowland Group Limited (*)	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	0	0%	0	0%	4	67%	0	0%	6	67%
Sorbon Group Limited (parent company for Shanly Homes)	0	0%	0	0%	3	100%	0	0%	3	100%
St Modwen Group Holdings Company Limited	0	-	0	-	0	-	0	-	0	-
Story Homes Limited (*)	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited (*)	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	122	100%	0	0%	0	0%	0	0%	122	100%
Telford Homes Limited	38	69%	0	0%	13	24%	0	0%	55	93%
Tilia Homes Limited	7	100%	0	0%	0	0%	0	0%	7	100%
Vistry Group PLC	0	0%	0	0%	0	0%	0	0%	80	0%
Broadthorpe Limited (parent company for William Davis Homes) (*)	-	-	-	-	-	-	-	-	-	-
Weston Group PLC	13	62%	0	0%	8	38%	0	0%	21	100%
McCarthy & Stone Limited	0	-	0	-	0	-	0	-	0	-
Seven Capital PLC	0	0%	0	0%	0	0%	0	0%	5	0%
Wates Group Limited	0	0%	0	0%	0	0%	0	0%	7	0%
Watkin Jones PLC	0	0%	0	0%	6	100%	0	0%	6	100%
Other (combined total for all developers with 5 or fewer buildings each: Abbey Developments, Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	0	0%	2	40%	0	0%	0	0%	5	40%

## Social_1
Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 30 November 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [Note 34] [Note 35]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete [Note 37] [Note 54]	30	3%	174	18%	204	10%
Remediation started	273	28%	252	26%	525	27%
Remediation works planned	359	37%	299	31%	658	34%
Remediation plans unclear from survey	311	32%	248	25%	559	29%
Work is not required	2	0.21%	4	0.40%	6	0.30%
Total buildings [Note 36]	975	100%	977	100%	1,952	100%

## Social_2
Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 November 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level survey, as of 30 November 2023
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than 5 buildings [Note 50] [Note 51]	Total number of buildings over 11 metres	Number of buildings assessed and identified as having EWS life-critical fire-safety defects [Note_35] [Note 52]	% buildings assessed and identified as having EWS life-critical fire-safety defects
Total (all providers)	17269	1911	11%
A2Dominion Housing Group Limited	208	37	18%
Abri Group Limited	35	1	3%
Accent Group Limited	7	1	14%
Acis Group Limited	12	0	0%
Agudas Israel Housing Association Limited	20	5	25%
Anchor Hanover Group	33	10	30%
Ashford Borough Council	19	0	0%
Ashton Pioneer Homes Limited	7	0	0%
Aster Group Limited	43	6	14%
B3 Living Limited	11	5	45%
Beyond Housing Limited	11	1	9%
Birkenhead Forum Housing Association Limited* [Note 53]	9	0	0%
Birmingham City Council	205	129	63%
Bolton at Home Limited	9	0	0%
Bournemouth, Christchurch and Poole Council	14	0	0%
bpha Limited	27	1	4%
Brighter Places	15	0	0%
Brighton and Hove City Council	59	0	0%
Bristol City Council	192	42	22%
Broadland Housing Association Limited	10	0	0%
Bromford Housing Group Limited	13	2	15%
Cambridge City Council	13	0	0%
Central Bedfordshire Council* [Note 53]	9	0	0%
Chartford Housing Limited	9	0	0%
Christian Action (Enfield) Housing Association Limited	13	3	23%
Citizen Housing Group Limited	60	0	0%
City of Doncaster Council	9	9	100%
City of London Corporation	39	0	0%
City of Westminster Council	506	0	0%
Clarion Housing Group Limited	546	93	17%
Curo Group (Albion) Limited	149	0	0%
Dacorum Borough Council	15	3	20%
Dudley Metropolitan Borough Council	49	10	20%
East End Homes Limited	43	6	14%
Eastlight Community Homes Limited	14	6	43%
Ekaya Housing Association Limited	10	0	0%
Epping Forest District Council	10	9	90%
Estuary Housing Association Limited	94	1	1%
Exeter City Council	7	0	0%
Fairhazel Co-operative Limited	12	0	0%
First Choice Homes Oldham Limited	7	2	29%
Flagship Housing Group Limited	11	1	9%
Folkestone and Hythe District Council	15	0	0%
ForHousing Limited	28	0	0%
Gateshead Metropolitan Borough Council	26	3	12%
Gateway Housing Association Limited	21	0	0%
Gentoo Group Limited	32	5	16%
Golding Homes Limited	8	3	38%
Gosport Borough Council	6	0	0%
Gravesham Borough Council	7	0	0%
Great Places Housing Group Limited	15	4	27%
GreenSquareAccord Limited	20	14	70%
Haringey London Borough Council	80	45	56%
Harlow District Council	14	2	14%
Heart of Medway Housing Association Limited	7	1	14%
Hexagon Housing Association Limited	21	18	86%
HFL Homes Limited	6	0	0%
Hightown Housing Association Limited	17	2	12%
Home Group Limited	71	23	32%
Housing 21	21	0	0%
Housing For Women	20	0	0%
Hyde Housing Association Limited	191	34	18%
Incommunities Limited	33	12	36%
Inquilab Housing Association Limited	6	0	0%
Irwell Valley Housing Association Limited	13	2	15%
Islington and Shoreditch Housing Association Limited	44	8	18%
Jigsaw Homes Group Limited	19	8	42%
Karbon Homes Limited	34	15	44%
Kingston upon Hull City Council	29	0	0%
Kirklees Metropolitan Borough Council	21	15	71%
Lambeth and Southwark Housing Association Limited	9	0	0%
Leeds City Council	131	0	0%
Leicester City Council	11	0	0%
LiveWest Homes Limited	54	6	11%
Livv Housing Group	9	0	0%
London & Quadrant Housing Trust	689	75	11%
London Borough of Barking and Dagenham	33	2	6%
London Borough of Barnet	48	7	15%
London Borough of Brent	167	4	2%
London Borough of Camden Council	837	5	1%
London Borough of Croydon	52	16	31%
London Borough of Ealing	53	16	30%
London Borough of Enfield	64	4	6%
London Borough of Hackney	462	6	1%
London Borough of Hammersmith and Fulham	231	7	3%
London Borough of Havering Council	17	0	0%
London Borough of Hounslow	54	0	0%
London Borough of Islington	382	0	0%
London Borough of Lambeth	421	0	0%
London Borough of Lewisham	137	3	2%
London Borough of Newham	90	55	61%
London Borough of Redbridge	19	1	5%
London Borough of Sutton	60	1	2%
London Borough of Tower Hamlets	322	27	8%
London Borough of Waltham Forest	61	23	38%
London Borough of Wandsworth	363	2	1%
Look Ahead Care and Support Limited	10	2	20%
Luton Borough Council	15	0	0%
Magenta Living	11	3	27%
Manchester City Council	51	3	6%
Midland Heart Limited	20	1	5%
Moat Homes Limited	21	4	19%
New Foundations Housing Association Limited	6	0	0%
Newark and Sherwood District Council	6	0	0%
Newcastle City Council	55	0	0%
Newlon Housing Trust	85	49	58%
North London Muslim Housing Association Limited	12	10	83%
Norwich City Council	25	2	8%
Notting Hill Genesis	925	10	1%
Nottingham City Council	24	0	0%
Nottingham Community Housing Association Limited	13	0	0%
Octavia Housing	90	18	20%
One Manchester Limited	22	0	0%
One Vision Housing Limited	8	0	0%
Onward Group Limited	51	11	22%
Orbit Group Limited	80	20	25%
Origin Housing Limited	108	14	13%
Oxford City Council	7	0	0%
P3 Housing Limited	18	0	0%
Paradigm Housing Group Limited	26	0	0%
Paragon Asra Housing Limited	80	20	25%
Peabody Trust	1237	175	14%
Phoenix Community Housing Association (Bellingham and Downham) Limited	15	4	27%
Pinnacle Spaces Limited	6	0	0%
Places for People Group Limited	81	16	20%
Platform Housing Group Limited	17	1	6%
Plus Dane Housing Limited	12	0	0%
Plymouth Community Homes Limited	55	0	0%
Poplar Housing And Regeneration Community Association Limited	119	11	9%
Populo Homes	7	0	0%
Portsmouth City Council	55	16	29%
Providence Row Housing Association	11	0	0%
Quo Vadis Trust	12	0	0%
Raven Housing Trust Limited	11	0	0%
Reading Borough Council	18	0	0%
Regenda Limited	17	2	12%
Richmond Housing Partnership Limited	42	15	36%
Rochdale Boroughwide Housing Limited	12	7	58%
Rooftop Housing Group Limited	7	1	14%
Royal Borough of Greenwich	477	0	0%
Royal Borough of Kensington and Chelsea	143	4	3%
Royal Borough of Kingston Upon Thames	34	0	0%
Salix Homes Limited	19	0	0%
Salvation Army Housing Association	15	0	0%
Sanctuary Housing Association	368	35	10%
Sandwell Metropolitan Borough Council	55	1	2%
Seymour Housing Co-operative Limited	8	0	0%
Sheffield City Council	358	0	0%
Shepherds Bush Housing Association Limited	58	3	5%
Soho Housing Association Limited	47	0	0%
Solihull Metropolitan Borough Council	37	16	43%
South Tyneside Council	8	0	0%
Southampton City Council	201	95	47%
Southend on Sea City Council	18	0	0%
Southern Housing	552	89	16%
Southwark Council	844	0	0%
Southway Housing Trust (Manchester) Limited	6	0	0%
Sovereign Housing Association Limited	305	68	22%
Spitalfields Housing Association Limited	11	0	0%
St Mungo Community Housing Association	20	1	5%
Stevenage Borough Council	10	7	70%
Stockport Homes Limited	30	0	0%
Stoke on Trent City Council	18	2	11%
Stonewater Limited	29	3	10%
Swindon Borough Council	8	0	0%
Tamworth Borough Council	7	0	0%
Teign Housing	8	1	13%
Thames Valley Housing Association Limited	234	96	41%
Thanet District Council	14	5	36%
The ExtraCare Charitable Trust	10	0	0%
The Guinness Partnership Limited	246	8	3%
The Housing Plus Group Limited	9	0	0%
The Industrial Dwellings Society (1885) Limited	31	0	0%
The Riverside Group Limited	301	91	30%
Thirteen Housing Group Limited	15	0	0%
Thurrock Council	18	0	0%
Together Housing Group Limited	45	0	0%
Torus62 Limited	6	0	0%
Tower Hamlets Community Housing	37	17	46%
Trident Housing Association Limited	12	0	0%
Vivid Housing Limited	37	2	5%
Wakefield And District Housing Limited	19	4	21%
Walsall Housing Group Limited	19	0	0%
Wandle Housing Association Limited	38	12	32%
Warwick District Council	17	5	29%
Watford Community Housing Trust	7	0	0%
Watmos Community Homes	34	0	0%
West Hampstead Housing Co-operative Limited* [Note 53]	11	0	0%
West Northamptonshire Council	12	9	75%
Wigan Council	7	0	0%
Winchester City Council	7	0	0%
Woking Borough Council	25	14	56%
Wolverhampton City Council	52	9	17%
Women's Pioneer Housing Limited	64	0	0%
Wythenshawe Community Housing Group Limited	12	5	42%
YMCA Downslink Group	6	0	0%
YMCA St Paul's Group	6	0	0%
Yorkshire Housing Limited	9	0	0%
Your Housing Group Limited	26	13	50%
Zebra Housing Association Limited	8	0	0%
Other RPs** [note 51]	493	24	5%

## Social_3
Provider by provider breakdown of buildings, by assessment status, England, 30 November 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level return, as of 30 November 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than 5 buildings [Note 50] [Note 51]	Progress with assessments
	Of the total number of buildings over 11m, buildings that…
	…have had an Assessment [Note 52]		…have not had an assessment		...have been assessed and identified as having EWS life-critical fire-safety [Note_35]
	Number	%	Number	%	Number	%
Total (all providers)	16798	97%	471	3%	1911	11%
A2Dominion Housing Group Limited	208	100%	0	0%	37	18%
Abri Group Limited	35	100%	0	0%	1	3%
Accent Group Limited	7	100%	0	0%	1	14%
Acis Group Limited	12	100%	0	0%	0	0%
Agudas Israel Housing Association Limited	20	100%	0	0%	5	25%
Anchor Hanover Group	33	100%	0	0%	10	30%
Ashford Borough Council	19	100%	0	0%	0	0%
Ashton Pioneer Homes Limited	7	100%	0	0%	0	0%
Aster Group Limited	43	100%	0	0%	6	14%
B3 Living Limited	11	100%	0	0%	5	45%
Beyond Housing Limited	11	100%	0	0%	1	9%
Birkenhead Forum Housing Association Limited* [Note 53]	9	100%	0	0%	0	0%
Birmingham City Council	205	100%	0	0%	129	63%
Bolton at Home Limited	9	100%	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	14	100%	0	0%	0	0%
bpha Limited	27	100%	0	0%	1	4%
Brighter Places	15	100%	0	0%	0	0%
Brighton and Hove City Council	0	0%	59	100%	0	0%
Bristol City Council	189	98%	3	2%	42	22%
Broadland Housing Association Limited	10	100%	0	0%	0	0%
Bromford Housing Group Limited	13	100%	0	0%	2	15%
Cambridge City Council	13	100%	0	0%	0	0%
Central Bedfordshire Council* [Note 53]	9	100%	0	0%	0	0%
Chartford Housing Limited	9	100%	0	0%	0	0%
Christian Action (Enfield) Housing Association Limited	13	100%	0	0%	3	23%
Citizen Housing Group Limited	60	100%	0	0%	0	0%
City of Doncaster Council	9	100%	0	0%	9	100%
City of London Corporation	39	100%	0	0%	0	0%
City of Westminster Council	506	100%	0	0%	0	0%
Clarion Housing Group Limited	534	98%	12	2%	93	17%
Curo Group (Albion) Limited	149	100%	0	0%	0	0%
Dacorum Borough Council	15	100%	0	0%	3	20%
Dudley Metropolitan Borough Council	49	100%	0	0%	10	20%
East End Homes Limited	43	100%	0	0%	6	14%
Eastlight Community Homes Limited	14	100%	0	0%	6	43%
Ekaya Housing Association Limited	10	100%	0	0%	0	0%
Epping Forest District Council	10	100%	0	0%	9	90%
Estuary Housing Association Limited	94	100%	0	0%	1	1%
Exeter City Council	7	100%	0	0%	0	0%
Fairhazel Co-operative Limited	12	100%	0	0%	0	0%
First Choice Homes Oldham Limited	7	100%	0	0%	2	29%
Flagship Housing Group Limited	11	100%	0	0%	1	9%
Folkestone and Hythe District Council	15	100%	0	0%	0	0%
ForHousing Limited	28	100%	0	0%	0	0%
Gateshead Metropolitan Borough Council	26	100%	0	0%	3	12%
Gateway Housing Association Limited	21	100%	0	0%	0	0%
Gentoo Group Limited	32	100%	0	0%	5	16%
Golding Homes Limited	8	100%	0	0%	3	38%
Gosport Borough Council	6	100%	0	0%	0	0%
Gravesham Borough Council	6	86%	1	14%	0	0%
Great Places Housing Group Limited	15	100%	0	0%	4	27%
GreenSquareAccord Limited	20	100%	0	0%	14	70%
Haringey London Borough Council	79	99%	1	1%	45	56%
Harlow District Council	14	100%	0	0%	2	14%
Heart of Medway Housing Association Limited	7	100%	0	0%	1	14%
Hexagon Housing Association Limited	21	100%	0	0%	18	86%
HFL Homes Limited	6	100%	0	0%	0	0%
Hightown Housing Association Limited	17	100%	0	0%	2	12%
Home Group Limited	71	100%	0	0%	23	32%
Housing 21	21	100%	0	0%	0	0%
Housing For Women	20	100%	0	0%	0	0%
Hyde Housing Association Limited	191	100%	0	0%	34	18%
Incommunities Limited	33	100%	0	0%	12	36%
Inquilab Housing Association Limited	6	100%	0	0%	0	0%
Irwell Valley Housing Association Limited	13	100%	0	0%	2	15%
Islington and Shoreditch Housing Association Limited	44	100%	0	0%	8	18%
Jigsaw Homes Group Limited	19	100%	0	0%	8	42%
Karbon Homes Limited	34	100%	0	0%	15	44%
Kingston upon Hull City Council	29	100%	0	0%	0	0%
Kirklees Metropolitan Borough Council	21	100%	0	0%	15	71%
Lambeth and Southwark Housing Association Limited	9	100%	0	0%	0	0%
Leeds City Council	131	100%	0	0%	0	0%
Leicester City Council	11	100%	0	0%	0	0%
LiveWest Homes Limited	54	100%	0	0%	6	11%
Livv Housing Group	9	100%	0	0%	0	0%
London & Quadrant Housing Trust	689	100%	0	0%	75	11%
London Borough of Barking and Dagenham	33	100%	0	0%	2	6%
London Borough of Barnet	47	98%	1	2%	7	15%
London Borough of Brent	167	100%	0	0%	4	2%
London Borough of Camden Council	837	100%	0	0%	5	1%
London Borough of Croydon	52	100%	0	0%	16	31%
London Borough of Ealing	53	100%	0	0%	16	30%
London Borough of Enfield	64	100%	0	0%	4	6%
London Borough of Hackney	459	99%	3	1%	6	1%
London Borough of Hammersmith and Fulham	231	100%	0	0%	7	3%
London Borough of Havering Council	17	100%	0	0%	0	0%
London Borough of Hounslow	54	100%	0	0%	0	0%
London Borough of Islington	373	98%	9	2%	0	0%
London Borough of Lambeth	421	100%	0	0%	0	0%
London Borough of Lewisham	137	100%	0	0%	3	2%
London Borough of Newham	90	100%	0	0%	55	61%
London Borough of Redbridge	19	100%	0	0%	1	5%
London Borough of Sutton	60	100%	0	0%	1	2%
London Borough of Tower Hamlets	322	100%	0	0%	27	8%
London Borough of Waltham Forest	61	100%	0	0%	23	38%
London Borough of Wandsworth	363	100%	0	0%	2	1%
Look Ahead Care and Support Limited	10	100%	0	0%	2	20%
Luton Borough Council	15	100%	0	0%	0	0%
Magenta Living	11	100%	0	0%	3	27%
Manchester City Council	51	100%	0	0%	3	6%
Midland Heart Limited	20	100%	0	0%	1	5%
Moat Homes Limited	21	100%	0	0%	4	19%
New Foundations Housing Association Limited	6	100%	0	0%	0	0%
Newark and Sherwood District Council	6	100%	0	0%	0	0%
Newcastle City Council	55	100%	0	0%	0	0%
Newlon Housing Trust	85	100%	0	0%	49	58%
North London Muslim Housing Association Limited	12	100%	0	0%	10	83%
Norwich City Council	25	100%	0	0%	2	8%
Notting Hill Genesis	925	100%	0	0%	10	1%
Nottingham City Council	24	100%	0	0%	0	0%
Nottingham Community Housing Association Limited	13	100%	0	0%	0	0%
Octavia Housing	90	100%	0	0%	18	20%
One Manchester Limited	22	100%	0	0%	0	0%
One Vision Housing Limited	8	100%	0	0%	0	0%
Onward Group Limited	51	100%	0	0%	11	22%
Orbit Group Limited	80	100%	0	0%	20	25%
Origin Housing Limited	108	100%	0	0%	14	13%
Oxford City Council	7	100%	0	0%	0	0%
P3 Housing Limited	18	100%	0	0%	0	0%
Paradigm Housing Group Limited	26	100%	0	0%	0	0%
Paragon Asra Housing Limited	80	100%	0	0%	20	25%
Peabody Trust	1237	100%	0	0%	175	14%
Phoenix Community Housing Association (Bellingham and Downham) Limited	14	93%	1	7%	4	27%
Pinnacle Spaces Limited	6	100%	0	0%	0	0%
Places for People Group Limited	81	100%	0	0%	16	20%
Platform Housing Group Limited	17	100%	0	0%	1	6%
Plus Dane Housing Limited	12	100%	0	0%	0	0%
Plymouth Community Homes Limited	55	100%	0	0%	0	0%
Poplar Housing And Regeneration Community Association Limited	119	100%	0	0%	11	9%
Populo Homes	7	100%	0	0%	0	0%
Portsmouth City Council	55	100%	0	0%	16	29%
Providence Row Housing Association	11	100%	0	0%	0	0%
Quo Vadis Trust	12	100%	0	0%	0	0%
Raven Housing Trust Limited	11	100%	0	0%	0	0%
Reading Borough Council	18	100%	0	0%	0	0%
Regenda Limited	17	100%	0	0%	2	12%
Richmond Housing Partnership Limited	38	90%	4	10%	15	36%
Rochdale Boroughwide Housing Limited	12	100%	0	0%	7	58%
Rooftop Housing Group Limited	7	100%	0	0%	1	14%
Royal Borough of Greenwich	245	51%	232	49%	0	0%
Royal Borough of Kensington and Chelsea	143	100%	0	0%	4	3%
Royal Borough of Kingston Upon Thames	34	100%	0	0%	0	0%
Salix Homes Limited	19	100%	0	0%	0	0%
Salvation Army Housing Association	15	100%	0	0%	0	0%
Sanctuary Housing Association	368	100%	0	0%	35	10%
Sandwell Metropolitan Borough Council	55	100%	0	0%	1	2%
Seymour Housing Co-operative Limited	8	100%	0	0%	0	0%
Sheffield City Council	358	100%	0	0%	0	0%
Shepherds Bush Housing Association Limited	58	100%	0	0%	3	5%
Soho Housing Association Limited	47	100%	0	0%	0	0%
Solihull Metropolitan Borough Council	37	100%	0	0%	16	43%
South Tyneside Council	8	100%	0	0%	0	0%
Southampton City Council	201	100%	0	0%	95	47%
Southend on Sea City Council	18	100%	0	0%	0	0%
Southern Housing	552	100%	0	0%	89	16%
Southwark Council	844	100%	0	0%	0	0%
Southway Housing Trust (Manchester) Limited	6	100%	0	0%	0	0%
Sovereign Housing Association Limited	305	100%	0	0%	68	22%
Spitalfields Housing Association Limited	11	100%	0	0%	0	0%
St Mungo Community Housing Association	19	95%	1	5%	1	5%
Stevenage Borough Council	10	100%	0	0%	7	70%
Stockport Homes Limited	30	100%	0	0%	0	0%
Stoke on Trent City Council	18	100%	0	0%	2	11%
Stonewater Limited	29	100%	0	0%	3	10%
Swindon Borough Council	8	100%	0	0%	0	0%
Tamworth Borough Council	7	100%	0	0%	0	0%
Teign Housing	8	100%	0	0%	1	13%
Thames Valley Housing Association Limited	140	60%	94	40%	96	41%
Thanet District Council	14	100%	0	0%	5	36%
The ExtraCare Charitable Trust	10	100%	0	0%	0	0%
The Guinness Partnership Limited	246	100%	0	0%	8	3%
The Housing Plus Group Limited	6	67%	3	33%	0	0%
The Industrial Dwellings Society (1885) Limited	31	100%	0	0%	0	0%
The Riverside Group Limited	301	100%	0	0%	91	30%
Thirteen Housing Group Limited	15	100%	0	0%	0	0%
Thurrock Council	18	100%	0	0%	0	0%
Together Housing Group Limited	45	100%	0	0%	0	0%
Torus62 Limited	6	100%	0	0%	0	0%
Tower Hamlets Community Housing	37	100%	0	0%	17	46%
Trident Housing Association Limited	12	100%	0	0%	0	0%
Vivid Housing Limited	37	100%	0	0%	2	5%
Wakefield And District Housing Limited	19	100%	0	0%	4	21%
Walsall Housing Group Limited	19	100%	0	0%	0	0%
Wandle Housing Association Limited	38	100%	0	0%	12	32%
Warwick District Council	17	100%	0	0%	5	29%
Watford Community Housing Trust	7	100%	0	0%	0	0%
Watmos Community Homes	34	100%	0	0%	0	0%
West Hampstead Housing Co-operative Limited* [Note 53]	11	100%	0	0%	0	0%
West Northamptonshire Council	12	100%	0	0%	9	75%
Wigan Council	7	100%	0	0%	0	0%
Winchester City Council	7	100%	0	0%	0	0%
Woking Borough Council	25	100%	0	0%	14	56%
Wolverhampton City Council	52	100%	0	0%	9	17%
Women's Pioneer Housing Limited	64	100%	0	0%	0	0%
Wythenshawe Community Housing Group Limited	12	100%	0	0%	5	42%
YMCA Downslink Group	6	100%	0	0%	0	0%
YMCA St Paul's Group	6	100%	0	0%	0	0%
Yorkshire Housing Limited	9	100%	0	0%	0	0%
Your Housing Group Limited	26	100%	0	0%	13	50%
Zebra Housing Association Limited	8	100%	0	0%	0	0%
Other RPs** [note 51]	446	90%	47	10%	24	5%

## Social_4
Provider by provider breakdown of buildings, by remediation status, England, 30 November 2023
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provieder that has submitted a building level return, as of 30 November 2023.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than 5 buildings [Note 50] [Note 51]	Remediation Status
	Number and proportion of buildings identified as having EWS life-critical fire-safety defects [Note 35], where remediation has…
	…not yet started		…not yet started, plans in place		... started		...complete [Note 54]
	Number	%	Number	%	Number	%	Number	%
Total (all providers)	549	29%	638	33%	543	28%	181	9%
A2Dominion Housing Group Limited	0	0%	22	59%	4	11%	11	30%
Abri Group Limited	0	0%	0	0%	1	100%	0	0%
Accent Group Limited	0	0%	0	0%	0	0%	1	100%
Acis Group Limited	-	-	-	-	-	-	-	-
Agudas Israel Housing Association Limited	5	100%	0	0%	0	0%	0	0%
Anchor Hanover Group	0	0%	6	60%	4	40%	0	0%
Ashford Borough Council	-	-	-	-	-	-	-	-
Ashton Pioneer Homes Limited	-	-	-	-	-	-	-	-
Aster Group Limited	0	0%	6	100%	0	0%	0	0%
B3 Living Limited	5	100%	0	0%	0	0%	0	0%
Beyond Housing Limited	1	100%	0	0%	0	0%	0	0%
Birkenhead Forum Housing Association Limited* [Note 53]	-	-	-	-	-	-	-	-
Birmingham City Council	2	2%	6	5%	17	13%	104	81%
Bolton at Home Limited	-	-	-	-	-	-	-	-
Bournemouth, Christchurch and Poole Council	-	-	-	-	-	-	-	-
bpha Limited	0	0%	1	100%	0	0%	0	0%
Brighter Places	-	-	-	-	-	-	-	-
Brighton and Hove City Council	-	-	-	-	-	-	-	-
Bristol City Council	0	0%	32	76%	10	24%	0	0%
Broadland Housing Association Limited	-	-	-	-	-	-	-	-
Bromford Housing Group Limited	2	100%	0	0%	0	0%	0	0%
Cambridge City Council	-	-	-	-	-	-	-	-
Central Bedfordshire Council* [Note 53]	-	-	-	-	-	-	-	-
Chartford Housing Limited	-	-	-	-	-	-	-	-
Christian Action (Enfield) Housing Association Limited	0	0%	3	100%	0	0%	0	0%
Citizen Housing Group Limited	-	-	-	-	-	-	-	-
City of Doncaster Council	0	0%	6	67%	3	33%	0	0%
City of London Corporation	-	-	-	-	-	-	-	-
City of Westminster Council	-	-	-	-	-	-	-	-
Clarion Housing Group Limited	0	0%	40	43%	44	47%	9	10%
Curo Group (Albion) Limited	-	-	-	-	-	-	-	-
Dacorum Borough Council	1	33%	2	67%	0	0%	0	0%
Dudley Metropolitan Borough Council	0	0%	0	0%	10	100%	0	0%
East End Homes Limited	0	0%	5	83%	1	17%	0	0%
Eastlight Community Homes Limited	0	0%	0	0%	0	0%	6	100%
Ekaya Housing Association Limited	-	-	-	-	-	-	-	-
Epping Forest District Council	0	0%	0	0%	9	100%	0	0%
Estuary Housing Association Limited	1	100%	0	0%	0	0%	0	0%
Exeter City Council	-	-	-	-	-	-	-	-
Fairhazel Co-operative Limited	-	-	-	-	-	-	-	-
First Choice Homes Oldham Limited	0	0%	0	0%	2	100%	0	0%
Flagship Housing Group Limited	0	0%	0	0%	1	100%	0	0%
Folkestone and Hythe District Council	-	-	-	-	-	-	-	-
ForHousing Limited	-	-	-	-	-	-	-	-
Gateshead Metropolitan Borough Council	2	67%	0	0%	1	33%	0	0%
Gateway Housing Association Limited	-	-	-	-	-	-	-	-
Gentoo Group Limited	4	80%	0	0%	1	20%	0	0%
Golding Homes Limited	0	0%	1	33%	2	67%	0	0%
Gosport Borough Council	-	-	-	-	-	-	-	-
Gravesham Borough Council	-	-	-	-	-	-	-	-
Great Places Housing Group Limited	0	0%	4	100%	0	0%	0	0%
GreenSquareAccord Limited	1	7%	3	21%	10	71%	0	0%
Haringey London Borough Council	0	0%	6	13%	39	87%	0	0%
Harlow District Council	0	0%	0	0%	0	0%	2	1
Heart of Medway Housing Association Limited	0	0%	0	0%	0	0%	1	1
Hexagon Housing Association Limited	15	83%	0	0%	1	6%	2	0.111111111
HFL Homes Limited	-	-	-	-	-	-	-	-
Hightown Housing Association Limited	1	50%	0	0%	1	50%	0	0
Home Group Limited	0	0%	5	22%	18	78%	0	0
Housing 21	-	-	-	-	-	-	-	-
Housing For Women	-	-	-	-	-	-	-	-
Hyde Housing Association Limited	20	59%	3	9%	11	32%	0	0
Incommunities Limited	12	100%	0	0%	0	0%	0	0
Inquilab Housing Association Limited	-	-	-	-	-	-	-	-
Irwell Valley Housing Association Limited	1	50%	1	50%	0	0%	0	0
Islington and Shoreditch Housing Association Limited	0	0%	7	88%	1	13%	0	0
Jigsaw Homes Group Limited	0	0%	1	13%	7	88%	0	0
Karbon Homes Limited	14	93%	1	7%	0	0%	0	0
Kingston upon Hull City Council	-	-	-	-	-	-	-	-
Kirklees Metropolitan Borough Council	0	0%	12	80%	3	20%	0	0
Lambeth and Southwark Housing Association Limited	-	-	-	-	-	-	-	-
Leeds City Council	-	-	-	-	-	-	-	-
Leicester City Council	-	-	-	-	-	-	-	-
LiveWest Homes Limited	1	17%	1	17%	4	67%	0	0
Livv Housing Group	-	-	-	-	-	-	-	-
London & Quadrant Housing Trust	40	53%	10	13%	17	23%	8	0.106666667
London Borough of Barking and Dagenham	2	100%	0	0%	0	0%	0	0
London Borough of Barnet	0	0%	7	100%	0	0%	0	0
London Borough of Brent	1	25%	3	75%	0	0%	0	0
London Borough of Camden Council	0	0%	5	100%	0	0%	0	0
London Borough of Croydon	16	100%	0	0%	0	0%	0	0
London Borough of Ealing	16	100%	0	0%	0	0%	0	0
London Borough of Enfield	0	0%	4	100%	0	0%	0	0
London Borough of Hackney	4	67%	0	0%	2	33%	0	0
London Borough of Hammersmith and Fulham	0	0%	4	57%	3	43%	0	0
London Borough of Havering Council	-	-	-	-	-	-	-	-
London Borough of Hounslow	-	-	-	-	-	-	-	-
London Borough of Islington	-	-	-	-	-	-	-	-
London Borough of Lambeth	-	-	-	-	-	-	-	-
London Borough of Lewisham	0	0%	0	0%	3	100%	0	0
London Borough of Newham	42	76%	1	2%	12	22%	0	0
London Borough of Redbridge	1	100%	0	0%	0	0%	0	0
London Borough of Sutton	0	0%	1	100%	0	0%	0	0
London Borough of Tower Hamlets	12	44%	11	41%	4	15%	0	0
London Borough of Waltham Forest	17	74%	6	26%	0	0%	0	0
London Borough of Wandsworth	0	0%	2	100%	0	0%	0	0
Look Ahead Care and Support Limited	0	0%	1	50%	1	50%	0	0
Luton Borough Council	-	-	-	-	-	-	-	-
Magenta Living	0	0%	3	100%	0	0%	0	0
Manchester City Council	0	0%	3	100%	0	0%	0	0
Midland Heart Limited	0	0%	0	0%	0	0%	1	1
Moat Homes Limited	0	0%	2	50%	2	50%	0	0
New Foundations Housing Association Limited	-	-	-	-	-	-	-	-
Newark and Sherwood District Council	-	-	-	-	-	-	-	-
Newcastle City Council	-	-	-	-	-	-	-	-
Newlon Housing Trust	1	2%	43	88%	5	10%	0	0
North London Muslim Housing Association Limited	0	0%	10	100%	0	0%	0	0
Norwich City Council	0	0%	0	0%	2	100%	0	0
Notting Hill Genesis	2	20%	1	10%	6	60%	1	0.1
Nottingham City Council	-	-	-	-	-	-	-	-
Nottingham Community Housing Association Limited	-	-	-	-	-	-	-	-
Octavia Housing	18	100%	0	0%	0	0%	0	0
One Manchester Limited	-	-	-	-	-	-	-	-
One Vision Housing Limited	-	-	-	-	-	-	-	-
Onward Group Limited	0	0%	5	45%	6	55%	0	0
Orbit Group Limited	0	0%	2	10%	18	90%	0	0
Origin Housing Limited	4	29%	8	57%	2	14%	0	0
Oxford City Council	-	-	-	-	-	-	-	-
P3 Housing Limited	-	-	-	-	-	-	-	-
Paradigm Housing Group Limited	-	-	-	-	-	-	-	-
Paragon Asra Housing Limited	11	55%	7	35%	2	10%	0	0
Peabody Trust	77	44%	39	22%	53	30%	6	0.034285714
Phoenix Community Housing Association (Bellingham and Downham) Limited	0	0%	2	50%	2	50%	0	0
Pinnacle Spaces Limited	-	-	-	-	-	-	-	-
Places for People Group Limited	0	0%	4	25%	12	75%	0	0
Platform Housing Group Limited	1	100%	0	0%	0	0%	0	0
Plus Dane Housing Limited	-	-	-	-	-	-	-	-
Plymouth Community Homes Limited	-	-	-	-	-	-	-	-
Poplar Housing And Regeneration Community Association Limited	3	27%	4	36%	3	27%	1	0.090909091
Populo Homes	-	-	-	-	-	-	-	-
Portsmouth City Council	12	75%	4	25%	0	0%	0	0
Providence Row Housing Association	-	-	-	-	-	-	-	-
Quo Vadis Trust	-	-	-	-	-	-	-	-
Raven Housing Trust Limited	-	-	-	-	-	-	-	-
Reading Borough Council	-	-	-	-	-	-	-	-
Regenda Limited	0	0%	1	50%	1	50%	0	0
Richmond Housing Partnership Limited	10	67%	3	20%	2	13%	0	0
Rochdale Boroughwide Housing Limited	0	0%	0	0%	7	100%	0	0
Rooftop Housing Group Limited	1	100%	0	0%	0	0%	0	0
Royal Borough of Greenwich	-	-	-	-	-	-	-	-
Royal Borough of Kensington and Chelsea	1	25%	1	25%	0	0%	2	0.5
Royal Borough of Kingston Upon Thames	-	-	-	-	-	-	-	-
Salix Homes Limited	-	-	-	-	-	-	-	-
Salvation Army Housing Association	-	-	-	-	-	-	-	-
Sanctuary Housing Association	13	37%	19	54%	1	3%	2	0.057142857
Sandwell Metropolitan Borough Council	1	100%	0	0%	0	0%	0	0
Seymour Housing Co-operative Limited	-	-	-	-	-	-	-	-
Sheffield City Council	-	-	-	-	-	-	-	-
Shepherds Bush Housing Association Limited	0	0%	1	33%	1	33%	1	0.333333333
Soho Housing Association Limited	-	-	-	-	-	-	-	-
Solihull Metropolitan Borough Council	0	0%	12	75%	4	25%	0	0
South Tyneside Council	-	-	-	-	-	-	-	-
Southampton City Council	0	0%	14	15%	81	85%	0	0
Southend on Sea City Council	-	-	-	-	-	-	-	-
Southern Housing	19	21%	58	65%	12	13%	0	0
Southwark Council	-	-	-	-	-	-	-	-
Southway Housing Trust (Manchester) Limited	-	-	-	-	-	-	-	-
Sovereign Housing Association Limited	20	29%	13	19%	25	37%	10	0.147058824
Spitalfields Housing Association Limited	-	-	-	-	-	-	-	-
St Mungo Community Housing Association	1	100%	0	0%	0	0%	0	0
Stevenage Borough Council	7	100%	0	0%	0	0%	0	0
Stockport Homes Limited	-	-	-	-	-	-	-	-
Stoke on Trent City Council	2	100%	0	0%	0	0%	0	0
Stonewater Limited	0	0%	3	100%	0	0%	0	0
Swindon Borough Council	-	-	-	-	-	-	-	-
Tamworth Borough Council	-	-	-	-	-	-	-	-
Teign Housing	0	0%	1	100%	0	0%	0	0
Thames Valley Housing Association Limited	87	91%	1	1%	8	8%	0	0
Thanet District Council	0	0%	5	100%	0	0%	0	0
The ExtraCare Charitable Trust	-	-	-	-	-	-	-	-
The Guinness Partnership Limited	0	0%	6	75%	2	25%	0	0
The Housing Plus Group Limited	-	-	-	-	-	-	-	-
The Industrial Dwellings Society (1885) Limited	-	-	-	-	-	-	-	-
The Riverside Group Limited	0	0%	69	76%	10	11%	12	0.131868132
Thirteen Housing Group Limited	-	-	-	-	-	-	-	-
Thurrock Council	-	-	-	-	-	-	-	-
Together Housing Group Limited	-	-	-	-	-	-	-	-
Torus62 Limited	-	-	-	-	-	-	-	-
Tower Hamlets Community Housing	0	0%	12	71%	4	24%	1	0.058823529
Trident Housing Association Limited	-	-	-	-	-	-	-	-
Vivid Housing Limited	1	50%	0	0%	1	50%	0	0
Wakefield And District Housing Limited	0	0%	4	100%	0	0%	0	0
Walsall Housing Group Limited	-	-	-	-	-	-	-	-
Wandle Housing Association Limited	4	33%	8	67%	0	0%	0	0
Warwick District Council	0	0%	5	100%	0	0%	0	0
Watford Community Housing Trust	-	-	-	-	-	-	-	-
Watmos Community Homes	-	-	-	-	-	-	-	-
West Hampstead Housing Co-operative Limited* [Note 53]	-	-	-	-	-	-	-	-
West Northamptonshire Council	1	11%	0	0%	8	89%	0	0
Wigan Council	-	-	-	-	-	-	-	-
Winchester City Council	-	-	-	-	-	-	-	-
Woking Borough Council	0	0%	14	100%	0	0%	0	0
Wolverhampton City Council	0	0%	9	100%	0	0%	0	0
Women's Pioneer Housing Limited	-	-	-	-	-	-	-	-
Wythenshawe Community Housing Group Limited	0	0%	0	0%	5	100%	0	0
YMCA Downslink Group	-	-	-	-	-	-	-	-
YMCA St Paul's Group	-	-	-	-	-	-	-	-
Yorkshire Housing Limited	-	-	-	-	-	-	-	-
Your Housing Group Limited	7	54%	5	38%	1	8%	0	0
Zebra Housing Association Limited	-	-	-	-	-	-	-	-
Other RPs** [note 51]	6	25%	8	33%	10	42%	0	0

## JIT_1
Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 March 2024
Back to Contents
This worksheet contains one table. All figures are for the number of Joint Inspection Team training sessions attended by local authority officers.
Local Authority [note_18]	Intro to Fire Safety (Level 1) Number	Intermediate Fire Safety: Theoretical HHSRS assessments (Level 2 Part 1) Number	Intermediate Fire Safety: Practical HHSRS assessments (Level 2 Part 2) Number
Barking and Dagenham	0	0	0
Barnet	4	3	3
Birmingham	10	6	7
Bournemouth, Christchurch and Poole	10	4	1
Bradford	24	4	1
Brent	1	4	0
Brighton and Hove	0	0	0
Bristol, City of	10	4	2
Bromley	3	0	0
Calderdale	3	1	0
Camden	16	12	5
City of London	8	4	1
Croydon	26	3	4
Dacorum	4	2	1
Ealing	10	3	2
Gateshead	6	3	0
Greenwich	2	4	5
Hackney	18	3	4
Hammersmith and Fulham	20	3	9
Haringey	4	2	0
Harrow	1	0	0
Hillingdon	3	1	0
Hounslow	4	3	0
Ipswich	0	0	0
Islington	11	6	1
Kensington and Chelsea	0	0	1
Kingston upon Thames	3	0	0
Kirklees	2	1	0
Lambeth	16	3	7
Leeds	6	1	1
Leicester	0	0	0
Lewisham	5	2	1
Liverpool	32	12	3
Maidstone	0	0	0
Manchester	8	4	1
Merton	6	2	0
Medway	12	5	0
Milton Keynes	6	4	3
Newcastle upon Tyne	6	3	2
Newham	10	5	0
North Somerset	8	3	2
Norwich	11	7	0
Nottingham	34	8	6
Plymouth	3	2	1
Portsmouth	2	5	0
Richmond and Wandsworth	8	5	4
Reading	15	3	1
Redbridge	4	1	1
Salford	11	7	0
Sheffield	0	0	0
Slough	5	7	0
Southampton	1	0	0
Southwark	7	0	0
Sunderland	3	3	2
Sutton	2	0	0
Thanet	2	1	0
Tower Hamlets	9	9	1
Trafford	7	3	0
Waltham Forest	6	2	3
Westminster	17	5	1
Windsor and Maidenhead	8	4	0
Others	414	123	58
Total	887	315	145

## Enforcement_1
Enforcement action taken by local authorities against high-rise buildings under the Housing Act (2004) by remediation programme status, England, 28 March 2024
Back to Contents
This worksheet contains one table. All figures are for the number of enforcement actions by local authority and by the type of remediation programme each building is in [note_15].
Local Authority [note_2]	BSF only (non-ACM cladding only) / Number	ACM cladding only / Number	BSF (non-ACM) and ACM cladding / Number	Not in any remediation fund (non-ACM cladding only) / Number	Total / Number
Barking and Dagenham	1	0	0	0	1
Barnet	1	3	1	2	7
Birmingham	3	0	0	0	3
Bournemouth, Christchurch and Poole	2	2	0	1	5
Bradford	0	1	0	0	1
Brent	0	2	0	0	2
Brighton and Hove	0	0	0	0	0
Bristol, City of	1	1	0	0	2
Bromley	0	0	0	0	0
Calderdale	0	0	0	0	0
Camden	15	1	0	20	36
City of London	1	0	0	2	3
Croydon	2	0	1	0	3
Dacorum	0	0	0	0	0
Ealing	2	1	1	0	4
Gateshead	0	0	0	0	0
Greenwich	4	0	0	1	5
Hackney	3	3	2	3	11
Hammersmith and Fulham	9	1	0	33	43
Haringey	0	0	0	0	0
Harrow	0	0	0	0	0
Hillingdon	3	0	0	2	5
Hounslow	0	0	0	1	1
Ipswich	0	0	0	0	0
Islington	1	0	0	0	1
Kensington and Chelsea	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0
Kirklees	0	0	0	0	0
Lambeth	2	2	0	0	4
Leeds	0	0	0	0	0
Leicester	0	0	0	0	0
Lewisham	0	0	0	0	0
Liverpool	3	1	4	1	9
Maidstone	0	0	0	0	0
Manchester	0	0	0	0	0
Medway	0	1	0	0	1
Merton	0	0	0	0	0
Milton Keynes	0	0	0	0	0
Newcastle upon Tyne	6	0	0	5	11
Newham	10	1	1	9	21
North Somerset	0	0	0	0	0
Norwich	0	0	0	0	0
Nottingham	2	1	0	1	4
Plymouth	1	0	0	0	1
Portsmouth	0	1	0	2	3
Reading	0	0	0	0	0
Redbridge	2	0	0	0	2
Salford	1	0	0	0	1
Sheffield	1	0	0	0	1
Slough	0	0	0	0	0
Southampton	3	0	0	0	3
Southwark	26	3	3	21	53
Sunderland	0	0	0	0	0
Sutton	0	0	1	0	1
Thanet	0	0	0	0	0
Tower Hamlets	13	0	5	6	24
Trafford	0	0	0	0	0
Waltham Forest	1	0	0	0	1
Wandsworth	1	2	1	0	4
Westminster	32	4	6	11	53
Windsor and Maidenhead	0	0	0	0	0
Others	12	0	2	13	27
Total	164	31	28	134	357

## Enforcement_2_
Building inspections conducted by local authorities, England, 28 March 2024
Back to Contents
This worksheet contains one table. All figures are for the number of inspections by type of rating outcome.
Local Authority [note_2]	Inspections with the building rated Category 1 [note_16] / Number	Inspections with the building rated Category 2 [note_16] / Number	Rating outcome to be confirmed / Number	Total / Number
Barking and Dagenham	0	1	0	1
Barnet	5	2	0	7
Birmingham	0	2	1	3
Bournemouth, Christchurch and Poole	5	0	0	5
Bradford	0	1	0	1
Brent	1	1	0	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	2	0	2
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	0	35	1	36
City of London	2	0	1	3
Croydon	1	1	1	3
Dacorum	0	0	0	0
Ealing	1	3	0	4
Gateshead	0	0	0	0
Greenwich	2	1	2	5
Hackney	6	3	2	11
Hammersmith and Fulham	0	39	5	44
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	0	5	0	5
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	0	1	1
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	4	4	1	9
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	0	9	2	11
Newham	10	9	2	21
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	1	3	0	4
Plymouth	1	0	0	1
Portsmouth	0	1	2	3
Reading	0	0	0	0
Redbridge	0	1	1	2
Salford	0	1	0	1
Sheffield	0	0	1	1
Slough	0	0	0	0
Southampton	1	0	2	3
Southwark	25	25	3	53
Sunderland	0	0	0	0
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	5	12	7	24
Trafford	0	0	0	0
Waltham Forest	0	1	0	1
Wandsworth	1	3	0	4
Westminster	6	47	0	53
Windsor and Maidenhead	0	0	0	0
Others	12	13	2	27
Total	94	227	37	358

## Enforcement_3
Statutory notices served by local authorities under the Housing Act (2004), England, 28 March 2024
Back to Contents
This worksheet contains one table. All figures are for number of statutory notices served, broken down by type of notice, for each Local Authority.
Local Authority [note_2]	Improvement notices / Number	Hazard awareness notices / Number	Prohibition orders / Number	Total / Number
Barking and Dagenham	0	0	0	0
Barnet	7	0	0	7
Birmingham	1	0	0	1
Bournemouth, Christchurch and Poole	3	0	0	3
Bradford	1	0	0	1
Brent	0	0	0	0
Brighton and Hove	0	0	0	0
Bristol, City of	0	0	0	0
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	9	2	0	11
City of London	1	0	0	1
Croydon	0	0	0	0
Dacorum	0	0	0	0
Ealing	2	0	0	2
Gateshead	0	0	0	0
Greenwich	1	0	0	1
Hackney	8	0	0	8
Hammersmith and Fulham	0	2	0	2
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	2	1	0	3
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	0	0	0
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	4	0	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	6	0	0	6
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	2	3	0	5
Newham	11	0	0	11
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	2	0	0	2
Plymouth	1	0	0	1
Portsmouth	1	0	0	1
Reading	0	0	0	0
Redbridge	0	0	0	0
Salford	0	0	0	0
Sheffield	0	0	0	0
Slough	0	0	0	0
Southampton	0	0	0	0
Southwark	17	1	0	18
Sunderland	0	0	0	0
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	6	4	0	10
Trafford	0	0	0	0
Waltham Forest	0	0	0	0
Wandsworth	1	0	0	1
Westminster	1	14	1	16
Windsor and Maidenhead	0	0	0	0
Others	15	0	0	15
Total	105	27	1	133

## Enforcement_4
Number of building inspections by local authorities supported by the Joint Inspection Team, England, 28 March 2024
Back to Contents
This worksheet contains one table. All figures are for the number of inspections supported by the Joint Inspection Team.
Local Authority [note_2]	Inspections supported by the Joint Inspection Team [note_17] / Number
Barking and Dagenham	0
Barnet	4
Birmingham	3
Bournemouth, Christchurch and Poole	2
Bradford	0
Brent	2
Brighton and Hove	0
Bristol, City of	0
Bromley	0
Calderdale	0
Camden	5
City of London	0
Croydon	3
Dacorum	0
Ealing	4
Gateshead	0
Greenwich	5
Hackney	8
Hammersmith and Fulham	2
Haringey	0
Harrow	0
Hillingdon	2
Hounslow	1
Ipswich	0
Islington	1
Kensington and Chelsea	0
Kingston upon Thames	0
Kirklees	0
Lambeth	2
Leeds	0
Leicester	0
Lewisham	0
Liverpool	7
Maidstone	0
Manchester	0
Medway	0
Merton	0
Milton Keynes	0
Newcastle upon Tyne	1
Newham	16
North Somerset	0
Norwich	0
Nottingham	2
Plymouth	1
Portsmouth	2
Reading	0
Redbridge	2
Salford	1
Sheffield	1
Slough	0
Southampton	3
Southwark	3
Sunderland	0
Sutton	1
Thanet	0
Tower Hamlets	10
Trafford	0
Waltham Forest	1
Wandsworth	4
Westminster	2
Windsor and Maidenhead	0
Others	8
Total	109