Board of Commissioners – Action Log – Updated 23/06/2022
Meeting Date & Agenda Item	Action Number	Action	Owner	Target Date	Action Update	Status / Date Closed
21/06/2022 / Item 5	1	To review the scoring of risk FC19, retain and recruit	Sarah Coombes	23/07/22	Completed.	29/06/22
21/06/2022 / Item 5	2	Safeguarding to be added to the December agenda	Sarah Coombes	07/12/22	Completed.	29/06/22
21/06/2022 / Item 8	3	Discussion on ecosystem markets to be held at a future date	Sarah Coombes	07/12/22	Noted for future meetings as a potential agenda item	29/06/22
21/06/2022 / Item 11	4	To provide a briefing note to commissioners prior to FWAC meetings	Richard Stanford	07/12/22	Admin process being updated with new staff joining the Commissioners Office to help provide the required information.
21/06/2022 / Item 12	5	To invite the Non-Executive Directors to the December meeting	Sarah Coombes	07/12/22	Completed.	29/06/22