## Sheet1
Workstream	Fewer women entering the criminal justice system and reoffending
Commitment	Activity	State of delivery	Update
POLICING: / The Ministry of Justice, Home Office, College of Policing, National Police Chiefs’ Council (NPCC) and the Association of Police and Crime Commissioners (APCC) will work together to ensure police forces understand and respond effectively to the needs of vulnerable women when they first come into contact with the police.	Through the NPCC leadership, develop a Tactical Toolkit by the end of March 2023, to enable Forces to more easily identify and access existing practice. This will be followed by the development of national evidence-based guidance to promote innovative and effective initiatives to improve policing’s response to women in or at risk of contact with the criminal justice system.	IN PROGRESS	A draft Tactical Toolkit has been prepared. Various stakeholders, including the Expert Group on Women in the Criminal Justice System have been invited to comment and options for publication are currently being considered. An NPPC Delivery Group on Women in the criminal justice system has been established and will consider next steps on developing national guidance. With regards to the publishing of the toolkit, we are hoping for spring/summer 2024 subject to identification of a platform that supports sharing with forces, partners and the public.
	Review use and effectiveness of Out of Court Disposals (OOCDs) in responding to the particular needs of women, including opportunities to attach women specific conditions such as referral to a women's centre for support to address her needs.	IN PROGRESS	Discussions underway with NPCC on delivering this commitment. / Separately, the consultation on the Code of Practice of the Statutory Two Tier Framework for OOCDs closed in October 2023. The MoJ received over 100 detailed responses which are currently being reviewed, and a Government Response will be published in spring 2024.
DIVERSION: / We will work with police and L&D partners on better identifying and diverting women out of the criminal justice system into support, where appropriate.	Undertake a review of the L&D women’s service to identify best practice and produce a lessons learned report, which will offer information and support to areas who wish to further develop their L&D women’s service. The review will contribute to ongoing service development during 2023.	IN PROGRESS	Review completed with principles that should be applied to female L&D pathways presented to a workshop in January 2023. These focus on Female specific care, informed by knowledge and understanding of the differences, inequalities and varying needs of women in touch with the criminal justice system experience. Work is underway on further development of the female pathway in discussion with NHSE, DHSC, MOJ and HO.

	Publish guidance by the end of April 2023 to support women to understand what happens at each stage of the criminal justice system, from arrest to sentencing, including the role of practitioners that women will encounter and the meaning of terminology they are likely to hear. The guidance will benefit all women in contact with the criminal justice system, while also reflecting the specific needs of those from ethnic minority backgrounds.	IN PROGRESS	Guidance is complete and we are working towards publication in the spring.
STATUTORY AND VOLUNTARY PARTNERS WORKING TOGETHER MORE EFFECTIVELY: / Many women in or at risk of contact with the criminal justice system have multiple and complex needs and make repeated demands on health and other statutory services. We know that bringing these services and charities together to work in partnership to address the needs of this group of women can improve outcomes, including diverting them away from offending behaviour and reducing demand on services.	Publish guidance for local areas on how they can make sure organisations are working together to addressing the complex needs of women in or at risk of contact with the justice system, by the end of January 2023.	COMPLETED	Whole System Approaches best practice events were held in January 2023 and the outputs from those have been published by the APCC due to rules around content that is permitted on gov.uk.
	Undertake a grants competition for up to £24m multi-year grant funding to support vital community services for women and encourage more joined up local partnership working to address women’s needs.	COMPLETED	Grants totalling up to £14 million were awarded in early 2023 for the period 2022-2025. Forty women's community sector organisations received funding for core costs or to fund new services and interventions, and 4 PCCs received funding of up to a further £1 million to encourage more joined up local partnership working. We are currently undertaking feasibility work to establish the best evaluation approach for a full impact evaluation. We are continuing to monitor the impact of the funding biannually through the use of 'monitoring forms' completed by sector organisations.
	Continue to support the delivery of DLUHC’s Supporting Families programme, which works with local areas to offer support to families facing multiple disadvantages including women in the criminal justice system and their families. With an additional £200m investment over the next three years already confirmed, the programme will aim to support a further 300,000 vulnerable families. Supporting Families is committed to driving strong multi-agency local partnerships in every local authority and helping build mature local and national data systems.	IN PROGRESS	The Supporting Families programme has continued to help families with multiple and complex needs to make significant positive changes to their lives. Between April 2021 and March 2024, there were 221,813 successful family outcomes. Funding has been secured for the programme up to 2025. / The programme moved to DfE on the 1st April 2024, to bring together the spectrum of reforms around Family Help. The programme will continue to join up with MoJ.
	Support adults facing multiple disadvantage through the Changing Futures programme led by the Department for Levelling Up, Housing and Communities (DLUHC). The programme aims to reduce offending and reoffending (among other outcomes) through locally led initiatives that coordinate support around the person, such as enhanced service hubs in Lancashire that bring together housing, drug treatment, health and mental health support, so people facing multiple problems get the joined-up help they need to change their lives for the better.	IN PROGRESS	All 15 funded areas are delivering support to people experiencing multiple disadvantage and have prepared system change and sustainability plans to preserve the benefits of the programme beyond the funded period. The programme has supported over 3,700 beneficiaries to date, and government has committed to extend funding through the Shared Outcomes Fund to continue national policy development and learning as well as local delivery into 2025.

NON-POLICE PROSECUTIONS: / We will work with non-police prosecutors to explore options for addressing gender disproportionality in prosecutions, identifying vulnerability and signposting women into support.	Work with the Department for Digital, Culture, Media and Sport and the BBC to explore options for the piloting of enforcement officers signposting women to support, in order to understand the effectiveness of this approach.	IN PROGRESS	BBC has launched a pilot working with StepChange, an independent debt support charity, to refer those experiencing difficulty with TV licence payments and pause enforcement action. Results will be reviewed once the pilot is complete to assess whether anything further, including support specifically tailored to women, is needed. The BBC committed to publish an annual progress update, with the first expected in summer 2024.
Workstream	More women managed effectively in the community
Commitment	Activity	RAG Rating	Update
WORKING WITH COURTS: / We will work with courts to raise awareness and increase understanding of the specific issues faced by women who offend, including those of ethnic minority women. We will do this by sharing up-to-date information on the suitability and availability of community sentence options and evidence of good and effective practice.	Develop, deliver and maintain briefing materials that support regular information sharing sessions, starting in early 2023, for the judiciary and all those who work in courts. The materials will raise awareness of the specific issues faced by women who offend and increase understanding of the possible implications and opportunities of sentencing	COMPLETED	Judicial briefing materials have been created to help raise awareness of the specific issues faced by criminalised women and available community based sentencing options. / These materials comprise of a set of 3 short videos looking at: / - Women’s distinct needs in the Criminal Justice System / - Implications for custody (including remand) / - Opportunities (available in the community as alternatives to custody) / They have been shared as part of existing regional engagement events with judicial colleagues (including sentencers and legal advisors) and delivered to frontline court practitioners. These materials will be kept under review, and updated/ amended/ added to periodically.

COMMUNITY SENTENCES: / We aim to reduce the proportion of all women sentenced to immediate custody, especially on short sentences. Our A Smarter Approach to Sentencing White Paper (September 2020) set out our plans for tougher, better monitored and more effective community sentencing options, which provide appropriate punishment but also address the underlying drivers of offending and offer support for those who want to turn their lives around. We will ensure courts have evidence-based and robust community sentencing options that provide women with those opportunities, including piloting a residential women’s centre (RWC) for women in Wales.	Trial Problem Solving Courts (now known as Intensive Supervision Courts), including one site in Birmingham that will focus exclusively on women.	IN PROGRESS	A pilot of Intensive Supervision Courts (ISCs) launched in June 2023. ISCs aim to address the root cause of offending by addressing underlying needs. / Sentencing in Birmingham, an ISC site focused exclusively on women, commenced in July 2023, and sentence management through this model is underway. The pilot will run until December 2024, with a process and evaluation impact to follow to assess the pilot's success.

	Explore options for increasing residential provision that could be used as part of a robust community order as an alternative to a short custodial sentence, allowing a woman to stay closer to her family and community with support to address needs underlying her offending behaviour.	COMPLETED	Our CAS1 Approved Premises (AP) estate for women has expanded. CAS1 AP are available for women presenting complex needs, and a medium, high or very high risk of serious harm. Use of CAS1 AP for community sentences with a requirement to reside is being actively pursued. We have ensured that our courts systems are being updated to better enable colleagues to recommend these sentences to the court. / We are also increasing voluntary sector provided provision and have supported roll out of residential alternatives to custody through grant awards to Trevi, Willowdene and Nelson Trust.

	By mid 2024 the national roll out of Community Sentence Treatment Requirement sites will be completed in addition to providing Mental Health Treatment Requirement pathways for all adults which will include bespoke women’s pathways	IN PROGRESS	We are continuing to support NHS England in their rollout of primary care MHTRs across England. Primary Care MHTRs will be available to sentencers in all criminal courts by mid-2024, with coverage currently standing at over 80%.

	We will publish an evaluation of the PSR pilot in spring 2023 and at that point will consider next steps.	COMPLETED	The PSR process evaluation was published in June 2023. Going forward the Probation Service is testing new ways of working via the Pathfinder to Improved Pre-Sentence Advice (PIPA) project. This launched in Autumn 2023 in the South-Central region and will test a revised PSR format, optimal delivery timeframes for completion of PSRs, and better targeting of probation’s resource in court to facilitate early identification of cases that may benefit from a PSR.
REMAND: / We will seek to encourage alternatives to remand in custody where it is in the interests of justice to do so. On average, female offenders commit less serious offences than male offenders and often pose a low or medium risk of serious harm to the public. In 12 months to December 2021, in the female estate the rate of self-harm was higher among remand prisoners than among sentenced prisoners (4,673 incidents per 1,000 prisoners on remand and 3,315 incidents per 1,000 sentenced prisoners)	Commence first hearing bail report pilots in Cardiff and Ipswich magistrates’ courts by the end of 2022 to ensure those courts receive advice from the Bail Information Service (BIS) on all women defendants. Ensure that BIS takes into account cultural factors and sensitivities in helping to ensure the prioritisation and appropriate use of bail for women from minority groups and those who are foreign nationals. Increase the use of electronic monitoring where this can reduce remand to custody.	IN PROGRESS	The existing Bail Information Service (BIS) project is currently delivered in around 30 public sector reception prisons. Bail Information Officers (BIOs) also currently produce Bail Information Reports (BIRs) at first hearings in Cardiff, Liverpool, Manchester and Blackburn magistrates’ courts. As BIS continues to expand, more BIRs will be produced at first hearings, enabling more informed bail decisions to be made on all women at the earliest opportunity. / On August 28th 2023 the Ministry of Justice published the ‘Electronic Monitoring Court Bail Protocol' for England and Wales. This sets out key information for those involved in imposing and managing electronically monitored conditions of court bail. It helps to raise awareness of, and greater confidence in, the use of Electronic Monitoring as a valuable tool to help manage the risk that defendants may pose while on bail in the community to ensure that defendants are only remanded in custody as a last resort. / The department has worked closely with stakeholders including the police, the CPS and the judiciary to inform them of the availability and capability of EM conditions for court bail as an alternative to remand in custody where appropriate.

	Remove the power of courts to remand defendants to prison for their own protection solely on the grounds of mental health. Clauses were included in the draft Mental Health Bill published on 27 June 2022.	OFF TRACK	The draft Mental Health Bill, published in June 2022, set out proposed reforms to prevent remands for 'own protection' solely on mental health grounds. The Bill was not introduced in the fourth parliamentary session but we remain committed to tackling this issue through non-legislative means. That's why we are piloting a Regional Health and Justice Hub in the Northeast of England, delivered in partnership with NHS England and HMCTS. Through the Hub, we’ll work to improve the way that courts, health services and prisons work together at a local level to better support defendants with severe mental illness, with the aim of smoothing the pathway into the right treatment for defendants, whether that is in hospital or in the community.

Workstream	Better outcomes for women in custody
Commitment	Activity	RAG Rating	Update
SAFETY: / We will improve safety for all women in custody, and reduce the severity and instances of self-harm through the expansion of therapeutic services and reducing the need for women to move between prisons.	Develop and publish a Young Women's (18-25) Strategy that spans the whole of the criminal justice system, including best practice guidance to support young women in custody	IN PROGRESS	Working across government to understand the current landscape of services that young women interact with both before and during contact with the criminal justice system. / We have been exploring options for co-production of the strategy with women with lived experience of the criminal justice system and with frontline practitioners. / Operational guidance for working with young women in custody has been published internally for staff to access.
	Develop and test a bespoke approach to managing young women in two prisons, including providing a ‘step-down’ approach to bridging the gap between the high level of support provided in Youth Custody services and adult custodial provision.	IN PROGRESS	Pilots are being mobilised in HMP Bronzefield and HMP Styal. Currently recruiting staff to support this. This project is expected to be fully mobilised by summer 2024.

	Expand therapeutic services to meet the needs of the most vulnerable women in our care by the recruitment of additional psychology staff by March 2023.	COMPLETED	We have filled 19 posts across women's prisons. The new services include individual sessions with women in prison to understand their experiences. This is also being utilised by operational staff to support individualised responses to women in prison. Given the bespoke nature of a lot of this work, the work being completed in prison with women varies in nature and is highly responsive to their needs. The work is being delivered through the Early Days project and the Young Adults project by onsite psychologists at each establishment.

	Seek to reduce the distance from home and self-harm linked to the impact of moves between prisons for women by exploring options for HMP/YOI Downview and HMP/YOI Drake Hall to receive women from the courts.	IN PROGRESS	Options have been explored to enable HMP Downview & HMP Drake Hall to receive women from the courts. Due to the finance required to make these changes it has been decided at HMPPS Higher Leadership Team that they are to be pursued though the next Spending Review.
	Develop and pilot an enhanced approach to supporting women in their first weeks in custody, when they are often at their most vulnerable.	COMPLETED	Five prisons are now operating the Early Days project: HMP Bronzefield, HMP Styal, HMP Eastwood Park, HMP Newhall and HMP Foston Hall. This includes one-to-one psychological input and group work. We have recruited 15 staff including prison officers and psychologists who are supporting this project.

OUR WORKFORCE: / We will professionalise the prison and probation workforce though training, guidance and the introduction of new roles, better enabling them to meet the needs of women in custody.	By March 2023, introduce a new process to attract and select new Prison Officers with the right experience and skills to work specifically in women’s prisons.	COMPLETED	The new process to attract and select staff is now implemented and has supported a healthier pipeline of staff coming into the prison estate. In addition, bespoke training for new Prison Officers in the women's estate commenced in September 2023 and has received positive feedback.

	Improve access to support for domestic abuse or sexual violence by the recruitment of specialist workers in women’s prisons.	COMPLETED	Domestic Abuse support workers are now in post in women's prisons in England. Evaluation for this project is currently being designed.

	Work with partners to develop a pilot for up to three social workers in women’s prisons to support mothers in custody, increase uptake of Mother and Baby Unit (MBU) places, support women through family court processes and prepare mothers for resettlement with their children.	COMPLETED	Four Social workers are now in post and supporting women with access to Social Care in the community and Mother & Baby Unit's in custody. Evaluation work is now underway.

	Complementing wider cultural competency training for HMPPS staff through the Race Action Programme, we will develop training for staff working with foreign national offender and ethnic minority women in offender management and rehabilitation, to increase awareness of the impact of culture, faith, and sustaining family relationships	IN PROGRESS	Design of e-learning package expected to be completed in 2024. Development has been delayed to make way for wider demands for learning products. Alternative options of delivering this package are being explored in the meantime.
	In 2023, introduce additional family engagement workers in prisons to support women in maintaining healthy family relationships during their sentence and prepare for resettlement.	IN PROGRESS	The family engagement worker (FEW) grant has been awarded to PACT and is being mobilised. FEW's are in post now in seven prisons with recruitment continuing for the remaining positions. There are two tranches of training occurring for the new recruits in family conferencing and the staff are becoming embedded into the prison sites and with other departments.

HEALTH AND WELLBEING: / We are committed to providing women in custody with equivalent health care to that which they would receive in the community. Effectively addressing health and wellbeing is essential to improved outcomes and resettlement on release from custody.	Develop operational guidance to enable staff to understand better the relationship needs of ethnic minority women, where these differ from the majority prison population.	COMPLETED	Guidance has been published internally and is available to HMPPS staff who work with women both in prisons and in probation. The guidance has also been included in the internal national families intranet site.
	Work with the Department for Education to consider options to improve the visibility of children of prisoners within the education system, while working to collectively understand the scale of the issue.	IN PROGRESS	Our statutory guidance, ‘Working Together to Safeguard Children’, updated in December 2023, is clear that local areas should have a comprehensive range of effective, evidence-based services to support children and families when they need it. It highlights dependent children of incarcerated parents and carers as a cohort which practitioners should be particularly aware of and provide appropriate needs-based advice and support [where needed]. / These children’s circumstances vary considerably and therefore local authorities and their partners are best placed to determine what support is needed – whether early help, statutory social care services, or support for other needs such as mental health. / Schools play a crucial role in ensuring the best interests of children. Working Together places a strong expectation on all safeguarding partners to set out clearly how all schools in their area will be engaged with multi-agency safeguarding arrangements. We have strengthened the roles and responsibilities of education settings to encourage their involvement both strategically and operationally as part of the update to statutory guidance, Working Together (2023). / In Stable Homes, Built on Love, we outlined our plans for building on the strengths of early help services through the implementation of Family Help. Through the £45m Families First for Children Pathfinder programme, we will test how multi-disciplinary family help teams can improve the support children and families receive. Dorset, Lincolnshire and Wolverhampton are the areas included in our first pilot and we have recently completed a co-design process to design new local systems. The second wave of pathfinder local authorities will be announced in the spring.

	Through the Better Outcomes through Linked Data (BOLD) Project we will explore data sharing to improve our understanding of the number of children with parents in prison and how parental incarceration impacts children’s outcomes, including education, employment and future offending.	IN PROGRESS	The BOLD project continues to link and share data, in order to produce an analytical report on the scale of parental imprisonment. We expect findings from this part of the project to be published by end of spring 2024. We are also exploring data sharing to improve our understanding of how parental incarceration impacts children's outcomes, which will continue during 2024.

	Complete and publish the joint NHS England and HMPPS Women’s Prisons Health and Social Care Review and agree next steps for taking forward its findings and recommendations.	IN PROGRESS	The Women’s Prisons Health and Social Care Review was published in November 2023. We are working collaboratively with NHSE on the development of the delivery plan, which is due in spring 2024.

	Introduce health and perinatal pathway managers in closed women's prisons by March 2023, to provide leadership to ensure that women receive timely and appropriate care.	COMPLETED	H&PN Managers are in post. Process evaluations are currently taking place.

PRISON CONDITIONS: / We are committed to a women’s estate that offers decent accommodation that supports rehabilitation.	Develop Design Standards for new accommodation in the women’s prison estate that will support effective rehabilitation, building on our learning from current work developing new facilities in the women’s estate.	IN PROGRESS	We have already made good progress developing designs for open and closed gender-specific and trauma-informed (GSTI) accommodation for the women’s estate. / We have secured planning approval for three of the five sites (in the case of one site this is subject to Section 106 agreement), with work continuing to secure planning approval for the remaining two. GSTI design work completed to date will stand us in good stead, subject to fiscal considerations, for recommending the building of such accommodation in the future. This will further support achievement of our outcomes in relation to women in custody.

	Continue work to deliver new facilities in women’s prisons, through a combination of Open and Closed places. New open provision at a greater number of sites will enable women to progress within their establishment without the need to move further from home, allowing them to maintain family ties and support networks. This will improve opportunities for education and employment closer to home, and increase stability, which is important for women in custody.	OFF TRACK	Prison projects are complex capital projects, which are being delivered within challenging market conditions. As with other construction programmes, women's estate expansion plans have been affected by high levels of inflation over the last year, which has had a material impact on estimated costs. Amid these ongoing fiscal challenges, we are taking a responsible approach and pausing our plans to build. . / However, we remain committed to delivering gender-specific and trauma-informed (GSTI) approaches that will support more effective rehabilitation for women in the criminal justice system and have already made good progress developing designs for open and closed GSTI accommodation for the women’s estate. / We have secured planning approval for three of the five sites (in the case of one site this is subject to Section 106 agreement), with work continuing to secure planning approval for the remaining two. GSTI design work completed to date will stand us in good stead, subject to fiscal considerations, for recommending the building of such accommodation in the future.

	Develop the principles for our longer-term ambition to introduce smaller, trauma-responsive custodial environments for women on short sentences. This will focus on how to provide community-based provision in a prison setting, with a focus on addiction issues and complex needs, and on keeping women close to home.	IN PROGRESS	We have developed some broad principles for these units and how they can fit in to the future women’s estate. We will continue to develop these based on the gender specific and trauma informed design standards and learnings from other jurisdictions, including the Community Custody Units opened in Scotland.

Workstream	Better outcomes on resettlement
Commitment	Activity	RAG Rating	Update
EDUCATION AND EMPLOYMENT: / We will take action to raise the level of numeracy, literacy, skills, and qualifications of women so that they are more likely to secure jobs or apprenticeships on release.	Develop curriculum guidance to ensure it is gender responsive, trauma informed and include provision that supports prisoners to develop wellbeing, confidence, motivation and resilience building skills.	COMPLETED	Guidance has been published to support prison Governors and their teams when designing, delivering and evaluating the curriculum. The guidance encourages a curriculum that meets the needs of prisoner cohorts and drives quality and progress towards meaningful outcomes.

	Enable all female prisoners to develop personal learning plans so they can track their education and skills achievements throughout their sentences, by March 2025.	IN PROGRESS	Following extensive user research, the new Manage Learning and Work Progress service has been built and is now live as a Private Beta in 5 Prisons for testing; one of these prisons is a Female offender site. Further iterations of the service are being developed and released on a continual basis, and public beta (nationally available) of the service is on track for delivery in spring/summer 2024.

	Deliver the Employment Innovation Fund over a three-year period, to enable Governors to work with more employers and training providers to repurpose workshops, deliver sector specific skills training to meet the changing needs of the economy and smooth the path from prison to employment	IN PROGRESS	The law has been changed to allow serving prisoners to start an apprenticeship in custody. We are delivering the Literacy Innovation Fund in 15 prisons, testing approaches to reading and literacy education and gathering evidence on what works. / HMP Academies is onboarding a number of suppliers onto a national Framework Agreement for future call-off by individual prisons during 2024. / The Future Skills Programme is delivering sector-specific training courses linked to job vacancies in 23 prisons. This includes two prisons in the women’s estate (HMP New Hall and HMP Low Newton), where participants will be provided with training to become third sector caseworkers. Participants who complete the course will receive up to three months employment and housing support post release.

	As part of the Government’s 10-year drugs plan, DWP committed to invest £21m to expand Individual Placement and Support for Drug and Alcohol Dependency across England by 2025 to support those in treatment, including male and female offenders, to overcome barriers to employment; and £8m in wider employment support, including a peer mentoring programme to help individuals with a dependency move into recovery and closer to work.	IN PROGRESS	DWP, working in partnership with DHSC, is rolling out IPS employment support for those dependent on drugs or alcohol across England, due to complete March 2025. The department has also successfully implemented a peer mentoring test across selected Jobcentres in London, Hampshire, Merseyside, Hull and North Wales.

	Invest in expert support in prisons, such as Head of Education, Skills and Work specialists (HoESWs), who will work to improve education and employment results.	COMPLETED	Following the national rollout of the Head of Education, Skills and Work role across the whole estate in September 2023, there is now a HoESW in post in every female prison. / Whilst still new in post, HoESWs are already driving forward important work to improve ESW provision and employment/prisoner resettlement outcomes on release. Following a comprehensive training and induction period, HoESWs are working to develop new curriculums to meet prisoner need, improving education, skills and work activity attendance, and creating more opportunities within Prison Industries to develop employability skills and embed functional learning within workshops.

	Ensure all women’s prisons have an ID and Banking Administrator to ensure women have ID and a bank account on release.	COMPLETED	ID and Banking Administrators have been recruited to all 12 women’s prisons. 435 bank accounts have been successfully opened this calendar year, while 1783 IDs have also been purchased during this period. All 12 sites are also in a position to offer a driving licences as a form of photo ID, with 7 of the sites successfully obtaining these on behalf of prisoners already.
	Hold an employment conference in January 2023 to increase awareness of employment opportunities and the different challenges that women face when leaving prison. At the event, we will gather feedback and capture best practice to develop women-specific guidance for Employment Advisory Boards so that they are able to positively impact the lives of women prison leavers, reduce re-offending and meet employers’ recruitment needs.	COMPLETED	Following the Womens Estate EAB Conference we developed women-specific guidance for the EABs. This guidance focused on the barriers faced by women in and leaving prison, and includes examples of best practice in which the EABs have supported to overcome some of these barriers.
	Introduce Support Managers for those with additional learning needs to all women’s prisons by March 2024, helping to ensuring that those prisoners can access education, skills and work opportunities.	COMPLETED	Neurodiversity Support managers are recruited into all women's prisons. The Neurodiversity Support Managers across the female estate have established a Support Manager Network for neurodiversity in women's prisons which is working to ensure a joined up approach to supporting women's needs in prisons and developing consistent links with community support on release.
	Roll out Employment hubs, Employment Advisory Boards and Employment Leads in all women’s prisons by the end of March 2023 to provide better employment support.	COMPLETED	Prison Employment Leads have been recruited, and Employment Hub and Employment Advisory Boards set up in every women's prison prior to March 2023. These initiatives continue to support women into employment on release as they transition from implementation to BAU.

ACCOMODATION AND FAMILY: / We will ensure that no female offenders subject to probation supervision leave prison homeless and that probation supervision in the community addresses concerns about inappropriate accommodation. We will also smooth the return to society by making best use of Open prison places and Release on Temporary Licence, which allows some prisoners to leave prison for a day or overnight, including to find and attending work and rebuild family ties.	Ensure that a minimum 10% of beds delivered through the Community Accommodation Service (Tiers 1, 2 and 3) are allocated to women in women-only properties so that they feel safe, especially those with backgrounds of abuse.	COMPLETED	A minimum of 10% of beds delivered through CAS (CAS1, CAS2 & CAS3) are allocated to women in women-specific properties. In CAS1 the provision for women supports both prison leavers and those on community sentences, providing an alternative to custodial sentences. In CAS2 the provision for women includes additional CCTV as well as support for women, and CAS2 properties are also available for women who have children who are able to live with them. CAS3 provides accommodation dedicated to single gender usage.

	DLUHC will invest over £2bn to tackle homelessness and rough sleeping, demonstrating a commitment to programmes like Accommodation for Ex-Offenders, a local authority-led scheme to help prison leavers into rented accommodation.	IN PROGRESS	DLUHC's commitments are set out in the Ending Rough Sleeping for Good strategy (published September 2022). DLUHC launched phase 2 of the Accommodation for Ex-Offenders scheme on 1 April 2023, allocating an additional £26m to 111 local authorities over 2023/24 and 2024/25. DLUHC's Q2 data shows that 857 new tenancies have been created since April 2023, including 49 for female ex offenders.

	Create more Open prison places providing a greater geographical spread and increase the number of women categorised to Open conditions where appropriate, to help them resettle into the community.	OFF TRACK	Prison builds are complex capital projects, which are being delivered within challenging market conditions. As with other construction programmes, women’s estate expansion plans which included open accommodation have been affected by high levels of inflation over the last year, which have had a material impact on estimated costs. Amid these ongoing fiscal challenges, we are taking a responsible approach and pausing our plans to build, however we remain committed to delivering GSTI approaches that will support more effective rehabilitation for women in the criminal justice system. / We have secured planning approval for three of the five sites (in the case of one site this is subject to Section 106 agreement), with work continuing to secure planning approval for the remaining two. GSTI design work completed to date will stand us in good stead, subject to fiscal considerations, for recommending the building of such accommodation in the future.

	Recruit up to nine FTE Strategic Housing Specialists across women’s prisons to improve housing outcomes for prison leavers.	COMPLETED	There are currently 9 FTE Strategic Housing Specialists working across the female estate. HMPPS Strategic Housing Specialists are responsible for strengthening partnership working with key partners, including Local Authorities, and housing providers, to improve processes and pathways in order to reduce the number of prison leavers released into homelessness.

RESETTLEMENT PASSPORTS: / We will develop a resettlement passport that provides women with the key information and services that they need to adjust to life in society.	Continue to develop the design of Resettlement Passports, including testing with prison and probation staff, charities, and prisoners to ensure it adapts to challenges faced by certain groups, including female offenders.	IN PROGRESS	Development of Resettlement Passports is ongoing, informed by extensive scoping and user testing with HMPPS staff, prisoners, people on probation, and voluntary sector organisations. This will include delivery of two practical and personalised digital tools that organise and record key resettlement information and services needed to support an effective transition into the community: Prepare Someone for Release for staff and Plan Your Future for prison leavers. Following the conclusion of live testing, a first iteration of both tools will be rolled-out across the estate by December 2024. Both tools will be tested in women's prisons before full roll out.

CONTINUITY OF HEALTHCARE: / We will improve continuity of health care, ensuring women leaving prison have a dedicated point of contact to support them in engaging with the NHS services that they need.	Work with NHS RECONNECT to continue roll-out to ensure women leaving prison have a dedicated point of contact to support them in engaging with NHS services.	IN PROGRESS	Roll out is continuing across prisons in England. As of November 2023 the service was rolled out at 83% of prisons in England. Work continues across all services to increase awareness of RECONNECT. Close working continues to be encouraged between RECONNECT services and HMPPS Health and Justice Partnership co-ordinators. Information has been provided to HMPPS to be incorporated into the HMPPS Accommodation Guidance for Women. Work additionally continues to progress on the development of RECONNECT national communication materials including a leaflet about the service and a video advising of the service

	Recruit Health and Justice Partnership Coordinators to all Probation Regions to improve pathways into healthcare services across the Probation system, including improving continuity of care in their area so that those leaving prison can access treatment and support	IN PROGRESS	Recruitment of 45 Health and Justice Partnership coordinators and 12 managers is now completed. The roles are located within all 12 probation regions. Improving continuity of care for prison leavers is one of their strategic aims and the posts are working with partners to build strong relationships and develop and improve pathways. / As of October 2023, the continuity of care figure stood at 49%. We have seen an important increase in performance over the last 12-month period of 12%.

	Roll out additional laptops and licences to prisons to increase the number of prisoners able to attend initial appointments with community drug treatment providers virtually prior to release and increasing access to tele-recovery services.	IN PROGRESS	Roll out of Telemedicine laptops commenced on a regional basis, starting in Wales, and all prisons received laptops before 31 March. / One of the key issues we are looking to address with the current stage of rollout (Wave 3) is the collection and monitoring of data. All data is being collected, following roll out, from the end of April 2024. This data will include: / - The HMP location of a laptop; / - How often a laptop is used; / - How long a single session lasts; / - What the session is e.g. mutual aid or pre-release meeting with community service provider. / Wave 1 and 2 were distributed during the pandemic and the only data currently collected on these laptops was when they were last turned on.