## External Plan Format
Magnox Limited Procurement Plan as at end of April 2024
1
UNIQUE EXTERNAL REF | DIRECTORATE OR CATEGORY TEAM | SITE | CONTRACT DESCRIPTION (Values in brackets represent anticipated duration) | CATEGORY | CONTACT | PROCUREMENT ROUTE | BANDING | PIN or PRE QUAL ADVERT PUBLISH DATE | ITT ISSUE (a) Actual (f) Forecast |  | CONTRACT AWARD DATE (a) Actual (f) Forecast |  | CONTRACTOR / SUPPLIER Tend: Tenderers or Contractor(s) if awarded | STATUS
C10498 | Decommissioning | Trawsfynydd | Rolling Programme of Decommissioning - Laser Trials Trawsfynydd | Design services/support | claire.scott@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2023-05-11 | (a) | 2024-05-05 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C14691 | Decommissioning | Harwell | Building at Harwell Demolition | Decommissioning, Demolition & Deplant | david.m.sanderson@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2023-12-07 | (a) | 2024-05-05 | (f) | Tend: Altrad Support Services Limited,Costain Limited,NSG Environmental Ltd,Nuvia Limited,KDC Contractors Limited,KELTBRAY LIMITED,Celadon Alliance | 10. Identification of preferred bidder
C15220 | Decommissioning | Oldbury | Oldbury Turbine Hall - Data Quality Objective | Design services/support | paul.phillips@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2023-12-07 | (a) | 2024-06-04 | (f) | Tend: Jacobs U.K. Limited | 10. Identification of preferred bidder
C15906 | Decommissioning | Oldbury | OTC Demolition | Decommissioning, Demolition & Deplant | david.m.sanderson@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2024-05-05 | (f) | 2024-09-02 | (f) | Not yet confirmed | 07. ITT in preparation
C15918 | Decommissioning | Trawsfynydd | Trawsfynydd - Reactor Retrievals SD4 Main Retrievals & Processing Facilities | Design services/support | claire.scott@magnoxsites.com | FTS Restricted | £1m to £5m | 2023-10-11 | 2024-02-05 | (a) | 2024-06-04 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C16013 | Decommissioning | Hinkley | Hinkley R1 & R2 Pipe Bridges | Decommissioning, Demolition & Deplant | sarah.j.deeble@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2024-05-05 | (f) | 2024-08-03 | (f) | Not yet confirmed | 07. ITT in preparation
C17680 | Decommissioning | Trawsfynydd | Reactor Retrievals Enablers - Environmental Impact Assessment | Design services/support | claire.scott@magnoxsites.com | DPS Call-Off | £500k to £1m | n/a | 2024-05-05 | (f) | 2024-08-03 | (f) | Not yet confirmed | 02. Strategy being developed
C17960 | Decommissioning | Harwell | Pathfinder - Building at Harwell | Decommissioning, Demolition & Deplant | Shelley.Lawrence@magnoxsites.com | Mini Competition F/W | £5m to £10m | n/a | 2025-01-10 | (f) | 2025-07-09 | (f) | Not yet confirmed | 01. On the horizon
C18569 | Decommissioning | Maentwrog | Maentwrog - Generator Outage Technical Support | Design services/support | claire.scott@magnoxsites.com | Other - No Competition | <£100K | n/a | 2024-03-06 | (a) | 2024-03-06 | (a) | JACOBS CLEAN ENERGY LTD | 11. Contract awarded
C18610 | Decommissioning | Trawsfynydd | BATS 070 280224 CS AW Electrical Support for Scheme Design | Design services/support | claire.scott@magnoxsites.com | DPS Call-Off | £100k to £500k | n/a | 2024-03-06 | (a) | 2024-06-04 | (f) | Tend: More than 10 | 09. Tenders being assessed
C19788 | Decommissioning | Maentwrog | Maentwrog Unit 1 Generator/Turbine Overhaul - Outage 2024 | Engineering | claire.scott@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2024-04-05 | (a) | 2024-05-05 | (f) | Not yet confirmed | 08. ITT issued
DEC 0121 | Decommissioning | Hinkley; Oldbury; Sizewell; Wylfa | BATS 068 020124 KC AW Bats requirement for GRR Compliance & End States WMP&SWEC | Manpower | kim.cook@magnoxsites.com | DPS Call-Off | £500k to £1m | n/a | 2024-01-06 | (a) | 2024-04-05 | (a) | Galson Sciences Limited. | 11. Contract awarded
DEC 0439 | Decommissioning | Oldbury | Oldbury Turbine Hall Demolition | Decommissioning, Demolition & Deplant | paul.phillips@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2024-12-01 | (f) | 2025-12-06 | (f) | Not yet confirmed | 01. On the horizon
DEC 0492 | Decommissioning | Wylfa | Control and Instrumentation (C&I) Overlay System | Engineering | claire.scott@magnoxsites.com | Mini Competition F/W | £1m to £5m | n/a | 2025-08-08 | (f) | 2026-02-04 | (f) | Not yet confirmed
DEC 0529 | Decommissioning | Chapelcross | Chapelcross Ponds Decommissioning-Divers | Engineering | Shelley.Lawrence@magnoxsites.com | FTS Open | £1m to £5m | n/a | 2025-03-11 | (f) | 2025-09-07 | (f) | Not yet confirmed
DEC 0597 | Decommissioning | Trawsfynydd | Reactor Buildings Height Reduction (EXECUTION phase) | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | FTS Comp Proc with Negotiation | £50m to £100m | 2022-12-06 | 2023-10-08 | (a) | 2025-03-11 | (f) | Not yet confirmed | 10. Identification of preferred bidder
DEC 0601 | Decommissioning | Harwell | Project Demolition (phase 4) | Engineering | Shelley.Lawrence@magnoxsites.com | FTS Open | £10m to £25m | n/a | 2024-12-01 | (f) | 2025-06-09 | (f) | Not yet confirmed
DEC 0699 | Decommissioning | Harwell | Project Enabling Works - Char Execution (phase 3) | Engineering | Shelley.Lawrence@magnoxsites.com | Non-FTS Competition | £500k to £1m | n/a | 2024-08-03 | (f) | 2025-02-09 | (f) | Not yet confirmed | 01. On the horizon
DEC 0708 | Decommissioning | Dungeness | Dismantle A Frame Crane & Remove Skip Mast | Decommissioning, Demolition & Deplant | david.m.sanderson@magnoxsites.com | FTS Open | <£100K | n/a | 2024-12-01 | (f) | 2025-03-11 | (f) | Not yet confirmed
DEC 0720 | Decommissioning | Trawsfynydd | Ponds Complex Demolition - Execution | Decommissioning, Demolition & Deplant | ruth.cox@magnoxsites.com | FTS Comp Proc with Negotiation | £5m to £10m | n/a | 2025-05-10 | (f) | 2026-09-12 | (f) | Not yet confirmed
DEC 0738 | Decommissioning | Winfrith | Winfrith Sea Pipeline - Marine Engineering (civil) Consultant | Engineering | janet.smith@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2024-10-02 | (f) | 2025-02-09 | (f) | Not yet confirmed | 02. Strategy being developed
DEC 0764 | Decommissioning | Harwell | Project Enabling Works Electrical Overlay (line 6) (PHASE TBC) | Engineering | Shelley.Lawrence@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2024-11-01 | (f) | 2025-05-10 | (f) | Not yet confirmed
DEC 0785 | Decommissioning | Dungeness | DNA Boilers - Waste Clearance Facility - fit-out | Construction | david.m.sanderson@magnoxsites.com | Other - No Competition | <£100K | n/a | 2024-12-01 | (f) | 2025-02-09 | (f) | Not yet confirmed | 01. On the horizon
DEC 0807 | Decommissioning | Trawsfynydd | Rolling Prog of Decom (RPD) - Scheme Design - Building Modifications | Design services/support | claire.scott@magnoxsites.com | FTS Restricted | £500k to £1m | n/a | 2024-11-01 | (f) | 2025-01-10 | (f) | Not yet confirmed | 07. ITT in preparation
DEC 0841 | Decommissioning | Winfrith | SGHWR Manufacture and Oversee the Installation of a Can Compactor | Engineering | pauline.z.mackemsley@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2024-03-06 | (a) | 2024-06-04 | (f) | Not yet confirmed | 08. ITT issued
FRM 0171 | Decommissioning | Dungeness | Package 1: Demolition & Boiler and ancillary equipment removal (Dungeness) | Decommissioning, Demolition & Deplant | nicola.j.smith-lee@magnoxsites.com | FTS Comp Proc with Negotiation | £50m to £100m | 2023-02-07 | 2023-06-10 | (a) | 2025-10-07 | (f) | Tend: More than 10 | 10. Identification of preferred bidder
C10070 | Ops & Enablers | Enablers/Not Location Specific | Occupational Health (inc DNA Testing) 26+ | Support Services | Amy.Vale@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2024-09-02 | (f) | 2025-04-10 | (f) | Not yet confirmed | 01. On the horizon
C13038 | Ops & Enablers | Enablers/Not Location Specific | Drawing Management System - 2026 | IT hardware/software | jayne.chalmers@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2025-09-07 | (f) | 2026-03-06 | (f) | Not yet confirmed
C14078 | Ops & Enablers | Enablers/Not Location Specific | ERP, FP&A and Talent Management - 2024 Stage A - Planning | IT hardware/software | jayne.chalmers@magnoxsites.com | G-Cloud F/W Call off | £5m to £10m | n/a | 2024-01-06 | (a) | 2024-04-05 | (a) | Unit 4 Business Software Ltd | 11. Contract awarded
C14396 | Ops & Enablers | Enablers/Not Location Specific | SD WAN and WiFi ongoing support | IT hardware/software | jonathan.harris@magnoxsites.com | Other - No Competition | £500k to £1m | n/a | 2024-03-06 | (a) | 2024-05-05 | (f) | Not yet confirmed | 09. Tenders being assessed
C15381 | Ops & Enablers | Enablers/Not Location Specific | Access & Insulation Services 2024-2028 | Construction | alex.macdonald@magnoxsites.com | FTS Restricted | £50m to £100m | 2024-05-03 | 2024-05-05 | (f) | 2024-10-02 | (f) | Not yet confirmed
C16731 | Ops & Enablers | Enablers/Not Location Specific | Consolidated Testing Services - 2025 | IT hardware/software | jayne.chalmers@magnoxsites.com | G-Cloud F/W Call off | £1m to £5m | n/a | 2024-10-02 | (f) | 2025-04-10 | (f) | Not yet confirmed | 01. On the horizon
C16929 | Ops & Enablers | Enablers/Not Location Specific | HR Permanent Recruitment | Support Services | alwena.owen@magnoxsites.com | FTS Open | £1m to £5m | 2024-06-03 | 2024-07-04 | (f) | 2025-02-09 | (f) | Not yet confirmed | 02. Strategy being developed
C17087 | Ops & Enablers | Enablers/Not Location Specific | Supply of new Metrology Instruments (Installed and Portable) | Engineering | caroline.j.milner@magnoxsites.com | DPS Set up | £5m to £10m | n/a | n/a | (f) | n/a | (f) | Not yet confirmed | 01. On the horizon
C17250 | Ops & Enablers | Dounreay; Enablers/Not Location Specific | Workplace Services 2027 - PIN | Support Services | steven.j.lock@magnoxsites.com | Market Engagement | £250m plus | 2024-04-10 | n/a | (f) | n/a | (f) | Not Applicable | Market Engagement
C17387 | Ops & Enablers | Bradwell; Dungeness; Sizewell | Civils Support DPS - South East Region | Construction | adrian.h.williams@magnoxsites.com | DPS Set up | £5m to £10m | n/a | n/a | (a) | n/a | (a) | Dynamic Purchasing System ('DPS') now open for supplier registration and pre-qualification | 11. Contract awarded
C17506 | Ops & Enablers | Chapelcross | Chapelcross New Potable Water Main - Supply & install | Utilities | andrew.dobson@magnoxsites.com | Non-FTS Competition | £500k to £1m | n/a | 2024-02-05 | (a) | 2024-06-04 | (f) | Tend: Story Contracting Ltd,R H Irving Construction Ltd,J Murphy and Sons Ltd,Scottish Water Business Stream Ltd,Panco No 9,WaterWise Utilities | 10. Identification of preferred bidder
C17613 | Ops & Enablers | Dungeness | Dungeness A - Reactor 2 Cladding Reinstatement | Construction | steven.j.lock@magnoxsites.com | Direct Award F/W | £1m to £5m | n/a | 2024-01-06 | (a) | 2024-03-06 | (a) | Altrad Support Services Limited | 12. Contract in place
C17864 | Ops & Enablers | Dungeness | Dungeness Site - Upgrade of Fire Panels | Maintenance | sukyee.hermon@magnoxsites.com | Other - No Competition | £100k to £500k | n/a | 2024-02-05 | (a) | 2024-02-05 | (a) | Channel Fire Systems Limited | 12. Contract in place
C17868 | Ops & Enablers | Enablers/Not Location Specific | IT Hardware Refresh 2024-25 | IT hardware/software | debbie.collin@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2024-02-05 | (a) | 2024-04-05 | (a) | Insight Direct (UK) Ltd | 11. Contract awarded
C17872 | Ops & Enablers | Hinkley | Hinkley Asset Care Work Packages 2024 | Construction | adrian.h.williams@magnoxsites.com | Non-FTS Competition | £1m to £5m | n/a | 2024-05-05 | (f) | 2024-06-04 | (f) | Not yet confirmed | 02. Strategy being developed
C18837 | Ops & Enablers | Enablers/Not Location Specific | BATS 069 200224 ES AW - Civil Engineering Support to NRS Ltd | Design services/support | anna.h.walker@magnoxsites.com | DPS Call-Off | £500k to £1m | n/a | 2024-03-06 | (a) | 2024-08-03 | (f) | Tend: More than 10 | 09. Tenders being assessed
C19775 | Ops & Enablers | Winfrith | Winfrith Site - Main Gate Reconfiguration - Design | Maintenance | sukyee.hermon@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2024-06-04 | (f) | 2024-07-04 | (f) | Not yet confirmed | 07. ITT in preparation
C19785 | Ops & Enablers | Enablers/Not Location Specific | Vehicle Lease and Fleet Management 25-29 EOI Lot 1 | Support Services | holly.griffith@magnoxsites.com | Market Engagement | £1m to £5m | 2024-05-29 | n/a | (f) | n/a | (f) | Not Applicable | Market Engagement
C19793 | Ops & Enablers | Chapelcross; Hunterston | Civils Support DPS - Scottish Region - Pre-Qualification | Construction | adrian.h.williams@magnoxsites.com | DPS Set up | £1m to £5m | 2024-05-17 | n/a | (a) | n/a | (a) | Dynamic Purchasing System ('DPS') being prepared for supplier registration and pre-qualification | 02. Strategy being developed
FRM 0129 | Ops & Enablers | Enablers/Not Location Specific | Site Security Maintenance Systems 2023+ | Maintenance | alex.macdonald@magnoxsites.com | Mini Competition F/W | £10m to £25m | n/a | 2023-05-11 | (a) | 2024-05-05 | (f) | Tend: More than 10 | 10. Identification of preferred bidder
FRM 0168 | Ops & Enablers | Enablers/Not Location Specific | Legal Services 2022+ | Support Services | gissela.m.hughes@magnoxsites.com | CCS F/W Call off | £1m to £5m | n/a | 2024-06-04 | (f) | 2024-09-02 | (f) | Not yet confirmed | 02. Strategy being developed
FRM 0182 | Ops & Enablers | Enablers/Not Location Specific | Land Quality Services 2024+ | Remediation & Environmental Services | Kwadwo.Awuku@magnoxsites.com | FTS Open | £10m to £25m | n/a | 2023-06-10 | (a) | 2024-06-04 | (f) | Tend: More than 10 | 10. Identification of preferred bidder
C12530 | Waste | Wylfa | Wylfa HAW LAW Facility Building | Waste management, disposal & storage | fiona.pearse@magnoxsites.com | FTS Restricted | £10m to £25m | 2024-07-29 | 2024-09-02 | (f) | 2025-02-09 | (f) | Not yet confirmed | 02. Strategy being developed
C14832 | Waste | Harwell | Harwell POCO Project Support | Design services/support | danielle.staples@magnoxsites.com | DPS Call-Off | £1m to £5m | n/a | 2023-07-10 | (a) | 2024-02-05 | (a) | Cavendish Nuclear | 12. Contract in place
C16672 | Waste | Enablers/Not Location Specific | Production of Spacers | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | DPS Call-Off | £1m to £5m | n/a | 2023-11-07 | (a) | 2024-02-05 | (a) | Neos Nuclear Limited, Graham Engineering Ltd | 12. Contract in place
C16954 | Waste | Chapelcross | Lease of 7.5T Drop side for Chapelcross | Support Services | julie.a.jones@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2023-11-07 | (a) | 2024-06-04 | (f) | Tend: Atkins Limited,One NDA,NRG Riverside,Enterprise Rent-A-Car UK Ltd,Dawsongroup bus and coach ltd,LC Vehicle Hire,Riverside Truck Rental LTD (Trading as NRG Riverside) | 10. Identification of preferred bidder
C17289 | Waste | Trawsfynydd | 4m Box Fabrication Optimisation Study | Design services/support | pauline.z.mackemsley@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2023-12-07 | (a) | 2024-04-05 | (a) | NIS ltd | 11. Contract awarded
C17610 | Waste | Hinkley | Hinkley - Design, supply and installation of 415V Switchboard | Consumables | karen.maguire@magnoxsites.com | Non-FTS Competition | £500k to £1m | n/a | 2024-05-05 | (f) | 2024-11-01 | (f) | Not yet confirmed | 02. Strategy being developed
C17624 | waste | Chapelcross | Manufacture and Supply of Remote Handling Equipment and Loading Baskets | Engineering | llyr.williams@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2024-01-06 | (a) | 2024-04-05 | (a) | Lyndhurst Precision Engineering | 11. Contract awarded
C17676 | Waste | Hinkley | Hinkley - Modifications to Nuclear Ventilation | Construction | danielle.staples@magnoxsites.com | Non-FTS Competition | £1m to £5m | n/a | 2024-01-06 | (a) | 2024-06-04 | (f) | Not yet confirmed | 10. Identification of preferred bidder
C17684 | Waste | Hinkley | Lease of 32T Hookloader HPA026 | Plant & Equipment & Materials | julie.a.jones@magnoxsites.com | Non-FTS Competition | £100k to £500k | n/a | 2024-01-06 | (a) | 2024-03-06 | (a) | NRG Riverside | 12. Contract in place
C18847 | Waste | Hunterston | Provision of 3m3 Drums for Hunterston | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | DPS Call-Off | £500k to £1m | n/a | 2024-04-05 | (a) | 2024-08-03 | (f) | Tend: More than 10 | 08. ITT issued
C19763 | Waste | Oldbury | EofI Oldbury - Design and Build of Advanced Vacuum Drying System facility | Construction | sophie.papworth@magnoxsites.com | Market Engagement | £1m to £5m | 2024-04-22 | n/a | (f) | n/a | (f) | Not Applicable | Market Engagement
WAS 0126 | Waste | Hinkley | Package 03 - SPF9f Waste Characterisation | Waste management, disposal & storage | danielle.staples@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2025-12-06 | (f) | 2026-04-05 | (f) | Not yet confirmed
WAS 0646 | Waste | Wylfa | Wylfa DCIC Storage Building Detailed Design and Construction | Construction | llyr.williams@magnoxsites.com | Non-FTS Competition | £1m to £5m | n/a | 2024-09-02 | (f) | 2025-03-11 | (f) | Not yet confirmed | 01. On the horizon
WAS 0676 | Waste | Harwell | Bulk Depleted Uranium Disposals @ Harwell | Waste management, disposal & storage | pauline.z.mackemsley@magnoxsites.com | FTS Open | £1m to £5m | n/a | 2025-05-10 | (f) | 2025-11-06 | (f) | Not yet confirmed
WAS 0755 | Waste | Harwell | Mezzanine Floor and Goods Lift | Construction | danielle.staples@magnoxsites.com | Non-FTS Competition | <£100K | n/a | 2023-10-08 | (a) | 2024-03-06 | (a) | Echo Engineering | 12. Contract in place