To:	Suzanne Newton Senior Responsible Owner for the Making Tax Digital Programme

From:	Jim Harra, Chief Executive, of HMRC; and
Nick Smallwood, Chief Executive Officer of the Infrastructure and Projects Authority

January 2024

Dear Suzanne,

APPOINTMENT AS SENIOR RESPONSIBLE OWNER FOR THE Making Tax Digital Programme

I am pleased to confirm your appointment as joint Senior Responsible Owner (SRO) of the Making Tax Digital Programme with effect from the date of this letter.
This letter sets out your responsibilities and the support you can expect from your department and the Infrastructure and Projects Authority.
You will be directly accountable to me as HMRC Chief Executive and to ExCom as owners of the HMRC Major Change Portfolio.
You and Jonathan Athow (DG for Customer Strategy and Tax Design) will jointly be appointed in the SRO role. This will give the programme a wide set of complementary skills and capabilities to help it succeed and ensure that any risks are managed effectively. You will be responsible for leading on programme delivery expertise whilst providing support and leadership to the Programme Director and Programme team. Jonathan will be responsible for leading on policy advice, strategy and Ministerial interaction. You and Jonathan will jointly lead and manage relationships with agents and software developers.
You will have joint personal responsibility for the delivery of Making Tax Digital Programme and will be held accountable for the delivery of its objectives, in line with policy intent and outcomes expected. This encompasses securing and protecting its vision, ensuring that it is governed responsibly, reported on honestly, escalated appropriately and for influencing the context, culture, and operating environment of the Making Tax Digital Programme. You are also responsible for ensuring the ongoing viability of the Making Tax Digital Programme and recommending its pause or termination if appropriate. Where issues arise which you are unable to resolve, you are responsible for escalating these to HMRC Executive Committee.
You remain accountable to Ministers, as set out in the Civil Service Code, and should deliver the project in accordance with the objectives and policy intent as set by Ministers.
In addition to your internal accountabilities, SROs for GMPP projects and programmes are personally accountable to Parliamentary Select Committees. This means that, from the date of this letter, you will be held personally accountable to and could be called by Select Committees to account for and explain the decisions and actions you have taken to deliver Making Tax Digital Programme.
It is important to be clear that your accountability relates only to implementation, within the agreed terms in this letter; it will remain for the Minister to account for the relevant policy decisions and development.
More information on this is set out in Giving Evidence to Select Committees - Guidance for Civil Servants, sometimes known as the Osmotherly Rules. Information on the roles and responsibilities of the SRO are detailed in the Infrastructure and Project Authority’s guidance on the role of the senior responsible owner. You should also make yourself familiar with the Government Functional Standard for Project Delivery, the requirements of the Government Project Delivery Framework, and the guidance and requirements for project delivery as set by HMRC.

Time commitment and tenure
This role will require at least 20% of your time to enable effective delivery of the role and execute your responsibilities in full (dual SRO commitment totalling 40%).
You are required to undertake this role until managed closure of the programme is achieved or, by agreement, until delivery of a specific milestone, end of phase or gate is achieved. Progress towards this will be reflected in your personal objectives. Any changes to the agreed time commitment or tenure of the role, as set out above, will require both departmental and Infrastructure & Projects Authority consent.

Objectives and performance criteria
The policy intent supported by this Making Tax Digital Programme is set out in Appendix B.
Any proposed changes to scope which impacts on this intent or the realisation of benefits must be authorised by HMRC Change Portfolio and may be subject to further levels of approval.
The objectives and vision of the project, together with your personal objectives and performance criteria are also set out within Appendix B.
You are expected to run your project in accordance with the Government Functional Standard for Project Delivery, the other Functional Standards as applicable to this Making Tax Digital Programme and the requirements of the Government Project Delivery Framework.

Extent and limit of accountability
Finance and Controls
HM Treasury spending controls will apply on the basis set out within the department’s delegated authority letter. Where the Making Tax Digital Programme exceeds the delegated authority set by HM Treasury, the Treasury Approval Point process will apply, and the details of each approval process must be agreed with your HM Treasury spending team. You should consult departmental finance colleagues on how to go about this.
You should note that where expenditure is considered novel, contentious, repercussive, or likely to result in costs to other parts of the public sector, HM Treasury approval will be required, regardless of whether the programme expenditure exceeds the delegated authority set by HM Treasury. If in doubt about whether approval is required you should, in the first instance, consult departmental finance colleagues before raising with the relevant HM Treasury spending team.
The overall estimated budget, resourcing requirements and tolerances for your project/programme will be agreed as part of the approval process. You will be expected to deliver within these tolerances and report quarterly on these as part of GMPP reporting.
You should operate at all times within the rules set out in Managing Public Money. In addition, you must be mindful of, and act in accordance with, the specific HM Treasury delegated limits and Cabinet Office controls relevant to Making Tax Digital Programme. Information on these controls can be found here: Cabinet Office controls.
In accordance with the guidance on managing public money, the SRO must advise the Accounting Officer of any significant issues relating to regularity, propriety, feasibility and value for money, as well as any significant deviations from the approved business case, which might lead them to reassess the project.

Delegated authority
You are:
- authorised to approve expenditure in line with the funding agreed by ExCom (via its sub-boards), or other authorised bodies and individuals under HMRC financial governance;
- responsible for ensuring that where a change impacts on the scope, costs, benefits or planned delivery milestones agreed as part of an approved Business Case, it is dealt with via the HMRC Change Portfolio; and
- Required to recommend to HMRC Executive Committee, via its sub-board, the need to either pause or terminate the programme where necessary and in a timely manner.
These authority limits are subject to change and other conditions or tolerances may be set as part of the business case approval and ongoing monitoring processes which you should then operate within.
Where issues arise which take you outside of these authority limits which you are unable to resolve, you are responsible for escalating these issues to the ExCom, via its sub-board, as appropriate.

Appointments
You should appoint a full time programme director to support you in the management of this Making Tax Digital Programme and make other appointments as required for the control and delivery of your programme within your delegated authority.

Governance and assurance
You should pay attention to ensuring effective governance for your programme, including the establishment of a programme board with appropriate membership and clear terms of reference.
As primary owner, you must ensure that the Making Tax Digital Programme secures business case approval from HMRC Investment Board, HMRC Change, Assurance and Investment Board, HM Treasury and Cabinet Office. You should also ensure that the Making Tax Digital Programme remains aligned to the strategic outcomes, costs, timescales, and benefits in line with the approved business case as well as monitoring the context within which the programme is being delivered to ensure it remains valid.
Where a change impacts the scope, costs, benefits, or planned delivery milestones agreed as part of an agreed business case, you are responsible for following the agreed change request approval process and setting a new, approved, business case baseline.
You should ensure that an accounting officer assessment is completed alongside the approval of the Outline Business Case and that this is published on GOV.UK as part of the government’s transparency requirements on major projects. You are responsible for bringing to the attention of the accounting officer any material changes in the programme which could require a new accounting officer assessment to be completed and published. Guidance on completing accounting officer assessments for major projects is available from HM Treasury.
Although you are directly accountable for this programme, you are also expected to support delivery of the department’s overall strategic objectives. This means that you are expected to work collaboratively with other SROs and project directors in adjacent projects and programmes and with the HMRC Major Change portfolio management office and portfolio director to manage dependencies, resources, schedules, and funding to support delivery of the overall change the department needs to achieve its strategic objectives.
You should ensure that appropriate and proportionate assurance is in place and agree on the level and frequency of assurance reviews through the maintenance of an integrated assurance and approvals plan. You should develop this plan and its maintenance in collaboration with the Departmental Assurance Coordinator and the Infrastructure and Projects Authority.

Making Tax Digital Programme status, reporting and transparency requirements
The Making Tax Digital Programme status at the date of your appointment is reflected in the most recent quarterly return on the programme to the Infrastructure and Projects Authority and is the agreed position as you assume formal ownership of the programme.
You are responsible for ensuring the honest and timely reporting on the position of the programme to the Infrastructure and Projects Authority while it remains on the GMPP and for providing reports and information to the HMRC Major Change portfolio management office as required. To help meet the government's Net Zero ambition this reporting will start to include carbon measurement. Information on the programme will be published annually by the Infrastructure and Projects Authority.

Development and support
As a graduate of the Major Projects Leadership Academy and an accredited Master practioner, you are expected to maintain your continuing professional development as a project leader, including your status as an accredited assurance reviewer. To maintain your accreditation, you will be required to participate in a review at least once every 12 months.
The department will assist you in securing the necessary resources to support the Making Tax Digital programme, and will set clear guidance, requirements and standards, which align to the Government Functional Standard on Project Delivery, to enable good governance and effective delivery. You will be part of the department’s cohort of major project leaders who will be expected to support each other, share good practice and lessons learned and to collectively develop solutions. You should liaise with the current Government Head of Project Delivery Function at the IPA (Nick Smallwood) to discuss maintaining and enhancing your personal programme delivery skills.
The Infrastructure and Projects Authority will be available to you for support, advice, and assurance throughout the programmes time on the GMPP.
HMRC Executive Committee will provide ongoing oversight and support and will take steps to help resolve and escalate risks, issues or constraints that are acting as a blocker to successful delivery.
We would like to take this opportunity to wish you every success in your role as SRO.

Yours sincerely,

JIM HARRA		NICK SMALLWOOD

Chief Executive / HM Revenue & Customs		Chief Executive Officer / Infrastructure and Projects Authority

CONFIRMATION OF ACCEPTANCE OF APPOINTMENT

I confirm that I accept the appointment of Senior Responsible Owner for the Making Tax Digital Programme, including my personal accountability for implementation, as set out in the letter above.

Suzanne Newton

Date 31/05/2024

To:	Jonathan Athow Senior Responsible Owner for the Making Tax Digital Programme

From:	Jim Harra, Chief Executive, of HMRC; and
Nick Smallwood, Chief Executive Officer of the Infrastructure and Projects Authority

March 2024

Dear Jonathan,

APPOINTMENT AS SENIOR RESPONSIBLE OWNER FOR THE Making Tax Digital Programme

I am pleased to confirm your appointment as joint Senior Responsible Owner (SRO) of the Making Tax Digital Programme with effect from the date of this letter.
This letter sets out your responsibilities and the support you can expect from your department and the Infrastructure and Projects Authority.
You will be directly accountable to me as HMRC Chief Executive and to ExCom as owners of the HMRC Major Change Portfolio.
You and Suzanne Newton (DG Change Delivery Group) will jointly be appointed in the SRO role. This will give the programme a wide set of complementary skills and capabilities to help it succeed and ensure that any risks are managed effectively. You will be responsible for leading on policy advice, strategy and Ministerial interaction and Suzanne will be responsible for leading on programme delivery expertise whilst providing support and leadership to the Programme Director and Programme team. You and Suzanne will jointly lead and manage relationships with agents and software developers.
You will have joint personal responsibility for the delivery of Making Tax Digital Programme and will be held accountable for the delivery of its objectives, in line with policy intent and outcomes expected. This encompasses securing and protecting its vision, ensuring that it is governed responsibly, reported on honestly, escalated appropriately and for influencing the context, culture, and operating environment of the Making Tax Digital Programme. You are also responsible for ensuring the ongoing viability of the Making Tax Digital Programme and recommending its pause or termination if appropriate. Where issues arise which you are unable to resolve, you are responsible for escalating these to HMRC Executive Committee.
You remain accountable to Ministers, as set out in the Civil Service Code, and should deliver the project in accordance with the objectives and policy intent as set by Ministers.
In addition to your internal accountabilities, SROs for GMPP projects and programmes are personally accountable to Parliamentary Select Committees. This means that, from the date of this letter, you will be held personally accountable to and could be called by Select Committees to account for and explain the decisions and actions you have taken to deliver Making Tax Digital Programme.
It is important to be clear that your accountability relates only to implementation, within the agreed terms in this letter; it will remain for the Minister to account for the relevant policy decisions and development.
More information on this is set out in Giving Evidence to Select Committees - Guidance for Civil Servants, sometimes known as the Osmotherly Rules. Information on the roles and responsibilities of the SRO are detailed in the Infrastructure and Project Authority’s guidance on the role of the senior responsible owner. You should also make yourself familiar with the Government Functional Standard for Project Delivery, the requirements of the Government Project Delivery Framework, and the guidance and requirements for project delivery as set by HMRC.

Time commitment and tenure
This role will require at least 20% of your time to enable effective delivery of the role and execute your responsibilities in full (dual SRO commitment totalling 40%).
You are required to undertake this role until managed closure of the programme is achieved or, by agreement, until delivery of a specific milestone, end of phase or gate is achieved. Progress towards this will be reflected in your personal objectives. Any changes to the agreed time commitment or tenure of the role, as set out above, will require both departmental and Infrastructure & Projects Authority consent.

Objectives and performance criteria
The policy intent supported by this Making Tax Digital Programme is set out in Appendix B.
Any proposed changes to scope which impacts on this intent or the realisation of benefits must be authorised by HMRC Change Portfolio and may be subject to further levels of approval.
The objectives and vision of the project, together with your personal objectives and performance criteria are also set out within Appendix B.
You are expected to run your project in accordance with the Government Functional Standard for Project Delivery, the other Functional Standards as applicable to this Making Tax Digital Programme and the requirements of the Government Project Delivery Framework.

Extent and limit of accountability
Finance and Controls
HM Treasury spending controls will apply on the basis set out within the department’s delegated authority letter. Where the Making Tax Digital Programme exceeds the delegated authority set by HM Treasury, the Treasury Approval Point process will apply, and the details of each approval process must be agreed with your HM Treasury spending team. You should consult departmental finance colleagues on how to go about this.
You should note that where expenditure is considered novel, contentious, repercussive, or likely to result in costs to other parts of the public sector, HM Treasury approval will be required, regardless of whether the programme expenditure exceeds the delegated authority set by HM Treasury. If in doubt about whether approval is required you should, in the first instance, consult departmental finance colleagues before raising with the relevant HM Treasury spending team.
The overall estimated budget, resourcing requirements and tolerances for your project/programme will be agreed as part of the approval process.  You will be expected to deliver within these tolerances and report quarterly on these as part of GMPP reporting.
You should operate at all times within the rules set out in Managing Public Money. In addition, you must be mindful of, and act in accordance with, the specific HM Treasury delegated limits and Cabinet Office controls relevant to Making Tax Digital Programme. Information on these controls can be found here: Cabinet Office controls.
In accordance with the guidance on managing public money, the SRO must advise the Accounting Officer of any significant issues relating to regularity, propriety, feasibility and value for money, as well as any significant deviations from the approved business case, which might lead them to reassess the project.

Delegated authority
You are:
authorised to approve expenditure in line with the funding agreed by ExCom (via its sub-boards), or other authorised bodies and individuals under HMRC financial governance;
responsible for ensuring that where a change impacts on the scope, costs, benefits or planned delivery milestones agreed as part of an approved Business Case, it is dealt with via the HMRC Change Portfolio; and
Required to recommend to HMRC Executive Committee, via its sub-board, the need to either pause or terminate the programme where necessary and in a timely manner.
These authority limits are subject to change and other conditions or tolerances may be set as part of the business case approval and ongoing monitoring processes which you should then operate within.
Where issues arise which take you outside of these authority limits which you are unable to resolve, you are responsible for escalating these issues to the ExCom, via its sub-board, as appropriate.

Appointments
You should appoint a full time programme director to support you in the management of this Making Tax Digital Programme and make other appointments as required for the control and delivery of your programme within your delegated authority.

Governance and assurance
You should pay attention to ensuring effective governance for your programme, including the establishment of a programme board with appropriate membership and clear terms of reference.
As primary owner, you must ensure that the Making Tax Digital Programme secures business case approval from HMRC Investment Board, HMRC Change, Assurance and Investment Board, HM Treasury and Cabinet Office. You should also ensure that the Making Tax Digital Programme remains aligned to the strategic outcomes, costs, timescales, and benefits in line with the approved business case as well as monitoring the context within which the programme is being delivered to ensure it remains valid.
Where a change impacts the scope, costs, benefits, or planned delivery milestones agreed as part of an agreed business case, you are responsible for following the agreed change request approval process and setting a new, approved, business case baseline.
You should ensure that an accounting officer assessment is completed alongside the approval of the Outline Business Case and that this is published on GOV.UK as part of the government’s transparency requirements on major projects. You are responsible for bringing to the attention of the accounting officer any material changes in the programme which could require a new accounting officer assessment to be completed and published. Guidance on completing accounting officer assessments for major projects is available from HM Treasury.
Although you are directly accountable for this programme, you are also expected to support delivery of the department’s overall strategic objectives. This means that you are expected to work collaboratively with other SROs and project directors in adjacent projects and programmes and with the HMRC Major Change portfolio management office and portfolio director to manage dependencies, resources, schedules, and funding to support delivery of the overall change the department needs to achieve its strategic objectives.
You should ensure that appropriate and proportionate assurance is in place and agree on the level and frequency of assurance reviews through the maintenance of an integrated assurance and approvals plan. You should develop this plan and its maintenance in collaboration with the Departmental Assurance Coordinator and the Infrastructure and Projects Authority.

Making Tax Digital Programme status, reporting and transparency requirements
The Making Tax Digital Programme status at the date of your appointment is reflected in the most recent quarterly return on the programme to the Infrastructure and Projects Authority and is the agreed position as you assume formal ownership of the programme.
You are responsible for ensuring the honest and timely reporting on the position of the programme to the Infrastructure and Projects Authority while it remains on the GMPP and for providing reports and information to the HMRC Major Change portfolio management office as required. To help meet the government's Net Zero ambition this reporting will start to include carbon measurement.  Information on the programme will be published annually by the Infrastructure and Projects Authority.

Development and support
As your joint SRO is an MPLA graduate and an accredited Master Practitoner, we do not expect you to undertake the Major Projects Leadership Academy but we do ask that you undertake appropriate SRO training to provide the core learning for the role. This could be undertaking the Orchestrating Major Programmes course for Director Generals or the SRO fundamentals course.
The department will assist you in securing the necessary resources to support the Making Tax Digital programme, and will set clear guidance, requirements and standards, which align to the Government Functional Standard on Project Delivery, to enable good governance and effective delivery. You will be part of the department’s cohort of major project leaders who will be expected to support each other, share good practice and lessons learned and to collectively develop solutions. You should liaise with the current Government Head of Project Delivery Function at the IPA (Nick Smallwood) to discuss maintaining and enhancing your personal programme delivery skills.
The Infrastructure and Projects Authority will be available to you for support, advice, and assurance throughout the programmes time on the GMPP.
HMRC Executive Committee will provide ongoing oversight and support and will take steps to help resolve and escalate risks, issues or constraints that are acting as a blocker to successful delivery.
We would like to take this opportunity to wish you every success in your role as SRO.
Yours sincerely,

JIM HARRA		NICK SMALLWOOD

Chief Executive / HM Revenue & Customs		Chief Executive Officer / Infrastructure and Projects Authority

CONFIRMATION OF ACCEPTANCE OF APPOINTMENT

I confirm that I accept the appointment of Senior Responsible Owner for the Making Tax Digital Programme, including my personal accountability for implementation, as set out in the letter above.

Jonathan Athow

31 May 2024