Terms of reference
An evaluation draw-down service for FCDO’s Evidence Fund
July 2024
Purpose
The purpose of this draw-down contract is to generate a set of project-level evaluations of the work of the Evidence Fund. The Evidence Fund facilitates access to new research among FCDO staff and their national counterparts on a demand responsive basis. The Fund produces primary research, including thematic and portfolio evaluations, and secondary research, particularly rapid reviews.
Each project-level evaluation conducted via the service should focus on a single Evidence Fund project – or a cluster of similar projects – and answer one or more questions about the relevance, coherence, efficiency, effectiveness, impact and/or sustainability of projects (OECD, 2021).
The project-level evaluations are intended to inform FCDO’s understanding of when and for whom this form approach to increasing evidence use works, and how best to implement and complement such support. Evaluations produced via the draw-down service will likely be brought together in a final portfolio evaluation as the programme comes to an end (currently planned for March 2027) and will influence the design of successor initiatives.
Additionally, FCDO may require others forms of evaluative activity to be conducted via the draw-down service, potentially including evaluability assessment, the aforementioned portfolio-level evaluation and value for money analysis.
Background
FCDO’s Evidence Fund is a vehicle for commissioning primary research, thematic and portfolio evaluations, and systematic evidence synthesis on a demand-responsive basis. Research commissioned through the Evidence Fund responds directly to the evidence needs of FCDO staff and/or their national counterparts in the geographies in which FCDO works. Outputs are typically produced within 6-12 months of a request for evidence.
Evidence Fund activity can be divided into discrete instances of support to users – or projects. Each project involves the external commissioning of a piece of research tailored to the needs of the expected user, for example, an FCDO policy team or a government ministry in a low- or middle-income country. A proportion of this research is global in scope – particularly commissioned evidence synthesis – while a large part is focused on FCDO’s geographic priorities in sub-Saharan Africa and the Indo-Pacific. Topics of research include HMG’s international development priorities – see HMG (2023) – and those on the foreign policy and diplomatic side of the business.
The Evidence Fund has delivered more than 100 pieces of research to date since the start of implementation in 2020. Examples of research produced through the Evidence Fund include:
- Strengthening inclusive education in the Rwandan education system
- Re FORM: lessons for urban governance futures from the pandemic
- Climate smart agriculture thematic review
- Rapid evidence assessment on the impacts of climate change on migration patterns
Teams conducting the research are commonly employed by universities, think tanks and/or private sector organisations with research expertise. The Evidence Fund is managed by an experienced group of FCDO staff in evidence brokering and commissioning roles, FCDO programme management staff, and an external fund manager. This group:
- Solicits and shapes requests for research.
- Sets out the requirements for the research in the form of terms of reference.
- Launches and manages procurement of research partners.
- Facilitates interaction between users and research teams.
- Quality assures outputs.
- Supports consideration and application of research findings to policy problems.
- Manages the financial and legal elements of projects, among other contributions along the user pathway.
The use of research evidence in decision-making is often the targeted distal outcome of Evidence Fund projects – and enhanced international development or diplomacy outcomes is the intended impact.1 Projects aim to achieve this by influencing the proximal outcomes: capability, opportunity and motivation to use research, commonly considered requisite for behaviour change, largely through enablement (Michie et al., 2011). They may do this via a number of theorised channels, or mechanisms, outlined by Langer et al. (2016):
- Building positive attitudes towards evidence use.
- Generating agreement on policy-critical research questions and the evidence needed to answer them.
- Communicating and providing access to evidence.
- Interaction and relationship-building between researchers and decision-makers.
- Developing skills among decision-makers in identifying and using evidence.
- Influencing decision-making structures and processes.
Projects perhaps most commonly seek to increase evidence use by enhancing policy-makers opportunity to use evidence via generating agreement on evidence needs, providing access to evidence and facilitating researcher-user interaction.
Projects, while united by a common primary outcome and several key elements, such as the production of research, will, however, be implemented in very different contexts, combine different components and produce different outcomes to differing extents. The variety of tasks required, the range of expertise required to successfully deliver support, and the flexibility those involved are permitted means Evidence Fund projects are complex interventions with unpredictable effects (Skivington et al., 2021). As a result, the Evidence Fund will work for some groups, in some contexts, some of the time. By building a bank of project-level evaluations, the draw-down service will support FCDO to begin to understand when, for whom and why (or why not) the Evidence Fund increases the use of evidence in FCDO and among our partners.
More information on the programme can be found on its DevTracker page.
Methods
The delivery partner will propose a tailored approach to each request and lead the delivery and publishing of project-level Evidence Fund evaluations. This involves different streams of work:
Phase 1: Inception - developing the service (September-October 2024)
During the inception phase, the delivery partner will need to consider:
- Building understanding of the intervention and its delivery:
  - Review key Evidence Fund documents.
  - Speak with key stakeholders.
  - Build a sense of the pipeline for project-level evaluations.
- Prioritisation and refinement of requests:
  - Developing a format in which requests should be received.
  - Establishing criteria for prioritising requests.
  - Developing an approach for working with requesters to refine objectives and research questions.
- Methodological approaches:
  - Setting out how appropriate methodological approaches will be identified for each project-level evaluation.
  - Developing an approach to estimating skill and time requirements for project-level evaluations.
  - Determine whether and how ethics approval will need to be sought.
- Mobilisation of expertise:
  - Determine how appropriate expertise will be identified and mobilisation, potentially at relatively short notice.
  - Possibly, build an ex-ante network of experts and/or sources of knowledge on research evaluation.
  - Consider how FCDO staff will be involved in the design and delivery of evaluations.
- Outputs and formats:
  - Determine what kind of outputs will be produced in what formats, and how this will flex according to demand from users.
  - Specify standards for quality and comprehensiveness of outputs.
- Peer review:
  - Establish a process for peer review of project-level evaluations.
  - Develop a protocol for the peer review process to ensure credibility and reliability.
  - Identify and engage potential peer reviewers.
- User support:
  - Establish how user will be supported to digest and apply the findings of project-level evaluations.
- User feedback mechanism:
  - Design a system for collecting and analysing user feedback.
  - Consider how feedback to continuously improve the service.
- Timelines and reporting:
  - Develop a reporting mechanism to keep FCDO updated on progress.
  - Schedule regular review meetings with FCDO stakeholders.
- Risk management:
  - Identify potential risks and develop mitigation strategies.
  - Regularly review and update the risk management plan.
  - Identify potential risks associated with subcontracting and develop mitigation strategies.
  - Establish contingency plans to address any issues or failures in subcontractor performance.
  - Be aware of potential coordination challenges and establish robust mechanisms to manage them.
  - Clearly define accountability for both the delivery partner and subcontractors to avoid any ambiguity in responsibilities.
- Confidentiality and data protection:
  - Ensure that confidentiality agreements are signed by all subcontractors.
  - Outline data protection policies and ensure subcontractors comply with relevant regulations.
- Compliance and ethics:
  - Ensure that the service complies with all relevant ethical guidelines and regulations.
  - Develop a compliance checklist and process for conducting regular audits.
An inception report addressing the point above will be the output of this first phase.
Phase 2: Implementation – delivering project-level evaluations
Delivery of evaluation will be the delivery partner’s primary task. Each evaluation will require a tailored approach to be set out in a protocol. To develop an approach, the delivery partner will need to engage with FCDO staff involved in project delivery to understand the nature of the project, review project materials, develop specific research questions and discuss possible methods. The number of evaluation questions for each evaluation should number no more than three. Effectiveness and sustainability are the criteria most likely to be the focus of project evaluation.
There are a range of methods that could be suitable for evaluating the effectiveness and sustainability of Evidence Fund projects. These include both “forward tracing” and “backward tracing” approaches (Newson et al., 2018).
Potentially appropriate methods that trace forwards from evidence brokering and the delivery of demand-responsive research to policy impacts include many of the theory-based approaches set out in the Magenta Book (HMT, 2020). The only evaluation of Evidence Fund support to date used outcome harvesting, for example (Achillini & Burge, 2024). Other common theory-based methods, such as contribution analysis (Riley et al., 2018), and process tracing (Delahais & Toulemonde, 2017), have been used to evaluate the impact of research. Quantitative methods have also been used in the evaluation of evidence brokering and commissioning (Moore et al., 2017; Wilson et al., 2017).
Approaches that begin with policy outcomes and trace backwards to identify the influence of research on decision-making are less frequently codified. New approaches continue to be developed, for example decision sampling (Mackie et at., 2021) and knowledge utilisation analysis (Jørgensen, 2024). Given evaluation of research and evidence brokering is an evolving field, delivery partners are welcome to innovate and develop new approaches as long as data collection and analysis methods are systematic, and minimising threats to validity is a central consideration.
The impact of research output on development and diplomatic outcomes is of considerable interest to FCDO, as these areas are critical to its objectives. However, they are also among the most challenging aspects to measure. Therefore, the FCDO would welcome any suggestions or methodologies that delivery partners can offer to assess these impacts. External expertise and innovative approaches in this area will be instrumental in helping the FCDO achieve a more comprehensive understanding and evaluation of its efforts
The method or combination of methods chosen for each evaluation will depend on the project-specific research questions, the nature of the project and existing knowledge. Evaluations for a number of specific projects are currently envisioned, including:
- A prospective new service within the Evidence Fund for delivering demand-responsive rapid reviews to FCDO staff (see here).
- An ongoing piece of research into security-sensitive issues in the Middle East.
- An evidence gap map on conflict and atrocity prevention interventions, and supplementary outputs designed to support users.
- FCDO funding to support the development of the kelp sector in South Africa.
These project-level evaluations are unlikely to require in-person data collection. The delivery partner should consider the need for ethics approval for each project-level evaluation.
Ideally, the service would offer roles in evaluations teams to FCDO staff interesting building evaluation capability. This may include members of FCDO’s evaluation cadre as well as research advisers working within the Evidence Fund. Evidence Fund staff would not be part of research teams evaluating projects that they helped to deliver.
Phase 2 deliverables include:
- Protocols for individual project-level evaluations.
- Publishable reports for each project-level evaluation.
- Ideally, several published journal articles.
Final outputs of all evaluations of Evidence Fund projects involving ODA-funded research are expected to be published on the relevant gov.uk website. Further publication in academic journals – both papers focused on the findings of evaluations and those on evaluation methods – will be encouraged and facilitated through the contract to increase wider stakeholder knowledge of the effects of demand-responsive research services and methods to evaluate them. Appropriate venues may include Evidence & Policy, Health Research Policy and Systems, Research Evaluation, Systematic Reviews, and Implementation Science.
Evaluations of sensitive projects involving non-ODA research are not expected to be published.
It should be noted that additional evaluation activities may be requested by the Evidence Fund. These may include:
- Evaluability assessments, particularly for portfolio-level effectiveness, value for money and process evaluations.
- A final portfolio evaluation drawing the individual project-level elevations produced via this service focused on effectiveness.
- Process and value for money evaluation.
Additional evaluation activity, where agreed, will produce further outputs. The scope and timing of this work will be discussed and agreed between FCDO and the delivery partner.
Budget and timeline
The total budget for the draw-down service is up to £500,000. This covers all costs involved in setting up and delivering the service. Each project-level evaluation is expected to cost between £10,000 and £50,000. The service is expected to deliver a minimum of 10 evaluations.
It is currently envisioned that inception will begin in autumn 2024, and the service will begin delivering evaluations before the end of the calendar year or in early 2025. Evaluations of multiple projects may need to be conducted simultaneously. The service is expected to run until the end of the Evidence Fund in March 2027.
The Evidence Fund reserves the right to expand or extend the scope of services provided by the delivery partner. This potential expansion or extension may be particularly relevant if the end date of the Evidence Fund is extended. The expanded scope may include additional evaluation activities as discussed above.
Requirements of delivery partner
- Significant experience conducting research on evidence use in public policy and administration.
- Expertise in a range of potentially appropriate “small n” impact evaluation approaches. Process and economic evaluation would be an advantage.
- Experience producing research for national or international governmental organisations.
- At least one team member with security clearance or a commitment to obtain security clearance (ideally to DV level) to enable evaluation of sensitive non-ODA research delivered by the Evidence Fund.
Technical proposals should briefly set out how the delivery partner(s) will design and deliver the service. They should include names and profiles of personnel involved in delivery and their roles (CVs can be included in an annex).
Technical Evaluation criteria
Technical proposals, which should not exceed 15 pages (excluding CVs), will be evaluated against four core criteria: (1) experience and expertise in evaluation, (2) proposed methodology and approach, (3) team composition and qualifications, and (4) quality assurance and risk management.
Table 1. Technical selection criteria
Criteria	Sub-criteria	Weighting
Experience and expertise in evaluation	Methods expertise, particularly in theory-based evaluation; experience of conducting research on evidence use in public policy and administration.	40%
Proposed methodology and approach	Understanding of the terms of reference; approach to working with FCDO to design and deliver the service; knowledge and appropriate application of relevant evaluation methods.	40%
Team composition and qualifications	Team Structure and roles.	10%
Quality assurance and risk management	Quality assurance processes; risk management.	10%

Commercial Evaluation
The commercial aspect of the proposals will account for 20% of the overall scoring. This will be broken down as follows:
- International Rate Card (10%): 50% of the commercial score will be based on the supplier’s international rate card. Suppliers are required to submit their rate card, which will be evaluated for competitiveness and cost-effectiveness.
- Costing of Example Project-level evaluation (10%): The remaining 50% of the commercial score will be based on the costing of an example project-level evaluation, as detailed in Annex B. Suppliers are required to provide a detailed budget for the example project, which will be assessed for accuracy, feasibility, and value for money.
Bidding process
Technical and commercial proposals for the Rapid Review draw-down service should be sent as two separate files to by uk_evidence_fund_administration@pwc.com (17:00 GMT). Since these will be assessed independently of each other, they should, in no case, be combined or cross-referenced.
The instructions for submitting the tender and details on scoring methodology and evaluation criteria are detailed in ITT Volume 1. The application forms for submitting the technical proposal (sent as a clearly titled PDF file) are detailed in ITT Volume 3 and ITT Volume 4 provides the Pro Formas for the commercial proposal.
Administrative arrangement
The study will be supported through The Evidence Fund, an FCDO programme intended to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2022, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects, conduct due diligence assessments on prospective sub- contracted Research Pool providers, where relevant, and manage research and evaluation contracting.
Constraints & dependencies
The Crown will retain all intellectual property right to any outputs, evidence and knowledge products produced by the service.
The outputs of the supplier will not use any dedicated branding but the standard branding and logos of FCDO.
Duty of Care
The supplier is responsible for the safety and well-being of their Personnel and Third Parties affected by their activities under this contract, including appropriate security arrangements. They will also be responsible for the provision of suitable security arrangements for their domestic and business property.
Please note, it is assumed that no travel will happen for the purposes of this review and that it will be conducted virtually, meaning that no face-to-face interviews should happen, and presentations should be given virtually, where required.
Delivery Chain Mapping
In advance of any release of funds, the Supplier will be required to produce a ‘delivery chain risk map’ which should, where possible, identify all partners (funding and non-funding e.g. legal/contributions in kind) involved in the delivery of this study. This is applicable only if the lead organisation engages downstream partners/subcontractors.
Safeguarding
FCDO places utmost importance on all potential partners’ ability to safeguard children, young people and vulnerable adults they work with from sexual exploitation and abuse, and their ability to protect staff and volunteers. The Supplier Code of Conduct will be included in the terms and conditions of the Contract. New compliance checking mechanisms are now in place to review supplier documentation, their approaches to legal compliance and demonstration of good practice in meeting international principles on labour and ethical employment and to provide assurance that whistleblowing systems are accessible across delivery chains. FCDO will monitor risk and mitigation plans throughout the project cycle. The commitments made by all organisations in receipt of FCDO funding need to provide spending teams with concrete assurance that the new enhanced safeguarding standards are being applied. The approach will help to promote the adoption of new standards for all organisations in the aid sector.
Ethical principles and standards
Suppliers are required to refer to ethical guidelines available at https://www.gov.uk/government/publications/dfid-ethical-guidance-for-research-evaluation-and-monitoring-activities. Bidders should include a statement in their proposals, confirming that the study will comply with ethical guidelines as mentioned above. This is a mandatory requirement.
Research for Development outputs (R4D)
FCDO requires that all final research output(s) from this funding are uploaded to Research for Development Outputs (R4D) on GOV.UK. By law documents published on GOV.UK must comply with the  Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.  This is so they can be used by as many people as possible, including those with disabilities. Further information on open document formats and content accessibility on GOV.UK can be accessed here  https://www.gov.uk/guidance/content-design/planning-content.  Uploading final output(s) to Research for Development Outputs on GOV.UK does not exclude these outputs from being uploaded to other websites or platforms and repositories.
General Data Protection Regulations (GDPR)
Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Annex 1, and the standard clause 30 in section 2 of the contract.

Annex A
Schedule of Processing, Personal Data and Data Subjects
This schedule must be completed by the Parties in collaboration with each other before the processing of Personal Data under the Contract.
The completed schedule must be agreed formally as part of the contract with FCDO and any changes to the content of this schedule must be agreed formally with FCDO under a Contract Variation.
Description	Details
Identity of the Controller and Processor for each Category of Data Subject	The Parties acknowledge that for the purposes of the Data Protection Legislation, the following status will apply to personal data under this contract: / The Parties acknowledge that Clause 30.2 Protection of Personal Data and 30.4 (Section 2 of the Below Threshold contract) shall not apply for the purposes of the Data Protection Legislation as the Parties are independent Controllers in accordance with Clause 30.3 in respect of Personal Data necessary for the administration and/or fulfilment of this contract”.

Annex B
Example Project-level evaluation
Please refer to the fictional project below and complete Volume X, example Commercial Pro Forma of the application form.
Project Title:
Project-level evaluation of Climate Adaptation Strategies for Smallholder Farmers in Sub-Saharan Africa
Project Overview:
The FCDO Research Hub in South Africa has commissioned research on climate adaptation strategies for smallholder farmers in Sub-Saharan Africa. The objective of this project-level evaluation is to evaluate the effectiveness and impact of the research. The selected supplier will be responsible for conducting a project-level evaluation, collecting and analysing data, and presenting the findings within a three-month timeframe.
Scope of Work:
Project Planning and Design:
- Develop a detailed evaluation protocol, including objectives, methodology, and timeline.
- Select appropriate case study participants (FCDO research hub in SSA, FCDO research users).
Data Collection:
- Conduct qualitative interviews with selected stakeholders.
- Gather secondary data from existing research.
Data Analysis:
- Analyse qualitative data using appropriate methods to identify common themes and patterns.
- Synthesise findings to draw comprehensive conclusions.
Reporting and Presentation:
- Prepare a case study outlining the evaluation methodology, findings, and recommendations.
- Present findings to key stakeholders in a clear and engaging manner.
- Provide actionable recommendations for improving the effectiveness of the research.
Deliverables:
- Evaluation protocol and timeline
- Interview instruments
- Data collection summary (interview transcripts)
- Final comprehensive case study with findings and recommendations
- Presentation slides for stakeholder meeting
Cost Proposal:
Potential suppliers are requested to provide a detailed cost breakdown for the following:
1. Question refinement and methodology development
2. Data collection and analysis
3. Reporting and dissemination
4. Fee Rates
5. Total project cost