TERMS OF REFERENCE

Promoting Export-led Economic Transformation under the SACUM/UK Economic Partnership Agreement

Background

Trade is a pre-requisite for development which creates jobs, stimulates investment, attracts technology, and generates foreign exchange to service debt and access global public goods. Few countries have shown sustained growth or reduction in poverty levels without significant growth in trade flows[1]. Developing countries that are open to trade and have embraced comprehensive trade liberalisation have been shown to benefit from faster economic growth and have seen incomes that are 10-20% higher than those in other less open economies after a decade[2]. Since 1990, developing countries have increased their share in global exports from 16% to 30%, helping to cut the proportion of the world’s population living in extreme poverty from 36% to 9%[3].
[1] Higgins, K., Prowse, S. (2010) ‘Trade, growth and poverty: making Aid for Trade work for inclusive growth and poverty reduction’
[2] Irwin, D. (2019) ‘Does Trade Reform Promote Economic Growth? A Review of Recent Evidence’
[3] WB, WTO (2020) Role of Trade in COVIDv3 (wto.org)

The preferential trading arrangements afforded by the SACU+M/UK Economic Partnership Agreement[4] (EPA) can be an important tool for economic development in the Southern African Customs Union (SACU) and in Mozambique through export growth. However, not all flows of trade and investment are equal in their potential to support development outcomes. How trade is promoted also matters to ensure more people can participate, losses are mitigated, and the largest gains accrue most to the poorest and more vulnerable segments of society. The benefits of trading under an EPA may not be used in practice, and there is limited evidence[5] on what improvements to the EPA over time would effectively promote inclusive, sustainable, export-led economic transformation in the SACU and in Mozambique.
[4] SACUM-UK economic partnership agreement (EPA) - GOV.UK (www.gov.uk)
[5] The ongoing review of the EU/SADC EPA study outputs are published: Resources (fta-evaluation.eu)

Project Scope / Objectives of the study

The EPA commits the UK to development cooperation with Mozambique and the SACU. This includes UK support to implementation of the Agreement through appropriate and effective UK funding mechanisms, in consultation with SACU partners and Mozambique (Article 12 of the EPA). Since the EPA entered into force in 2021, the FCDO has provided a small number of short-term, targeted interventions to support the Agreement’s implementation. Now, the FCDO wishes to learn lessons from these interventions and other relevant programming[6], additional robust analysis, and be further guided by requests from our partners in the SACU and in Mozambique to honour these commitments for the benefit of inclusive, sustainable economic transformation in the region.
[6] Programme Completion Review and other materials from the Southern Africa Trade Programme will be provided

So, essentially, the exam question is ‘what works’ with UK partners in the SACU+M/UK EPA to promote jobs and improved livelihoods for the poorest and most vulnerable across the region through export growth and diversification. The study should focus on Botswana, Eswatini, Lesotho, Namibia and Mozambique, given a separate, complementary South Africa focussed research project. The study should address:

- Which (goods and services) sectors and specific value chains[7] should the UK focus on to promote inclusive growth and poverty reduction in Mozambique and the SACU? A robust framework for this assessment should be in evidence (i.e., analysis of political economy, feasibility, job creation, sectoral linkages, product complexity, inclusion, gender, and environmental factors) and provide a basis for potential replication of the value chain identification exercise to other geographies.
  [7] As an illustrative example, a focus on high-value agriculture and agri-processing exports from Mozambique, specifically coffee
- What should the UK do to stimulate imports from Mozambique and the SACU in areas of UK demand to best promote inclusive, effective, and sustainable export-led development across the region (e.g. market access improvements, capacity building?)
- How do these recommendations translate into implementation of, and future improvements to, the SACU+M/UK EPA?
- How should these interventions be designed to support intra-regional trade, including promoting trade the under the African Continental Free Trade Area (AfCFTA), and complement wider UK policy and programmatic efforts on trade for development, including the UK Developing Countries Trading Scheme (DCTS)[8] and Growth Gateway[9].
  [8] The DCTS cuts tariffs, removes conditions and simplifies trading rules for 65 developing countries, including Lesotho and Mozambique.
  [9] Growth Gateway connects UK and partner country business across Africa to UK government trade and investment initiatives and provides export advice and online information tools to support their trade and investment journeys.

The primary recipients of this project will be British High Commissions in Botswana, Eswatini, Lesotho, Namibia and Mozambique, and the FCDO-DBT Trade for Development Department. These audiences are intended to use the project deliverables to:

- Inform implementation and future improvement of the SACU+M/UK EPA, including delivering on the Agreement’s development cooperation commitments and during upcoming reviews, and to complement wider UK trade policy development, including the DCTS and support for the AfCFTA.
- Inform the Trade Centre of Expertise[10] delivery and other programmatic interventions by posts across the region and/or centrally managed programmes focussed on export promotion.
  [10] See more on the planned Trade Centre of Expertise in the ICAI follow-up report on Aid for Trade (May 2024) ICAI follow-up review of 2022-23 reports - ICAI (independent.gov.uk)

Specialist knowledge of the region is required, as well as the skills and proven experience to assess how trade policy and programmes successfully drive export promotion for the benefit of inclusive, sustainable growth. The focus is on the geographies of Botswana, Eswatini, Lesotho, Namibia and Mozambique (as the UK’s partners in the SACU+M/UK EPA, along with South Africa, where a separate programme is underway) and the poorest and most vulnerable segments of the population whose livelihoods can be supported through intra-regional and international trade over the medium term.

Methodology

A desk-based literature review is envisaged prior to visits in Botswana, Eswatini, Lesotho, Namibia and Mozambique. Quantitative assessment and evaluation of export trends, potential and development impacts will be required, based on a rigorous assessment of the literature and available data to evidence the theory of change from trade policy and programmatic interventions to developmental impacts (i.e., jobs, livelihoods). Qualitative assessment and evaluation of the expected development benefits of potential new programmatic interventions, regulatory engagements, and improvements to the SACU+M/UK EPA is also expected. The literature review will make use of previous relevant, systematic, reliable evaluations on trade for development programmes by the UK and other partners, e.g. the EU, in the southern African region[11]. Details of previous programming related to the SACU+M/UK EPA, and additional requests for support from the SACU Secretariat and governments across the region, will also be provided. During in-country visits, interviews and focus groups with stakeholders from government, private sector, academia, and civil society are expected.
[11] E.g. ICAI review on UK Aid for Trade (2023), DFID trade development work in Southern Africa (2013), World Bank research on Deep Trade Agreements, Harvard Growth Lab diagnostics (including on Namibia), UN Library Articles (e.g. on North-South participation in global value chains), Trade Mark Africa publications.

Uptake and Dissemination

The research outputs should inform engagement with government, private sector enterprises and civil society across Mozambique and the SACU, in addition to the primary audience. The supplier should support a sustainable process for this uptake and engagement through providing, alongside the final research report, the following or similar engagement materials:
- Presentation (slides and recording, hosted on an easily accessible channel e.g. YouTube)
- Infographics or other easily accessible and digestible summaries of key findings and recommendations
- Participation in study launch events, workshops or similar (e.g. hybrid webinars) advertised and tailored inclusively across the different (geographical, professional, language) audiences.

Administrative arrangement

The study will be supported through The Evidence Fund, an FCDO programme intended to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes. In 2022, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects, conduct due diligence assessments on prospective sub- contracted Research Pool providers, where relevant, and ​​​​manage research and evaluation contracting.

Time frame, deliverables, and budget (upper limit)

ITT speculative timeline

Activity	Timeline
ITT Sent to Suppliers and published on Funding Finder	Monday 12th of August 2024
Deadline for Clarification Questions	Friday 16th of August 2024, at 4 pm Central Africa Time
Clarification Responses	Tuesday 20th of August 2024
Deadline for Applications	Monday 26th of August 2024 at 4 pm Central Africa Time
Anticipated Award Date	Monday 2nd of September 2024
Due Diligences and contract signing process	7 to 10 working days
Inception meeting with supplier	TBD

Deliverables
The study should be completed in a period of 10-12 weeks, starting September 2024. The delivery plan will be as per the table below:

Milestone	Deliverable	Delivery timelines ​​
Output 1	Project Initiation Plan / Steps towards this output to align with suggested methodology, but could include: / Project initiation meeting / Agree parameters of desk review and identify key documentation / Agree list of topics to cover in interviews/focus groups and identify key respondents / Submit draft project plan / Agree project plan	Week 1
Output 2	Interim Report / Steps towards this output to align with suggested methodology but could include: / Complete the desk-based literature review / Summarise emerging findings from above into interim report and present to FCDO, prioritising the identification of specific value chains and with early recommendations for policy and programmatic interventions based on evaluation of previous support and requests from the SACU and Mozambique	Week 3
Output 3	End of Project Report / Steps towards this output to align with suggested methodology but could include: / Complete and analyse interviews/focus groups / Bring together all findings (inc. desk review) into draft final report and submit to FCDO / Meeting to present findings to core FCDO project team / Revise draft report post-meeting / comments receipt / Submit final report with concrete policy and programmatic recommendations	Week 9
Output 4	Dissemination products (all in English and Portuguese): / Full report / Executive summary report / PowerPoint deck summarising the project / Infographics summarising key findings and recommendations / Recorded seminar, in English with Portuguese translation, presenting key findings and providing opportunity to discuss with primary audience and external stakeholders	Week 10

Budget (upper limit)

The total budget for the study should not exceed £150,000 excluding taxes. Costs of workshops should be explicitly built into the budget.

Skill Requirements / expertise needed

Local knowledge, sensitivities, and expertise working in Botswana, Eswatini, Lesotho, Namibia, and Mozambique in the areas outlined below:
- Significant experience and proven impact through similar studies focussed on value chain/sectoral development.
- Expertise related to trade policy/agreements, facilitation, and programming.
- Expertise in trade and climate policy and programmes, so recommendations are centred on sustainable approaches to development.
- Skills and capacity convene representative stakeholders ensuring an inclusive approach, focussed on improving outcomes for the poorest.
- Delivery of robust, policy applicable research that is value for money and can inform practical recommendations.
- Gender and conflict sensitive approach to research.

Bidding process

Tenders must be sent to the e-mail address of the Evidence Fund Manager:
evidence.fund@integrityglobal.com

Your Tender should be submitted in English and be set out in 3 main parts (A, B, & C) along with the letter and declaration to accompany tenders (Volume 8), as outlined below.

Letter and Declaration to Accompany Tenders (Volume 8)
Part A - Application (to include Forms A, B, C, D & E from Volume 3)
Part B - Technical (to include Form F from Volume 3 and Long Form CVs)
Part C - Using the Commercial Proformas provided in (Volume 4) in both excel and .pdf formats

Electronic File size per submission, must not exceed 10MB.

Tenders must be sent to the e-mail address of the Evidence Fund Manager evidence.fund@integrityglobal.com. The Tender covering e-mail must state the following:
- ITT Title
- Due Date of Tender
- Name of Tenderer

For clarifications regarding this ITT, please submit questions on or before the request for clarification deadline of Friday 16th of August 2024, at 4 pm Central Africa Time. We shall revert thereafter on Tuesday 20th of August 2024.
Participating in this ITT or winning the contract will not exclude the entity from bidding or taking part in projects related to the delivery of any forthcoming programme in this subject area. Additionally, all outputs from this project will be publicly available.

Duty of care

The Supplier is responsible for the safety and well-being of their personnel and relevant third parties affected by their activities under this assignment, including appropriate security arrangements where needed.

General Data Protection Regulation (GDPR)

Please refer to the details of the GDPR relationship status and personal data (where applicable) for this project as detailed in Annex 1, and the standard clause 30 in section 2 of the contract.

Delivery Chain Mapping

In advance of any release of funds, the Supplier will be required to produce a ‘delivery chain risk map’ which should, where possible, identify all partners (funding and non-funding e.g. legal/contributions in kind) involved in the delivery of this study. This is applicable only if the lead organisation engages downstream partners.

Safeguarding

FCDO places utmost importance on all potential partners’ ability to safeguard children, young people and vulnerable adults they work with from sexual exploitation and abuse, and their ability to protect staff and volunteers. The Supplier Code of Conduct will be included in the terms and conditions of the Contract. New compliance checking mechanisms are now in place to review supplier documentation, their approaches to legal compliance and demonstration of good practice in meeting international principles on labour and ethical employment and to provide assurance that whistleblowing systems are accessible across delivery chains. FCDO will monitor risk and mitigation plans throughout the project cycle. The commitments made by all organisations in receipt of FCDO funding need to provide spending teams with concrete assurance that the new enhanced safeguarding standards are being applied.  The approach will help to promote the adoption of new standards for all organisations in the aid sector.

Ethical principles and standards

Suppliers are required to refer to ethical guidelines available at https://www.gov.uk/government/publications/dfid-ethical-guidance-for-research-evaluation-and-monitoring-activities. Bidders should include a statement in their proposals, confirming that the study will comply with ethical guidelines as mentioned above. This is a mandatory requirement.

Climate and environment considerations
The impacts of our changing climate are already affecting many countries where the UK delivers programming. In July 2019, the UK announced a commitment to align all Official Development Assistance (ODA) to the goals of the United Nations Framework Convention on Climate Change (UNFCCC) Paris Agreement. The Government has now committed to ensure that all new bilateral UK ODA aligns with the Paris Agreement in 2023. The UK government will no longer provide any new direct financial or promotional support for the fossil fuel energy sector overseas and it will ensure that relevant programmes do not undermine the ambition in countries’ Nationally Determined Contributions (NDC) and National Adaptation Plans (NAP).
Research for Development outputs (R4D)

FCDO requires that all final research output(s) from this funding are uploaded to Research for Development Outputs (R4D) on GOV.UK. By law documents published on GOV.UK must comply with the  Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.  This is so they can be used by as many people as possible, including those with disabilities. Further information on open document formats and content accessibility on GOV.UK can be accessed here  https://www.gov.uk/guidance/content-design/planning-content.  Uploading final output(s) to Research for Development Outputs on GOV.UK does not exclude these outputs from being uploaded to other websites or platforms and repositories.
Annex 1

Schedule of Processing, Personal Data and Data Subjects
This schedule must be completed by the Parties in collaboration with each-other before the processing of Personal Data under the Contract.
The completed schedule must be agreed formally as part of the contract with FCDO and any changes to the content of this schedule must be agreed formally with FCDO under a Contract Variation.
Description	Details
Identity of the Controller and Processor for each Category of Data Subject	The Parties acknowledge that for the purposes of the Data Protection Legislation, the following status will apply to personal data under this contract: / The Parties acknowledge that Clause 30.2 Protection of Personal Data and 30.4 (Section 2 of the Below Threshold contract) shall not apply for the purposes of the Data Protection Legislation as the Parties are independent Controllers in accordance with Clause 30.3 in respect of Personal Data necessary for the administration and/or fulfilment of this contract”.

Annex 2: Summary Risk Assessment Matrix

Title:  Promoting Export-led Economic Transformation under the SACUM/UK Economic Partnership Agreement
Location: South Africa
Date of assessment: July 2024
Assessing officials: FCDO Programme Team

Theme	FCDO Risk score

OVERALL RATING
FCDO travel advice
Host nation travel advice
Transportation	2
Security	2
Civil unrest	3
Violence/crime	3
Espionage	2
Terrorism	2
War	2
Hurricane	1
Earthquake	3
Flood	3
Medical Services	2
Nature of Project/ Intervention	1

1 / Very Low risk	2 / Low risk	3 / Med risk	4 / High risk	5 / Very High risk
Low		Medium	High Risk