## Slide 1: EMFF Update
Growth Programme Board March 2024

## Slide 2
EMFF COMMITTED & SPEND SUMMARY
Area | EMFF Commitment (£m) | EMFF Spend (£m) | EMFF % Spend vs Committed
Core | £43.1 | £40.1 | 93%
Data Collection Framework | £21.1 | £21.1 | 100%
Control and Enforcement | £15.0 | £13.4 | 89%
A total of 1578 projects funded in the programme period
£83m of EMFF plus £13m National funding committed to projects (includes Core Scheme, Data Collection Framework and Control and Enforcement elements)
£77m EMFF plus £12m National funding spent against projects to end December 2023

## Slide 3
COMMITMENTS AND SPEND – KEY CORE AREAS
Area | Number of projects | EMFF Commitment (£m) | EMFF Spend (£m) | EMFF % Spend vs Committed
Overall Core | 1512 | £43.1 | £40.1 | 93%
Health and Safety | 481 | £2.8 | £2.8 | 100%
Limiting Fishing Impact | 275 | £2.9 | £2.9 | 100%
Adding Value to Catch | 119 | £0.9 | £0.84 | 94%
Ports and Harbours | 123 | £12.8 | £12.4 | 97%
Aquaculture | 54 | £2.7 | £2.6 | 96%
Seafood Processing | 89 | £5.1 | £4.5 | 88%
Human Capital, Training | 22 | £2.5 | £1.9 | 76%
Marine Environment | 64 | £5.4 | £5.3 | 98%
£2.2m further core spend to date in 2024 taking us to present committed vs spend of 98% scheme expenditure to date

## Slide 4: EMFF CORE SCHEME - VOL APPROVED PROJECTS IN POPULAR AREAS
Number of approved projects under the most popular articles

## Slide 5: POST PROJECT MONITORING
Work on Post Project Monitoring (PPM) is ongoing
Projects eligible for PPM at 3 years following final payment date
PPM sampling strategy in place and agreed by Audit Authority and UK Managing Authority
Performance against wide range of project targets and deliverables analysed to provide data to establish the benefits of the scheme in line with Union Priorities and industry need
To date PPM data received in respect of 235 projects

## Slide 6: POST PROJECT MONITORING CONT’D
PPM for 235 projects – cumulative benefits:
  Employment maintained in the seafood industry – >2000 FTE
  Employment created – 62 FTE
  Increased annual net profit - £1.5m
  Estimated reduction in accidents at sea – 51

## Slide 7: Scheme Impact Evaluation
A scheme impact evaluation is required by Article 56 of the Common Provisions Regulation
Completed by external evaluator, Air Quality Consultants (AQC)
Scheme Impact Evaluation Report was submitted to the Commission ahead of the Regulatory deadline of 31 December 2023
Preliminary findings were presented by AQC during the annual meeting with the EMFF Monitoring Committee in October 2023

## Slide 8: Next Steps
Work on closure activities will continue during 2024
On course to submit final Statement of Spend and complete accounts in July 2024
PPM will continue beyond 2024 as projects continue to qualify