## Slide 1
ERDF Update
Growth Programme Board
19th March 2024

## Slide 2
Programme Performance
Programme Commitment 2014-20
The overall commitment level achieved was £3.227bn. This compared to the original programme budget of £2.846bn in 2016, representing a commitment level of 113% original budget.
Regular revisions of the budget due to volatile exchange rates meant in 2022/23, the budget was revised to £3.163bn.
In the final year, efforts were made for additional commitments to manage changing programme values.
These included :
  Project changes agreed for organisations for over 50% of projects to deliver out contracts
  Additional funding to Financial Instruments
  Additional flexibilities for Venture Capital funds for equity investments
Compared to the latest programme value of £3,163bn, this gave an overall commitment of 102%.

## Slide 3
COMMITMENT LEVELS - CATEGORY OF REGION
Category of Region | Allocation (ERDF £) | Commitment (ERDF £) | % Commitment to Allocation
More Developed | £1,809,044,130.94 | £1,887,428,076.33 | 104%
Transition | £944,682,524.72 | £945,967,546.32 | 100%
Less Developed | £408,907,536.39 | £394,150,273.06 | 96%
Total | £3,162,634,192.06 | £3,227,545,895.71 | 102%

## Slide 4
Programme Performance
Programme Expenditure and Claims
A total of 1082 Projects were contracted in the programme overall
The Covid Pandemic meant there were delays in delivery of many projects and after review with the ERDF team, these were given extended time to deliver expenditure and outputs.
This meant over 50% of projects (640) were live in 2023, many extended beyond 3 years
A total of £779m (25% budget) with some 2200 claims was paid out in 2023 which involved a large amount, of claims and assurance work.
A total of 640 (59%) of final claims for projects were paid in 2023
The additional investment in Financial Instruments in 2023 amounted to £120.4m with an additional £62m in equity investments in venture capital funds
Despite the actions to maximise spend and contractual agreements there was some project slippage. Total claims paid were £3.012bn
As of 29th February, 8 claims remain to be paid out of around 14,000 in the programme.

## Slide 5
Performance Framework Expenditure
Targets
Each Priority Axis within a Category of Region had specific performance framework expenditure targets for total expenditure (investment including match funding)
The minimum threshold to meet with the EC was 65%
The programme was revised in 2022 to consider the issues around delivery and implications for the performance framework expenditure
Outcomes
All regions contracted sufficient projects to achieve the minimum Performance Framework expenditure threshold.
All main programme targets have achievement above 65% of the minimum threshold. These are 7 in Less Developed, 6 are Transition and 6 in more developed

## Slide 6
Performance Framework Outputs
Targets
Each Priority Axis within a Category of Region had specific performance framework output targets
The minimum threshold to meet with the EC was 65%
Current position
We still have further outputs to collect as we have some post contract monitoring !
C1: No of enterprises receiving support. | P3: Additional businesses with broadband access min 30Mbps.
C34: Estimated Green House Gas reductions. | P6: Business & properties with reduced flood risk.
C23: Surface area of habitats supported. | C14a: Length of track reconstructed or upgraded roads;
P7: Length of Railway with new/enhanced signalling. | I6: No. of local development strategies in place.

## Slide 7
Performance Framework Outputs
Challenges
Less developed Region
PA2 : P3 Output: Additional businesses with broadband access min 30Mbps. Contracted figure is 64.9%. However, actuals significantly exceed contracts and achieved outputs are 105.9% to PF target
PA4: C34 Output : Estimated Greenhouse Gas Reductions. Contracted figure is (62.0%). Current actuals are 47% to target. The low rate is a result of research projects which deliver a comparatively smaller number of outputs (E.G Geothermal) However we have a project which is due to deliver its outputs in 2024 and will provide sufficient outputs to achieve 78% of the PF target.
PA7 : C14 Roads output : Total length of re-constructed or upgraded roads. Currently for the A30 construction project over 100% of the target has been contracted but no outputs have yet been achieved. The outputs are due to be delivered in June 2024, which will achieve sufficient outputs to exceed the PF target.

## Slide 8
Performance Framework Outputs
Challenges
More developed Region
PA2 :PA5 – P6: Business premises with reduced flood risk. Sufficient outputs had been contracted to meet minimum threshold (contracted was 69.6% to target). However, a project requested to withdraw in May 2023 due to project delays. Removal of the projects contracted outputs resulted in a total of 59.7% to PF target. Total achieved is 56.4%.
In budget terms PA5 represents around £30m of the £4.1bn of investment for More developed region
The challenges in delivering PA 5 have been discussed regularly with the EC. Historically there have been issues with implementation of Priority Axis 5 having been compounded by extreme flooding in 2015/16 and 2019/20 requiring the Environment Agency (EA) to undertake a full review of their activities. This led to delays due to the need to undertake further re-modelling to reflect impacts of climate change before their revised flood risk assessment could be applied to flood-prevention schemes and ERDF projects.

## Slide 9
Covid-19 ERDF Response
Welcome Back Fund
Provided funding to 98% of Local Authorities to support business communities and high streets after Covid-19 lockdowns.
£83m paid out to local authorities to produce local economy action plans
303 outputs achieved against target of 250 – 121% to target
Growth Hubs Support: Visitor Economy and COVID-19 Response Business Support
Additional £30m ERDF for Growth Hubs to provide support to businesses to respond to Covid-19 and to support the visitor economy sector
Funding for 1-2-1 specialist advice or small 100% funded grants for new or adapted equipment
Paid out £28m, supported 8,500 SMEs, C2 outputs, 141 P3

## Slide 10
Evaluation
Phase 3 National Evaluation
Fieldwork concluded and draft reports submitted in Q3 2023.
Comprehensive external peer review of economic analysis required before publication ongoing
To expedite publication of other evaluation material (in particular, What Works and delivery lessons learned), asking for reports to be revised to remove content still under review. Ministerial sub then sent up for approval to publish
Economic analysis then published once data quality meets rigorous standards acceptable for publication
Project Summative Assessment
190 final project summative assessments published externally
Permission to publish a further batch of reports from projects closing in 2023
Plans to create a directory of reports by project type so practitioners can easily find relevant reports
Further Plans for Evaluation
Discussions with analytical team to undertake some further What Works analysis on projects completing in late 2022/23

## Slide 11
Programme Closure Team
Closure team of 33 people in place to manage programme closure requirements, managed by David Read
Remainder of ERDF staff redeployed within DLUHC in Feb 2024
Work Includes :
  Final ECPA to be submitted in May 2024
  Final year of A127 audits
    24 in Semester 1
    13 in Semester 2
    Final Sample to be selected once final ECPA submitted
  Final closure pack to be submitted to the EC by 15th Feb 2025 including :
    Final Implementation Report
    Accounts for final accounting year
    Management Declaration and annual summary
    Audit opinion and control report
  Ongoing project monitoring requirements

## Slide 12: Research and Innovation Support

## Slide 13
Programme Commitments
290 Projects Funded to Deliver R&I Support
£612,437,459
ERDF Spend by Grant Recipients
£644,363,098
ERDF Commitment for R&I Support
£1,244,606,419
Total Project Value
Funded Projects Focused On :
Research and innovation infrastructure
Innovation support for business,
Research collaborations
Grants/finance for R&I
Notes: Research and innovation infrastructure, largely aligning with SO1.1, which comprised 44 funded projects and covered all projects in which capital expenditure was the main focus (either equipment or buildings).
Innovation support for business, closely aligning with SO1.2, which comprised 180 projects and covered support activities focused on improving innovation through the use of structured knowledge sharing and learning.
Research collaborations, closely aligning with SO1.3, which comprised 63 projects in which support activities involved collaboration and partnership between a research support provider and a business beneficiary.
Grants/finance for R&I

## Slide 14
Output Achievements
33,538
Businesses Supported
6,522
Businesses Introduced New Products to Market
7,211
New Jobs as a Result of Support
4,695
Start-ups Supported
10,263
Businesses Introduced New to Firm Products
9,957
Businesses Engaging in Research Collaborations

## Slide 15
Case Studies

## Slide 16
Case Studies

## Slide 17: SME Support and Financial Instruments

## Slide 18
Programme Commitments – SME Support
423 Projects Funded to Deliver SME Support
£947,707,506
ERDF Spend by Grant Recipients
£1,064,799,977
ERDF Commitment for SME Support
£2,054,753,915
Total Project Value
Funded Projects Focused On :
Advice, support and grants to support business startups.
General business advice and support.
Sector-focused business advice and support
International trade support
New workspace – incubator, managed and grow-on space

## Slide 19
Output Achievements – SME Support
47,206
SMEs Receiving Grants
60,335
Potential Entrepreneurs Supported
92,258
SMEs Receiving Consultancy Support
72,354
New Jobs Created in Supported SMEs
24,727
Start-ups Supported
£647,424,527
Private Sector Leverage Induced
1,154
New Products to Market and
11,549
New Products to Firm

## Slide 20
Case Studies

## Slide 21
Case Studies

## Slide 22
Financial Instruments

## Slide 23
Achievements – Financial Instruments
£633m
ERDF invested
£403m
Access to Finance for SMEs
2,731
Investments
17,443
New Jobs Created in Supported SMEs
63,884 tonnes
Co2 Savings
Over £1.7bn
Private Sector Leverage
95,000 m2
Public or Commercial Buildings Built or Renovated
£230m
Urban Development Funds and Energy Efficiency
40.5m KwH
Energy Savings
35
Investments
437
New Enterprises
Over £1.5bn
Total FI Project value
Notes: C32 Decrease of Annual Primary Energy Consumption of Public Building - Energy Savings KwH
Error in GPB FI table NPIF Private Sector Leverage – £664,301,006

## Slide 24
Case Studies

## Slide 25: Low Carbon Support

## Slide 26
Programme Commitments – Low Carbon Support
163 Projects Funded to Deliver Low Carbon Support
£617,062,771
ERDF Spend by Grant Recipients
£648,072,479
ERDF Commitment for Low Carbon Support
£1,309,919,739
Total Project Value
Funded Projects Focused On :
Increasing Small-scale Renewable Energy Schemes,
Improving Energy Efficiency In SMEs,
Increasing Energy Efficiency In Homes And Public Buildings,
The Implementation Of Whole-place Low-carbon Solutions, And
Increasing The Use Of Low-carbon Technologies

## Slide 27
Output Achievements – Low Carbon Support
17,320 Businesses Supported
339,532
Tonnes of Carbon Dioxide Saved
214,257,144 KWh's/year Reduction of Energy Consumption in Public Buildings
8,734
Households with Improved Energy Consumption
1,341
Businesses Introduced New to Firm Products
1,811
Businesses Engaging in Research Collaborations

## Slide 28
Case Studies
The Smart Energy Islands project showed how different innovative energy technologies can work together to decarbonise the energy mix.
The project brought together a range of different technologies such as Renewables, Passivhaus and home energy management systems to demonstrate how energy supply and demand can be balanced through the innovative use of electric vehicle and home battery solutions.
The project doubled the island's renewable energy capacity and cut costs to the consumer.
Hitachi Smart Energy Islands
ERDF Support: £8.6 million

## Slide 29
Case Studies

## Slide 30: Capital Infrastructure

## Slide 31
Programme Commitments – Capital Infrastructure
197 Capital Infrastructure Projects
£454,803,400
ERDF Spend by Grant Recipients
£475,982,136
ERDF Commitment for Capital Infrastructure
£979,166,115
Total Project Value
Funded Projects Focused On :
New or Refurbished Research and Innovation Facilities
New SME Workspace – Incubator, Managed and Grow-on Space
Flood Protection Investment
Environmental Improvements
Improved and Sustainable Transport Infrastructure

## Slide 32
Output Achievements – Capital Infrastructure
74,249 m2
New or Refurbished R&I
Infrastructure
3,029 ha
Habitats with Improved Conservation Status
232,855 m2
New or Refurbished SME Workspace and Incubator Units
260 ha
Rehabilitated Public Land
6,072
Businesses with Reduced Risk of Flooding
271
Electric Vehicle Charging Points and
6
Multimodal Connection Points
43 km
Railway with Enhanced Signalling Installation
14 km
Upgraded Road (*)
(*) To be completed in 2024

## Slide 33
Case Studies

## Slide 34
Case Studies