# Activity Based Budgeting Examples

Example 1: The following table is not an ABB. It provides little useful information about how the proposed project budget will be spent. There is no breakdown of costs within each Expenditure Category and no timeline to show when costs will be incurred or which particular activity they are assigned to. As such it is not possible to assess the cost of individual activities or whether the budget is realistic, justifiable or value for money.

Expenditure Category		Total Cost
Personnel		11075
Travel		9000
Accommodation & Subsistence		6000
Capital		20000
Monitoring and Evaluation		1600
Admin/Mgt		9425
Other		9800
	66900

Example 2:
The following table is better. Although lacking any time-based considerations it does provide some insights into the component parts of each activity, namely, what they are and how much they will cost. It shows individual and comparative costs for each activity, allowing Project Teams to assess whether funds are being appropriately assigned. It can be used as a stepping stone towards a fully developed ABB.

Activity	Components	Total Cost (£)	Sub-Totals (£)		%age
Visit to UK by 8 Scientists	Flights	£7,200	£11,280		27%
	Subsistence	£1,200
	Hotels	£2,880
Develop written recommendations and methodology for local implementation, arising from visit	Scientists’ Fees	£12,000	£12,400		30%
	Books, materials and printing	£400
Training on the Recommendations arising from the Visit / (4 x half-day training)	Venue and Catering	£5,000	£5,630		13%
	Trainer’s Fees	£400
	Materials	£230
Follow-up Training – Review Action Plan Implementation / (4 x one-day training)	Venue and Catering	£4,000	£5,030		12%
	Trainer’s Fees	£800
	Materials	£230
Project Management	Project Manager	£3,500	£4,500		11%
	Secretary	£1,000
Evaluation	Local consultant fees	£2,500	£2,850		7%
	Travel costs	£350
TOTAL		£41,690	£41,690		100%

Example 3:

Activities can now be assigned a date along a timeline to show when they will occur using a simple GANNT chart.

Example 3 identifies blocks of activities against particular months. This can be further broken down to show more detail e.g. more rows can be added under each activity in order to list all key tasks needed to achieve that activity, and more columns can be added to break down months into weeks and even days for tasks and activities that are time critical. The amount of detail shown depends on the timeline and complexity of the project and activities.

Activity	May	June	July	August	September	October
Visit to UK by 8 Scientists
Develop written recommendations and methodology for local implementation, arising from visit
Training on the Recommendations arising from the Visit / (4 x half-day training)
Follow-up Training – Review Action Plan Implementation / (4 x one-day training)
Project Management
Evaluation

Figures from Example 2 can now be transferred into Example 3, adding additional rows and columns as necessary.

Due to Resource Accounting principles, the FCDO is liable for payment once an activity has taken place. Therefore, activity costs listed in a GANNT chart need to reflect the timing of the activity, not when payment will be made (actual payments may occur before or after the activity itself is completed).

See Example 4 below for a complete ABB.
Example 4: An Activity Based Budget

Activity	Details	April	May	June	July	August	September	October	November	Totals
Visit to UK by 8 Scientists	Flights-Economy		£7,200							£11,280
	Subsistence		£1,200
	Hotels		£2,880
Develop written recommendations and methodology for local implementation, arising from visit	Scientists’ Fees			£12,000						£12,400
	Books, mat. & printing			£400
Training on the Recommendations arising from the Visit (4 x half-day training)	Venue & Catering				£5,000					£5,630
	Trainers’ Fees				£400
	Materials				£230
Follow-up Training – Review Action Plan Implementation (4 x one-day training)	Venue & Catering						£4,000			£5,030
	Trainers’ Fees						£800
	Materials						£230
Project Management	Project Manager		£700	£700	£700	£700	£700			£4,500
	Secretary		£200	£200	£200	£200	£200
Evaluation	Local consultants’ fees							£2,500		£2,850
	Travel costs							£350
Totals		£0	£12,180	£13,300	£6,530	£900	£5,930	£2,850	£0	£41,690

This Example provides the minimum level of detail needed for Programme Teams to assess value for money, per activity, for this project.

Following the technical evaluation, this proposed costing will be assessed and used to determine which proposals represent value for money. It will also serve as a basis of negotiation before award of the grant and signing the Agreement.

The FCDO reserves the right to request additional cost information if the evaluation committee has concerns of the reasonableness, realism, or completeness of the proposed cost.