# BHC Tanzania’s Sustainable Growth and Investment Partnerships Evaluation: Terms of Reference

## Introduction
The United Kingdom’s Foreign, Commonwealth and Development Office (“FCDO”) is seeking a service provider (“Supplier”) to design and deliver an evaluation of the British High Commission (BHC) in Tanzania’s work on sustainable growth and investment partnerships. The Tanzania Country Plan sets out the UK’s strategy for facilitating growth and investment in Tanzania. This takes a “cross HMG partnerships approach” drawing on the full range of levers available to the UK – including development funding, commercial and trading relationships, policy and diplomatic engagement and UK loan and financing facilities and expertise.
The evaluation will review the office’s implementation of Goal 3 of Tanzania’s Country Plan (Growth and Finance) – along with its predecessors – which aims to improve the business environment and increase investment and reduce barriers to trade, including from and with the UK, to facilitate more inclusive and sustainable growth. The review will specifically focus on the use, achievements and challenges of an increased focus on a ‘whole of government partnerships’ approach to development set out in the Tanzania British Investment Partnership Strategy. This is defined as a focus on delivering through mutual partnerships – particularly with the Tanzanian Government and UK and Tanzania private sector – and the use of all UK’s levers, financing and relationships, across HMG and beyond, to deliver development outcomes. This has been the focus of the approach to supporting sustainable prosperity in Tanzania, bringing together relevant FCDO central and bilateral ODA programmes, UK diplomacy, commercial relationships and technical assistance, Department for Business and Trade facilitation and different UK financing instruments (eg UK Export Finance, British International Investment) to strengthen Tanzanian and UK investment and the business enabling environment. This is in line with the new Labour Government’s plans for International Development based on ‘genuine respect and partnership with the global South to support our common interests’, and with ‘economic transformation’ as an international development priority. See Annexes for more detail.
UK support to help tackle climate challenges and strengthen governance and human capacity in Tanzania also contributes to sustainable growth and investment in Tanzania, but the proposed focus of this evaluation will be on the work covered by the Growth and Finance goal: increased investment and trade and a better business environment. The rationale is to help keep the evaluation manageable, and that these are the areas which best encapsulate the partnerships approach to development.
The purpose of the evaluation is two-fold: to identify opportunities to help (i) strengthen the UK’s approach to sustainable growth and investment in Tanzania (Tanzania Country Plan Goal 3); and (ii) more effectively plan, implement, monitor and evaluate a “partnership approach to development” (going beyond programmes and working across HMG and other UK relationships).

## Objective of the evaluation
The evaluation will improve understanding of the UK’s contribution to growth and investment in Tanzanian over the last few years and of how best to implement and manage UK interventions to maximise the benefit from a whole of Government partnership approach. The proposal is that this is achieved through: (i) identifying and understanding examples of major successes and challenges of FCDO’s economic work over the last five years (focusing on economic productivity, investment and trade and the enabling business environment); and (ii) evaluating the role, successes and risks of a whole of government partnership approach. The intention is that this study will also help FCDO develop an evaluation method which could be used for a whole of government partnership approach more widely.
The Supplier is expected to deliver the contract through two main outputs:
Output 1: Inception report to confirm evaluation questions, develop the evaluation approach and plan, and review and confirm data sources.
Output 2: Full evaluation, providing a report and use and influence products and activities.

## Recipients
The main recipient is the Growth and Prosperity Team in the BHC Tanzania.
There are three key audiences for the evaluation: (1) the Growth and Prosperity team in Tanzania to understand sustainable prosperity success and how to enhance delivery in Tanzania; (2) HQ economic growth teams to support their work on economic policy across FCDO; and (3) other teams in Tanzania and HQ interested in delivering development objectives through a whole of Government partnership approach.

## Scope of the evaluation
Programme Management
The Supplier will provide the appropriately skilled personnel and systems to ensure the successful day to day management of the Contract including project leadership, financial management, risk management, logistics, and administrative duties.
Evaluation services
The evaluation should be focused on developing an understanding of how different partnerships and levers across HMG have helped deliver results and impacts, and on how this can be further enhanced.
The proposal is for the evaluation to focus on the economic outcomes (productivity and jobs, investment and trade and enabling business environment). Within this, due to resources available, the proposal is that the evaluation primarily focuses on case studies and outcome mapping of areas of most impact, challenge or innovation, through reviewing selected outcome trajectories (to be confirmed during the inception). This should allow the evaluators to unpack what worked and why more clearly.
The Supplier will provide appropriately skilled staff and systems to deliver the project outputs:
OUTPUT 1: Inception Report
OUTPUT 2: Final Evaluation Report and influence and use products and activities

## Contract budget and timeframe
The maximum budget available will be £120,000 (which includes all applicable taxes and expenses but excludes UK VAT). This is covered in more detail in Volume 5 (draft contract) of the ITT pack.
The evaluation contract is initially expected to run for 7 months from October 2024 to April 2025, with the inception period from Oct – Nov 2024 and the evaluation conducted from January to March 2025. It is expected that most of the work will be undertaken in October/November 2024 and January-February 2025.

## Requirements (Key deliverables and outputs)
Output	Description	Date
Inception Report (no longer than 20 pages, excluding supporting annexes), including: / Theory of Change. / Mapping and review of available data and evidence / Evaluation design and tools, stakeholder mapping / Use and influence plan / Initial outcome mapping / Workplan, including key dates and deliverables / Risks / Budget	To include: / • Reviewing and documenting existing strategies and data sources (eg Country Plan Goal and monitoring, Tanzanian BIP strategy, relevant programmes) – see ‘Data Sources’ section for more detail. / • Finalising scope, timing and deliverables of evaluation, including areas of focus and proposed dissemination. / • Synthesising baseline information, including initial outcome harvesting / mapping (or other outcome focused method) of key change trajectories. / • Key Informant Interviews (KIIs) with the main BHC Tanzania stakeholders and wider evidence / document review. BHC Tanzania Sustainable Prosperity Team meeting on the draft inception findings. / Documenting ways of working and planning and monitoring processes for non-programme elements. / • Evaluation Design / Protocol Report developed, including an evaluation matrix with questions, data collection and analysis plan, management of ethical standards. / Use and influence plan setting out dissemination products (such as learning briefs, slide pack or case studies) and dissemination activities to promote use and maximise impact. This should include a HMG dissemination workshop.	Expected Oct-Nov 2024
Evaluation Report, including: / Validation workshop / Dissemination, use and influence activities. / 2 page summary (evaluation digest) using FCDO template for publication.	Activities are to be finalised during inception, but are roughly expected to include: / • Outcome harvesting (or alternative) with HMG teams and relevant partners across sustainable growth and investment pathways identified in inception. / • Light touch situational / context /political economy analysis / • KIIs with internal and external stakeholders, document review / • Qualitative analysis / synthesis validation of outcome claims / • Validation workshop with BHC Tanzania and draft report for comment from core team / • Development of final report and any other evaluative and dissemination products. / Influence and use activities, which should include a HMG workshop.	To be confirmed during inception, but expected around Jan – April 2025: / Draft evaluation report early March 2025 / Final evaluation report incorporating EQUALS and FCDO comments by end March 2025 / Dissemination activities: April 2025

## Methodology
The evaluation supplier is expected to finalise the methodology as part of the inception process. It is expected that the evaluation would be a theory-based qualitative evaluation. Strategies, planning and monitoring processes for cross HMG and non-programme elements are not as well established as for programme work. Hence we have included a significant inception period as this is likely to involve creating a basis for the evaluation from various existing strategies and documents, alongside key informant interviews with relevant FCDO and HMG staff. The Country Plan and its monitoring framework sets out and tracks high level outcomes, the British Investment Partnership Strategy in Tanzania sets out what a partnership approach looks like in practice in Tanzania, and different elements of implementation are set out in different documents including relevant programme Business Cases and Annual Reviews, UK-Tanzania agreements (eg Business Forum tracker and Mutual Prosperity Partnership), and plans from other parts of HMG (Department of Business and Trade, British International Investment). A substantial inception phase is planned to enable the Supplier to finalise and agree the basis for the evaluation drawing on these sources. One objective of the evaluation is to review existing approaches to non-programme work and propose light touch and realistic opportunities to strength planning, monitoring and evaluation of these non-programme elements.
The inception will be able to draw from an evaluability study conducted in late 2023 for an evaluation of the Tanzania BIP Strategy. The evaluation has now been broadened to focus on implementation of the economic Country Plan Goal, so the evaluability study is not directly relevant. However the inception can still draw from the methodology ideas and data/activity mapping.
We expect key methods / data collection processes to include:
- Light touch context and political access and influence assessment
- Outcome focused evaluation techniques to record and evidence the main events and processes that led to selected outcome trajectories. This may be through using any of the following: outcome mapping / harvesting, process tracing, contribution tracing etc. It is suggested that the inception phase includes a backwards look of a few selected successes (an outcome harvest) alongside setting out anticipated trajectories to be reviewed during the full evaluation. This would enable the evaluation to unpick how outcomes have been supported in the past and the relative contribution and intended and unintended consequences of a range of different UK levers.
- Case study or stories of change – one or two focused case studies for the selected outcome trajectories with the most results, learning or innovation. The initial proposal, to be confirmed during the inception, is that these focus on tax reform and UK commercial facilitation (possibilities include BHC facilitation with UK companies working in Tanzania: Gridworks and de la rue; and of UK export finance for Tanzanian infrastructure).
- Key Informant Interviews (KIIs): in-depth interviews with the people who had been most involved in the respective outcome trajectory and delivery of the UK’s growth and investment work within FCDO and beyond.
- Contribution Analysis: The evaluators should also consider whether contribution analysis would be appropriate and useful to understand more broadly how selected outcomes are being achieved.
- Process evaluation of design and implementation processes of non-programme areas of work, bearing in mind realistic expectations around staffing resources and cross HMG/organisation coordination.
- Exploration of inclusion/gender.
- An Influence and Use plan.
The final report should be shared in draft 3 weeks before the final deadline, to allow time for comments from FCDO to be incorporated, including through a presentation on emerging findings to FCDO.
It is expected that at least some of the main evaluation would be carried out in person in Tanzania.
In line with the FCDO Evaluation Policy, the inception and evaluation reports must be quality assured by EQUALS 2. The final report will be published alongside an FCDO management response. The Supplier is expected to put any sensitive information in an internal annex so the main report can be published.
Evaluation questions
The evaluation will use the OECD-DAC criteria, with a particular focus on efficiency (in terms of how a whole of Government partnership approach is implemented) and effectiveness (in terms of examples and drivers for success of UK interventions in this area).
Suggested evaluation questions are below. The evaluation team is expected to elaborate on these high-level questions during the inception period.
1. What are the main lessons from selected UK achievements to support sustainable growth and investment in the last 5 years? What were the main drivers which supported or constrained these successes? How, and in what ways, have differing UK levers (diplomatic / influencing, expertise, commercial, programme delivery, financing etc.) been used and helped achieve these successes? Have there been any unexpected outcomes or risks from an increased focus on a ‘whole of Government partnerships’[1] approach?
  [1] Defined as more focus on delivering through mutual partnerships and on using the full range of UK levers and partnerships across HMG and beyond.
2. How well does BHC Tanzania’s current strategy for growth and investment build on these lessons and reflect the whole of Government partnerships to development?
3. How well does the current strategy and workplan address cross cutting HMG objectives such as gender, social inclusion, environment and conflict?
4. How effective are the planning, coordination and delivery mechanisms in helping BHC Tanzania utilise a whole of Government partnerships approach to development to maximise its contribution to growth and investment outcomes and minimise any risks?

Main data sources:	Indication of quality of data:
Analysis and evidence underpinning growth and investment work: including the Country Plan, BIP Strategy, the BHC Tanzania Inclusive Growth Diagnostic, tax environment and Foreign Direct Investment analysis.	Strong: Comprehensive robust data and analysis available from FCDO and externally.
Workplans and follow up for specific streams of influencing work: including Prosperity team workplan, UK-Tanzania business forum Joint Action Plan and tracker, Africa Investment Summit plans, Department of Business and Trade (DBT) plans, Mutual Prosperity Partnership agreement.	Mixed: some influencing workstreams have robust systematic reporting, others are more inconsistent.
Robust M&E data from the major programmes which support the growth and investment, including Business Cases, logframes and Annual Reviews for the Programme for Prosperity Programme, Corridors for Growth and Trade Mark East Africa.	Strong: Comprehensive and robust data available from existing programmes.
Internal 6 monthly outcome identification and tracking exercise conducted from early 2024.	Weak: process light touch and only started in 2024
6-monthly reviews of the UK Tanzania Country Plan from Oct 2023, including major indicators of policy and programming.	Weak: process only started in 2023, and only a small amount of information is related to growth and investment

The evaluation will focus on the whole of Government partnerships approach. The approach and data sources around this are still emerging as different Government Departments have different M&E systems and requirements and there are more limited M&E processes and expectations for non-programme interventions. Tools to help evaluate diplomatic initiatives from a country development perspective are being developed but are in their infancy. Much of the other evidence base will be qualitative and will need to be generated by the evaluation team through structured interviews and outcome harvesting. The evaluation team would be expected to use multiple data sources and triangulate across evidence sources when possible. Each key finding presented in the final evaluation report should be clearly supported by evidence generated as part of the evaluation. The evaluation team should develop a robust process to evaluate and present the strength of the evidence that underpin any finding, with the bid and inception report setting out the process to be used. The final report should include an evidence table as an Annex to present the evidence underpinning each finding and the strength of the evidence base.
Use and Influence
The Inception Report should include a Use and Influence Plan. This would set out what evaluation products and dissemination activities would be appropriate to support use of the findings. This should include a clear summary, a validation workshop with the relevant FCDO team on the draft report, and a broader HMG wide presentation on the final report. The team should also consider the value of additional products and activities during inception, such as learning briefs, case studies and broader stakeholder dialogue on the findings. Recommendations should focus on realistic proposals, which take in to account likely capacity and engagement of different actors.

## Team Structure
The evaluation team would ideally include:
- Significant breadth of experience in delivering evaluations using the methods outlined above, including qualitative comparative analysis or other deep qualitative data collection and analysis expertise (ideally with the FCDO in Tanzania / Africa, and ideally conducting innovative evaluations)
- Senior technical expertise in: economic development, trade and investment, political economy and diplomacy / influencing.
- Experience in organisational development and learning, and ideally in UK/FCDO government strategy and implementation processes and in dealing with potentially sensitive topics.
- At least one team member based in Tanzania or the region.
Evaluation team members should be free from any significant conflict of interest arising from being involved in the activities being evaluated. The evaluation team is expected to have some level of independence from growth/investment policies and implementation in Tanzania, while recognising that in country experience might necessitate some involvement in these areas.
Given the budget, a smaller team, with fewer team members having more days would be preferred.
## Contract Management
The contract will be subject to a break point at the end of the inception period, when both FCDO and the contractor need to be satisfied that the proposed evaluation design will be feasible and useful.

## Scaling Up or down
FCDO reserves the right to scale down or terminate this contract in line with the Terms and 10 ITT_5378 - Volume 3 Terms of Reference but not limited to the project not achieving intended objectives, a change in the security and/or political circumstances of Tanzania, political economy reasons or a shortage of funds.

## Reporting Requirements
In addition to the deliverables highlighted above, the Supplier will be expected to produce full invoices once the agreed deliverable has been approved. This is covered in more detail in Volume 1 (ITT Instructions) of the ITT pack.

## Payment by results
Payment will be made on the submission and acceptance of key milestones:
- Satisfactory inception report provided on or before 3 months after contract signing, in line with requirements in Section 6 and achieving at least a ‘pass’ by EQUALS2 quality assurance process (or alternative independent quality assurance system of similar independence and quality proposed by the consultants).
- Draft evaluation report provided to the agreed timeline and scope set out in the agreed Inception Report, including clear results and recommendations, and in line with good evaluation practices and achieving at least a ‘pass’ by the EQUALS2 quality assurance process (or alternative).
- Final evaluation report provided to the agreed timeline, incorporating all major comments by EQUALs and the FCDO team, and successful implementation of agreed Influence and Use plan.
The Supplier will be required to deliver effective financial management and demonstrate value for money.

## Contract Oversight Requirements
The FCDO contact people for the supplier will be Sarah Hennell (BHC Tanzania results adviser – coordinator).
The supplier will be responsible for organising and managing the logistics for the team, setting up meetings and any presentations. FCDO will provide introductions with people in FCDO and externally if needed, will facilitate internal presentations and meetings with any senior external partners, will provide key reference documentation, and provide timely feedback.

## Stakeholders
The evaluation will be steered by the BHC Tanzania economic development coordination group, which brings together the key people working on economic development in Tanzania from FCDO and Department of Business and Trade (DBT). This group will provide feedback on the inception report, and the draft final report.
The evaluation team is expected to interview other key stakeholder which the UK works with to deliver the BIP as part of their consultations and data collection within the main evaluation, including:
- Government of Tanzania
- World Bank
- IMF
- Technical Assistance providers
- UK Business Group in Tanzania
- Other donors.
The evaluation is not being conducted in partnership with others as we are primarily interested in the impact of the UK’s approach and levers. However it may be possible and useful to explore the approach and success of influencing within one or two other major stakeholders as a comparison. This should be explored in the inception phase.

## Administrative Arrangement
The study would be supported through The Evidence Fund, an FCDO programme intended to support a broad spectrum of FCDO’s evidence needs to inform policy and programming decisions. The expected impact of the programme is to help develop evidence-informed policies, programmes and practices which contribute to development outcomes.
In 2022, FCDO appointed PwC and Integrity as Fund Manager (FM) to oversee and manage the Evidence Fund. The Fund Manager’s primary responsibility is to manage procurement competitions for research and evaluation projects, conduct due diligence assessments on prospective sub- contracted Research Pool providers, where relevant, and manage research and evaluation contracting.

## Gender Equality and inclusion
The Supplier should set out how they would incorporate gender issues within data collection, analysis and dissemination, including understanding and tracking women’s empowerment, to ensure accurate information on women’s and men’s perspectives of the programme. All recommendations should include consideration of gender issues.
For FCDO, disability inclusive development means that people with disabilities are systematically and consistently included in and benefit from international development. The Supplier should outline their approach to disability inclusion and how people with disabilities will be considered as part of the evaluation, data collection and analysis.
There are established processes and expectations in place which encourage all FCDO programmes to consider gender and inclusion issues in design, implementation and monitoring of programmes. For example, our programmes use the 2X challenge to report investments when relevant. It would be particularly useful for the evaluation to consider how gender and inclusion are promoted and reported across non-programme parts of the portfolio and whether there are opportunities to strengthen this. BHC Tanzania has conducted and is implementing a WOW helpdesk report on supporting economic opportunities for women in Tanzania, providing an overview of current opportunities.

## Other requirements (Ethics, GDPR, data access, safeguarding, branding, transparency)
- The evaluation bid should demonstrate compliance with FCDO’s Environmental and social safeguarding (see page 9).
- It is not expected that any digital tools will be used to collect data or influence activities, but if any are planned suppliers should demonstrate that they adhere to the Principles for Digital Development (see FCDO Technology Strategy 2017 to 2020).
- While it is unlikely that there will be need for advanced ethical processes, all evaluation activities should follow FCDO’s Ethical Guidance for Research, Evaluation and Monitoring Activities. This should be set out in the bid and inception report.
- FCDO will have unlimited access to the material produced by the supplier in accordance with our policy on open access to data as expressed in our general conditions of contract
- FCDO requires suppliers receiving and managing funds to release open data on how this money is spent, in a common, standard, re-usable format, and to require this level of information from immediate sub-contractors, sub-agencies and partners. It is a contractual requirement for all Suppliers to comply with this, and to ensure they have the appropriate tools to enable routine financial reporting, publishing of accurate data and providing evidence of this. Further IATI information is available from: http://www.aidtransparency.net
- The bid and inception should confirm how the evaluation will be consistent with GDPR requirements. Further information is at: Guide to the general data protection regulation.
- The final report should be branded according to current UK branding guidance for ODA funded programmes
- The Supplier shall commit to prevent all forms of modern-day slavery. The Supplier shall ensure accountability and fair recruitment process for its staff and consultants that will be involved in the delivery of the contract.
- The Supplier is expected to uphold the principles of ‘do no harm’ throughout all activities. The Supplier should confirm how it will adhere to FCDO’s safeguarding standards (as set out in the Due Diligence guide for external partners) that cover partner policies and processes on safeguarding, whistleblowing, human resources, risk management, codes of conduct and governance.
- Note: FCDO will have unlimited access to the material produced by the supplier in line with FCDO’s general conditions of contract.

## Safeguarding
FCDO places utmost importance on all potential partners’ ability to safeguard children, young people and vulnerable adults they work with from sexual exploitation and abuse, and their ability to protect staff and volunteers. The Supplier Code of Conduct will be included in the terms and conditions of the Contract. New compliance checking mechanisms are now in place to review supplier documentation, their approaches to legal compliance and demonstration of good practice in meeting international principles on labour and ethical employment and to provide assurance that whistleblowing systems are accessible across delivery chains. FCDO will monitor risk and mitigation plans throughout the project cycle. The commitments made by all organisations in receipt of FCDO funding need to provide spending teams with concrete assurance that the new enhanced safeguarding standards are being applied.  The approach will help to promote the adoption of new standards for all organisations in the aid sector.
## Ethical principles and standards
Suppliers are required to refer to ethical guidelines available at https://www.gov.uk/government/publications/dfid-ethical-guidance-for-research-evaluation-and-monitoring-activities. Bidders should include a statement in their proposals, confirming that the study will comply with ethical guidelines as mentioned above. This is a mandatory requirement.
## Research for Development outputs (R4D)
FCDO requires that all final research output(s) from this funding are uploaded to Research for Development Outputs (R4D) on GOV.UK. By law documents published on GOV.UK must comply with the  Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.  This is so they can be used by as many people as possible, including those with disabilities. Further information on open document formats and content accessibility on GOV.UK can be accessed here  https://www.gov.uk/guidance/content-design/planning-content.  Uploading final output(s) to Research for Development Outputs on GOV.UK does not exclude these outputs from being uploaded to other websites or platforms and repositories.

## Duty Of Care and Security
The Supplier is responsible for the safety and well-being of their Personnel and Third Parties affected by their activities under this Contract. They will also be responsible for the provision of suitable security arrangements for their domestic and business property. The respective FCDO Programme Offices will share available information with the Supplier on security status and developments in-country where appropriate.
The Supplier is responsible for ensuring appropriate safety and security briefings for all their Personnel working under the Contract and ensuring that their Personnel register and receive security briefings. Travel advice is available on the FCDO website (https://www.gov.uk/foreign-travel-advice/tanzania ) and the Supplier must ensure they (and their Personnel) are up to date with the latest position.
Some documents and discussions will be of a diplomatic or sensitive nature, so will require the supplier to have security clearance.

## Delivery Chain Risk Mapping
Delivery Chain Risk Mapping is a process that identifies and captures, usually in visual form, the name of all suppliers involved in delivering a specific good, service or charge. It is now also a requirement to report on all levels of contracted work being allocated to Small and Medium sized Enterprises (SME) and other sub-contracted organisations to the government SME Small Business Policy team. As part of the contractual compliance checking process, Suppliers will be required to submit returns providing these details.

## Risks and dependencies
- Broad nature of growth and investment work: This will be mitigated by focusing on growth and finance elements (business environment, investment/trade, economic productivity), on targeted outcome areas, and including a specific focus on the results and lessons from a whole of Government partnerships approach.
- Timely access to documents: BHC Tanzania will facilitate access to internal documents, but this will depend on staff from across the mission’s availability and access to those documents. We will provide adequate lead in time to mitigate the risk that there are delays in document access.
- Staff / partner turnover: staff and other partners who were engaged in FCDO’s economic work, and therefore have a valuable contribution to the findings, may have moved to different posts within FCDO or other organisations. BHC will endeavour to facilitate access to those staff that have moved on wherever possible, but this remains a risk.
- Difficulty accessing main relevant external partners. This should be explored during the inception phase, but our understanding of the relationships is that these will be accessible.
- Availability of data sources. The monitoring data for some of the non-programme activities is patchy. Some of the information can be obtained through interviews and the evaluation is expected to consider recommendations of how data could be improved in future.
- Lack of experience of conducting this kind of evaluation. This is a new type of evaluation, not focused on the traditional ‘programme’ with established design and M&E processes. This is mitigated by having a substantial inception period, and focusing on clear and practical evaluation questions and methods (outcome harvesting on pre-selected outcomes, review of processes) which should ensure a base of useful evaluation information.
The supplier will be required to elaborate on key risks and mitigation strategies as part of the inception phase.

## Instructions
Technical and financial proposals should be sent as two separate files to uk_evidence_fund_administration@pwc.com by 20/09/2024 (23:59 GMT). Since these will be assessed independently of each other, they should, in no case, be combined or cross-referenced.
The instructions for submitting the tender and details on scoring methodology and evaluation criteria are detailed in ITT Volume 1. The application forms for submitting the technical proposal (sent as a clearly titled PDF file) are detailed in ITT Volume 3 and ITT Volume 4 provides the Pro Formas for the commercial proposal.
Bids should be a maximum of 15 pages (non-inclusive of long format CVs and with any additional information in Annexes) and contain the following information:
Bid section & weight	Indicative no of pages	Criteria
Proposed team (CVs in annex) / 35%	4 pages (plus CVs in annex)	Small, balanced team, including expertise and experience in line with Section 8. / Individual experience of similar projects. / Leadership includes considerable breadth of relevant evaluation expertise.
Relevant experience of the bidding organisation / 10%	1 page	Organisational experience of similar projects.
Methodology and approach, including levels of effort, timeframes, approach to quality assurance / 45%	8 pages	Clear, concise and proportionate approach / Outline of approach to evaluability assessment / Proposed methodology aligned to the evaluation purpose and questions / Internal mechanisms for ensuring quality and adhering to requirements in TOR
Risks / 10%	1 page	Clear risk matrix, which outlines potential risks and mitigations to evaluability, data collection, analysis and use of findings.

# Annex A - Schedule of Processing, Personal Data and Data Subjects

This schedule must be completed by the Parties in collaboration with each other before the processing of Personal Data under the Contract.
The completed schedule must be agreed formally as part of the contract with FCDO and any changes to the content of this schedule must be agreed formally with FCDO under a Contract Variation.
Description	Details
Identity of the Controller and Processor for each Category of Data Subject	The Parties acknowledge that for the purposes of the Data Protection Legislation, the following status will apply to personal data under this contract / 1) The Parties acknowledge that Clause 33.2 and 33.4 (Section 2 of the contract) shall not apply for the purposes of the Data Protection Legislation as the Parties are independent Controllers in accordance with Clause 33.3 in respect of Personal Data necessary for the administration and / or fulfilment of this contract. / 2) For the avoidance of doubt the Supplier shall provide anonymised data sets for the purposes of reporting on this project and so FCDO shall not be a Processor in respect of anonymised data as it does not constitute Personal Data.

# ANNEX B – Tanzania Country Plan Goal 3 and BIP Strategy Summary

Tanzania Country Plan – Goal 3 Summary
Goal 3: Growth and finance: Better business environment delivers better quality jobs, more inclusive and sustainable growth; and more investment and trade, including from UK, private capital and IFIs.
Priority UK outcomes:
More progressive economic, business and trade reforms
- Increased financing for key economic infrastructure projects
- Reduced barriers to trade
- Improved coordination and delivery in priority sectors for inclusive, sustainable growth
Better evidence-based decision making
More evidence based national strategies, policies or business environment improvements.
Increased quality investment in priority sectors
- Increased investment in priority sectors
- Improved growth of agri-processing, manufacturing and horticulture verses agriculture.
Increased UK trade and FDI
- Increased UK export finance
- Increased trade, including with the UK
Tanzania British Investment Partnerships Strategy Summary
The Tanzania British Investment Partnerships (BIP) strategy sets out BHC’s strategy for taking a whole of Government partnerships approach to economic development work and provides an overarching analysis of priorities and opportunities.
The BIP strategy aims to ensure we use all UK sources of finance (eg development finance, export finance, blended finance and guarantees) alongside UK expertise, diplomacy and commercial relationships to increase investment and growth overseas and in the UK.
The Tanzania BIP Strategy has four priority pillars: productivity and good jobs; enabling environment; human development and climate and environment. The BIP sets out how BHC Tanzania will use HMG staff and relationships, experts, UK financing mechanisms and programmes. It provides an umbrella strategy for the work by various UK Government Departments in Tanzania, primarily FCDO, DBT and HMRC. The BIP was developed in the context of a newly merged Department and reduced ODA budgets over the last two years.
In line with the new ways of working aspiration of FCDO, the BIP strategy aims to utilise all different levers of HMG to maximise the UK’s impact based on effective partnerships. This includes UK technical expertise (through consultants and HMG experts), commercial relationships, diplomacy, policy engagement and financing instruments. The BIP workplan has three core delivery modalities: Strategy & Policy; Diplomacy & Influencing, and Programme Delivery. Activities and programmes are both centrally managed and managed at a country level. As budgets were cut over the last few years, greater focus was placed on diplomacy and influencing as a core HMG lever. These levers have been used at different intensities across work strands, often with purposeful sequencing and integration to achieve greatest impact.
The UK uses a variety of levers to facilitate economic development in Tanzania. The main activities include:
- Bilateral programmes: Productivity for Prosperity, TradeMark East Africa and Corridors for Growth
- Regional and Central programmes: International Growth Centre, TaxDev, Financial Deepening Trust
- Technical assistance from HMRC, ODI and UK supported research and analysis
- Diplomacy, facilitation and policy from FCDO and Department of Business and Trade (DBT) around economic issues
- Facilitation and engagement with UK and Tanzania private sector by FCDO and DBT
- UK facilitation of major events (eg UK business forum, Africa Investment Summit)
- UK facilitation of new and increased finance and loans, including UK imports and exports and UK export finance and British International Investment (BII)
These activities combine to influence and improve key stakeholders and decision-making processes in the Government of Tanzania and the private sector: leading to improvements to Tanzania’s economic, business, infrastructure and trade policies and increased investment in priority sectors which support inclusion and poverty reduction and also strengthen UK investment and trade. More focused, shorter term, policy outcomes are identified based on the context and UK comparative advantage. These currently include: tax and critical mineral reform, macro-economic policy and strategy, Vision 2025 evidence base, and expanding UK-Tanzania trade and UK investment.

# ANNEX C: ECONOMIC AND INVESTMENT CONTEXT IN TANZANIA

Following two decades of sustained growth, Tanzania reached a critical milestone in July 2020, when it formally graduated from low-income country to lower-middle-income country status. Tanzania’s achievement reflects sustained macroeconomic stability that has supported growth as well as the country’s rich natural endowments and strategic geographic position.

Tanzania’s growth has been impressive; however, the larger development agenda remains more challenging. The Tanzanian Development Vision (TDV) 2025 envisages Tanzania as a middle-income country with well-developed human capital, an ample supply of high-quality livelihood opportunities and broad-based gains in living standards. To achieve this Tanzania must turn its impressive record of growth into widespread improvements in poverty reduction and other development indicators. In January 2024 the World Bank noted that “Tanzania still faces stubbornly high levels of poverty, in part because of dependence on low productivity agriculture, lack of infrastructure, poor access to markets, low levels of education, limited access to educational and employment opportunities, and population growth. Tanzania is water stressed, with knock-on effects on energy production, agriculture, and the livelihoods of the poorest communities. There are also large rural-urban disparities in incomes, job opportunities, electricity access, and basic services such as maternity care, water, and sanitation. Tanzania’s urban population is growing rapidly”.

Tanzania is an outlier amongst countries to have reached LMIC status. The average poverty rate based on the international extreme poverty line of US$2.15 per day for a country that has just achieved LMIC status is 30 percent, yet Tanzania’s extreme poverty rate remains close to 50 percent. Rapid population growth, slow and uneven job creation, low levels of education and limited access to education and employment opportunities, especially among women and girls, have reduced the inclusiveness of Tanzania’s economic expansion, blunting its effect on poverty reduction.

The structure of the economy has barely changed in the last decade with most of the labour force still working in low productivity agriculture. Sectors that are growing quickly employ relatively few people, meaning the gains from growth are not broadly distributed and the economy remains concentrated in producing a few commodities. This lack of diversification leaves Tanzania exposed to increasingly frequent global shocks.

Rapid population growth of 3.2 percent per year presents the most pressing development challenge. The economy needs to create around 1.3 million jobs per year to absorb new labour market entrants and needs to rapidly expand investments in human capital. Tanzania’s dependency ratio is high at 86 (67 in Kenya and 70 in Rwanda) meaning more financial stress on the working population to support the increasingly young population.

There is clear Government of Tanzania commitment to delivering economic growth. The Government of Tanzania are acutely aware of these challenges and the sixth phase government have prioritised attracting Foreign Direct Investment as a route to increasing productivity and catalysing economic transformation. As one of the largest holders of Foreign Direct Investment (FDI) stock in Tanzania the UK is well placed to support this agenda. High profile business forums have resulted in the UK agreeing a joint action plan with the Government of Tanzania, to work on priority economic reform areas; tax, business environment, predictable policy and investment promotion.

# ANNEX D: TENTATIVE BHC TANZANIA GROWTH AND INVESTMENT THEORY OF CHANGE

A tentative Theory of Change for the Tanzanian’s growth and investment work is set out on Slide 2. This sets out at a high level the main relevant areas of engagement in relation to the investment partnership in Tanzania (what we expect to deliver.. ), the main expected outcomes (what we expect to achieve… ), and the impact. The Supplier will review and if needed revise this Theory of Change to provide the basis for the evaluation during inception.

Annex A sets out the main activities currently in place to deliver these outcomes..