Call for Proposals
15th September 2024
WITHOUT COMMITMENT
Background
1. The Foreign, Commonwealth & Development Office (FCDO) is inviting detailed proposals from non-profit organisation(s) (including UN agencies) to strengthen innovation and technology across West Africa, in close partnership with country Governments.
2. Named after a medieval learning institution in West Africa, this Call for Proposals (CfP) is called Sankore, and is a new delivery mechanism that will form part of the wider Africa Technology and Innovation Partnerships (UK-ATIP) Programme.

Lead Implementing Partner and Downstream Partners
1. The objective of this call for proposals (CfP) is to award an Accountable Grant to non-profit organisation(s) (including UN Agencies) registered in either Ghana or Nigeria. The organisation(s) will be identified through this CfP, and will lead the delivery of the entire project (i.e. as Lead Implementing Partner). This is a non-contractual process and will follow the FCDO approach to Accountable Grants.
2. The Lead Implementing Partner will be responsible for the project delivery, but is free to select their team of downstream partners. Downstream partners may be based in West Africa or internationally. As such, the Lead Implementing Partner is expected to manage and coordinate all the activities of the downstream partners, manage, and mitigate all related risks and issues, and ensure the effective delivery of project results.

Geographic Scope & Funding Duration
Funding available for this project will be up to £1.9 million. The focus countries for this project are Ghana and Nigeria. It is expected that a resource allocation of roughly 90% will be spent on the focus countries, and 10% on other countries in the region. The project will run for 12-15 months. FCDO will have the right to increase or decrease the life and budget of the Accountable Grant Agreement(s) resulting from this CfP. Payments to the Lead Implementing Partner will be made monthly or quarterly, based on actuals.

Objectives/Project Activity Framework
1. This mechanism is designed to provide high quality contextually appropriate support to the Government in Ghana and Nigeria, and improve overall localisation of project delivery. The following headings form the technical framework for the CfP:
  1. Support the UK Government’s partnership with Government in Ghana and Nigeria on Science, Technology and Innovation:
    1. The UK and Ghana have signed a bilateral MoU and strategy (executive summary included as an Annex A). We seek proposals for support to Operationalise the UK-Ghana Science Technology and Innovation Strategy. This support should include helping establish the oversight committee and supporting priority activities. Further, to provide dedicated technical support for the Ministry of Environment, Science, Technology, and Innovation (MESTI) to deliver the Government of Ghana commitments and allocate 0.5 GNI to R&D through a Research Fund.
    2. Support the UK’s work in partnership with the Federal Ministry of Innovation, Science and Technology (FMIST) in Nigeria. This should include a review of existing UK-Nigeria partnerships, which could form the basis of a bilateral strategy. Support the Ministry’s plans to establish a National Research Fund.
  2. Work with MESTI and FMIST to facilitate the commercialisation of innovative solutions in priority economic sectors e.g. agriculture, energy that have the potential to drive economic growth, and support value addition processes that enable the outputs to meet local, regional and international quality standards and good manufacturing practices to enable business development.
  3. Improving the innovation and/or technology policy and regulatory environment in Nigeria or Ghana, in partnership with FMIST and MESTI.
  4. Strengthen Government Digital Delivery Services in Nigeria and Ghana and enhance the capacity of public sector institutions to leverage digital technologies for efficient and transparent governance. The project will require implementing a mechanism to review existing service delivery frameworks, collaboratively design a service delivery model, and deliver a digital service delivery pilot or sandbox in collaboration with the relevant regulatory agencies and selected Ministries, Departments and Agencies of government.
  5. Develop a demand responsive helpdesk to support technology and innovation systems strengthening projects (between £10K-£100K) in partnership with FCDO, responding rapidly and directly to national and regional demand in Nigeria, Ghana, and capacity for French speaking countries in West Africa. This service should include flexible budgeting and ensure that work can be undertaken by the right people, without the need for waiting for procurement or contracting.
  6. Additional project activity within the scope of the ATIP Business Case, suggested by the organization(s) developing the proposal.

Key Requirements:
1. Delivery Model: an Accountable Grant (AG) with a Lead Implementing Partner lead based in Nigeria or Ghana as prime.
2. Results Framework and Project Targets: All proposals should include a Results Framework and the anticipated project targets, including targets for women and youth. The Results Framework must include clear indications of how results and impacts will be measured.
3. Project Activities: The proposals should provide details of proposed activities under each component and related costs over the project's lifecycle.

Indicative Budget Breakdown per Component
This is an indicative budget and should be readapted to suit your application.
Project Framework	Indicative Amount
a. Support the UK Government’s partnership with Government in Ghana and Nigeria	£400,000
b. Work with MESTI and FMIST to facilitate the commercialisation of innovative solutions in priority economic sectors	£400,000
c. Improving the innovation and/or technology policy and regulatory environment	£250,000
d. Strengthen Government Digital Delivery Services in Nigeria and Ghana	£250,000
e. Develop a demand responsive helpdesk to support technology and innovation system	£400,000
f. Additional project activity within the scope of the ATIP Business Case	£200,000
	Total = £1,900,000m

1. The Bidder will be expected to submit a budget using the Accountable Grant budget template available on GOV.UK.
2. The budget should include all include all delivery costs and any associated costs. The FCDO recognises the importance of Non-Project Attributable Costs (NPAC), and these costs should be included in the budget. No additional funding will be provided.
3. Selected Lead Implementing Partner(s) will sign an Accountable Grant Agreement (AGA) or a Memorandum of Understanding (MoU) with FCDO.

Project Management:
1. The Lead Implementing Partner should propose a core team of organisations to deliver the proposed activities as per the call for proposals. The proposed core team should have expertise in the key project technical areas, and experience working in the targeted geographies, along with essential competencies around project management and delivery. All proposals should outline the core team members, clearly articulating their roles and responsibilities.
2. The Lead Implementing Partner will be responsible for and ensure effective and efficient delivery of the downstream partners. The Lead Implementing Partner will ensure that downstream partners deliver to proposed time, cost, quality standards and performance, and ensure they comply with UK policies on child protection, gender, sexual exploitation, abuse and harassment (SEAH), social and environmental safeguards.

Reporting, Monitoring & Evaluation Requirements
1. Monitoring, Evaluation, Learning and Adaptation (MELA) and Risk Management: Proposals should provide a MELA plan and risk management plan. The Lead Implementing Partner will monitor progress of all activities towards the pre-agreed targets, and take proactive remedial action, offering support as needed to ensure partners meet their intended outcomes and results. This includes implementing robust and proactive performance management approaches, to track implementation and monitor project results. The Lead Implementing Partner will undertake regular monitoring meetings and visits, with a focus on assessing quality of delivery, and ensuring issues are identified and addressed in good time. FCDO field visits or monitoring visits should also be expected. In case of weak or slow delivery, the Lead Implementing Partner will use project improvement plans to address any weaknesses, and manage early closures, if required and agreed by FCDO.
2. Accountable Grant Management. This Accountable Grant is designed to be flexible, to adapt to the needs of Government partners. Therefore, FCDO and the Lead Implementing Partner, will need to collaborate closely on the Accountable Grant Workplan. In the first month of the Accountable Grant, the Lead Implementing will agree a high level workplan with FCDO to manage the Accountable Grant. The partner is expected to organise monthly in-person progress meetings with FCDO. The FCDO has staff based in Lagos, Abuja and Accra, and the meetings will virtually connect those locations. At these meetings the workplan will be reviewed, based on updates, and will form the core part of the activity management.
3. Quarterly Financial and Risk Reporting. The Lead Implementing Partner is expected to provide error free, relevant, and factual quarterly financial reports and update on any risk register changes. The financial report is expected to provide a breakdown of costs and expenses incurred in the quarter, against each component’s activities outlined in the budget. The report should provide variances between actual/forecast and budgeted costs. FCDO will require forecasts to be updated at least monthly, and shared with FCDO through monthly in-person progress meetings and quarterly financial reports. The financial reports should present delivery against high-level agreed results to demonstrate Value for Money (VfM).

Due Diligence
1. A Due Diligence Assessment (DDA) will be carried out on the selected Lead Implementing Partner organisation, prior to signing of the Accountable Grant Agreement to help identify and manage risks that could undermine the effective use of FCDO funds. Before entering any formal arrangement, FCDO must have a satisfactory level of assurance that the Lead Implementing Partner has the requisite capacity to deliver, account for funds, and report effectively. Any risks within the identified tolerance levels must be included in the risk matrix, mitigated, and managed.
2. The Lead Implementing Partner will be responsible for conducting the due diligence assessment of the downstream partners, taking on overall risk management and accountability for the quality of work delivered in the project. The Lead Implementing Partner must demonstrate a full and comprehensive approach for undertaking due diligence assessment of its downstream partners and provide this evidence to FCDO during the DDA process. As part of FCDO’s risk management process and to obtain further assurances across the delivery chain, FCDO may choose to commission specific project audits of all, or some of the sub-grantees' organisations.
3. The Lead Implementing Partner is responsible for providing capacity building for downstream partners as needed, to ensure that they can deliver effective, high quality project implementation, ensuring VfM is tracked and monitored effectively.

Duty of Care:
The Lead Implementing Partner and downstream partner are responsible for ensuring appropriate safety and security briefings, for all their personnel working under this agreement, including supply chain members and third parties involved in their project activities. Travel advice is available on the FCDO website, and consortium partners must ensure they (and their personnel) and supply chain members are up to date with the latest advice.

Inception Phase Deliverables:
1. when due diligence has been carried out, the project implementation will begin as soon as possible, with a maximum four (4) week inception phase, during which the following documents must be submitted:
  1. Finalise and agree with FCDO the implementation workplan. Deliverable: Implementation workplan.
  2. Lead Implementing Partner’s Due Diligence Assessment (DDA) of downstream partners completed and agreed action tracker finalised. Deliverable: Due Diligence Assessment reports and supporting evidence.
  3. Lead Implementing Partner signs agreements with all the named downstream partners. Deliverable: Signed partner agreements.
  4. Lead Implementing Partner ensures monitoring and evaluation measures are well set-up. Deliverable: FCDO approved MELA plan.
  5. Lead Implementing Partner ensures the best Value for Money (VfM) practices are identified and well set -up. Deliverable: VfM framework.
  6. Lead Implementing Partner prepares a comprehensive risk management and mitigation matrix. Deliverable: Risk register (template attached) and Delivery Chain Risk Mapping.
  7. Lead Implementing Partner finalises the theory of change, log frame target and programme targets. Deliverable: SANKORE log frame (template attached).

If any of these deliverables are not complete within the inception period, then FCDO may approve the Lead Implementing Partner to continue with finalising the inception deliverables, whilst starting implementation. However, due to the tight timeframes, the inception phase will not be extended (unless there are very compelling and unforeseen circumstances).

Proposal Guidelines & Evaluation Criteria:

Following the award of a grant, FCDO will work alongside the Lead Implementing Partner to further develop the programme during implementation. FCDO reserves the right to not fund, if the proposals do not meet the required standards. FCDO is also able to set up multiple agreements, if a single proposal does not meet the full scope adequately. The following table summarises the actions you will need to take to respond to this call.

STAGE	TASK
Proposal	Complete the following documents / Technical Proposal Template (20 pages max) / CVs of the team / Proposal budget - using the budget template (in GBP) / Risk register / Log frame targets using the existing ATIP logframe indicators / Proof of legal registration in Ghana or Nigeria (e.g. CAC documents) / Emailing your application: Please email your completed proposal (including the required documents above) to: accra.warih@fcdo.gov.uk / The deadline for the receipt of your applications is Friday, 25th October 2024, 12pm (UK Time). Enquiries must be submitted to the same email by 12th October 2024. / All Proposals should be submitted in English using the Proposal template. Where necessary, Visuals (figures and diagrams) should be included in a single (small) file attached as an annex. / The CVs should be in a separate document with the title CVs of the team. / When submitting your Proposal please: save the Proposal Template as Sankore Proposal Submission - [Lead organisations name].
Indicative application timelines	Applications are assessed and scored, and successful proposal(s) selected: 3 weeks. / Due diligence, [optional] proposal development in consultation with FCDO, and grant arrangements: 1 month / Inception phase: budget must include activities for this phase. Duration: 4 weeks / Start date for project implementation including inception phase: January 2025

   PROPOSAL: EVALUATION CRITERIA
Criteria	Sub-Criteria
Quality and suitability of the proposal: / Proposal provides strategic fit to the project objectives as detailed in the Call for Proposals (CfP).	Quality and suitability of proposal. Proposal provides strategic fit to the projects objectives in the call for proposals. Relevance of proposal to Objectives / Project Activity Framework. / Proposals will be evaluated based on key requirements first. Only those that meet these key requirements will then be assessed against the remaining criteria. / Project risk register and indicative log frame targets (using the existing ATIP log frame indicators). / Overall approach demonstrating quality, coherence, and suitability to deliver against the programme objectives & Theory of Change. / Suitability of Monitoring, Evaluation and Learning (MELA) framework, including a Value for Money approach. / Demonstrable experience in working with Governments in West Africa – and commitment to working to support Government colleagues to deliver the outcomes they are targeting. / Demonstrated experience leading projects of a similar geographic and technical scope. / Simple governance structure with clear accountability resting with Grant leads based in Nigeria or Ghana. / Proposals that include co-financing or in-kind support will be considered an advantage. / Delivery Chain Mapping includes clear roles and responsibilities for all the downstream partners. / Demonstrated ability (including through the workplan) to kick-off project implementation within the first month of agreement signing. / Proposal must show clear development impact and continuity beyond this project lifecycle.
Delivery capabilities and geographic spread of downstream partners	Demonstrated ability to manage AG mechanisms and effectively manage downstream partners to ensure efficient project. / Demonstrated understanding of local context, geographic reach and properly articulated approach to addressing issues with short-, medium- and longer-term outputs and outcomes developed.
Quality and suitability of the proposed team	A clear governance structure – which explicitly details how decisions will be made if there are disagreements between partners. / The capacity of the lead implementing partner and downstream partners to deliver.
Financial Criteria	Direct programme costs as a proportion of the overall budget and maximised value for money.

Annexure