Please enter the date the risk was added to the risk register in the DD/MM/YYYY format
## Project  Title
Please fill in the requested details below
Grant holder organisation name
PO Number
Grant reference number
Project partners (if relevant)
Project title
Project start date
Project end date
Person(s) responsible for risk updates

## FCDO Risk Guidance
Please read all guidance below before updating your risk register
Why: To provide all project partner(s) and FCDO with up to date information about substantial project risks and changes that could affect achieving the project objectives. This will help both parties to adequately identify, manage, mitigate, and, when necessary, escalate, substantial risks within the project . It will also inform quick and better decision making at all levels within the project, how risk is managed and lessons learnt during implementaion could be shared across the office and with other similar/future projects. / How should this Template be used?: Before preparing your Risk Register, you should read the full guidance notes. This template asks you to identify potential risk, the likelihood of occuring, the possible impact if the risk materiales on the project and the mitigation strategies to minimise it. When is this Report due?: The Risk Register is due at the beginning of the project and updated every quarter and submitted as an annex to the quarterly report on the agreed date for submission of quarterly report. Your risks must be reported in line with FCDO's structure, descriptions and ratings used included in this template. / This risk register should be used a live project management tool and historical record for the duration of your FCDO grant. Any risks that are closed/resolved over the course of the quarter should be moved to the bottom of the table and greyed out using the fill cell colour function in excel. The open risks should remain at the top of table without any colour fill in the cells. / Implementing Partners are expected to consider and document risks that are likely to occur in the coming months due to the scheduled activities or events on the horizon as well as any longer term, broader risks. It is expected that a range of risks from the seven FCDO categories are identified and documented. Please try to think beyond the more generic risks such as drought, political instability, or natural disasters and also include those that are directly related to the day-to-day delivery and operations of your project. / Recommend the need to consider all type of risks, including fiduciary and safeguarding. Avoid general statements such as “there is a risk of fraud” or “ there could be safeguarding risks” when recording these types of risks in the register. Fraud and safeguarding incidents are committed by individuals or organisations so when articulating these kinds of risks be specific about: / • Who will cause or could commit the risk? / • What activity will they undertake? What can happen? / • What the outcome will be? What can be the impact? / The project level risk register should be used in conjunction with the delivery chain risk map template as they complement each other and provide a more complete picture of what can affect the project. The delivery chain risk map captures risks specific to the delivery model and tiered funding structure. It should reflect the main risks specific to each tier of the chain.

Risk appetite / Risk appetite: For FCDO, risk appetite is “the amount of risk which the organisation is prepared to accept, tolerate or be exposed to at any point in time”. Risk is inherent in the challenging contexts in which we operate, so we aim to find an acceptable balance between the costs of managing the risks, and the likely costs and impacts if the risks materialise, as well as the costs of not acting. / Risk appetite is helpful in determining: / - How we should respond to risk when it materialises: we can respond to risk in five ways: / o Tolerate — consciously accept the level of risk; minor risks, particularly where they might require considerable action to reduce further, can be tolerated. This usually can ocurr when there are elements of the risk out of our or the partner's control (e.g. conflict, natural disaster...) or mitigations have limited effect. / o Transfer — transfer the risk to another party, for example, a delivery partner or by contracting insurance when possible ; / o Terminate — avoid, reduce the scope or funding of or terminate the activity or circumstance that gives rise to the risk; manage appropriately and proportionately the situation / o Treat — take action to change the likelihood that the risk will materialise or the impact should it materialise; most risks fall in this category — where we are looking to mitigate it by reducing the likelihood and/or the impact of the risk / o Take more risk: take more risk to pursue an opportunity / - When partners should escalate risks and changes: Partners should inform FCDO and document changes and risks that can potentially affect achieving objectives of the project or FCDO's reputation. These should be reflected in the risk register, included in the quarterly report to inform regular discussions. If a risk needs to be escalated, once mitigations are deemed to have reduced the likelihood or impact, risks can be de-escalated again.

RISK Categories / External Context: External context risk arising from the environment which we do not have control over but can affect the implementation of the programme. Examples of external context risk are Political, legal and judicial environment, conflict, economic and environmental factors. / Financial & Fiduciary: These are risks arising from our funds being used for unintended purposes or not managed in accordance with requirements and constraints, or poor management of assets/liabilities, resulting in weak value for money, compliance and delivery failures and reputational damage. FCDO will not tolerate our money being mishandled, misappropriated, or otherwise spent beyond the pre-agreed scope of our programmes. We take a zero-tolerance approach to fraud and corruption and report all suspicions and instances to reportingconcerns@FCDO.gov.uk. All fraud cases are recorded, reviewed and appropriate action taken. Lessons learned are shared to raise awareness and build knowledge of types of risks, enablers/red flags, and controls. / Operational: These are risks arising from weaknesses in the delivery of internal capacity to effectively oversee the implementation of the project and duty of care to staff. Examples include security, legal, technology and information and property risks, impacting delivery, capacity of staff, skills, knowledge and technical capability of staff and implementing partners, complexity of delivery chains, location, Complex governance structure etc / Safeguarding: These are risks arising from failure to establish and maintain strong safeguards to prevent harm to beneficiaries of your programmes, staff and those implementing the programmes, the communities where we work, or the environment, resulting in ethical violations and reputational damage. Since early 2018, FCDO has been focusing in particular on mitigating the risks of sexual exploitation and abuse and sexual harassment across the aid sector: FCDO expects all our partners to follow our lead and apply robust safeguards and reporting measures, through their own processes. / Policy and Programme Delivery: These are risks arising from implementation of the programme due to weaknesses in influence and engagement, programme delivery, commercial management, resourcing and/or operational support. / Reputational: risk arising from political or adverse events, including delivery failures and ethical violations, damaging FCDO’s and/or the UK’s reputation. We expect implementing partners to report on and mitigate potential reputational / People: These are risks arising from weaknesses in leadership and engagement, culture and behaviours and/or workforce capacity and capability, impacting on performance.

					his risk relates to our internal capacity to effectively oversee the implementation of the programme and duty of care to staff and implementing partners. Examples includes but not limited to capacity of staff, skills, knowledge and technical capability of staff and implementing partners, Complexity of delivery chains, location, Insufficient resources undermine staff morale and ability to deliver, Complex governance structure etc.

## Completing the RR
FCDO Risk Register Template
1 Risk Register / Field Guidance / The 'Name' field is a short risk title as a shorthand reference. / The 'Risk Description' field should set out a clear and concise description covering the cause, the risk event which the cause triggers and the consequence of the risk event. / The 'Risk Category' should identify the most appropriate risk category / The 'Proximity' field is the timeframe in which the risk might be expected to materialise. This is a best estimate. / 'Gross Likelihood' and 'Gross Impact' are the initial risk assessments before any risk treatment has been carried out and together make a risk rating (Minor, Moderate, Major, Severe). We should consider impact on our delivery/performance and our reputation. 'Residual Likelihood' and 'Residual Impact' are our risk assessments after risk treatment and should be based on current progress in implementing mitigations, rather than future mitigations not yet implemented. ' Risk Response' is how the risk is treated ( Terminate, Treat, Transfer or Tolerate). Please use the slection from the dropdown list. / 'Trend' indicates whether the risk is rising, steady or reducing relative to last review. / 'Risk Owner' is the individual who takes responsibility the risk . This individual retains ownership for the life of the risk until formally changed on the register. / The 'Mitigation Strategy' sets out how the risk is being treated. Please indicate if there are elements that are out of the control as this informs decisions. / 'Comments' can be used to capture discussion points. / 'Status' denotes whether a risk is active or closed. A closed risk is one that has gone away or has been successfully treated. (A risk that has materialised might still need to be kept in the register as, unless fully disapeared, it can become an issue again) / 'Risk Appetite' should be taken from the Risk Appetite Worksheet for the appropriate category.
3 Workbook Management The formulae in this workbook are not protected in order to allow the addition of new rows into the risk register. To add new rows, copy a complete blank row and use the 'Insert Copied Cells' command. This will replicate the formulae.

## Risk Register
Risk Register: Add Name of DG/Directorate/Post/Programme

S/N	Date risk was added	Risk Description (cause, event, consequence)	Risk Category	Proximity	Gross Likelihood	Gross Impact	Gross Risk Rating (autofills)	Risk Response	Indicators and triggers	Mitigation Strategy (including timescales)	Residual Likelihood	Residual Impact	Residual Risk Rating (autofills)	Trend/ Trajectory	Risk Owner	Progress in Implementing Mitigation Strategy	Last Updated / (DD/MM/YY)	Status	Escalated By? (Name of Risk Owner)	Escalation Type: For Information or Support	Date Escalated To This Register / (DD/MM/YY)	Escalated Further? (Name of Senior Manager/Board)	Escalation Type: For Information or Support	Date Escalated Further / (DD/MM/YY)	Date Removed	CLOSING RISKS
0		DO NOT FILL THIS ROW					#N/A		State triggers that could result in the risk materialising	Detail associated controls and mitigation actions			#N/A	↓					Did the risk materialise? When closing out the risk, confirm if the risk materialised	Date risk closed. When the risk has passed and is no longer open, enter the date the status was changed to 'closed'
1		Insecurity i.e. actions of armed state and non-state groups in Burkina Faso s					#N/A					#N/A
2					#N/A					#N/A
3					#N/A					#N/A
4					#N/A					#N/A
5					#N/A					#N/A
6					#N/A					#N/A
7					#N/A					#N/A
8					#N/A					#N/A
9					#N/A					#N/A
10					#N/A					#N/A
11					#N/A					#N/A
12					#N/A					#N/A
13					#N/A					#N/A
14					#N/A					#N/A
15					#N/A					#N/A
16					#N/A					#N/A

## Additional Code book
	Tolerate		Minimal
	Treat		Cautious
Terminate need to be nuanced.	Terminate		Receptive
	Transfer		Eager
	Tolerate and Treat

## Cell data Dont Change!
Impact	Likelihood	Appetite		Proximity		Escalation Decision		Escalation Level
Insignificant	Unlikely	Minimal	Minor	0-3months		Not accepted – content with director oversight		Project or Programme
Minor	Possible	Cautious	Moderate	3-6months		Accepted for additional DG oversight		Mission or Department
Moderate	Likely	Receptive	Major	6-12months		Accepted for additional DG oversight and support		Directorate
Major	Highly Likely	Eager	Severe	>12 months				Directorate General
Severe	Almost Certain
						Escalation Type
						For Information
						For Support
Yes	No
Minor	Moderate	Major
Trend
→	↑	↓	New

		PRR Strategic Risk Report References
Almost CertainInsignificant	Minor	1 Strategy / and context - HMG coherence
LikelyInsignificant	Minor	2 Strategy / and context- Strategic competition
PossibleInsignificant	Minor	3 Strategy / and context - Conflict and security
UnlikelyInsignificant	Minor	4 Strategy / and context - Allies and partners
UnlikelyMinor	Minor	5 Strategy / and context - Global economy
PossibleMinor	Minor	6 Policy and programme delivery - UK/EU future relationship negotiations
LikelyMinor	Minor	7 Policy and programme delivery - COVID-19 international response
Almost CertainMinor	Moderate	8 Policy and programme delivery - Supply chains
UnlikelyModerate	Minor	9 Policy and programme delivery -Climate and environment
PossibleModerate	Moderate	10 Policy and programme delivery - Humanitarian response
LikelyModerate	Moderate	11 People - Workforce
Almost CertainMajor	Severe	12 People - Change management
UnlikelyMajor	Moderate	13 People - Duty of care
Highly Likelyinsignificant	Minor	14 Public service delivery and operations - Crisis and consular
Highly LikelyMinor	Moderate	15 Public service delivery and operations - Estate and security
Highly LikelyModerate	Major	16 Public service delivery and operations - Data and cyber-security
Highly LikelyMajor	Severe	17 Financial and fiduciary - Public spending commitments
Highly LikelySevere	Severe	18 Financial and fiduciary - Fraud and aid diversion
PossibleMajor	Major	19 Safeguarding - Sexual exploitation, abuse and harassment
LikelyMajor	Major	20 Reputational - Reputation
Almost CertainMajor	Severe
Almost CertainModerate	Major
UnlikelySevere	Major
PossibleSevere	Severe
LikelySevere	Severe
Almost CertainSevere	Severe

Reputational
Financial and Fiduciary
Safeguarding
People
Public Service Delivery and Operations
Policy and Programme Delivery
Strategy and Context