## Cover
Building Safety Remediation Data Release, England: 31 August 2024
Back to Contents
Background
This publication provides data on 1) the remediation progress across MHCLG’s Building Safety Remediation portfolio, covering buildings in the ACM programme, Building Safety Fund, Cladding Safety Scheme, developer remediation contract and reported by registered providers of social housing, 2) Progress with remediation of high-rise (18 metres and over in height) residential buildings (including student accommodation and hotels) and publicly owned buildings with ACM cladding systems unlikely to meet Building Regulations in the ACM programme, 3) the progress of the Waking Watch Relief Fund and Waking Watch Replacement Fund, 4) progress with remediation of high-rise residential buildings with non-ACM cladding systems assessed as eligible for funding from the Building Safety Fund , 5) Progress with the applications for and remediation of medium-rise (11 – 18 metres in height) residential buildings in England and high-rise residential buildings outside of London with non-ACM cladding systems in the Cladding Safety Scheme, 6) progress of remediation of residential buildings 11 metres and over in height with life-safety defects under the developer remediation contract, 7) progress of remediation of residential buildings 11 metres and over in height with unsafe cladding reported by registered providers of social housing, 8) enforcement action taken by local authorities against 11m+ residential buildings with cladding defects under the Housing Act 2004.
Tables on the ACM programme, BSF, CSS, developer remediation contract and social housing surveys include buildings which can be in multiple schemes or data collections so counting across tables can result in double counting. Tab Combined_2 provides an overall summary of all remediation progress, without double counting.
Publication dates
The data tables in this spreadsheet were originally published on 19 September 2024.
The next publication is scheduled for 24 October 2024.
Useful Information
Further information on the data collection, data quality and definitions is available in the Technical Note published alongside these statistics.
Technical Note
Contact details
We are committed to improving and broadening this data release further in the months ahead and would welcome feedback both on the content of this data release and what could be further done in the future.
BuildingSafetyData2@communities.gov.uk
NewsDesk@communities.gov.uk
Date published: 19 September 2024

## Table_of_Contents
Building Safety Remediation Data Release Contents
Worksheet Name	Worksheet Title
Cover	Background information about the statistics.
Notes	Notes found in the tables.
ACM_1	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 August 2024
ACM_2	Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 August 2024
ACM_3	Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 August 2024
ACM_4	ACM remediation progress by local authority, England, 31 August 2024
ACM_5	ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 August 2024
ACM_6	ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 August 2024
ACM_7	Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 31 August 2024
ACM_8	ACM remediation progress by sources of funding, England, 31 August 2024
ACM_9	Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 August 2024
ACM_10	Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 August 2024
ACM_11	Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, time series, 31 August 2024
WWRF_1	Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 August 2024
WWRF_2	Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 August 2024
WWRF_3	Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 August 2024
BSF_1	Remediation status of eligible buildings within BSF by tenure, England, 31 August 2024
BSF_2	BSF remediation progress of eligible buildings by region, England, 31 August 2024
BSF_3	BSF number of eligible buildings with funding approved and expenditure amounts by tenure, England, 31 August 2024
BSF_4	BSF remediation progress of eligible buildings by local authority, England, 31 August 2024
BSF_5	Remediation status of eligible buildings within BSF, time series, England, 31 August 2024
Combined_1	Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 August 2024
Combined_2	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 August 2024
Combined_3	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, by local authority, England, 31 August 2024
Combined_4	Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys by remediation status, England, 31 August 2024
Combined_5	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by tenure, 31 August 2024
Combined_6	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, time series, 31 August 2024
Combined_7	Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by region, 31 August 2024
CSS_1	Application status of buildings within the CSS, England, 31 August 2024
CSS_2	CSS remediation progress by region, England, 31 August 2024
CSS_3	CSS remediation progress by height, England, 31 August 2024
CSS_4	CSS remediation progress by tenure, England, 31 August 2024
CSS_5	CSS number of eligible buildings by funding allocations, expenditure and tenure, England, 31 August 2024
CSS_6	CSS remediation progress, time series, England, 31 August 2024
Social_1	Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 31 August 2024
Social_2	Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 June 2024
Social_3	Provider by provider breakdown of buildings, by assessment status, England, 30 June 2024
Social_4	Provider by provider breakdown of buildings, by remediation status, England, 30 June 2024
Social_5	Remediation status of buildings with cladding defects monitored under the social housing surveys, time series, England, 30 June 2024
Developer_1	Remediation status of buildings covered by the developer remediation contracts by height group, England, 31 August 2024
Developer_2	Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 July 2024
Developer_3	Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 July 2024
Developer_4	Developer by developer breakdown of buildings covered by the developer remediation contract, by assessment status, England, 31 July 2024
Developer_5	Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 July 2024
Developer_6	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 July 2024
Developer_7	Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 31 July 2024
Developer_8	Developer by developer breakdown of buildings requiring remediation, which had not started works in the previous quarter England, 31 July 2024
Developer_9	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 31 July 2024
Developer_10	Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 31 July 2024
Developer_11	Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 31 July 2024
Developer_12	Remediation status of buildings requiring works under the developer remediation contract, time series, England, 31 July 2024
Enforcement_1	Enforcement action taken by local authorities against 11m+ buildings under the Housing Act (2004) by remediation programme status, England, 31 August 2024
Enforcement_2	Building inspections conducted by local authorities, England, 31 August 2024
Enforcement_3	Statutory notices served by local authorities under the Housing Act (2004), England, 31 August 2024
Enforcement_4	Number of building inspections by local authorities supported by the Joint Inspection Team, England, 31 August 2024
JIT_1	Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 August 2024

## Notes
Notes
Back to Contents
Note	Note Explanation	Note Location
[note 1]	Vacant buildings detailed in this table are included in table ACM_1 and ACM_2.	ACM_3
[note 2]	This table excludes local authorities with fewer than 10 high-rise residential buildings, regardless of whether they have unsafe cladding, and groups local authority figures into bands. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	ACM_4, Enforcement_1, Enforcement_2, Enforcement_3, Enforcement_4
[note 3]	Yet to complete remediation includes all dwellings in buildings that are yet to complete remediation works on-site	ACM_7
[note 4]	Social Sector Fund: Payments are made as cash grants, and will be payable in two tranches. The government will pay 80% of eligible costs at stage one. Once building owners confirm that they have tendered for the removal and replacement of cladding systems and work has started on site, we will make the first payment. Then we will pay the remaining 20% of eligible costs once building owners have submitted further evidence and confirmed final costs.	ACM_8
[note 5]	Private Sector Fund: The majority of private sector buildings receiving government funding for ACM remediation are funded through the Private Sector Cladding Remediation Fund. Payments from the Private Sector Cladding Remediation Fund will be made as cash grants and will be made on the basis of monthly valuations of work carried out on site, with an appropriate degree of due diligence, mirroring industry standard practice. Following Practical Completion the government will withhold a final payment which will be made on completion of the defects liability period. Eight private sector buildings are receving government funding from the Building Safety Fund, so do not appear in the totals in table ACM_9, but do in ACM_8.	ACM_8, ACM_9
[note 6]	The approved figure for the Private and Social Sector ACM Cladding Remediation Funds incorporates tendering support for applicants and approved project cost overrun. This figure reflects funding for the costs of remediation of unsafe ACM cladding only.	ACM_10
[note 7]	The Private Sector ACM Cladding Remediation Fund approved funding figure does not yet include any funds that will be reimbursed by developers who have signed the Pledge in relation to buildings they had a role in developing or refurbishing which have received government funding. All eligible applications to the Private Sector ACM Cladding Remediation Fund will be funded.	ACM_10
[note 8]	Expenditure for the Private and Social Sector ACM Cladding Remediation Funds is based on grant payments made by Delivery Partners to the applicant.	ACM_10
[note 9]	Private Sector ACM Cladding Remediation Fund (PSCRF) expenditure includes spend for non-ACM remediation works on buildings with unsafe ACM cladding funded through the PSCRF and therefore can exceed the amount approved which reflects unsafe ACM cladding remediation costs only.	ACM_10
[note 10]	Total figures may not sum due to rounding.	ACM_11, WWRF_1, WWRF_2, WWRF_3, BSF_1, BSF_2, BSF_3, BSF_5, Combined_4
[note 11]	The first tranche of the Waking Watch Relief Fund was administered by eight local/combined authorities alongside MHCLG. Further information on funding allocations by administering authority is available in the Waking Watch Relief Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_2
[note 12]	The Waking Watch Replacement Fund was administered by five local/combined authorities alongside MHCLG. Further information on funding allocations by administering authority is available in the Waking Watch Replacement Fund guidance at https://www.gov.uk/guidance/waking-watch-replacement-fund-2023	WWRF_3
[note 13]	Remediation complete figures in this table include buildings that have completed remediation but are still awaiting building control sign off.	BSF_2
[note 14]	Private sector and social sector financial viability buildings can receive pre-tender support allocation in addition to their full applications funding, but not all buildings receive this therefore these numbers cannot be added together to directly give a total.	BSF_3
[note 15]	This table includes allocation figures for buildings which have only non-ACM cladding and buildings which have both non-ACM and ACM cladding.	BSF_3
[note 16]	For buildings with both ACM and non-ACM cladding in this table, 'Remediation not Started' is assigned for buildings that have not started works on either type of cladding. 'Remediation Started' is assigned for buildings where work has started on remediating at least one type of cladding. 'Remediation complete: awaiting building control sign off' is assigned for buildings that have completed remediation but sign off is required for work on remediating at least one type of cladding. 'Remediation complete' is assigned for buildings that have completed, and received sign off, on works for the remediation of both types of cladding.	Combined_1, Combined_2, Combined_7
[note 17]	Buildings can be in multiple schemes and data collections. These tables show the unique number of buildings across the schemes without double counting buildings where they are in multiple schemes. The total here will be lower than the summed total number of buildings reported in each scheme.	Combined_1, Combined_2, Combined_7
[note 18]	Where buildings are in multiple schemes or data collections, the remediation stage assigned follows the rules in Note_16 for buildings in both the BSF and ACM programme. For further overlaps, remediation stages are assigned from schemes in this priority order: ACM, BSF, (or combined ACM and BSF), CSS, developer returns, social housing returns	Combined_2, Combined_7
[note 19]	Enforcement action is where an inspection under the Housing Act 2004's Housing Health and Safety Rating System has been organised/undertaken, and includes where a statutory notice has also then been served.	Enforcement_1
[note 20]	The Housing Health and Safety Rating System (HHSRS) is a risk-based assessment evaluation tool to help local authorities identify and protect against potential risks and hazards to health and safety from any deficiencies identified in residential premises. Each hazard has a weighting which will help determine whether the building is rated as having risks which are either category 1 or category 2. Where a risk is deemed to be category 1, a local authority has a duty to take enforcement action; where a risk is deemed to be category 2, an authority has the power to take action.	Enforcement_2
[note 21]	The Government-funded Joint Inspection Team, hosted by the Local Government Association, carries out building inspections on behalf of local authorities and provides expert advice to local authorities on enforcement on buildings with unsafe cladding.	Enforcement_4
[note 22]	The number of training sessions for Wandsworth and Richmond are combined as Merton, Wandsworth and Richmond operate a joint service where Merton officers attend training on behalf of Richmond and Wandsworth.	JIT_1
[note 23]	Buildings confirmed by delivery partners to be transferred to developers or the Cladding Safety Scheme have been withdrawn from the Building Safety Fund, which has led to a decrease in the number of eligible buildings in the Fund. The number of eligible buildings may continue to decrease as more buildings are confirmed as developer or CSS transfers out of the fund.	BSF_1, BSF_2, BSF_4, BSF_5
[note 24]	The Building Safety Fund first opened to registrations from June to July 2020 receiving registrations from 3,488 buildings. In July 2022 the Building Safety Fund reopened to new applications; this remains open to new applications from buildings in London over 18 metres in height (high-rise buildings outside of London can apply for remediation via the Cladding Safety Scheme). Buildings from both application periods are now combined as one Building Safety Fund, so numbers include both application periods.	BSF_1, BSF_2, BSF_3, BSF_4, BSF_5
[note 25]	Some buildings have an unknown remediation status reported by the developer. These have been interpreted as ‘Remediation not started – no plans in place’.	Developer_1
[note 26]	The buildings reported in this table as requiring remediation are estimated by MHCLG using information provided by developers in their data return and other data available within the department. In this table, a building is defined as requiring works under the developer remediation contract if it is either self-reported by the developer as requiring works; is an eligible building in the BSF or ACM and the developer has agreed to re-imburse the funds; has had money paid out by the BSF or ACM; or has a self-reported work status of either: works completed, works started, or works not started but plans in place. / They therefore differ from other published tables which reference only to the number of 'self-reported' buildings requiring works.	Developer_1
[note 27]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which are not being completed through government funds, unless they have Other Non-External Wall systems defects which the developer is remediating directly. The tables shows the number of buildings which have not yet started works; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Plans under Development' or where no status was provided. The table shows the estimated or actual start date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet started remediation work, but have an estimated or actual start date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_6, Developer_7
[note 28]	This table covers only buildings which have been self-reported by the developer as requiring works under the data return field Does this building require works?. This differs from the total figure of buildings requiring remediation in Developer_1, as that number is an estimate and includes the subset of buildings developers have self-reported. Please see [note 26] for further information)	Developer_3, Developer_4
[note 29]	The table holds data for 53 developers who have signed the contract. Data for one developer who signed the contract on the 31 January 2024 and data for a developer who has gone into administration are not included in this release. Data for the recent signatory will be added to future releases. / Some data has been supressed, as seen in the row 'Other (combined total for all developers with 5 or fewer buildings each' summarises information of 12 developers with five or fewer buildings, this includes: Abbey Developments, Allison Homes, Bloor, CG Fry, Courdace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata and William Davis. This data has been supressed due to the number of buildings being fewer than six and is represented in the data with a dash (-) in the data.	Developer_3, Developer_4, Developer_5, Developer_6, Developer_7, Developer_8, Developer_9, Developer_10, Developer_11
[note 30]	A building is interpreted as having an assessment if one or more of the following fields show as 'Yes' in the developer data return: Have you carried out an assessment of whether External Wall System (EWS) works are required on this building?; Have you carried out an assessment of whether non-EWS (other fire safety defects) works are required on this building?; Does the Building have an FSA?; Does the Building have an FRAEW?; or Does this building require works?	Developer_4
[note 31]	This column removes buildings requiring works which are being completed through government funds and reimbursed by the developer, as the developer cannot influence the pace of remediation on these buildings. However, those buildings being completed through government funds but which have Other Non-Externall Wall systems defects are included as the developer is remediating these directly themselves.	Developer_3
[note 32]	The data here is comprised of 'Don't know', 'Don't know - no assessment made' and blanks in response to the field 'Does this building require works?' regardless of whether the building has had an assessment or not.	Developer_3
[note 33]	The total estimated cost of remediation is based on the actual or estimated cost of remediating EWS and non-EWS defects reported by developers, and an assumed average where a cost has not been reported (averages are based on the developer-reported costs, by height).	Developer_2
[Note 34]	Data is taken from a building level survey issued to Registered Providers of Social Housing on their 11 metre plus buildings and is correct as at 30 June 2024. / Landlords were asked to respond to the survey for buildings in which they are the responsible entity. A 'Responsible Entity' is the organisation that has the legal obligation or right to carry out the remediation works. The Responsible Entity may be the building’s freeholder or head leaseholder, registered provider of social housing or a management company or Right To Manage (RTM) company that has primary responsibility for the repair of the property. / As a result, buildings within the survey may comprise of mixed tenure dwellings e.g., private leasehold and social rented dwellings, however remedial works will fall under the responsibility of the responding landlord. / Furthermore, landlords were asked to provide information on any life critical fire safety (LCFS) defects, which the survey defined as defects, shrinkages, faults or other failings in a building that give rise to fire safety risks. These are identified by: / 1) a Fire Risk Appraisal of External Wall construction (FRAEW) undertaken in accordance with PAS 9980 that assesses the external wall construction or cladding as not “medium - tolerable” (or better); or / 2) a fire risk assessment (FRA) that assesses the relevant parts of the building as high risk or medium risk or equivalent according to industry standards.	Social_1
[Note 35]	A building with EWS 'cladding defects' reported by Registered Providers of social housing' is defined as a building which has at least one Life-critical Fire-safety defect relating to an External Wall System (EWS) cladding defect. These buildings may also include non-cladding associated defects.	Social_1; Social_2a and Social 2b; Social_3; Social_4a and Social 4b
[Note 36]	The number of buildings identified as 'Remediation complete' may not match the number of social buildings being reported and complete under the BSF, ACM, CSS or developer contract due to the following: / 1) Non-responses to building level survey issued to Registered Providers of Social Housing - a small number or landlords did not respond to the survey, which means some buildings remediated through other remediation schemes may not be captured. / 2) Differences in how buildings are reported in the building level survey issued to Registered Providers of Social Housing - some buildings which have already completed remediation via other schemes have been reported as having no Life-Critical Fire-Safety defects in the survey, as the latest fire safety assessment has concluded that the the building is safe. Subsequently, the landlord has reported that no defects are present in the survey and have left the remediation category blank.	Social_1
[Note 37]	The data here includes buildings in the building level survey issued to Registered Providers of Social Housing, which may have also applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract. These are not excluded from the Social Housing Sector Management Information tables (Social_1).	Social_1
[note 38]	The total number of social high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 2 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 39]	The total number of social high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 1 building that falls under the developer remediation contract.	ACM_8
[note 40]	The total number of private high-rise buildings receiving government funding for the remediation of ACM cladding currently includes 20 buildings that fall under the developer remediation contract. These buildings will either be transferred from government funds, or will remain in the funds with developers reimbursing the department for the remediation costs.	ACM_8
[note 41]	The total number of private high-rise buildings not receiving government funding for the remediation of ACM cladding currently includes 69 buildings that fall under the developer remediation contract.	ACM_8
[note 42]	Data for the ACM, BSF and CSS are updated monthly. Developer data and data reported by Registered Providers of social housing are updated quarterly.	Combined_2, Combined_6, Combined_7
[note 43]	The number of buildings associated with particular expenditures paid out may also include buildings where a full reimbursement of funding has taken place, including those where required under the developer contract.	BSF_3
[note 44]	Buildings receive expenditure funding in stages and therefore these figures should not be used to calculate the average expenditure paid out to each building.	BSF_3, CSS_5
[note 45]	In this table where a local authority has 5 or fewer eligible BSF buildings, the numbers provided are banded. In all other cases the numbers are provided. These disclosure control measures are in place to prevent the identification of one or more buildings with cladding systems unlikely to meet Building Regulations in these areas.	BSF_4
[note 47]	One building with a live application to the CSS are in Northern Ireland, the remainder are in England.	CSS_1
[note 48]	Three eligible buildings in the CSS are in Northern Ireland, the remainder are in England.	CSS_1, CSS_2, CSS_3, CSS_4
[Note 50]	The data in this table is derived from the building level survey which has been submitted by Registered Providers of Social Housing on their 11 metre plus buildings and is correct as at 30 June 2024. It covers buildings in England over 11m which contain at least 1 unit of social housing for which the social housing provider is the Responsible Entity. / Some buildings in this table may have applied and are eligible for other remediation schemes e.g., ACM, BSF, CSS and developer contract.	Social_2a and Social 2b; Social_3; Social_4a and Social_4b
[Note 51]	Registered social housing providers who have five or fewer 11m+ buildings (which may or may not require EWS life-critical fire-safety works) have been grouped together in the ‘Other RPs’ row in the data table, in order to avoid inadvertently identifying individual buildings with EWS life-critical fire-safety defects.	Social_2a and Social 2b; Social_3; Social_4a and Social_4b
[Note 52]	A building works assessments should comply with the requirements of the Fire Safety Order, for example a Fire Risk Assessment or Fire Risk Appraisal of External Walls assessment (FRAEW).	Social_2a and Social_2b; Social_3
[Note 54]	Buildings reported as having completed remediation in the building level survey may require reassessment to confirm the building is now safe.	Social_1; Social_4a and Social_4b
[note 55]	These buildings are the subset of buildings which in the last developer data return (as at 31 October 2023), required remediation works, had not yet started remediation, but had an estimated or actual start date between 1 November 2023 and 31 January 2024. This table displays their current remediation status based on the data as at 31 January 2024.	Developer_8
[note 56]	The numbers reported in this table are a subset of the buildings which are self-reported by the developer as requiring remediation and which are not being completed through government funds, unless they have Other Non-External Wall systems defects the developer is remediating directly. The tables shows the number of buildings which have not yet started completed; this is a combination of buildings which are 'Remediation not started - Plans in Place' and 'Remediation not started - No Plans in Place', 'Remediation Started'. The table shows the estimated or actual completion date of works, where available. / This differs from the numbers provided in Developer_1 as it only looks at buildings which have not yet completed remediation work, but have an estimated or actual completion date included in the return and the buildings requiring works are calculated differently as per [note 26].	Developer_9, Developer_10
[Note 57]	Funding allocations of Full Applications Approved has reduced from previously published figures. This is the result of a data reconciliation exercise, where buildings transferring from the BSF to the Responsible Actors Scheme and Cladding Safety Scheme have had their BSF funding allocation removed.	BSF_3
[Note 58]	The 'Other' tenure includes buildings that are recorded in the ACM programme as student, hotel or public buildings.	Combined_5
[Note 59]	The estimates in this table include buildings which are: / a) reported in the latest survey (as at 30 June 2024) as having unsafe cladding at the time of their most recent assessment; / b) reported in previous surveys (as at 30 November 2023 and as at 31 March 2024) as having unsafe cladding which have completed remediation since then; / c) reported in the latest survey (as at 30 June 2024) as having unsafe cladding found since June 2017 but prior to the most recent survey, which have since been remediated; / d) being monitored under another government programme (BSF, ACM, CSS or RAS) due to having unsafe cladding.	Social_1
[Note 60]	Until May 2024, private sector funding allocations and expenditures included buildings which have successful social sector financial viability claims. This is because both private sector and social sector financial viability buildings receive full government funding, whereas those in the social sector receive partial funding dependant on the number of eligible leaseholders who pay a service charge. For full details please refer to the accompanying technical note.	[BSF_3]
[Note 61]	Until the May 2024 data release, social sector buildings with a successful financial viability claim were included in the "Private" figures due to them receiving funding for all work, rather than a percentage based on the number of leaseholders that pay a service charge. These buildings are now split out into the "social sector financially viability" category. Further details on the difference between these can be found in the accompanying technical note.	[BSF_1]
[Note 62]	This table depicts the number of buildings that are estimated to require works which have transferred from the Building Safety Fund (BSF), having been eligible at some point. This figure is based on the developer's dataset definition of a building and differs to the number reported by the BSF because of difference in building definitions.	Developer_1
[Note 63]	The estimates in this table include buildings which are reported in the latest survey (as at 30 June 2024) as having unsafe cladding at the time of their most recent works assessment. They do not include buildings which are reported in the latest survey (30 June 2024) as having unsafe cladding found since June 2017, which have since been remediated. / They also do not include buildings that were identified through other government programmes (BSF, ACM, CSS or RAS) but were not identified by social housing providers as having unsafe cladding.	Social_1; Social 2b; Social 4b
[Note 64]	The December 2018 and December 2019 ACM remediation progress figures did not include the breakdowns for 'remediation started - cladding removed' and 'works complete awaiting building control signoff'. Those buildings which had started remediation and removed unsafe cladding are included in the 'remediation started' category, and those that were awaiting building control sign off may have been included in the 'completed remediation' category	ACM_11
[Note 65]	Up to October 2023 combined remediation progress in the Building Safety Fund (BSF) and ACM programme is shown. Between June 2023 and September 2023 there was a decrease in the number of buildings due to buildings transferring from the BSF to being remediated by developers. From October 2023 onwards combined remediation progress is shown across the BSF, ACM programme, Cladding Safety Scheme, developer remediation contract and as reported by registered providers of social housing.	Combined_6
[Note 66]	Between June 2023 and July 2023 there was a decrease in the number of buildings due to buildings transferring from the BSF to being remediated by developers.	BSF_5
[Note 67]	This table is updated quarterly with the latest data and therefore may not align with monthly figures where the programme data is updated.	Developer_12
[Note 68]	The estimates in this table include buildings which are reported in the latest survey (as at 30 June 2024) as having unsafe cladding: / a) at the time of their most recent assessment. / b) found since June 2017 but prior to the most recent survey, which have since been remediated. / The estimates in this table do not include buildings that were identified through other government programmes (BSF, ACM, CSS or RAS) but were not identified by social housing providers as having unsafe cladding.	Social_1; Social 2a; Social 4a
[Note 69]	In previous Building Safety Remediation releases, this table was known as 'Building inspections conducted by local authorities'. As of the August 2024 release, this table reports the category assigned from the most recent building inspection.	Enforcement_2
[Note 70]	The Mar-24 and Jun-24 estimates are not comparable to previous quarters due to a change in methodology in reporting social housing sector remediation. Since Mar-24, the estimates include buildings which have been reported by Registered Providers to have completed remediation since June 2017 but prior to the most recent assessment. They also include social buildings the department has identified in other remediation programmes as having unsafe cladding and are also being monitored in those programmes.	Social_5
[Note 71]	This table excludes local authorities with fewer than 10 11m+ buildings monitored with unsafe cladding. These disclosure control measures are in place to prevent the identification of one or more buildings with unsafe cladding in these areas.	Combined_3

## ACM_1
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, by tenure, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Tenure	Number of buildings this month	Number of buildings last month	Monthly change
Social sector residential	162	161	1
Private sector residential	241	239	2
Student accommodation	60	59	1
Hotels	32	32	0
Publicly-owned buildings	8	8	0
Total buildings	503	499	4

## ACM_2
Remediation status of buildings with ACM cladding systems unlikely to meet Building Regulations by tenure, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Remediation Category	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: all tenures / Number	Total: all tenures / Percentage (%)
Completed Remediation	134	83%	192	80%	54	90%	25	78%	7	88%	412	82%
Works complete awaiting building control signoff	9	6%	14	6%	2	3%	4	13%	1	13%	30	6%
Remediation started - cladding removed	18	11%	12	5%	0	0%	1	3%	0	0%	31	6%
Remediation started	0	0%	14	6%	2	3%	1	3%	0	0%	17	3%
Remediation plans in place	0	0%	7	3%	1	2%	0	0%	0	0%	8	2%
Reported an intent to remediate	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	1	1%	1	0%	1	2%	1	3%	0	0%	4	1%
Total buildings	162	100%	241	100%	60	100%	32	100%	8	100%	503	100%

## ACM_3
Remediation status of buildings yet to complete ACM remediation by tenure, England, 31 August 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff - Vacant	0	1	0	1	0
Remediation started - cladding removed - Vacant	0	1	0	0	0
Remediation started - Vacant	0	0	0	0	0
Remediation plans in place - Vacant	0	0	0	0	0
Reported an intent to remediate - Vacant	0	1	0	0	0
Remediation plan unclear - Vacant	0	0	0	0	0
Total vacant buildings	0	3	0	1	0

Remediation Category for occupied buildings	Social sector residential	Private sector residential	Student accommodation	Hotels	Publicly-owned buildings
Works complete awaiting building control signoff	9	13	2	3	1
Remediation started - cladding removed	18	11	0	1	0
Remediation started	0	14	2	1	0
Remediation plans in place	0	7	1	0	0
Reported an intent to remediate	0	0	0	0	0
Remediation plan unclear	1	1	1	1	0
Total occupied buildings	28	46	6	6	1

## ACM_4
ACM remediation progress by local authority, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_2]	Number of buildings identified with ACM cladding systems (unlikely to meet Building Regulations)	Number of buildings with ACM cladding systems (unlikely to meet Building Regulations) yet to be remediated	Percentage of buildings with ACM cladding systems completed remediation	Percentage of buildings with ACM cladding systems started or completed remediation
Barking and Dagenham	1 to 5	1 to 5	Between 50% and 99%	100%
Barnet	6 to 10	1 to 5	Between 50% and 99%	100%
Bedford	1 to 5	None	100%	100%
Birmingham	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Bournemouth, Christchurch and Poole	1 to 5	1 to 5	Less than 50%	100%
Bradford	1 to 5	None	100%	100%
Brent	11 to 20	11 to 20	Less than 50%	Between 50% and 99%
Brighton and Hove	1 to 5	None	100%	100%
Bristol, City of	6 to 10	None	100%	100%
Bromley	1 to 5	None	100%	100%
Calderdale	1 to 5	None	100%	100%
Camden	6 to 10	6 to 10	Less than 50%	Between 50% and 99%
City of London	1 to 5	None	100%	100%
Croydon	6 to 10	1 to 5	Between 50% and 99%	100%
Dacorum	1 to 5	None	100%	100%
Doncaster	1 to 5	None	100%	100%
Ealing	1 to 5	1 to 5	Between 50% and 99%	100%
Elmbridge	1 to 5	None	100%	100%
Gateshead	1 to 5	None	100%	100%
Greenwich	Over 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Hackney	11 to 20	1 to 5	Between 50% and 99%	100%
Hammersmith and Fulham	6 to 10	None	100%	100%
Haringey	6 to 10	1 to 5	Between 50% and 99%	100%
Harrow	1 to 5	None	100%	100%
Havering	1 to 5	None	100%	100%
Hillingdon	1 to 5	1 to 5	Between 50% and 99%	Between 50% and 99%
Hounslow	1 to 5	None	100%	100%
Islington	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Kensington and Chelsea	1 to 5	None	100%	100%
Kingston upon Thames	1 to 5	None	100%	100%
Kirklees	1 to 5	None	100%	100%
Lambeth	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Leeds	6 to 10	None	100%	100%
Leicester	1 to 5	None	100%	100%
Lewisham	1 to 5	1 to 5	Between 50% and 99%	100%
Lincoln	1 to 5	None	100%	100%
Liverpool	11 to 20	1 to 5	Between 50% and 99%	100%
Luton	1 to 5	1 to 5	Less than 50%	100%
Manchester	Over 20	1 to 5	Between 50% and 99%	100%
Medway	1 to 5	None	100%	100%
Merton	1 to 5	None	100%	100%
Milton Keynes	1 to 5	1 to 5	Less than 50%	100%
Newcastle upon Tyne	6 to 10	None	100%	100%
Newham	Over 20	1 to 5	Between 50% and 99%	100%
Norwich	6 to 10	1 to 5	Between 50% and 99%	100%
Nottingham	6 to 10	None	100%	100%
Oldham	1 to 5	None	100%	100%
Plymouth	1 to 5	None	100%	100%
Portsmouth	1 to 5	1 to 5	Between 50% and 99%	100%
Reading	1 to 5	1 to 5	Between 50% and 99%	100%
Redbridge	1 to 5	None	100%	100%
Salford	Over 20	6 to 10	Between 50% and 99%	100%
Sandwell	1 to 5	None	100%	100%
Sefton	1 to 5	None	100%	100%
Sheffield	6 to 10	1 to 5	Between 50% and 99%	100%
Slough	1 to 5	1 to 5	Between 50% and 99%	100%
Southend-on-Sea	1 to 5	1 to 5	Less than 50%	Less than 50%
Southwark	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Stockton-on-Tees	1 to 5	None	100%	100%
Sunderland	6 to 10	1 to 5	Between 50% and 99%	Between 50% and 99%
Sutton	1 to 5	1 to 5	Between 50% and 99%	100%
Tower Hamlets	Over 20	6 to 10	Between 50% and 99%	Between 50% and 99%
Trafford	1 to 5	None	100%	100%
Waltham Forest	1 to 5	None	100%	100%
Wandsworth	11 to 20	1 to 5	Between 50% and 99%	100%
Westminster	11 to 20	1 to 5	Between 50% and 99%	Between 50% and 99%
Windsor and Maidenhead	1 to 5	None	100%	100%
Wolverhampton	1 to 5	None	100%	100%

## ACM_5
ACM remediation progress by tenure for Greater Manchester, London and the Rest of England, 31 August 2024
Back to Contents
This worksheet contains three tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Manchester	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	38	81%	16	89%	5	100%	2	100%	0	0%	61	85%
Works complete awaiting building control signoff	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation started - cladding removed	9	19%	2	11%	0	0%	0	0%	0	0%	11	15%
Remediation started	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Plans in place	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	47	100%	18	100%	5	100%	2	100%	0	0%	72	100%

London	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	64	78%	134	80%	12	80%	11	73%	0	0%	221	79%
Works complete awaiting building control signoff	9	11%	6	4%	1	7%	2	13%	1	100%	19	7%
Remediation started - cladding removed	9	11%	9	5%	0	0%	1	7%	0	0%	19	7%
Remediation started	0	0%	11	7%	0	0%	1	7%	0	0%	12	4%
Plans in place	0	0%	6	4%	1	7%	0	0%	0	0%	7	2%
Responded with intent	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	1%	1	7%	0	0%	0	0%	2	1%
Total buildings	82	100%	168	100%	15	100%	15	100%	1	100%	281	100%

Rest of England	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	32	97%	42	76%	37	93%	12	80%	7	100%	130	87%
Works complete awaiting building control signoff	0	0%	8	15%	1	3%	2	13%	0	0%	11	7%
Remediation started - cladding removed	0	0%	1	2%	0	0%	0	0%	0	0%	1	1%
Remediation started	0	0%	3	5%	2	5%	0	0%	0	0%	5	3%
Plans in place	0	0%	1	2%	0	0%	0	0%	0	0%	1	1%
Responded with intent	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Remediation plan unclear	1	3%	0	0%	0	0%	1	7%	0	0%	2	1%
Total buildings	33	100%	55	100%	40	100%	15	100%	7	100%	150	100%

## ACM_6
ACM remediation progress by date identified with unsafe ACM cladding and by tenure, England, 31 August 2024
Back to Contents
This worksheet contains four tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Identified by 31 December 2019	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	Total: All Tenures / Number	Total: All Tenures / Percentage(%)
Remediation completed	128	83%	169	90%	51	98%	23	85%	7	88%	378	88%
Works complete awaiting building control signoff	8	5%	5	3%	1	2%	3	11%	1	13%	18	4%
Remediation started - cladding removed	18	12%	7	4%	0	0%	1	4%	0	0%	26	6%
Remediation started	0	0%	5	3%	0	0%	0	0%	0	0%	5	1%
Plans in place	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Responded with intent	0	0%	1	1%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	154	100%	188	100%	52	100%	27	100%	8	100%	429	100%

Identified by 31 December 2020	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	129	83%	184	87%	52	96%	24	83%	7	88%	396	86%
Works complete awaiting building control signoff	9	6%	10	5%	2	4%	4	14%	1	13%	26	6%
Remediation started - cladding removed	18	12%	9	4%	0	0%	1	3%	0	0%	28	6%
Remediation started	0	0%	6	3%	0	0%	0	0%	0	0%	6	1%
Plans in place	0	0%	2	1%	0	0%	0	0%	0	0%	2	0%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	156	100%	212	100%	54	100%	29	100%	8	100%	459	100%

Identified by 31 December 2021	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	133	83%	188	83%	53	95%	25	81%	7	88%	406	84%
Works complete awaiting building control signoff	9	6%	11	5%	2	4%	4	13%	1	13%	27	6%
Remediation started - cladding removed	18	11%	12	5%	0	0%	1	3%	0	0%	31	6%
Remediation started	0	0%	11	5%	0	0%	1	3%	0	0%	12	2%
Plans in place	0	0%	3	1%	1	2%	0	0%	0	0%	4	1%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	0	0%	0	0%	0	0%	0	0%	0	0%
Total buildings	160	100%	226	100%	56	100%	31	100%	8	100%	481	100%

Identified by 31 December 2022	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	133	83%	190	82%	53	95%	25	81%	7	88%	408	84%
Works complete awaiting building control signoff	9	6%	13	6%	2	4%	4	13%	1	13%	29	6%
Remediation started - cladding removed	18	11%	12	5%	0	0%	1	3%	0	0%	31	6%
Remediation started	0	0%	12	5%	0	0%	1	3%	0	0%	13	3%
Plans in place	0	0%	3	1%	1	2%	0	0%	0	0%	4	1%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	160	100%	232	100%	56	100%	31	100%	8	100%	487	100%

Identified by 31 December 2023	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	134	83%	190	80%	53	91%	25	81%	7	88%	409	83%
Works complete awaiting building control signoff	9	6%	14	6%	2	3%	4	13%	1	13%	30	6%
Remediation started - cladding removed	18	11%	12	5%	0	0%	1	3%	0	0%	31	6%
Remediation started	0	0%	13	5%	2	3%	1	3%	0	0%	16	3%
Plans in place	0	0%	6	3%	1	2%	0	0%	0	0%	7	1%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Total buildings	161	100%	237	100%	58	100%	31	100%	8	100%	495	100%

All buildings identified	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Student accommodation / Number	Student / accommodation / Percentage (%)	Hotels / Number	Hotels / Percentage (%)	Publicly-owned buildings / Number	Publicly-owned buildings / Percentage (%)	All Tenures / Number	All Tenures / Percentage(%)
Remediation completed	134	83%	192	80%	54	90%	25	78%	7	88%	412	82%
Works complete awaiting building control signoff	9	6%	14	6%	2	3%	4	13%	1	13%	30	6%
Remediation started - cladding removed	18	11%	12	5%	0	0%	1	3%	0	0%	31	6%
Remediation started	0	0%	14	6%	2	3%	1	3%	0	0%	17	3%
Plans in place	0	0%	7	3%	1	2%	0	0%	0	0%	8	2%
Responded with intent	0	0%	1	0%	0	0%	0	0%	0	0%	1	0%
Remediation plan unclear	1	1%	1	0%	1	2%	1	3%	0	0%	4	1%
Total buildings	162	100%	241	100%	60	100%	32	100%	8	100%	503	100%

## ACM_7
Number of dwellings in buildings identified with unsafe ACM cladding by remediation status, England, 31 August 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed	9,800	15,400	18,500	25,200	28,300
Works complete awaiting building control signoff	300	900	1,000	1,200	1,300
Yet to complete remediation [note_3]	1,800	3,300	3,400	5,100	5,200
Occupied and yet to complete remediation	1,800	3,200	3,300	5,000	5,100

Leasehold dwellings	Dwellings in social sector buildings: estimate	Dwellings in private sector buildings: Low estimate	Dwellings in private sector buildings: High estimate	Total dwellings: Low estimate	Total dwellings: High estimate
Remediation completed	2,800	15,400	18,500	18,200	21,300
Works complete awaiting building control signoff	100	900	1,000	1,000	1,100
Yet to complete remediation [note_3]	500	3,300	3,400	3,800	3,900
Occupied and yet to complete remediation	500	3,200	3,300	3,700	3,800

## ACM_8
ACM remediation progress by sources of funding, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category	In social fund / [note 4]	Not in social fund	Private: government funded / [note 5]	Private: not government funded
Remediation completed	127	7	83	109
Works complete awaiting building control signoff	9	0	7	7
Remediation started - cladding removed	8	10	10	2
Remediation started	0	0	10	4
Plans in place	0	0	6	1
Responded with intent	0	0	0	1
Remediation plan unclear	0	1	0	1
Total	144	18	116	125

## ACM_9
Application progress of ACM buildings funded by the Private Sector Cladding Remediation Fund within and outside of London, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Category	Number of buildings inside London	Number of buildings outside London
No contact with delivery partners	0	0
Preparing application	0	0
Eligibility application submitted	0	0
Eligibility approved	0	0
Applications approved: for pre-contract support	2	1
Full cost application submitted	0	0
Applications approved: for full costs	66	39
TOTAL	68	40

## ACM_10
Funding approved and expenditure by the Private Sector Cladding Remediation Fund and Social Sector Cladding Remediation Fund, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Funding	Social Sector / (£ million)	Private Sector / (£ million)
Approved [note_6, note_7]	297	232
Expenditure [note_8, note_9]	271	310

## ACM_11
Number of buildings identified with ACM cladding systems unlikely to meet Building Regulations, time series, 31 August 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note 64]	Dec-18 / Number	Dec-19 / Number	Dec-20 / Number	Dec-21 / Number	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number
Completed Remediation	67	135	216	289	354	357	357	357	359	360	364	367	368	369	369	388	397	399	401	401	405	406	408	411	412
Works complete awaiting building control signoff			33	64	53	50	51	51	51	52	51	52	54	53	53	34	28	31	32	32	30	30	29	27	30
Remediation started - cladding removed			48	57	35	36	36	37	38	38	38	36	35	37	38	39	37	35	33	33	33	33	32	33	31
Remediation started	101	123	120	39	21	21	21	21	19	18	15	15	13	13	13	15	14	15	19	21	19	18	18	17	17
Remediation plans in place	171	104	32	15	13	12	11	12	12	14	14	15	15	15	15	14	13	14	9	7	8	8	8	8	8
Reported an intent to remediate	40	78	11	15	9	9	11	10	10	7	7	5	5	3	3	1	2	1	1	1	1	1	1	1	1
Remediation plan unclear	58	10	2	2	2	3	3	2	1	1	1	1	2	2	4	5	5	1	1	1	2	2	2	2	4
Total buildings	437	450	462	481	487	488	490	490	490	490	490	491	492	492	495	496	496	496	496	496	498	498	498	499	503

Remediation Category [note 10]	Dec-18 / Percentage (%)	Dec-19 / Percentage (%)	Dec-20 / Percentage (%)	Dec-21 / Percentage (%)	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 / Percentage (%)	May-24 / Percentage (%)	Jun-24 / Percentage (%)	Jul-24 / Percentage (%)	Aug-24 / Percentage (%)
Completed Remediation	15%	30%	47%	60%	73%	73%	73%	73%	73%	73%	74%	75%	75%	75%	75%	78%	80%	80%	81%	81%	81%	82%	82%	82%	82%
Works complete awaiting building control signoff			7%	13%	11%	10%	10%	10%	10%	11%	10%	11%	11%	11%	11%	7%	6%	6%	6%	6%	6%	6%	6%	5%	6%
Remediation started - cladding removed			10%	12%	7%	7%	7%	8%	8%	8%	8%	7%	7%	8%	8%	8%	7%	7%	7%	7%	7%	7%	6%	7%	6%
Remediation started	23%	27%	26%	8%	4%	4%	4%	4%	4%	4%	3%	3%	3%	3%	3%	3%	3%	3%	4%	4%	4%	4%	4%	3%	3%
Remediation plans in place	39%	23%	7%	3%	3%	2%	2%	2%	2%	3%	3%	3%	3%	3%	3%	3%	3%	3%	2%	1%	2%	2%	2%	2%	2%
Reported an intent to remediate	9%	17%	2%	3%	2%	2%	2%	2%	2%	1%	1%	1%	1%	1%	1%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%
Remediation plan unclear	13%	2%	0%	0%	0%	1%	1%	0%	0%	0%	0%	0%	0%	0%	1%	1%	1%	0%	0%	0%	0%	0%	0%	0%	1%
Total buildings	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## WWRF_1
Waking Watch Relief and Replacement Fund applications, buildings and approved funding, 31 August 2024
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Tranche	Applications	Buildings	Approved Applications	Approved Buildings	Leasehold dwellings in approved buildings	Approved Funding / (£ million)	Mean Waking Watch cost per month per dwelling in approved buildings / (£)	Median Waking Watch cost per month per dwelling in approved buildings / (£)	Buildings with alarm installation complete
Waking Watch Relief Fund	329	468	212	320	24,700	27.3	169	104	304
Waking Watch Replacement Fund	38	67	25	47	2,200	2.4	216	210	42
Total [note_10]	367	535	237	367	26,900	29.7	172	106	346

## WWRF_2
Waking Watch Relief Fund applications, buildings and approved funding by administering authority, 31 August 2024
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_11]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	9	8	1	0	0	11%	89%	9	8	89%	3%	1.6	200,826	180,147
Bristol	3	2	1	0	0	33%	67%	3	2	67%	1%	0.1	46,256	46,256
Greater London Authority	110	65	29	16	0	26%	59%	171	111	65%	35%	8.3	74,911	64,551
Greater Manchester Combined Authority	25	20	5	0	0	20%	80%	38	33	87%	10%	2.5	75,477	76,928
Leeds	10	9	0	1	0	0%	90%	12	11	92%	3%	1.8	162,466	124,500
Liverpool	18	17	1	0	0	6%	94%	19	18	95%	6%	1.7	94,400	63,784
Newcastle	3	3	0	0	0	0%	100%	3	3	100%	1%	0.4	128,496	163,181
Sheffield	6	5	0	1	0	0%	83%	7	6	86%	2%	0.5	88,753	87,828
MHCLG (1st Tranche)	35	21	14	0	0	40%	60%	55	39	71%	12%	2.7	69,807	65,577
MHCLG (2nd Tranche)	60	27	32	1	0	53%	45%	70	34	49%	11%	3.8	112,303	81,624
MHCLG (3rd Tranche)	50	35	14	1	0	28%	70%	81	55	68%	17%	3.9	70,341	57,389
MHCLG Total	145	83	60	2	0	41%	57%	206	128	62%	40%	10.4	81,324	65,486
Total [note_10]	329	212	97	20	0	29%	64%	468	320	68%	100%	27.3	85,371	67,894

## WWRF_3
Waking Watch Replacement Fund applications, buildings and approved funding by administering authority, 31 August 2024
Back to Contents
This worksheet contains one table.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Administering Authority [note_12]	Applications	Approved Applications	Rejected Applications	Withdrawn Applications	Pending Applications	Application rejection rate / Percentage (%)	Application approval rate / Percentage (%)	Buildings	Approved Buildings	Building approval rate / Percentage (%)	Approved buildings / (% share)	Approved Funding / (£ million)	Mean funding per building / (£)	Median funding per building / (£)
Birmingham	2	2	0	0	0	0%	100%	4	4	100%	9%	0.4	89,328	87,683
MHCLG	25	21	1	3	0	4%	84%	46	40	87%	85%	1.8	45,360	26,643
Greater Manchester Combined Authority	11	2	9	0	0	82%	18%	17	3	18%	6%	0.2	65,206	46,743
Leeds	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Liverpool	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Sheffield	0	0	0	0	0	0%	0%	0	0	0%	0%	0	0	0
Total [note_10]	38	25	10	3	0	26%	66%	67	47	70%	100%	2.4	50,369	30,209

## BSF_1
Remediation status of eligible buildings within BSF by tenure, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note 23][note 61]	Social sector residential (leaseholder) / Number	Social sector residential (leaseholder) / Percentage (%)	Social Sector Financial Viability Number	Social Sector Financial Viability Percentage (%)	Social Sector Total Number	Social Sector Total Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)	Total residential Number	Total residential Percentage (%)
Remediation complete	48	28%	4	20%	52	28%	158	26%	210	26%
Remediation complete: awaiting building control sign-off	19	11%	5	25%	24	13%	92	15%	116	14%
Remediation started	46	27%	0	0%	46	24%	145	24%	191	24%
Remediation not yet started	56	33%	11	55%	67	35%	221	36%	288	36%
Total buildings [note 10]	169	100%	20	100%	189	100%	616	100%	805	100%

## BSF_2
BSF remediation progress of eligible buildings by region, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note 23]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF / Percentage(%)	Not Started Remediation / Number	Not Started Remediation / Percentage(%)	Started Remediation / Number	Started Remediation / Percentage(%)	Completed Remediation [note_13] / Number	Completed Remediation [note_13] / Percentage(%)	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible BSF buildings that have started or completed remediation / Percentage (%)
North West	93	12%	7	2%	35	18%	51	16%	55%	92%
London	547	68%	263	91%	116	61%	168	52%	31%	52%
East of England	16	2%	2	1%	3	2%	11	3%	69%	88%
East Midlands	15	2%	2	1%	5	3%	8	2%	53%	87%
North East	8	1%	4	1%	1	1%	3	1%	38%	50%
South East	46	6%	2	1%	3	2%	41	13%	89%	96%
South West	25	3%	3	1%	11	6%	11	3%	44%	88%
West Midlands	12	1%	1	0%	4	2%	7	2%	58%	92%
Yorkshire and The Humber	43	5%	4	1%	13	7%	26	8%	60%	91%
Total [note 10]	805	100%	288	100%	191	100%	326	100%	40%	64%

## BSF_3
BSF number of eligible buildings by funding allocations, expenditure and tenure, England, 31 August 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.
Some cells in this table are empty because data is not available for these variables.
Table BSF_3a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the BSF .
Funding Allocations [note_15][note_57][note_60]	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Financial Viability Number of Buildings [Note 14]	Social Sector Financial Viability (£ millions)	Social Sector Residential (leaseholder) / Number of Buildings	Social Sector Residential (leaseholder) / (£ millions)	Total Funding / (£ millions)
Full Applications Approved	451	1,796	5	5
Pre-Tender Support Allocations	705	290	5	2
Total [note 10]		2,085		7	111	224	2,316

Table BSF_3b: Amount of expenditure from the BSF by tenure.
Expenditure [note_43][note_44][note_60]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Financial Viability Number of Buildings	Social Sector Financial Viability (£ millions)	Social Sector Residential (leaseholder) / Number of Buildings	Social Sector Residential (leaseholder) / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	756	1,513	9	6	88	175	853	1,695

## BSF_4
BSF remediation progress of eligible buildings by local authority, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.[note_23, note_24]
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_45]	Eligible Buildings in the BSF / Number	Eligible Buildings in the BSF yet to be remediated / Number	Completed Remediation / Percentage(%)	Started or Completed Remediation / Percentage(%)
Adur	1-5	0	100%	100%
Ashford	1-5	1-5	Less than 50%	100%
Barking and Dagenham	8	6	25%	75%
Barnet	1-5	1-5	Less than 50%	50-99%
Barnsley	1-5	0	100%	100%
Bexley	1-5	1-5	Less than 50%	100%
Birmingham	10	9	10%	100%
Bolton	1-5	1-5	50-99%	100%
Bournemouth, Christchurch and Poole	1-5	1-5	50-99%	100%
Bradford	1-5	1-5	Less than 50%	100%
Brent	22	21	5%	41%
Brighton and Hove	1-5	1-5	Less than 50%	100%
Bristol, City of	13	11	15%	77%
Bromley	6	3	50%	50%
Buckinghamshire	1-5	0	100%	100%
Calderdale	1-5	1-5	Less than 50%	100%
Cambridge	1-5	1-5	50-99%	100%
Camden	15	13	13%	53%
Chelmsford	1-5	0	100%	100%
City of London	1-5	1-5	Less than 50%	Less than 50%
Coventry	1-5	1-5	Less than 50%	Less than 50%
Croydon	16	12	25%	50%
Dorset	1-5	1-5	Less than 50%	100%
Ealing	9	8	11%	67%
Eastbourne	6	0	100%	100%
Enfield	6	6	0%	50%
Gateshead	1-5	1-5	50-99%	50-99%
Greenwich	16	13	19%	56%
Hackney	40	34	15%	53%
Hammersmith and Fulham	11	10	9%	9%
Haringey	7	4	43%	71%
Harrow	1-5	1-5	Less than 50%	50-99%
Havering	1-5	1-5	Less than 50%	100%
Hillingdon	8	8	0%	0%
Hounslow	16	12	25%	56%
Ipswich	6	6	0%	67%
Isle of Wight	1-5	1-5	Less than 50%	100%
Islington	23	22	4%	35%
Kensington and Chelsea	11	9	18%	64%
Kingston upon Thames	1-5	1-5	Less than 50%	Less than 50%
Kirklees	1-5	0	100%	100%
Lambeth	21	19	10%	48%
Lancaster	1-5	0	100%	100%
Leeds	31	17	45%	87%
Leicester	1-5	1-5	Less than 50%	50-99%
Lewes	1-5	0	100%	100%
Lewisham	8	7	13%	50%
Liverpool	19	16	16%	74%
Luton	1-5	1-5	Less than 50%	100%
Manchester	52	28	46%	98%
Mansfield	1-5	1-5	Less than 50%	100%
Medway	1-5	1-5	Less than 50%	100%
Merton	7	5	29%	43%
Middlesbrough	1-5	1-5	Less than 50%	Less than 50%
Milton Keynes	1-5	1-5	Less than 50%	50-99%
Newcastle upon Tyne	1-5	1-5	Less than 50%	50-99%
Newham	76	67	12%	46%
North Somerset	1-5	1-5	Less than 50%	100%
North Yorkshire	1-5	1-5	Less than 50%	100%
Nottingham	9	5	44%	100%
Peterborough	1-5	0	100%	100%
Plymouth	1-5	1-5	Less than 50%	100%
Portsmouth	1-5	1-5	50-99%	100%
Preston	1-5	0	100%	100%
Reading	13	2	85%	92%
Redbridge	6	2	67%	67%
Richmond upon Thames	1-5	0	100%	100%
Rother	1-5	1-5	Less than 50%	100%
Salford	15	5	67%	100%
Sevenoaks	1-5	1-5	Less than 50%	100%
Sheffield	1-5	1-5	Less than 50%	100%
Slough	1-5	1-5	Less than 50%	100%
Southampton	1-5	1-5	50-99%	100%
Southend-on-Sea	1-5	0	100%	100%
Southwark	37	33	11%	46%
Stevenage	1-5	1-5	50-99%	100%
Stockport	1-5	0	100%	100%
Sunderland	1-5	1-5	Less than 50%	Less than 50%
Surrey Heath	1-5	0	100%	100%
Sutton	1-5	1-5	Less than 50%	50-99%
Swindon	1-5	1-5	Less than 50%	100%
Tower Hamlets	115	85	26%	57%
Trafford	1-5	1-5	Less than 50%	Less than 50%
Wakefield	1-5	0	100%	100%
Waltham Forest	1-5	1-5	Less than 50%	Less than 50%
Wandsworth	12	8	33%	92%
Watford	1-5	0	100%	100%
Westminster	26	19	27%	62%
Worcester	1-5	1-5	Less than 50%	100%

## BSF_5
Remediation status of eligible buildings within BSF, time series, England, 31 August 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
From September 2023 the information provided in this data table includes buildings that applied in both application periods [note 24].
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_23, note_66]	Dec-21 / Number	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number
Remediation complete	0	10	11	11	28	37	37	39	46	49	101	124	135	141	143	155	158	168	176	190	200	210
Remediation complete: awaiting building control sign-off	18	86	93	97	96	102	107	114	117	122	84	75	77	90	107	106	106	109	111	112	121	116
Remediation started	150	247	254	268	266	261	263	264	253	254	258	260	268	255	246	237	247	245	235	222	197	191
Remediation not yet started	813	860	850	839	826	814	818	803	534	513	525	517	494	464	451	440	423	393	389	345	283	288
Total buildings	981	1203	1208	1215	1216	1214	1225	1220	950	938	968	976	974	950	947	938	934	915	911	869	801	805

Remediation Category [note_23, note_66]	Dec-21 / Percentage (%)	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 Percentage (%)	May-24 Percentage (%)	Jun-24 Percentage (%)	Jul-24 Percentage (%)	Aug-24 Percentage (%)
Remediation complete	0%	1%	1%	1%	2%	3%	3%	3%	5%	5%	10%	13%	14%	15%	15%	17%	17%	18%	19%	22%	25%	26%
Remediation complete: awaiting building control sign-off	2%	7%	8%	8%	8%	8%	9%	9%	12%	13%	9%	8%	8%	9%	11%	11%	11%	12%	12%	13%	15%	14%
Remediation started	15%	21%	21%	22%	22%	21%	21%	22%	27%	27%	27%	27%	28%	27%	26%	25%	26%	27%	26%	26%	25%	24%
Remediation not yet started	83%	71%	70%	69%	68%	67%	67%	66%	56%	55%	54%	53%	51%	49%	48%	47%	45%	43%	43%	40%	35%	36%
Total buildings [note_10]	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Combined_1
Remediation progress for buildings with unsafe ACM or being remediated in the Building Safety Fund, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17]	ACM cladding only / Number	ACM cladding only / Percentage (%)	Non-ACM cladding only in the BSF / Number	Non-ACM cladding only in the BSF / Percentage (%)	Both ACM and non-ACM cladding in the BSF / Number	Both ACM and non-ACM cladding in the BSF / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation completed	349	86%	168	24%	41	43%	558	46%
Works complete awaiting building control signoff	24	6%	109	15%	8	8%	141	12%
Remediation started	28	7%	167	24%	40	42%	235	19%
Remediation not started	7	2%	266	37%	6	6%	279	23%
Total	408	100%	710	100%	95	100%	1,213	100%

## Combined_2
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17, note_18, note_42]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	304	16%	1,088	39%	1,392	29%
Remediation underway	412	21%	573	20%	985	21%
In programme	1,234	63%	1,160	41%	2,394	50%
Total	1,950	100%	2,821	100%	4,771	100%

## Combined_3
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, by local authority, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Local Authority [note_71]	Buildings monitored	In programme / Percentage(%)	Remediation Underway / Percentage(%)	Completed Remediation / Percentage(%)
Barking and Dagenham	11-50	51%	26%	23%
Barnet	51-100	52%	6%	42%
Basingstoke and Deane	11-50	79%	0%	21%
Bexley	11-50	34%	53%	13%
Birmingham	101-200	20%	13%	68%
Bournemouth, Christchurch and Poole	11-50	29%	38%	33%
Bradford	11-50	76%	0%	24%
Brent	51-100	48%	15%	36%
Brighton and Hove	11-50	68%	22%	11%
Bristol, City of	101-200	79%	13%	8%
Bromley	11-50	31%	54%	15%
Cambridge	11-50	63%	19%	19%
Camden	51-100	54%	18%	28%
Chelmsford	11-50	9%	4%	87%
Croydon	51-100	56%	24%	21%
Dacorum	11-50	32%	53%	16%
Dartford	11-50	54%	35%	12%
Ealing	51-100	52%	10%	38%
Eastbourne	11-50	45%	0%	55%
Enfield	11-50	67%	0%	33%
Gateshead	11-50	64%	9%	27%
Greenwich	101-200	59%	10%	30%
Hackney	201-400	53%	19%	28%
Hammersmith and Fulham	11-50	70%	7%	23%
Haringey	51-100	26%	59%	15%
Harrow	11-50	48%	16%	36%
Havering	11-50	40%	51%	9%
Hertsmere	11-50	50%	38%	13%
Hillingdon	11-50	88%	0%	13%
Hounslow	51-100	45%	10%	45%
Ipswich	11-50	63%	17%	21%
Islington	101-200	70%	11%	18%
Kensington and Chelsea	11-50	36%	44%	20%
Kirklees	11-50	78%	6%	17%
Lambeth	101-200	59%	17%	24%
Leeds	51-100	39%	25%	36%
Leicester	11-50	65%	12%	24%
Lewisham	51-100	42%	26%	31%
Liverpool	51-100	44%	21%	35%
Maidstone	11-50	50%	13%	38%
Manchester	101-200	39%	19%	42%
Medway	11-50	19%	25%	56%
Merton	11-50	45%	25%	30%
Milton Keynes	11-50	50%	38%	12%
Newcastle upon Tyne	51-100	33%	8%	59%
Newham	201-400	64%	18%	18%
North Somerset	11-50	47%	47%	7%
Norwich	11-50	19%	33%	48%
Nottingham	11-50	53%	6%	41%
Oxford	11-50	33%	8%	58%
Plymouth	11-50	54%	25%	21%
Portsmouth	51-100	35%	33%	32%
Reading	11-50	47%	6%	47%
Redbridge	11-50	50%	21%	29%
Richmond upon Thames	11-50	29%	65%	6%
Salford	51-100	19%	34%	47%
Sheffield	11-50	54%	11%	36%
Slough	11-50	43%	9%	48%
Solihull	11-50	71%	0%	29%
Southampton	101-200	25%	68%	7%
Southwark	101-200	66%	10%	23%
Stevenage	11-50	75%	8%	17%
Sunderland	11-50	50%	0%	50%
Sutton	11-50	28%	50%	22%
Thanet	11-50	62%	0%	38%
Tower Hamlets	over 400	55%	17%	28%
Trafford	11-50	62%	0%	38%
Waltham Forest	11-50	76%	8%	16%
Wandsworth	51-100	48%	7%	45%
West Northamptonshire	11-50	38%	62%	0%
Westminster	51-100	54%	7%	39%
Woking	11-50	32%	64%	4%
Wolverhampton	11-50	69%	8%	23%

## Combined_4
Estimated number of dwellings in buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys by remediation status, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of dwellings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
All dwellings [note_10]	Estimated dwellings in 11-18m buildings	Estimated dwellings in 18m+ buildings	Estimated Total dwellings
Remediation complete (including those awaiting building control signoff)	11,000	76,000	87,000
Remediation underway	10,000	45,000	55,000
In programme	35,000	81,000	116,000
Total	56,000	202,000	258,000

## Combined_5
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by tenure, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_16, note_17, note_18, note_42]	Private / Number	Private / Percentage (%)	Social / Number	Social / Percentage (%)	Other [note 58] / Number	Other / Percentage (%)	Total / Number	Total / Percentage (%)
Remediation complete (including those awaiting building control signoff)	624	29%	676	27%	92	93%	1,392	29%
Remediation underway	407	19%	574	23%	4	4%	985	21%
In programme	1,149	53%	1,242	50%	3	3%	2,394	50%
Total	2,180	100%	2,492	100%	99	100%	4,771	100%

## Combined_6
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, time series, 31 August 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_16, note_17, note_18, note_42, note_65]	Dec-22 / Number	Jan-23 / Number	Feb-23 / Number	Mar-23 / Number	Apr-23 / Number	May-23 / Number	Jun-23 / Number	Jul-23 / Number	Aug-23 / Number	Sep-23 / Number	Oct-23 / Number	Nov-23 / Number	Dec-23 / Number	Jan-24 / Number	Feb-24 / Number	Mar-24 / Number	Apr-24 / Number	May-24 / Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number
Remediation complete (including those awaiting building control signoff)	448	456	461	477	492	499	508	523	535	544	703	777	797	815	863	976	991	1088	1332	1350	1392
Remediation underway	301	308	322	321	317	319	320	308	304	311	809	826	811	871	952	992	984	978	969	949	985
In programme	853	844	834	820	806	806	791	519	501	509	2285	2221	2231	2286	2277	2361	2361	2308	2312	2331	2394
Total	1602	1608	1617	1618	1615	1624	1619	1350	1340	1364	3797	3824	3839	3972	4092	4329	4336	4374	4613	4630	4771

Remediation Category [note_16, note_17, note_18, note_42, note_65]	Dec-22 / Percentage (%)	Jan-23 / Percentage (%)	Feb-23 / Percentage (%)	Mar-23 / Percentage (%)	Apr-23 / Percentage (%)	May-23 / Percentage (%)	Jun-23 / Percentage (%)	Jul-23 / Percentage (%)	Aug-23 / Percentage (%)	Sep-23 / Percentage (%)	Oct-23 / Percentage (%)	Nov-23 / Percentage (%)	Dec-23 / Percentage (%)	Jan-24 / Percentage (%)	Feb-24 / Percentage (%)	Mar-24 / Percentage (%)	Apr-24 / Percentage (%)	May-24 / Percentage (%)	Jun-24 / Percentage (%)	Jul-24 / Percentage (%)	Aug-24 / Percentage (%)
Remediation complete (including those awaiting building control signoff)	28%	28%	29%	29%	30%	31%	31%	39%	40%	40%	19%	20%	21%	21%	21%	23%	23%	25%	29%	29%	29%
Remediation underway	19%	19%	20%	20%	20%	20%	20%	23%	23%	23%	21%	22%	21%	22%	23%	23%	23%	22%	21%	20%	21%
In programme	53%	52%	52%	51%	50%	50%	49%	38%	37%	37%	60%	58%	58%	58%	56%	55%	54%	53%	50%	50%	50%
Total	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Combined_7
Remediation progress for unique buildings monitored by government in the ACM programme, BSF programme, the CSS, the developer remediation contracts, and social housing surveys, England, by region, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each region.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_16, note_17, note_18, note_42]	Total buildings monitored / Number	Total buildings monitored / Percentage(%)	In programme / Number	In programme / Percentage(%)	Remediation underway / Number	Remediation underway / Percentage(%)	Remediation complete (including those awaiting building control signoff) / Number	Remediation complete (including those awaiting building control signoff) / Percentage(%)	Buildings monitored that have completed Remediation / Percentage (%)	Buildings monitored that have started or completed remediation / Percentage (%)
North West	410	9%	153	6%	94	10%	163	12%	40%	63%
London	2636	55%	1434	60%	490	50%	712	51%	27%	46%
East of England	227	5%	107	4%	53	5%	67	5%	30%	53%
East Midlands	77	2%	44	2%	13	1%	20	1%	26%	43%
North East	82	2%	34	1%	5	1%	43	3%	52%	59%
South East	595	12%	251	10%	201	20%	143	10%	24%	58%
South West	312	7%	203	8%	66	7%	43	3%	14%	35%
West Midlands	273	6%	85	4%	38	4%	150	11%	55%	69%
Yorkshire and The Humber	159	3%	83	3%	25	3%	51	4%	32%	48%
Total	4771	100%	2,394	100%	985	100%	1392	100%	29%	50%

## CSS_1
Application status of buildings within the CSS, England, 31 August 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Pre - eligible buildings [note_47, note_48]	Number	Percentage (%)
Pre - application	923	70%
Live application	392	30%
Total pre-eligible buildings	1315	100%

Eligible buildings	Number	Percentage (%)
Works not started	395	98%
Works started	10	2%
Works completed	0	0%
Total eligible buildings	405	100%

## CSS_2
CSS remediation progress by region, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Region [note_48]	Eligible Buildings in the CSS / Number	Not Started Remediation / Number	Started Remediation / Number	Completed Remediation / Number	Eligible Buildings that have Completed Remediation / Percentage (%)	Eligible CSS buildings that have started or completed remediation / Percentage (%)
North West	70	69	1	0	0%	1%
London	123	120	3	0	0%	2%
East of England	37	36	1	0	0%	3%
East Midlands	27	27	0	0	0%	0%
North East	10	10	0	0	0%	0%
South East	55	51	4	0	0%	7%
South West	32	31	1	0	0%	3%
West Midlands	15	15	0	0	0%	0%
Yorkshire and The Humber	33	33	0	0	0%	0%
Northern Ireland	3	3	0	0	0%	0%
Total	405	395	10	0	0%	2%

## CSS_3
CSS remediation progress by height, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_48]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)
Remediation complete	0	0%	0	0%
Remediation started	9	4%	1	1%
In programme	233	96%	162	99%
Total buildings	242	100%	163	100%

## CSS_4
CSS remediation progress by tenure, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings unless otherwise stated.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category [note_48]	Social sector residential / Number	Social sector residential / Percentage (%)	Private sector residential / Number	Private sector residential / Percentage (%)
Remediation complete	0	0%	0	0%
Remediation started	2	2%	8	2%
In programme	80	98%	315	98%
Total buildings	82	100%	323	100%

## CSS_5
CSS number of eligible buildings by funding allocations, expenditure and tenure, England, 31 August 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables.
All figures are for number of buildings or financial amounts in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Table CSS_5a: Number of buildings and amount of funding allocated by funding type and tenure for buildings eligible for the BSF
Funding Allocations	Private Sector Residential / Number of Buildings [Note 14]	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Funding / (£ millions)
Works Package Approved	22	68.5	2	0.1	68.6
Pre-Tender Support Allocations	215	52.9	12	2.6	55.5
Total [note 10]	216	121.4	14	2.7	124.0

Table CSS_5b: Amount of expenditure from the CSS by tenure
Expenditure [note_44]	Private Sector Residential / Number of Buildings	Private Sector Residential / (£ millions)	Social Sector Residential / Number of Buildings	Social Sector Residential / (£ millions)	Total Number of Buildings	Total Expenditure / (£ millions)
Expenditure Paid	215	55.0	14	2.7	229	57.7

## CSS_6
CSS remediation progress, time series, England, 31 August 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings unless otherwise stated or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [note_48]	Oct-23 Number	Nov-23 Number	Dec-23 Number	Jan-24 Number	Feb-24 Number	Mar-24 Number	Apr-24 Number	May-24 Number	Jun-24 / Number	Jul-24 / Number	Aug-24 / Number
Remediation complete	0	0	0	0	0	0	0	0	0	0	0
Remediation started	0	0	0	0	1	2	2	2	6	8	10
In programme	48	75	104	127	151	168	199	222	282	371	395
Total buildings	48	75	104	127	152	170	201	224	288	379	405

Remediation Category [note_48]	Oct-23 Percentage (%)	Nov-23 Percentage (%)	Dec-23 Percentage (%)	Jan-24 Percentage (%)	Feb-24 Percentage (%)	Mar-24 Percentage (%)	Apr-24 Percentage (%)	May-24 Percentage (%)	Jun-24 Percentage (%)	Jul-24 Percentage (%)	Aug-24 Percentage (%)
Remediation complete	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%	0%
Remediation started	0%	0%	0%	0%	1%	1%	1%	1%	2%	2%	2%
In programme	100%	100%	100%	100%	99%	99%	99%	99%	98%	98%	98%
Total buildings	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%	100%

## Developer_1
Remediation status of buildings requiring works under the developer remediation contract by height group, England, 31 August 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - All Defect Types [Note_25, Note_26]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	146	20%	196	22%	342	21%
Remediation complete - awaiting building control sign-off	19	3%	49	6%	68	4%
Remediation started	125	17%	234	27%	359	22%
Remediation not Started - Plans in Place	222	30%	233	26%	455	28%
Remediation not Started - No Plans in Place	233	31%	169	19%	402	25%
Total	745	100%	881	100%	1626	100%

Remediation Category - Cladding Defects [Note_25, Note_26]	11-18m buildings / Number	11-18m buildings / Percentage (%)	18m+ buildings / Number	18m+ buildings / Percentage (%)	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	130	21%	190	23%	320	22%
Remediation complete - awaiting building control sign-off	16	3%	45	5%	61	4%
Remediation started	106	17%	228	28%	334	23%
Remediation not Started - Plans in Place	193	31%	225	27%	418	29%
Remediation not Started - No Plans in Place	175	28%	141	17%	316	22%
Total	620	100%	829	100%	1449	100%

Remediation Category - BSF Transfers [Note_25, Note_26, Note_62]	Total buildings / Number	Total buildings / Percentage (%)
Remediation complete	25	6%
Remediation complete - awaiting building control sign-off	14	3%
Remediation started	102	23%
Remediation not Started - Plans in Place	133	30%
Remediation not Started - No Plans in Place	167	38%
Total buildings	441	100%

## Developer_2
Estimated cost of buildings requiring works under the developer remediation contract by height, England, 31 July 2024
Back to Contents
This worksheet contains one table. All figures are for estimated cost of buildings identified as requiring works under the Developer Remediation Contract in GBP £ million.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Cost Category [Note_33]	11-18m / (£ millions)	18m+ / (£ millions)	Total / (£ millions)
Total estimated cost of works	869	2,411	3,281

## Developer_3
Developer by developer breakdown of buildings covered by the developer remediation contract, by number of buildings and remediation requirements, England, 31 July 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Developer [Note_29]	Number of buildings for which the developer has accepted responsibility under the contract	Number of buildings assessed and found to require remediation [Note_28]	Number of buildings assessed and found to require remediation, and which will be remediated by the developer directly (rather than being remediated through a government fund, with cost re-imbursed by developer) [Note 31]	Number of buildings where it is not known whether remediation is required [Note 32]	Number of buildings where no remediation is required
Total	4668	1480	1357	1353	1835
Abbey Developments Limited	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	54	15	1	37	2
Ballymore Limited	85	25	9	0	60
Barratt Developments PLC	701	196	182	416	89
Bellway PLC	499	134	121	297	68
The Berkeley Group Holdings PLC	820	80	69	31	709
Bewley Group Limited	9	5	3	0	4
Bloor Investments Limited	-	-	-	-	-
The British Land Company PLC	16	2	2	0	14
Cala Group (Holdings) Limited	22	1	1	21	0
Canary Wharf Group PLC	13	0	0	0	13
C.G. Fry and Son Limited	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	8	0	0	0	8
Crest Nicholson Holdings PLC	290	139	136	137	14
Croudace Homes Group Limited	-	-	-	-	-
Dandara Living Holdings Limited	21	19	13	0	2
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-
Fairview Holdings Limited	118	59	56	4	55
Frasers Property (UK) Ltd	23	0	0	10	13
Galliard Group Limited	105	19	19	20	66
MJ Gleeson PLC	17	13	12	4	0
Grosvenor Group Limited	16	8	8	0	8
Hill Holdings Limited	89	11	10	10	68
Hopkins Home Group Limited	-	-	-	-	-
Jelson Holdings Limited	7	2	2	3	2
Keepmoat Limited	-	-	-	-	-
Land Securities Group PLC	43	6	5	26	11
Lendlease Europe Holdings Limited	91	34	33	22	35
Pegasus Homes (formerly Lifestory Group)	18	1	1	0	17
London Square Development (Holdings) Limited	40	37	37	2	1
Miller Homes Limited	36	21	21	1	14
Morris Homes Group Limited	6	2	2	0	4
Morgan Sindall Group PLC (parent company for Lovell and Muse)	120	25	18	3	92
Persimmon Public Limited Company	64	49	48	0	15
Redrow PLC	129	76	72	48	5
Regal Holdco Limited (parent company for Regal London)	15	0	0	0	15
Rowland Group Limited	-	-	-	-	-
Rydon Group Holdings Limited	25	9	6	1	15
Sorbon Group Limited (parent company for Shanly Homes)	26	14	14	0	12
St Modwen Group Holdings Company Limited	13	0	0	8	5
Story Homes Limited	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-
Taylor Wimpey PLC	419	198	191	160	61
Telford Homes Limited	144	99	96	12	33
Tilia Homes Limited	8	8	8	0	0
Vistry Group PLC	291	119	109	22	150
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-
Weston Group PLC	88	21	21	2	65
McCarthy & Stone Limited	61	4	4	3	54
Seven Capital PLC	23	6	5	17	0
Wates Group Limited	25	8	8	8	9
Watkin Jones PLC	14	6	6	8	0
Bouygues (UK) Limited	35	4	4	19	12
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	21	5	4	1	15

## Developer_4
Developer by developer breakdown of buildings covered by the developer remediation contract, by assessment status, England, 31 July 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	Progress with assessments
	Buildings that…
	…have had an Assessment [Note 30]		…have not had an assessment		... have made a 5.4D(i) or 5.4D(ii) declaration		…have been assessed and confirmed to require remediation
Developer [Note_29]	Number	Percentage	Number	Percentage‎	Number 2	Percentage‎ 3	out of total buildings [Note_28]	out of total buildings	out of assessed buildings
Total	3758	81%	815	17%	95	2%	1480	32%	39%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	33	61%	21	39%	0	0%	15	28%	45%
Ballymore Limited	37	44%	0	0%	48	56%	25	29%	68%
Barratt Developments PLC	537	77%	164	23%	0	0%	196	28%	36%
Bellway PLC	293	59%	206	41%	0	0%	134	27%	46%
The Berkeley Group Holdings PLC	796	97%	24	3%	0	0%	80	10%	10%
Bewley Group Limited	9	100%	0	0%	0	0%	5	56%	56%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-
The British Land Company PLC	16	100%	0	0%	0	0%	2	13%	13%
Cala Group (Holdings) Limited	7	32%	15	68%	0	0%	1	5%	14%
Canary Wharf Group PLC	13	100%	0	0%	0	0%	0	0%	0%
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	8	100%	0	0%	0	0%	0	0%	0%
Crest Nicholson Holdings PLC	180	62%	110	38%	0	0%	139	48%	77%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	21	100%	0	0%	0	0%	19	90%	90%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	100	85%	0	0%	18	15%	59	50%	59%
Frasers Property (UK) Ltd	13	57%	10	43%	0	0%	0	0%	0%
Galliard Group Limited	102	97%	3	3%	0	0%	19	18%	19%
MJ Gleeson PLC	16	94%	1	6%	0	0%	13	76%	81%
Grosvenor Group Limited	8	50%	0	0%	8	50%	8	50%	100%
Hill Holdings Limited	80	90%	9	10%	0	0%	11	12%	14%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	7	100%	0	0%	0	0%	2	29%	29%
Keepmoat Limited	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	20	47%	23	53%	0	0%	6	14%	30%
Lendlease Europe Holdings Limited	77	85%	14	15%	0	0%	34	37%	44%
Pegasus Homes (formerly Lifestory Group)	18	100%	0	0%	0	0%	1	6%	6%
London Square Development (Holdings) Limited	40	100%	0	0%	0	0%	37	93%	93%
Miller Homes Limited	22	61%	0	0%	14	39%	21	58%	95%
Morris Homes Group Limited	6	100%	0	0%	0	0%	2	33%	33%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	120	100%	0	0%	0	0%	25	21%	21%
Persimmon Public Limited Company	64	100%	0	0%	0	0%	49	77%	77%
Redrow PLC	129	100%	0	0%	0	0%	76	59%	59%
Regal Holdco Limited (parent company for Regal London)	15	100%	0	0%	0	0%	0	0%	0%
Rowland Group Limited	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	25	100%	0	0%	0	0%	9	36%	36%
Sorbon Group Limited (parent company for Shanly Homes)	26	100%	0	0%	0	0%	14	54%	54%
St Modwen Group Holdings Company Limited	5	38%	8	62%	0	0%	0	0%	0%
Story Homes Limited	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	276	66%	143	34%	0	0%	198	47%	72%
Telford Homes Limited	140	97%	4	3%	0	0%	99	69%	71%
Tilia Homes Limited	8	100%	0	0%	0	0%	8	100%	100%
Vistry Group PLC	277	95%	14	5%	0	0%	119	41%	43%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-
Weston Group PLC	78	89%	10	11%	0	0%	21	24%	27%
McCarthy & Stone Limited	61	100%	0	0%	0	0%	4	7%	7%
Seven Capital PLC	6	26%	17	74%	0	0%	6	26%	100%
Wates Group Limited	21	84%	4	16%	0	0%	8	32%	38%
Watkin Jones PLC	6	43%	8	57%	0	0%	6	43%	100%
Bouygues (UK) Limited	28	80%	7	20%	0	0%	4	11%	14%
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	14	67%	0	0%	7	33%	5	24%	36%

## Developer_5
Developer by developer breakdown of buildings which are covered by the developer remediation contract requiring remediation, by remediation status, England, 31 July 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	Remediation Status
	Proportion of buildings being remediated by the developer directly where remediation is...
	…not yet started		... started or complete		... started		...complete		...completed buildings sign-off control
Developer [Note_29]	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total	804	59%	553	41%	306	23%	194	14%	53	4%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	1	100%	0	0%	0	0%	0	0%	0	0%
Ballymore Limited	2	22%	7	78%	0	0%	7	78%	0	0%
Barratt Developments PLC	114	63%	68	37%	16	9%	9	5%	43	24%
Bellway PLC	70	58%	51	42%	40	33%	11	9%	0	0%
The Berkeley Group Holdings PLC	22	32%	47	68%	9	13%	38	55%	0	0%
Bewley Group Limited	3	100%	0	0%	0	0%	0	0%	0	0%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-	-
The British Land Company PLC	0	0%	2	100%	2	100%	0	0%	0	0%
Cala Group (Holdings) Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Canary Wharf Group PLC	0	-	0	-	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	-	0	-	0	-	0	-	0	-
Crest Nicholson Holdings PLC	34	25%	102	75%	102	75%	0	0%	0	0%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0%	13	100%	13	100%	0	0%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	32	57%	24	43%	5	9%	19	34%	0	0%
Frasers Property (UK) Ltd	0	-	0	-	0	-	0	-	0	-
Galliard Group Limited	3	16%	16	84%	1	5%	14	74%	1	5%
MJ Gleeson PLC	9	75%	3	25%	3	25%	0	0%	0	0%
Grosvenor Group Limited	7	88%	1	13%	0	0%	1	13%	0	0%
Hill Holdings Limited	3	30%	7	70%	1	10%	6	60%	0	0%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0%	2	100%	0	0%	0	0%	2	100%
Keepmoat Limited	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	4	80%	1	20%	1	20%	0	0%	0	0%
Lendlease Europe Holdings Limited	28	85%	5	15%	5	15%	0	0%	0	0%
Pegasus Homes (formerly Lifestory Group)	1	100%	0	0%	0	0%	0	0%	0	0%
London Square Development (Holdings) Limited	37	100%	0	0%	0	0%	0	0%	0	0%
Miller Homes Limited	13	62%	8	38%	8	38%	0	0%	0	0%
Morris Homes Group Limited	0	0%	2	100%	1	50%	1	50%	0	0%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	8	44%	10	56%	4	22%	6	33%	0	0%
Persimmon Public Limited Company	26	54%	22	46%	16	33%	6	13%	0	0%
Redrow PLC	51	71%	21	29%	19	26%	2	3%	0	0%
Regal Holdco Limited (parent company for Regal London)	0	-	0	-	0	-	0	-	0	-
Rowland Group Limited	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	2	33%	4	67%	1	17%	0	0%	3	50%
Sorbon Group Limited (parent company for Shanly Homes)	7	50%	7	50%	5	36%	2	14%	0	0%
St Modwen Group Holdings Company Limited	0	-	0	-	0	-	0	-	0	-
Story Homes Limited	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	132	69%	59	31%	22	12%	36	19%	1	1%
Telford Homes Limited	92	96%	4	4%	1	1%	3	3%	0	0%
Tilia Homes Limited	8	100%	0	0%	0	0%	0	0%	0	0%
Vistry Group PLC	57	52%	52	48%	19	17%	30	28%	3	3%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-	-
Weston Group PLC	15	71%	6	29%	6	29%	0	0%	0	0%
McCarthy & Stone Limited	1	25%	3	75%	3	75%	0	0%	0	0%
Seven Capital PLC	5	100%	0	0%	0	0%	0	0%	0	0%
Wates Group Limited	4	50%	4	50%	2	25%	2	25%	0	0%
Watkin Jones PLC	6	100%	0	0%	0	0%	0	0%	0	0%
Bouygues (UK) Limited	3	75%	1	25%	1	25%	0	0%	0	0%
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	3	75%	1	25%	0	0%	1	25%	0	0%

## Developer_6
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates England, 31 July 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	Buildings that require remediation by the developer which have not yet started, with a start date…

	...at all		…within the next 12 months
Developer [Note_27, Note_29]	Number	Percentage	Number	Percentage‎
Total	610	76%	432	54%
Abbey Developments Limited	-	-	-	-
Allison Homes Group Limited	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0%	0	0%
Ballymore Limited	2	100%	2	100%
Barratt Developments PLC	108	95%	85	75%
Bellway PLC	59	84%	24	34%
The Berkeley Group Holdings PLC	22	100%	22	100%
Bewley Group Limited	1	33%	0	0%
Bloor Investments Limited	-	-	-	-
The British Land Company PLC	0	-	0	-
Cala Group (Holdings) Limited	0	0%	0	0%
Canary Wharf Group PLC	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	-	0	-
Crest Nicholson Holdings PLC	25	74%	21	62%
Croudace Homes Group Limited	-	-	-	-
Dandara Living Holdings Limited	0	-	0	-
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-
Fairview Holdings Limited	28	88%	16	50%
Frasers Property (UK) Ltd	0	-	0	-
Galliard Group Limited	2	67%	1	33%
MJ Gleeson PLC	8	89%	8	89%
Grosvenor Group Limited	0	0%	0	0%
Hill Holdings Limited	3	100%	3	100%
Hopkins Home Group Limited	-	-	-	-
Jelson Holdings Limited	0	-	0	-
Keepmoat Limited	-	-	-	-
Land Securities Group PLC	0	0%	0	0%
Lendlease Europe Holdings Limited	24	86%	22	79%
Pegasus Homes (formerly Lifestory Group)	1	100%	1	100%
London Square Development (Holdings) Limited	37	100%	37	100%
Miller Homes Limited	6	46%	6	46%
Morris Homes Group Limited	0	-	0	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	8	100%	5	63%
Persimmon Public Limited Company	26	100%	21	81%
Redrow PLC	51	100%	22	43%
Regal Holdco Limited (parent company for Regal London)	0	-	0	-
Rowland Group Limited	-	-	-	-
Rydon Group Holdings Limited	2	100%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	3	43%	3	43%
St Modwen Group Holdings Company Limited	0	-	0	-
Story Homes Limited	-	-	-	-
Strata Homes Group Limited	-	-	-	-
Taylor Wimpey PLC	84	64%	73	55%
Telford Homes Limited	31	34%	26	28%
Tilia Homes Limited	6	75%	4	50%
Vistry Group PLC	48	84%	25	44%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-
Weston Group PLC	15	100%	0	0%
McCarthy & Stone Limited	0	0%	0	0%
Seven Capital PLC	1	20%	1	20%
Wates Group Limited	3	75%	2	50%
Watkin Jones PLC	4	67%	0	0%
Bouygues (UK) Limited	0	0%	0	0%
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	2	67%	2	67%

## Developer_7
Developer by developer breakdown of buildings requiring remediation, which have not started works, with start dates by Financial Year England, 31 July 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	For buildings which have not yet started, start profiles by financial year...				Buildings which have not yet started, with...

Developer [Note_27, Note_29]	2024-2025	2025-2026	2026-2027	2027-2028	.. no start date provided	... start date prior to 2024-2025
Total	405	110	52	2	196	39
Abbey Developments Limited	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0	0	0	1	0
Ballymore Limited	2	0	0	0	0	0
Barratt Developments PLC	69	35	4	0	6	0
Bellway PLC	18	19	20	2	11	0
The Berkeley Group Holdings PLC	19	3	0	0	0	0
Bewley Group Limited	0	0	0	0	2	1
Bloor Investments Limited	-	-	-	-	-	-
The British Land Company PLC	0	0	0	0	0	0
Cala Group (Holdings) Limited	0	0	0	0	1	0
Canary Wharf Group PLC	0	0	0	0	0	0
C.G. Fry and Son Limited	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	0	0	0	0
Crest Nicholson Holdings PLC	25	0	0	0	9	0
Croudace Homes Group Limited	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0	0	0	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-
Fairview Holdings Limited	17	0	0	0	4	11
Frasers Property (UK) Ltd	0	0	0	0	0	0
Galliard Group Limited	2	0	0	0	1	0
MJ Gleeson PLC	8	0	0	0	1	0
Grosvenor Group Limited	0	0	0	0	7	0
Hill Holdings Limited	3	0	0	0	0	0
Hopkins Home Group Limited	-	-	-	-	-	-
Jelson Holdings Limited	0	0	0	0	0	0
Keepmoat Limited	-	-	-	-	-	-
Land Securities Group PLC	0	0	0	0	4	0
Lendlease Europe Holdings Limited	22	1	0	0	4	1
Pegasus Homes (formerly Lifestory Group)	1	0	0	0	0	0
London Square Development (Holdings) Limited	37	0	0	0	0	0
Miller Homes Limited	5	1	0	0	7	0
Morris Homes Group Limited	0	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	6	0	0	0	0	2
Persimmon Public Limited Company	20	1	0	0	0	5
Redrow PLC	10	17	24	0	0	0
Regal Holdco Limited (parent company for Regal London)	0	0	0	0	0	0
Rowland Group Limited	-	-	-	-	-	-
Rydon Group Holdings Limited	0	0	0	0	2	0
Sorbon Group Limited (parent company for Shanly Homes)	3	0	0	0	4	0
St Modwen Group Holdings Company Limited	0	0	0	0	0	0
Story Homes Limited	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-
Taylor Wimpey PLC	73	11	0	0	48	0
Telford Homes Limited	20	7	4	0	61	0
Tilia Homes Limited	6	0	0	0	2	0
Vistry Group PLC	34	10	0	0	9	4
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-
Weston Group PLC	0	0	0	0	0	15
McCarthy & Stone Limited	0	0	0	0	1	0
Seven Capital PLC	1	0	0	0	4	0
Wates Group Limited	2	1	0	0	1	0
Watkin Jones PLC	0	4	0	0	2	0
Bouygues (UK) Limited	0	0	0	0	3	0
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	2	0	0	0	1	0

## Developer_8
Developer by developer breakdown of buildings requiring remediation, which had not started works in the previous quarter England, 31 July 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	For buildings which had not started last quarter, but were due to start this quarter, current remediation status...
Developer [Note_29, Note_55]	... not started	... on-site	... total number due to start	% not started, that were due to start
Total	94	19	113	83%
Abbey Developments Limited	-	-	-	-
Allison Homes Group Limited	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0	0	-
Ballymore Limited	0	0	0	-
Barratt Developments PLC	9	0	9	100%
Bellway PLC	6	1	7	86%
The Berkeley Group Holdings PLC	8	1	9	89%
Bewley Group Limited	0	0	0	-
Bloor Investments Limited	-	-	-	-
The British Land Company PLC	0	0	0	-
Cala Group (Holdings) Limited	0	0	0	-
Canary Wharf Group PLC	0	0	0	-
C.G. Fry and Son Limited	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	0	-
Crest Nicholson Holdings PLC	17	2	19	89%
Croudace Homes Group Limited	-	-	-	-
Dandara Living Holdings Limited	0	0	0	-
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-
Fairview Holdings Limited	1	0	1	100%
Frasers Property (UK) Ltd	0	0	0	-
Galliard Group Limited	1	0	1	100%
MJ Gleeson PLC	4	0	4	100%
Grosvenor Group Limited	0	0	0	-
Hill Holdings Limited	0	0	0	-
Hopkins Home Group Limited	-	-	-	-
Jelson Holdings Limited	0	0	0	-
Keepmoat Limited	-	-	-	-
Land Securities Group PLC	0	0	0	-
Lendlease Europe Holdings Limited	0	0	0	-
Pegasus Homes (formerly Lifestory Group)	1	0	1	100%
London Square Development (Holdings) Limited	0	0	0	-
Miller Homes Limited	0	6	6	0%
Morris Homes Group Limited	0	0	0	-
Morgan Sindall Group PLC (parent company for Lovell and Muse)	3	0	3	100%
Persimmon Public Limited Company	8	0	8	100%
Redrow PLC	2	3	5	40%
Regal Holdco Limited (parent company for Regal London)	0	0	0	-
Rowland Group Limited	-	-	-	-
Rydon Group Holdings Limited	0	0	0	-
Sorbon Group Limited (parent company for Shanly Homes)	0	1	1	0%
St Modwen Group Holdings Company Limited	0	0	0	-
Story Homes Limited	-	-	-	-
Strata Homes Group Limited	-	-	-	-
Taylor Wimpey PLC	15	3	18	83%
Telford Homes Limited	1	0	1	100%
Tilia Homes Limited	5	0	5	100%
Vistry Group PLC	13	2	15	87%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-
Weston Group PLC	0	0	0	-
McCarthy & Stone Limited	0	0	0	-
Seven Capital PLC	0	0	0	-
Wates Group Limited	0	0	0	-
Watkin Jones PLC	0	0	0	-
Bouygues (UK) Limited	0	0	0	-
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	0	0	0	-

## Developer_9
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates England, 31 July 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	Buildings that require remediation by the developer which have not yet completed, with a completion date…
	...at all		…within the next 12 months
Developer [Note_29, Note_56]	Number	Percentage	Number	Percentage‎
Total	875	79%	322	29%
Abbey Developments Limited	-	-	-	-
Allison Homes Group Limited	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0%	0	0%
Ballymore Limited	2	100%	0	0%
Barratt Developments PLC	124	95%	34	26%
Bellway PLC	92	84%	16	15%
The Berkeley Group Holdings PLC	27	87%	23	74%
Bewley Group Limited	1	33%	0	0%
Bloor Investments Limited	-	-	-	-
The British Land Company PLC	2	100%	1	50%
Cala Group (Holdings) Limited	0	0%	0	0%
Canary Wharf Group PLC	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	-	0	-
Crest Nicholson Holdings PLC	107	79%	36	26%
Croudace Homes Group Limited	-	-	-	-
Dandara Living Holdings Limited	13	100%	0	0%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-
Fairview Holdings Limited	33	89%	18	49%
Frasers Property (UK) Ltd	0	-	0	-
Galliard Group Limited	4	100%	2	50%
MJ Gleeson PLC	11	92%	11	92%
Grosvenor Group Limited	0	0%	0	0%
Hill Holdings Limited	3	75%	3	75%
Hopkins Home Group Limited	-	-	-	-
Jelson Holdings Limited	0	-	0	-
Keepmoat Limited	-	-	-	-
Land Securities Group PLC	0	0%	0	0%
Lendlease Europe Holdings Limited	30	91%	4	12%
Pegasus Homes (formerly Lifestory Group)	1	100%	1	100%
London Square Development (Holdings) Limited	37	100%	37	100%
Miller Homes Limited	14	67%	2	10%
Morris Homes Group Limited	1	100%	1	100%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	12	100%	10	83%
Persimmon Public Limited Company	42	100%	14	33%
Redrow PLC	70	100%	15	21%
Regal Holdco Limited (parent company for Regal London)	0	-	0	-
Rowland Group Limited	-	-	-	-
Rydon Group Holdings Limited	3	100%	0	0%
Sorbon Group Limited (parent company for Shanly Homes)	7	58%	7	58%
St Modwen Group Holdings Company Limited	0	-	0	-
Story Homes Limited	-	-	-	-
Strata Homes Group Limited	-	-	-	-
Taylor Wimpey PLC	106	69%	28	18%
Telford Homes Limited	32	34%	3	3%
Tilia Homes Limited	5	63%	5	63%
Vistry Group PLC	60	79%	25	33%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-
Weston Group PLC	21	100%	21	100%
McCarthy & Stone Limited	3	75%	0	0%
Seven Capital PLC	0	0%	0	0%
Wates Group Limited	5	83%	3	50%
Watkin Jones PLC	4	67%	0	0%
Bouygues (UK) Limited	1	25%	0	0%
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	2	67%	2	67%

## Developer_10
Developer by developer breakdown of buildings requiring remediation, which have not completed works, with completion dates by Financial Year England, 31 July 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings for each developer that has signed the developer remediation contract, as of 31 July 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	For buildings which have not yet completed, completion profiles by financial year...					Buildings which have not yet completed, with...

Developer [Note_29, Note_56]	2024-2025	2025-2026	2026-2027	2027-2028	2028-2029	.. no completiondate provided	... completion date prior to 2024-2025
Total	251	313	187	75	24	241	19
Abbey Developments Limited	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0	0	0	0	1	0
Ballymore Limited	0	2	0	0	0	0	0
Barratt Developments PLC	20	30	38	21	15	6	0
Bellway PLC	12	24	19	26	5	18	6
The Berkeley Group Holdings PLC	14	10	3	0	0	4	0
Bewley Group Limited	0	0	0	0	0	2	1
Bloor Investments Limited	-	-	-	-	-	-	-
The British Land Company PLC	1	1	0	0	0	0	0
Cala Group (Holdings) Limited	0	0	0	0	0	1	0
Canary Wharf Group PLC	0	0	0	0	0	0	0
C.G. Fry and Son Limited	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	0	0	0	0	0	0
Crest Nicholson Holdings PLC	28	43	32	1	0	29	3
Croudace Homes Group Limited	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	1	3	5	4	0	0
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-
Fairview Holdings Limited	16	11	0	0	0	4	6
Frasers Property (UK) Ltd	0	0	0	0	0	0	0
Galliard Group Limited	3	1	0	0	0	0	0
MJ Gleeson PLC	8	3	0	0	0	1	0
Grosvenor Group Limited	0	0	0	0	0	7	0
Hill Holdings Limited	3	0	0	0	0	1	0
Hopkins Home Group Limited	-	-	-	-	-	-	-
Jelson Holdings Limited	0	0	0	0	0	0	0
Keepmoat Limited	-	-	-	-	-	-	-
Land Securities Group PLC	0	0	0	0	0	5	0
Lendlease Europe Holdings Limited	4	15	11	0	0	3	0
Pegasus Homes (formerly Lifestory Group)	1	0	0	0	0	0	0
London Square Development (Holdings) Limited	37	0	0	0	0	0	0
Miller Homes Limited	9	5	0	0	0	7	0
Morris Homes Group Limited	1	0	0	0	0	0	0
Morgan Sindall Group PLC (parent company for Lovell and Muse)	10	1	1	0	0	0	0
Persimmon Public Limited Company	9	23	10	0	0	0	0
Redrow PLC	11	16	21	19	0	0	3
Regal Holdco Limited (parent company for Regal London)	0	0	0	0	0	0	0
Rowland Group Limited	-	-	-	-	-	-	-
Rydon Group Holdings Limited	0	0	0	0	0	3	0
Sorbon Group Limited (parent company for Shanly Homes)	7	0	0	0	0	5	0
St Modwen Group Holdings Company Limited	0	0	0	0	0	0	0
Story Homes Limited	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-
Taylor Wimpey PLC	18	63	25	0	0	48	0
Telford Homes Limited	3	15	11	3	0	61	0
Tilia Homes Limited	5	0	0	0	0	3	0
Vistry Group PLC	16	31	13	0	0	16	0
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-
Weston Group PLC	10	11	0	0	0	0	0
McCarthy & Stone Limited	0	0	0	0	0	4	0
Seven Capital PLC	0	0	0	0	0	5	0
Wates Group Limited	3	2	0	0	0	1	0
Watkin Jones PLC	0	4	0	0	0	2	0
Bouygues (UK) Limited	0	1	0	0	0	3	0
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	2	0	0	0	0	1	0

## Developer_11
Developer by developer breakdown of buildings, covered by the developer remediation contract and require remediation (excluding completed buildings), by engagement method, England, 31 July 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each developer that has signed the developer remediation contract, as of 31 July 2024.
Some cells refer to notes which can be found in the 'Notes' worksheet.
	Buildings where the developer or 'responsible entity' has engaged with the leaseholders, freeholders, residents, occupiers and other users regarding works for buildings being remediated directly by the developer, excluding completed buildings, by...					Number of buildings being remediated by the developers, excluding completed buildings	Sum of communication
	... the Responsible Entity		... directly		... directly and by the Responsible Entity		... unconfirmed how
Developer [Note_29]	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total	692	62%	32	3%	135	12%	125	11%	1110	89%
Abbey Developments Limited	-	-	-	-	-	-	-	-	-	-
Allison Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Viva Midco Limited (parent company for Avant Homes)	0	0%	0	0%	0	0%	1	100%	1	100%
Ballymore Limited	2	100%	0	0%	0	0%	0	0%	2	100%
Barratt Developments PLC	0	0%	0	0%	0	0%	123	95%	130	95%
Bellway PLC	109	99%	0	0%	0	0%	0	0%	110	99%
The Berkeley Group Holdings PLC	29	94%	0	0%	2	6%	0	0%	31	100%
Bewley Group Limited	3	100%	0	0%	0	0%	0	0%	3	100%
Bloor Investments Limited	-	-	-	-	-	-	-	-	-	-
The British Land Company PLC	2	100%	0	0%	0	0%	0	0%	2	100%
Cala Group (Holdings) Limited	1	100%	0	0%	0	0%	0	0%	1	100%
Canary Wharf Group PLC	0	-	0	-	0	-	0	-	0	-
C.G. Fry and Son Limited	-	-	-	-	-	-	-	-	-	-
Churchill Living (formerly Churchill Retirement PLC)	0	-	0	-	0	-	0	-	0	-
Crest Nicholson Holdings PLC	105	77%	0	0%	0	0%	0	0%	136	77%
Croudace Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Dandara Living Holdings Limited	0	0%	0	0%	13	100%	0	0%	13	100%
Emerson Developments (Holdings) Limited (parent company for Jones Homes)	-	-	-	-	-	-	-	-	-	-
Fairview Holdings Limited	0	0%	2	5%	35	95%	0	0%	37	100%
Frasers Property (UK) Ltd	0	-	0	-	0	-	0	-	0	-
Galliard Group Limited	3	75%	0	0%	1	25%	0	0%	4	100%
MJ Gleeson PLC	7	58%	2	17%	3	25%	0	0%	12	100%
Grosvenor Group Limited	0	0%	5	71%	2	29%	0	0%	7	100%
Hill Holdings Limited	3	75%	0	0%	1	25%	0	0%	4	100%
Hopkins Home Group Limited	-	-	-	-	-	-	-	-	-	-
Jelson Holdings Limited	0	-	0	-	0	-	0	-	0	-
Keepmoat Limited	-	-	-	-	-	-	-	-	-	-
Land Securities Group PLC	0	0%	0	0%	0	0%	0	0%	5	0%
Lendlease Europe Holdings Limited	0	0%	0	0%	0	0%	0	0%	33	0%
Pegasus Homes (formerly Lifestory Group)	0	0%	1	100%	0	0%	0	0%	1	100%
London Square Development (Holdings) Limited	37	100%	0	0%	0	0%	0	0%	37	100%
Miller Homes Limited	13	62%	0	0%	5	24%	0	0%	21	86%
Morris Homes Group Limited	1	100%	0	0%	0	0%	0	0%	1	100%
Morgan Sindall Group PLC (parent company for Lovell and Muse)	5	42%	0	0%	7	58%	0	0%	12	100%
Persimmon Public Limited Company	39	93%	2	5%	0	0%	0	0%	42	98%
Redrow PLC	56	80%	14	20%	0	0%	0	0%	70	100%
Regal Holdco Limited (parent company for Regal London)	0	-	0	-	0	-	0	-	0	-
Rowland Group Limited	-	-	-	-	-	-	-	-	-	-
Rydon Group Holdings Limited	0	0%	0	0%	1	33%	0	0%	3	33%
Sorbon Group Limited (parent company for Shanly Homes)	0	0%	0	0%	12	100%	0	0%	12	100%
St Modwen Group Holdings Company Limited	0	-	0	-	0	-	0	-	0	-
Story Homes Limited	-	-	-	-	-	-	-	-	-	-
Strata Homes Group Limited	-	-	-	-	-	-	-	-	-	-
Taylor Wimpey PLC	154	100%	0	0%	0	0%	0	0%	154	100%
Telford Homes Limited	70	75%	0	0%	22	24%	0	0%	93	99%
Tilia Homes Limited	7	88%	0	0%	0	0%	0	0%	8	88%
Vistry Group PLC	31	41%	4	5%	11	14%	0	0%	76	61%
Broadthorpe Limited (parent company for William Davis Homes)	-	-	-	-	-	-	-	-	-	-
Weston Group PLC	13	62%	0	0%	8	38%	0	0%	21	100%
McCarthy & Stone Limited	0	0%	0	0%	0	0%	0	0%	4	0%
Seven Capital PLC	0	0%	0	0%	0	0%	1	20%	5	20%
Wates Group Limited	0	0%	1	17%	5	83%	0	0%	6	100%
Watkin Jones PLC	0	0%	0	0%	6	100%	0	0%	6	100%
Bouygues (UK) Limited	0	0%	0	0%	1	25%	0	0%	4	25%
Other (combined total for all developers with 5 or fewer buildings each: Allison Homes, Bloor, CG Fry, Croudace, Emerson Group (Jones Homes), Hopkins, Keepmoat Homes, Rowland, Story Homes, Strata, William Davis)	2	67%	1	33%	0	0%	0	0%	3	100%

## Developer_12
Remediation status of buildings requiring works under the developer remediation contract, time series, England, 31 July 2024
Back to Contents
This worksheet contains two tables, presented next to each other vertically with one blank row in between the tables. All figures are for number of buildings or percentage of buildings identified as requiring works under the Developer Remediation Contract.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category - All Defect Types [Note_25, Note_26, Note_67]	Oct-23 Number	Oct-23 Percentage (%)	Jan-24 Number	Jan-24 Percentage (%)	Apr-24 Number	Apr-24 Percentage (%)	Jul-24 Number	Jul-24 Percentage (%)
Remediation complete	262	19%	307	20%	362	23%	410	25%
Remediation started	211	16%	317	21%	365	23%	359	22%
Remediation not Started - Plans in Place	506	38%	512	34%	371	24%	455	28%
Remediation not Started - No Plans in Place	366	27%	364	24%	471	30%	402	25%
Total buildings	1345	100%	1500	100%	1569	100%	1626	100%

Remediation Category - Cladding Defects [Note_25, Note_26, Note_67]	Oct-23 Number	Oct-23 Percentage (%)	Jan-24 Number	Jan-24 Percentage (%)	Apr-24 Number	Apr-24 Percentage (%)	Jul-24 Number	Jul-24 Percentage (%)
Remediation complete	245	19%	284	20%	340	24%	381	26%
Remediation started	200	16%	303	22%	337	24%	334	23%
Remediation not Started - Plans in Place	476	37%	481	34%	345	24%	418	29%
Remediation not Started - No Plans in Place	352	28%	335	24%	406	28%	316	22%
Total buildings	1273	100%	1403	100%	1428	100%	1449	100%

## Social_1
Remediation status of buildings with cladding defects monitored under the social housing surveys, England, 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each tenure.
Some cells refer to notes which can be found in the 'Notes' worksheet.
Remediation Category - Social Buildings with Unsafe Cladding [Note 34] [Note 35] [Note 59]	11-18m buildings	11-18m buildings	18m+ buildings	18m+ buildings	Total buildings	Total buildings
	Number	Percentage (%)	Number	Percentage (%)	Number	Percentage (%)
Remediation complete [Note 37] [Note 54]	166	14%	475	37%	641	26%
Remediation complete - Awaiting building control sign-off	25	2%	37	3%	62	2%
Remediation started	315	26%	250	19%	565	23%
Remediation works planned	391	32%	308	24%	699	28%
Remediation plans unclear from survey	319	26%	221	17%	540	22%
Total buildings [Note 36]	1,216	100%	1,291	100%	2,507	100%

Social Buildings with Unsafe Cladding identified since June 2017, as reported by Social Housing Providers [Note 34] [Note 35] [Note 68]	11-18m buildings	11-18m buildings	18m+ buildings	18m+ buildings	Total buildings	Total buildings
	Number	Percentage (%)	Number	Percentage (%)	Number	Percentage (%)
Remediation complete - Prior to the most recent assessment	142	12%	371	27%	513	21%
Remediation complete - Since the most recent assessment [Note 54]	47	4%	61	4%	108	4%
Remediation started	314	26%	248	18%	562	23%
Remediation works planned	377	31%	297	21%	674	28%
Remediation plans unclear from survey	323	27%	406	29%	544	23%
Total buildings	1,203	100%	1,383	100%	2,401	100%

Remediation Category - Social Buildings with Unsafe Cladding at the Time of their Most Recent Assessment, as reported by Social Housing Providers [Note 34] [Note 35] [Note 63]	11-18m buildings	11-18m buildings	18m+ buildings	18m+ buildings	Total buildings	Total buildings
	Number	Percentage (%)	Number	Percentage (%)	Number	Percentage (%)
Remediation complete [Note 37] [Note 54]	22	2%	28	3%	50	3%
Remediation complete - Awaiting building control sign-off	25	2%	33	4%	58	3%
Remediation started	314	30%	248	30%	562	30%
Remediation works planned	377	36%	297	36%	674	36%
Remediation plans unclear from survey	323	30%	221	27%	544	29%
Total buildings	1,061	100%	827	100%	1,888	100%

## Social_2a
Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 June 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level survey, as of 30 June 2024
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51]	Total number of buildings over 11 metres	Number of buildings identified as having EWS life-critical fire-safety defects since June 2017 [Note_35] [Note_68]	% buildings identified as having EWS life-critical fire-safety defects since June 2017
Total (All Providers)	17436	2401	14%
A2Dominion Housing Group Limited	207	37	18%
Abri Group Limited	36	7	19%
Accent Group Limited	6	2	33%
Acis Group Limited	12	0	0%
Agudas Israel Housing Association Limited	20	0	0%
Anchor Hanover Group	36	10	28%
Ashford Borough Council	16	0	0%
Ashton Pioneer Homes Limited	10	0	0%
Aster Group Limited	43	7	16%
B3 Living Limited	11	5	45%
Beyond Housing Limited	10	0	0%
Birkenhead Forum Housing Association Limited	9	0	0%
Birmingham City Council	205	146	71%
Bolton at Home Limited	9	0	0%
Bournemouth, Christchurch and Poole Council	14	2	14%
bpha Limited	27	5	19%
Brighter Places	15	0	0%
Brighton and Hove City Council	81	0	0%
Bristol City Council	126	108	86%
Broadland Housing Association Limited	10	2	20%
Bromford Housing Group Limited	11	1	9%
Cambridge City Council	13	0	0%
Central Bedfordshire Council	9	1	11%
Christian Action (Enfield) Housing Association Limited	13	3	23%
Citizen Housing Group Limited	60	2	3%
City of Doncaster Council	9	5	56%
City of London Corporation	23	0	0%
City of Westminster Council	411	1	0%
Clarion Housing Group Limited	548	114	21%
Curo Group (Albion) Limited	149	5	3%
Dacorum Borough Council	15	4	27%
Dudley Metropolitan Borough Council	49	0	0%
East End Homes Limited	43	7	16%
Eastlight Community Homes Limited	14	6	43%
Ekaya Housing Association Limited	10	0	0%
Epping Forest District Council	10	1	10%
Estuary Housing Association Limited	94	1	1%
Exeter City Council	7	0	0%
Fairhazel Co-operative Limited	12	0	0%
First Choice Homes Oldham Limited	7	2	29%
Flagship Housing Group Limited	18	1	6%
Folkestone and Hythe District Council	15	0	0%
ForHousing Limited	26	11	42%
Gateshead Metropolitan Borough Council	25	0	0%
Gateway Housing Association Limited	23	1	4%
Gentoo Group Limited	32	11	34%
Golding Homes Limited	8	3	38%
Gosport Borough Council	6	0	0%
Gravesham Borough Council	7	0	0%
Great Places Housing Group Limited	16	5	31%
GreenSquareAccord Limited	22	15	68%
Haringey London Borough Council	91	46	51%
Harlow District Council	18	2	11%
Hastoe Housing Association Limited	6	3	50%
Heart of Medway Housing Association Limited	8	6	75%
Hexagon Housing Association Limited	21	20	95%
HFL Homes Limited	6	0	0%
Hightown Housing Association Limited	20	2	10%
Home Group Limited	71	29	41%
Housing 21	18	0	0%
Housing For Women	20	0	0%
Hyde Housing Association Limited	194	61	31%
Incommunities Limited	32	11	34%
Irwell Valley Housing Association Limited	13	6	46%
Islington and Shoreditch Housing Association Limited	44	14	32%
Jigsaw Homes Group Limited	19	11	58%
Karbon Homes Limited	34	16	47%
Karibu Community Homes Limited	10	0	0%
Kingston upon Hull City Council	26	0	0%
Kirklees Metropolitan Borough Council	21	15	71%
Lambeth and Southwark Housing Association Limited	11	0	0%
Leeds City Council	131	0	0%
Legal & General Affordable Homes Limited	6	0	0%
Leicester City Council	11	0	0%
LiveWest Homes Limited	52	6	12%
Livv Housing Group	9	0	0%
London & Quadrant Housing Trust	701	95	14%
London Borough of Barking and Dagenham	33	2	6%
London Borough of Barnet	48	7	15%
London Borough of Brent	167	4	2%
London Borough of Camden Council	949	12	1%
London Borough of Croydon	67	0	0%
London Borough of Ealing	52	16	31%
London Borough of Enfield	65	1	2%
London Borough of Hackney	462	10	2%
London Borough of Hammersmith and Fulham	231	7	3%
London Borough of Havering Council	21	0	0%
London Borough of Hillingdon	12	0	0%
London Borough of Hounslow	55	0	0%
London Borough of Islington	386	2	1%
London Borough of Lambeth	421	0	0%
London Borough of Lewisham	137	0	0%
London Borough of Newham	90	57	63%
London Borough of Redbridge	19	0	0%
London Borough of Sutton	60	1	2%
London Borough of Tower Hamlets	325	31	10%
London Borough of Waltham Forest	63	26	41%
London Borough of Wandsworth	363	2	1%
Look Ahead Care and Support Limited	10	2	20%
Luton Borough Council	15	0	0%
Magenta Living	11	3	27%
Manchester City Council	51	9	18%
Midland Heart Limited	19	1	5%
Moat Homes Limited	22	5	23%
New Foundations Housing Association Limited	6	0	0%
Newark and Sherwood District Council	6	0	0%
Newcastle City Council	55	0	0%
Newlon Housing Trust	85	50	59%
North London Muslim Housing Association Limited	12	9	75%
Norwich City Council	25	2	8%
Notting Hill Genesis	969	35	4%
Nottingham City Council	24	0	0%
Nottingham Community Housing Association Limited	13	1	8%
Octavia Housing	112	36	32%
One Manchester Limited	23	0	0%
One Vision Housing Limited	8	2	25%
Onward Group Limited	50	15	30%
Orbit Group Limited	79	23	29%
Origin Housing Limited	105	16	15%
Oxford City Council	8	6	75%
P3 Housing Limited	19	0	0%
Paradigm Housing Group Limited	24	5	21%
Paragon Asra Housing Limited	80	21	26%
Peabody Trust	1209	194	16%
Phoenix Community Housing Association (Bellingham and Downham) Limited	15	10	67%
Pinnacle Spaces Limited	6	0	0%
Places for People Group Limited	81	17	21%
Platform Housing Group Limited	16	1	6%
Plus Dane Housing Limited	12	0	0%
Plymouth Community Homes Limited	55	0	0%
Poplar Housing And Regeneration Community Association Limited	119	31	26%
Portsmouth City Council	55	27	49%
Providence Row Housing Association	11	1	9%
Raven Housing Trust Limited	11	0	0%
Reading Borough Council	18	7	39%
Regenda Limited	17	4	24%
Richmond Housing Partnership Limited	43	18	42%
Rochdale Boroughwide Housing Limited	14	7	50%
Rooftop Housing Group Limited	7	1	14%
Royal Borough of Greenwich	477	1	0%
Royal Borough of Kensington and Chelsea	145	4	3%
Royal Borough of Kingston Upon Thames	34	0	0%
Salix Homes Limited	20	8	40%
Salvation Army Housing Association	15	0	0%
Sanctuary Housing Association	430	58	13%
Sandwell Metropolitan Borough Council	55	1	2%
Sheffield City Council	358	0	0%
Shepherds Bush Housing Association Limited	57	9	16%
Soho Housing Association Limited	46	1	2%
Solihull Metropolitan Borough Council	37	16	43%
Southampton City Council	201	95	47%
Southend on Sea City Council	18	0	0%
Southern Housing	541	115	21%
Southwark Council	841	0	0%
Southway Housing Trust (Manchester) Limited	6	0	0%
Sovereign Housing Association Limited	310	91	29%
Spitalfields Housing Association Limited	11	4	36%
St Mungo Community Housing Association	21	1	5%
Stevenage Borough Council	11	5	45%
Stockport Homes Limited	30	0	0%
Stoke on Trent City Council	18	8	44%
Stonewater Limited	33	8	24%
Swindon Borough Council	8	0	0%
Tamworth Borough Council	7	0	0%
Teign Housing	8	1	13%
Thames Valley Housing Association Limited	255	110	43%
Thanet District Council	14	5	36%
The ExtraCare Charitable Trust	10	0	0%
The Guinness Partnership Limited	249	15	6%
The Housing Plus Group Limited	9	0	0%
The Industrial Dwellings Society (1885) Limited	35	0	0%
The Riverside Group Limited	301	91	30%
Thirteen Housing Group Limited	15	0	0%
Thurrock Council	18	0	0%
Together Housing Group Limited	45	12	27%
Torus62 Limited	6	0	0%
Tower Hamlets Community Housing	37	16	43%
Trident Housing Association Limited	12	0	0%
Vivid Housing Limited	54	9	17%
Wakefield And District Housing Limited	19	4	21%
Walsall Housing Group Limited	19	0	0%
Wandle Housing Association Limited	38	12	32%
Warwick District Council	16	5	31%
Watford Community Housing Trust	9	0	0%
Watmos Community Homes	29	0	0%
West Hampstead Housing Co-operative Limited	11	0	0%
West Northamptonshire Council	12	8	67%
Wigan Council	7	0	0%
Woking Borough Council	25	14	56%
Wolverhampton City Council	52	9	17%
Women's Pioneer Housing Limited	63	0	0%
Worthing Homes Limited	6	2	33%
Wythenshawe Community Housing Group Limited	12	7	58%
YMCA St Paul's Group	6	0	0%
Yorkshire Housing Limited	14	0	0%
Your Housing Group Limited	26	13	50%
Zebra Housing Association Limited	8	0	0%
Other RPs	519	32	6%

## Social_2b
Provider by provider breakdown of building stock and buildings requiring External Wall System (EWS) remediation, England, 30 June 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level survey, as of 30 June 2024
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51]	Total number of buildings over 11 metres	Number of buildings assessed as having EWS life-critical fire-safety defects at the time of their most recent assessment [Note_35] [Note_52] [Note_63]	% buildings assessed as having EWS life-critical fire-safety defects at the time of their most recent assessment
Total (All Providers)	17436	1888	11%
A2Dominion Housing Group Limited	207	37	18%
Abri Group Limited	36	2	6%
Accent Group Limited	6	0	0%
Acis Group Limited	12	0	0%
Agudas Israel Housing Association Limited	20	0	0%
Anchor Hanover Group	36	10	28%
Ashford Borough Council	16	0	0%
Ashton Pioneer Homes Limited	10	0	0%
Aster Group Limited	43	4	9%
B3 Living Limited	11	5	45%
Beyond Housing Limited	10	0	0%
Birkenhead Forum Housing Association Limited	9	0	0%
Birmingham City Council	205	22	11%
Bolton at Home Limited	9	0	0%
Bournemouth, Christchurch and Poole Council	14	0	0%
bpha Limited	27	2	7%
Brighter Places	15	0	0%
Brighton and Hove City Council	81	0	0%
Bristol City Council	126	108	86%
Broadland Housing Association Limited	10	1	10%
Bromford Housing Group Limited	11	1	9%
Cambridge City Council	13	0	0%
Central Bedfordshire Council	9	1	11%
Christian Action (Enfield) Housing Association Limited	13	3	23%
Citizen Housing Group Limited	60	2	3%
City of Doncaster Council	9	5	56%
City of London Corporation	23	0	0%
City of Westminster Council	411	1	0%
Clarion Housing Group Limited	548	114	21%
Curo Group (Albion) Limited	149	0	0%
Dacorum Borough Council	15	4	27%
Dudley Metropolitan Borough Council	49	0	0%
East End Homes Limited	43	6	14%
Eastlight Community Homes Limited	14	6	43%
Ekaya Housing Association Limited	10	0	0%
Epping Forest District Council	10	0	0%
Estuary Housing Association Limited	94	1	1%
Exeter City Council	7	0	0%
Fairhazel Co-operative Limited	12	0	0%
First Choice Homes Oldham Limited	7	0	0%
Flagship Housing Group Limited	18	1	6%
Folkestone and Hythe District Council	15	0	0%
ForHousing Limited	26	5	19%
Gateshead Metropolitan Borough Council	25	0	0%
Gateway Housing Association Limited	23	1	4%
Gentoo Group Limited	32	5	16%
Golding Homes Limited	8	3	38%
Gosport Borough Council	6	0	0%
Gravesham Borough Council	7	0	0%
Great Places Housing Group Limited	16	4	25%
GreenSquareAccord Limited	22	15	68%
Haringey London Borough Council	91	46	51%
Harlow District Council	18	2	11%
Hastoe Housing Association Limited	6	3	50%
Heart of Medway Housing Association Limited	8	0	0%
Hexagon Housing Association Limited	21	20	95%
HFL Homes Limited	6	0	0%
Hightown Housing Association Limited	20	2	10%
Home Group Limited	71	24	34%
Housing 21	18	0	0%
Housing For Women	20	0	0%
Hyde Housing Association Limited	194	39	20%
Incommunities Limited	32	11	34%
Irwell Valley Housing Association Limited	13	5	38%
Islington and Shoreditch Housing Association Limited	44	7	16%
Jigsaw Homes Group Limited	19	9	47%
Karbon Homes Limited	34	15	44%
Karibu Community Homes Limited	10	0	0%
Kingston upon Hull City Council	26	0	0%
Kirklees Metropolitan Borough Council	21	15	71%
Lambeth and Southwark Housing Association Limited	11	0	0%
Leeds City Council	131	0	0%
Legal & General Affordable Homes Limited	6	0	0%
Leicester City Council	11	0	0%
LiveWest Homes Limited	52	5	10%
Livv Housing Group	9	0	0%
London & Quadrant Housing Trust	701	71	10%
London Borough of Barking and Dagenham	33	2	6%
London Borough of Barnet	48	7	15%
London Borough of Brent	167	4	2%
London Borough of Camden Council	949	5	1%
London Borough of Croydon	67	0	0%
London Borough of Ealing	52	16	31%
London Borough of Enfield	65	0	0%
London Borough of Hackney	462	6	1%
London Borough of Hammersmith and Fulham	231	7	3%
London Borough of Havering Council	21	0	0%
London Borough of Hillingdon	12	0	0%
London Borough of Hounslow	55	0	0%
London Borough of Islington	386	0	0%
London Borough of Lambeth	421	0	0%
London Borough of Lewisham	137	0	0%
London Borough of Newham	90	49	54%
London Borough of Redbridge	19	0	0%
London Borough of Sutton	60	1	2%
London Borough of Tower Hamlets	325	27	8%
London Borough of Waltham Forest	63	23	37%
London Borough of Wandsworth	363	2	1%
Look Ahead Care and Support Limited	10	1	10%
Luton Borough Council	15	0	0%
Magenta Living	11	3	27%
Manchester City Council	51	7	14%
Midland Heart Limited	19	0	0%
Moat Homes Limited	22	4	18%
New Foundations Housing Association Limited	6	0	0%
Newark and Sherwood District Council	6	0	0%
Newcastle City Council	55	0	0%
Newlon Housing Trust	85	50	59%
North London Muslim Housing Association Limited	12	9	75%
Norwich City Council	25	2	8%
Notting Hill Genesis	969	0	0%
Nottingham City Council	24	0	0%
Nottingham Community Housing Association Limited	13	0	0%
Octavia Housing	112	34	30%
One Manchester Limited	23	0	0%
One Vision Housing Limited	8	0	0%
Onward Group Limited	50	7	14%
Orbit Group Limited	79	20	25%
Origin Housing Limited	105	16	15%
Oxford City Council	8	6	75%
P3 Housing Limited	19	0	0%
Paradigm Housing Group Limited	24	0	0%
Paragon Asra Housing Limited	80	19	24%
Peabody Trust	1209	185	15%
Phoenix Community Housing Association (Bellingham and Downham) Limited	15	4	27%
Pinnacle Spaces Limited	6	0	0%
Places for People Group Limited	81	4	5%
Platform Housing Group Limited	16	1	6%
Plus Dane Housing Limited	12	0	0%
Plymouth Community Homes Limited	55	0	0%
Poplar Housing And Regeneration Community Association Limited	119	8	7%
Portsmouth City Council	55	16	29%
Providence Row Housing Association	11	0	0%
Raven Housing Trust Limited	11	0	0%
Reading Borough Council	18	7	39%
Regenda Limited	17	3	18%
Richmond Housing Partnership Limited	43	18	42%
Rochdale Boroughwide Housing Limited	14	7	50%
Rooftop Housing Group Limited	7	1	14%
Royal Borough of Greenwich	477	1	0%
Royal Borough of Kensington and Chelsea	145	4	3%
Royal Borough of Kingston Upon Thames	34	0	0%
Salix Homes Limited	20	0	0%
Salvation Army Housing Association	15	0	0%
Sanctuary Housing Association	430	41	10%
Sandwell Metropolitan Borough Council	55	1	2%
Sheffield City Council	358	0	0%
Shepherds Bush Housing Association Limited	57	2	4%
Soho Housing Association Limited	46	0	0%
Solihull Metropolitan Borough Council	37	16	43%
Southampton City Council	201	95	47%
Southend on Sea City Council	18	0	0%
Southern Housing	541	110	20%
Southwark Council	841	0	0%
Southway Housing Trust (Manchester) Limited	6	0	0%
Sovereign Housing Association Limited	310	62	20%
Spitalfields Housing Association Limited	11	0	0%
St Mungo Community Housing Association	21	1	5%
Stevenage Borough Council	11	5	45%
Stockport Homes Limited	30	0	0%
Stoke on Trent City Council	18	8	44%
Stonewater Limited	33	4	12%
Swindon Borough Council	8	0	0%
Tamworth Borough Council	7	0	0%
Teign Housing	8	1	13%
Thames Valley Housing Association Limited	255	97	38%
Thanet District Council	14	5	36%
The ExtraCare Charitable Trust	10	0	0%
The Guinness Partnership Limited	249	13	5%
The Housing Plus Group Limited	9	0	0%
The Industrial Dwellings Society (1885) Limited	35	0	0%
The Riverside Group Limited	301	91	30%
Thirteen Housing Group Limited	15	0	0%
Thurrock Council	18	0	0%
Together Housing Group Limited	45	0	0%
Torus62 Limited	6	0	0%
Tower Hamlets Community Housing	37	15	41%
Trident Housing Association Limited	12	0	0%
Vivid Housing Limited	54	2	4%
Wakefield And District Housing Limited	19	4	21%
Walsall Housing Group Limited	19	0	0%
Wandle Housing Association Limited	38	12	32%
Warwick District Council	16	5	31%
Watford Community Housing Trust	9	0	0%
Watmos Community Homes	29	0	0%
West Hampstead Housing Co-operative Limited	11	0	0%
West Northamptonshire Council	12	8	67%
Wigan Council	7	0	0%
Woking Borough Council	25	14	56%
Wolverhampton City Council	52	9	17%
Women's Pioneer Housing Limited	63	0	0%
Worthing Homes Limited	6	1	17%
Wythenshawe Community Housing Group Limited	12	0	0%
YMCA St Paul's Group	6	0	0%
Yorkshire Housing Limited	14	0	0%
Your Housing Group Limited	26	13	50%
Zebra Housing Association Limited	8	0	0%
Other RPs	519	24	5%

## Social_3
Provider by provider breakdown of buildings, by assessment status, England, 30 June 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provider that has submitted a building level return, as of 30 June 2024
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51]	Progress with assessments
	Of the total number of buildings over 11m, buildings that…
	…have had a recent works assessment [Note 52]		…have not had a recent works assessment		…have been assessed and identified as having EWS life-critical fire-safety defects at the time of their most recent works assessment [Note_35] [Note_63]
	Number	Percentage	Number	Percentage‎	Number	Percentage
Total (All Providers)	17245	99%	191	1%	1888	11%
A2Dominion Housing Group Limited	207	100%	0	0%	37	18%
Abri Group Limited	36	100%	0	0%	2	6%
Accent Group Limited	6	100%	0	0%	0	0%
Acis Group Limited	12	100%	0	0%	0	0%
Agudas Israel Housing Association Limited	20	100%	0	0%	0	0%
Anchor Hanover Group	36	100%	0	0%	10	28%
Ashford Borough Council	16	100%	0	0%	0	0%
Ashton Pioneer Homes Limited	10	100%	0	0%	0	0%
Aster Group Limited	43	100%	0	0%	4	9%
B3 Living Limited	11	100%	0	0%	5	45%
Beyond Housing Limited	10	100%	0	0%	0	0%
Birkenhead Forum Housing Association Limited	9	100%	0	0%	0	0%
Birmingham City Council	205	100%	0	0%	22	11%
Bolton at Home Limited	9	100%	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	14	100%	0	0%	0	0%
bpha Limited	27	100%	0	0%	2	7%
Brighter Places	15	100%	0	0%	0	0%
Brighton and Hove City Council	81	100%	0	0%	0	0%
Bristol City Council	126	100%	0	0%	108	86%
Broadland Housing Association Limited	10	100%	0	0%	1	10%
Bromford Housing Group Limited	11	100%	0	0%	1	9%
Cambridge City Council	13	100%	0	0%	0	0%
Central Bedfordshire Council	9	100%	0	0%	1	11%
Christian Action (Enfield) Housing Association Limited	13	100%	0	0%	3	23%
Citizen Housing Group Limited	60	100%	0	0%	2	3%
City of Doncaster Council	9	100%	0	0%	5	56%
City of London Corporation	23	100%	0	0%	0	0%
City of Westminster Council	411	100%	0	0%	1	0%
Clarion Housing Group Limited	545	99%	3	1%	114	21%
Curo Group (Albion) Limited	149	100%	0	0%	0	0%
Dacorum Borough Council	15	100%	0	0%	4	27%
Dudley Metropolitan Borough Council	49	100%	0	0%	0	0%
East End Homes Limited	43	100%	0	0%	6	14%
Eastlight Community Homes Limited	14	100%	0	0%	6	43%
Ekaya Housing Association Limited	10	100%	0	0%	0	0%
Epping Forest District Council	10	100%	0	0%	0	0%
Estuary Housing Association Limited	94	100%	0	0%	1	1%
Exeter City Council	7	100%	0	0%	0	0%
Fairhazel Co-operative Limited	12	100%	0	0%	0	0%
First Choice Homes Oldham Limited	7	100%	0	0%	0	0%
Flagship Housing Group Limited	18	100%	0	0%	1	6%
Folkestone and Hythe District Council	15	100%	0	0%	0	0%
ForHousing Limited	26	100%	0	0%	5	19%
Gateshead Metropolitan Borough Council	25	100%	0	0%	0	0%
Gateway Housing Association Limited	23	100%	0	0%	1	4%
Gentoo Group Limited	32	100%	0	0%	5	16%
Golding Homes Limited	8	100%	0	0%	3	38%
Gosport Borough Council	6	100%	0	0%	0	0%
Gravesham Borough Council	7	100%	0	0%	0	0%
Great Places Housing Group Limited	15	94%	1	6%	4	25%
GreenSquareAccord Limited	22	100%	0	0%	15	68%
Haringey London Borough Council	86	95%	5	5%	46	51%
Harlow District Council	18	100%	0	0%	2	11%
Hastoe Housing Association Limited	6	100%	0	0%	3	50%
Heart of Medway Housing Association Limited	7	88%	1	13%	0	0%
Hexagon Housing Association Limited	21	100%	0	0%	20	95%
HFL Homes Limited	6	100%	0	0%	0	0%
Hightown Housing Association Limited	20	100%	0	0%	2	10%
Home Group Limited	71	100%	0	0%	24	34%
Housing 21	18	100%	0	0%	0	0%
Housing For Women	20	100%	0	0%	0	0%
Hyde Housing Association Limited	194	100%	0	0%	39	20%
Incommunities Limited	32	100%	0	0%	11	34%
Irwell Valley Housing Association Limited	13	100%	0	0%	5	38%
Islington and Shoreditch Housing Association Limited	44	100%	0	0%	7	16%
Jigsaw Homes Group Limited	19	100%	0	0%	9	47%
Karbon Homes Limited	34	100%	0	0%	15	44%
Karibu Community Homes Limited	6	60%	4	40%	0	0%
Kingston upon Hull City Council	26	100%	0	0%	0	0%
Kirklees Metropolitan Borough Council	21	100%	0	0%	15	71%
Lambeth and Southwark Housing Association Limited	11	100%	0	0%	0	0%
Leeds City Council	131	100%	0	0%	0	0%
Legal & General Affordable Homes Limited	6	100%	0	0%	0	0%
Leicester City Council	11	100%	0	0%	0	0%
LiveWest Homes Limited	52	100%	0	0%	5	10%
Livv Housing Group	9	100%	0	0%	0	0%
London & Quadrant Housing Trust	701	100%	0	0%	71	10%
London Borough of Barking and Dagenham	33	100%	0	0%	2	6%
London Borough of Barnet	48	100%	0	0%	7	15%
London Borough of Brent	167	100%	0	0%	4	2%
London Borough of Camden Council	949	100%	0	0%	5	1%
London Borough of Croydon	67	100%	0	0%	0	0%
London Borough of Ealing	52	100%	0	0%	16	31%
London Borough of Enfield	65	100%	0	0%	0	0%
London Borough of Hackney	460	100%	2	0%	6	1%
London Borough of Hammersmith and Fulham	231	100%	0	0%	7	3%
London Borough of Havering Council	21	100%	0	0%	0	0%
London Borough of Hillingdon	12	100%	0	0%	0	0%
London Borough of Hounslow	55	100%	0	0%	0	0%
London Borough of Islington	386	100%	0	0%	0	0%
London Borough of Lambeth	421	100%	0	0%	0	0%
London Borough of Lewisham	137	100%	0	0%	0	0%
London Borough of Newham	90	100%	0	0%	49	54%
London Borough of Redbridge	19	100%	0	0%	0	0%
London Borough of Sutton	60	100%	0	0%	1	2%
London Borough of Tower Hamlets	325	100%	0	0%	27	8%
London Borough of Waltham Forest	63	100%	0	0%	23	37%
London Borough of Wandsworth	363	100%	0	0%	2	1%
Look Ahead Care and Support Limited	10	100%	0	0%	1	10%
Luton Borough Council	15	100%	0	0%	0	0%
Magenta Living	11	100%	0	0%	3	27%
Manchester City Council	51	100%	0	0%	7	14%
Midland Heart Limited	19	100%	0	0%	0	0%
Moat Homes Limited	22	100%	0	0%	4	18%
New Foundations Housing Association Limited	6	100%	0	0%	0	0%
Newark and Sherwood District Council	6	100%	0	0%	0	0%
Newcastle City Council	55	100%	0	0%	0	0%
Newlon Housing Trust	85	100%	0	0%	50	59%
North London Muslim Housing Association Limited	12	100%	0	0%	9	75%
Norwich City Council	25	100%	0	0%	2	8%
Notting Hill Genesis	969	100%	0	0%	0	0%
Nottingham City Council	24	100%	0	0%	0	0%
Nottingham Community Housing Association Limited	13	100%	0	0%	0	0%
Octavia Housing	112	100%	0	0%	34	30%
One Manchester Limited	23	100%	0	0%	0	0%
One Vision Housing Limited	8	100%	0	0%	0	0%
Onward Group Limited	50	100%	0	0%	7	14%
Orbit Group Limited	79	100%	0	0%	20	25%
Origin Housing Limited	105	100%	0	0%	16	15%
Oxford City Council	8	100%	0	0%	6	75%
P3 Housing Limited	19	100%	0	0%	0	0%
Paradigm Housing Group Limited	24	100%	0	0%	0	0%
Paragon Asra Housing Limited	80	100%	0	0%	19	24%
Peabody Trust	1209	100%	0	0%	185	15%
Phoenix Community Housing Association (Bellingham and Downham) Limited	15	100%	0	0%	4	27%
Pinnacle Spaces Limited	6	100%	0	0%	0	0%
Places for People Group Limited	81	100%	0	0%	4	5%
Platform Housing Group Limited	16	100%	0	0%	1	6%
Plus Dane Housing Limited	12	100%	0	0%	0	0%
Plymouth Community Homes Limited	55	100%	0	0%	0	0%
Poplar Housing And Regeneration Community Association Limited	119	100%	0	0%	8	7%
Portsmouth City Council	55	100%	0	0%	16	29%
Providence Row Housing Association	11	100%	0	0%	0	0%
Raven Housing Trust Limited	11	100%	0	0%	0	0%
Reading Borough Council	18	100%	0	0%	7	39%
Regenda Limited	17	100%	0	0%	3	18%
Richmond Housing Partnership Limited	43	100%	0	0%	18	42%
Rochdale Boroughwide Housing Limited	14	100%	0	0%	7	50%
Rooftop Housing Group Limited	7	100%	0	0%	1	14%
Royal Borough of Greenwich	421	88%	56	12%	1	0%
Royal Borough of Kensington and Chelsea	145	100%	0	0%	4	3%
Royal Borough of Kingston Upon Thames	34	100%	0	0%	0	0%
Salix Homes Limited	20	100%	0	0%	0	0%
Salvation Army Housing Association	15	100%	0	0%	0	0%
Sanctuary Housing Association	430	100%	0	0%	41	10%
Sandwell Metropolitan Borough Council	55	100%	0	0%	1	2%
Sheffield City Council	358	100%	0	0%	0	0%
Shepherds Bush Housing Association Limited	57	100%	0	0%	2	4%
Soho Housing Association Limited	46	100%	0	0%	0	0%
Solihull Metropolitan Borough Council	37	100%	0	0%	16	43%
Southampton City Council	201	100%	0	0%	95	47%
Southend on Sea City Council	18	100%	0	0%	0	0%
Southern Housing	541	100%	0	0%	110	20%
Southwark Council	841	100%	0	0%	0	0%
Southway Housing Trust (Manchester) Limited	6	100%	0	0%	0	0%
Sovereign Housing Association Limited	309	100%	1	0%	62	20%
Spitalfields Housing Association Limited	11	100%	0	0%	0	0%
St Mungo Community Housing Association	21	100%	0	0%	1	5%
Stevenage Borough Council	11	100%	0	0%	5	45%
Stockport Homes Limited	30	100%	0	0%	0	0%
Stoke on Trent City Council	18	100%	0	0%	8	44%
Stonewater Limited	33	100%	0	0%	4	12%
Swindon Borough Council	8	100%	0	0%	0	0%
Tamworth Borough Council	7	100%	0	0%	0	0%
Teign Housing	8	100%	0	0%	1	13%
Thames Valley Housing Association Limited	150	59%	105	41%	97	38%
Thanet District Council	14	100%	0	0%	5	36%
The ExtraCare Charitable Trust	10	100%	0	0%	0	0%
The Guinness Partnership Limited	249	100%	0	0%	13	5%
The Housing Plus Group Limited	9	100%	0	0%	0	0%
The Industrial Dwellings Society (1885) Limited	35	100%	0	0%	0	0%
The Riverside Group Limited	301	100%	0	0%	91	30%
Thirteen Housing Group Limited	15	100%	0	0%	0	0%
Thurrock Council	18	100%	0	0%	0	0%
Together Housing Group Limited	45	100%	0	0%	0	0%
Torus62 Limited	6	100%	0	0%	0	0%
Tower Hamlets Community Housing	35	95%	2	5%	15	41%
Trident Housing Association Limited	12	100%	0	0%	0	0%
Vivid Housing Limited	54	100%	0	0%	2	4%
Wakefield And District Housing Limited	19	100%	0	0%	4	21%
Walsall Housing Group Limited	19	100%	0	0%	0	0%
Wandle Housing Association Limited	38	100%	0	0%	12	32%
Warwick District Council	16	100%	0	0%	5	31%
Watford Community Housing Trust	9	100%	0	0%	0	0%
Watmos Community Homes	29	100%	0	0%	0	0%
West Hampstead Housing Co-operative Limited	11	100%	0	0%	0	0%
West Northamptonshire Council	12	100%	0	0%	8	67%
Wigan Council	7	100%	0	0%	0	0%
Woking Borough Council	25	100%	0	0%	14	56%
Wolverhampton City Council	52	100%	0	0%	9	17%
Women's Pioneer Housing Limited	63	100%	0	0%	0	0%
Worthing Homes Limited	6	100%	0	0%	1	17%
Wythenshawe Community Housing Group Limited	12	100%	0	0%	0	0%
YMCA St Paul's Group	6	100%	0	0%	0	0%
Yorkshire Housing Limited	14	100%	0	0%	0	0%
Your Housing Group Limited	26	100%	0	0%	13	50%
Zebra Housing Association Limited	8	100%	0	0%	0	0%
Other RPs	508	98%	11	2%	24	5%

## Social_4a
Provider by provider breakdown of buildings, by remediation status, England, 30 June 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provieder that has submitted a building level return, as of 30 June 2024
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51]	Remediation Status
	Number and proportion of buildings identified as having EWS life-critical fire-safety defects [Note 35] [Note 68] since June 2017, where remediation...
	…plans are unclear from survey		…works are planned		…has started		... has completed since the most recent works assessment [Note 54]		... has completed prior to the most recent works assessment
	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total	544	23%	674	28%	562	23%	108	4%	513	21%
A2Dominion Housing Group Limited	0	0%	17	46%	7	19%	13	35%	0	0%
Abri Group Limited	0	0%	2	29%	0	0%	0	0%	5	71%
Accent Group Limited	0	0%	0	0%	0	0%	0	0%	2	100%
Acis Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Agudas Israel Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Anchor Hanover Group	0	0%	4	40%	6	60%	0	0%	0	0%
Ashford Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Ashton Pioneer Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Aster Group Limited	0	0%	4	57%	0	0%	0	0%	3	43%
B3 Living Limited	5	100%	0	0%	0	0%	0	0%	0	0%
Beyond Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Birkenhead Forum Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Birmingham City Council	0	0%	7	5%	15	10%	0	0%	124	85%
Bolton at Home Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	0	0%	0	0%	0	0%	0	0%	2	100%
bpha Limited	2	40%	0	0%	0	0%	0	0%	3	60%
Brighter Places	0	0%	0	0%	0	0%	0	0%	0	0%
Brighton and Hove City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Bristol City Council	85	79%	13	12%	10	9%	0	0%	0	0%
Broadland Housing Association Limited	1	50%	0	0%	0	0%	0	0%	1	50%
Bromford Housing Group Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Cambridge City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Central Bedfordshire Council	0	0%	1	100%	0	0%	0	0%	0	0%
Christian Action (Enfield) Housing Association Limited	3	100%	0	0%	0	0%	0	0%	0	0%
Citizen Housing Group Limited	0	0%	2	100%	0	0%	0	0%	0	0%
City of Doncaster Council	0	0%	0	0%	5	100%	0	0%	0	0%
City of London Corporation	0	0%	0	0%	0	0%	0	0%	0	0%
City of Westminster Council	1	100%	0	0%	0	0%	0	0%	0	0%
Clarion Housing Group Limited	0	0%	8	7%	99	87%	7	6%	0	0%
Curo Group (Albion) Limited	0	0%	0	0%	0	0%	0	0%	5	100%
Dacorum Borough Council	2	50%	0	0%	2	50%	0	0%	0	0%
Dudley Metropolitan Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
East End Homes Limited	0	0%	5	71%	0	0%	1	14%	1	14%
Eastlight Community Homes Limited	0	0%	0	0%	0	0%	6	100%	0	0%
Ekaya Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Epping Forest District Council	0	0%	0	0%	0	0%	0	0%	1	100%
Estuary Housing Association Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Exeter City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Fairhazel Co-operative Limited	0	0%	0	0%	0	0%	0	0%	0	0%
First Choice Homes Oldham Limited	0	0%	0	0%	0	0%	0	0%	2	100%
Flagship Housing Group Limited	0	0%	1	100%	0	0%	0	0%	0	0%
Folkestone and Hythe District Council	0	0%	0	0%	0	0%	0	0%	0	0%
ForHousing Limited	0	0%	5	45%	0	0%	0	0%	6	55%
Gateshead Metropolitan Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Gateway Housing Association Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Gentoo Group Limited	4	36%	0	0%	0	0%	1	9%	6	55%
Golding Homes Limited	1	33%	0	0%	2	67%	0	0%	0	0%
Gosport Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Gravesham Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Great Places Housing Group Limited	0	0%	4	80%	0	0%	0	0%	1	20%
GreenSquareAccord Limited	0	0%	0	0%	15	100%	0	0%	0	0%
Haringey London Borough Council	0	0%	8	17%	38	83%	0	0%	0	0%
Harlow District Council	0	0%	0	0%	0	0%	2	100%	0	0%
Hastoe Housing Association Limited	0	0%	2	67%	1	33%	0	0%	0	0%
Heart of Medway Housing Association Limited	0	0%	0	0%	0	0%	0	0%	6	100%
Hexagon Housing Association Limited	17	85%	1	5%	1	5%	1	5%	0	0%
HFL Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Hightown Housing Association Limited	1	50%	0	0%	1	50%	0	0%	0	0%
Home Group Limited	0	0%	11	38%	13	45%	0	0%	5	17%
Housing 21	0	0%	0	0%	0	0%	0	0%	0	0%
Housing For Women	0	0%	0	0%	0	0%	0	0%	0	0%
Hyde Housing Association Limited	0	0%	21	34%	6	10%	12	20%	22	36%
Incommunities Limited	11	100%	0	0%	0	0%	0	0%	0	0%
Irwell Valley Housing Association Limited	4	67%	1	17%	0	0%	0	0%	1	17%
Islington and Shoreditch Housing Association Limited	0	0%	7	50%	0	0%	0	0%	7	50%
Jigsaw Homes Group Limited	0	0%	2	18%	1	9%	6	55%	2	18%
Karbon Homes Limited	0	0%	14	88%	1	6%	0	0%	1	6%
Karibu Community Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Kingston upon Hull City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Kirklees Metropolitan Borough Council	0	0%	14	93%	1	7%	0	0%	0	0%
Lambeth and Southwark Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Leeds City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Legal & General Affordable Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Leicester City Council	0	0%	0	0%	0	0%	0	0%	0	0%
LiveWest Homes Limited	5	83%	0	0%	0	0%	0	0%	1	17%
Livv Housing Group	0	0%	0	0%	0	0%	0	0%	0	0%
London & Quadrant Housing Trust	35	37%	3	3%	17	18%	16	17%	24	25%
London Borough of Barking and Dagenham	2	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Barnet	0	0%	7	100%	0	0%	0	0%	0	0%
London Borough of Brent	1	25%	3	75%	0	0%	0	0%	0	0%
London Borough of Camden Council	0	0%	5	42%	0	0%	0	0%	7	58%
London Borough of Croydon	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Ealing	16	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Enfield	0	0%	0	0%	0	0%	0	0%	1	100%
London Borough of Hackney	4	40%	0	0%	2	20%	0	0%	4	40%
London Borough of Hammersmith and Fulham	0	0%	4	57%	3	43%	0	0%	0	0%
London Borough of Havering Council	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Hillingdon	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Hounslow	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Islington	0	0%	0	0%	0	0%	0	0%	2	100%
London Borough of Lambeth	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Lewisham	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Newham	44	77%	0	0%	5	9%	0	0%	8	14%
London Borough of Redbridge	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Sutton	1	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Tower Hamlets	4	13%	21	68%	2	6%	0	0%	4	13%
London Borough of Waltham Forest	17	65%	6	23%	0	0%	0	0%	3	12%
London Borough of Wandsworth	0	0%	2	100%	0	0%	0	0%	0	0%
Look Ahead Care and Support Limited	0	0%	0	0%	1	50%	0	0%	1	50%
Luton Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Magenta Living	0	0%	0	0%	3	100%	0	0%	0	0%
Manchester City Council	2	22%	5	56%	0	0%	0	0%	2	22%
Midland Heart Limited	0	0%	0	0%	0	0%	0	0%	1	100%
Moat Homes Limited	0	0%	2	40%	2	40%	0	0%	1	20%
New Foundations Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Newark and Sherwood District Council	0	0%	0	0%	0	0%	0	0%	0	0%
Newcastle City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Newlon Housing Trust	0	0%	42	84%	6	12%	2	4%	0	0%
North London Muslim Housing Association Limited	0	0%	9	100%	0	0%	0	0%	0	0%
Norwich City Council	0	0%	0	0%	2	100%	0	0%	0	0%
Notting Hill Genesis	0	0%	0	0%	0	0%	0	0%	35	100%
Nottingham City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Nottingham Community Housing Association Limited	0	0%	0	0%	0	0%	0	0%	1	100%
Octavia Housing	34	94%	0	0%	0	0%	0	0%	2	6%
One Manchester Limited	0	0%	0	0%	0	0%	0	0%	0	0%
One Vision Housing Limited	0	0%	0	0%	0	0%	0	0%	2	100%
Onward Group Limited	0	0%	2	13%	5	33%	0	0%	8	53%
Orbit Group Limited	0	0%	0	0%	20	87%	0	0%	3	13%
Origin Housing Limited	4	25%	10	63%	2	13%	0	0%	0	0%
Oxford City Council	6	100%	0	0%	0	0%	0	0%	0	0%
P3 Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Paradigm Housing Group Limited	0	0%	0	0%	0	0%	0	0%	5	100%
Paragon Asra Housing Limited	6	29%	10	48%	3	14%	0	0%	2	10%
Peabody Trust	73	38%	55	28%	38	20%	19	10%	9	5%
Phoenix Community Housing Association (Bellingham and Downham) Limited	0	0%	2	20%	2	20%	0	0%	6	60%
Pinnacle Spaces Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Places for People Group Limited	0	0%	3	18%	1	6%	0	0%	13	76%
Platform Housing Group Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Plus Dane Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Plymouth Community Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Poplar Housing And Regeneration Community Association Limited	0	0%	6	19%	2	6%	0	0%	23	74%
Portsmouth City Council	12	44%	4	15%	0	0%	0	0%	11	41%
Providence Row Housing Association	0	0%	0	0%	0	0%	0	0%	1	100%
Raven Housing Trust Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Reading Borough Council	0	0%	7	100%	0	0%	0	0%	0	0%
Regenda Limited	0	0%	1	25%	2	50%	0	0%	1	25%
Richmond Housing Partnership Limited	0	0%	5	28%	11	61%	2	11%	0	0%
Rochdale Boroughwide Housing Limited	0	0%	0	0%	7	100%	0	0%	0	0%
Rooftop Housing Group Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Royal Borough of Greenwich	1	100%	0	0%	0	0%	0	0%	0	0%
Royal Borough of Kensington and Chelsea	1	25%	0	0%	1	25%	2	50%	0	0%
Royal Borough of Kingston Upon Thames	0	0%	0	0%	0	0%	0	0%	0	0%
Salix Homes Limited	0	0%	0	0%	0	0%	0	0%	8	100%
Salvation Army Housing Association	0	0%	0	0%	0	0%	0	0%	0	0%
Sanctuary Housing Association	1	2%	35	60%	5	9%	0	0%	17	29%
Sandwell Metropolitan Borough Council	0	0%	1	100%	0	0%	0	0%	0	0%
Sheffield City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Shepherds Bush Housing Association Limited	1	11%	0	0%	1	11%	0	0%	7	78%
Soho Housing Association Limited	0	0%	0	0%	0	0%	0	0%	1	100%
Solihull Metropolitan Borough Council	0	0%	11	69%	0	0%	5	31%	0	0%
Southampton City Council	0	0%	14	15%	81	85%	0	0%	0	0%
Southend on Sea City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Southern Housing	6	5%	91	79%	10	9%	3	3%	5	4%
Southwark Council	0	0%	0	0%	0	0%	0	0%	0	0%
Southway Housing Trust (Manchester) Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Sovereign Housing Association Limited	17	19%	25	27%	18	20%	2	2%	29	32%
Spitalfields Housing Association Limited	0	0%	0	0%	0	0%	0	0%	4	100%
St Mungo Community Housing Association	0	0%	0	0%	1	100%	0	0%	0	0%
Stevenage Borough Council	5	100%	0	0%	0	0%	0	0%	0	0%
Stockport Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Stoke on Trent City Council	3	38%	3	38%	0	0%	2	25%	0	0%
Stonewater Limited	0	0%	3	38%	1	13%	0	0%	4	50%
Swindon Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Tamworth Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Teign Housing	0	0%	1	100%	0	0%	0	0%	0	0%
Thames Valley Housing Association Limited	80	73%	0	0%	17	15%	0	0%	13	12%
Thanet District Council	0	0%	5	100%	0	0%	0	0%	0	0%
The ExtraCare Charitable Trust	0	0%	0	0%	0	0%	0	0%	0	0%
The Guinness Partnership Limited	4	27%	6	40%	3	20%	0	0%	2	13%
The Housing Plus Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
The Industrial Dwellings Society (1885) Limited	0	0%	0	0%	0	0%	0	0%	0	0%
The Riverside Group Limited	0	0%	69	76%	18	20%	4	4%	0	0%
Thirteen Housing Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Thurrock Council	0	0%	0	0%	0	0%	0	0%	0	0%
Together Housing Group Limited	0	0%	0	0%	0	0%	0	0%	12	100%
Torus62 Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Tower Hamlets Community Housing	0	0%	3	19%	12	75%	0	0%	1	6%
Trident Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Vivid Housing Limited	1	11%	0	0%	1	11%	0	0%	7	78%
Wakefield And District Housing Limited	0	0%	4	100%	0	0%	0	0%	0	0%
Walsall Housing Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Wandle Housing Association Limited	0	0%	11	92%	1	8%	0	0%	0	0%
Warwick District Council	0	0%	5	100%	0	0%	0	0%	0	0%
Watford Community Housing Trust	0	0%	0	0%	0	0%	0	0%	0	0%
Watmos Community Homes	0	0%	0	0%	0	0%	0	0%	0	0%
West Hampstead Housing Co-operative Limited	0	0%	0	0%	0	0%	0	0%	0	0%
West Northamptonshire Council	0	0%	0	0%	8	100%	0	0%	0	0%
Wigan Council	0	0%	0	0%	0	0%	0	0%	0	0%
Woking Borough Council	0	0%	0	0%	14	100%	0	0%	0	0%
Wolverhampton City Council	0	0%	9	100%	0	0%	0	0%	0	0%
Women's Pioneer Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Worthing Homes Limited	0	0%	1	50%	0	0%	0	0%	1	50%
Wythenshawe Community Housing Group Limited	0	0%	0	0%	0	0%	0	0%	7	100%
YMCA St Paul's Group	0	0%	0	0%	0	0%	0	0%	0	0%
Yorkshire Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Your Housing Group Limited	7	54%	5	38%	1	8%	0	0%	0	0%
Zebra Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Other RPs	9	28%	4	13%	9	28%	2	6%	8	25%

## Social_4b
Provider by provider breakdown of buildings, by remediation status, England, 30 June 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings for each social housing provieder that has submitted a building level return, as of 30 June 2024
Some cells refer to notes which can be found in the 'Notes' worksheet.
Providers with more than five buildings over 11 metres [Note 50] [Note 51]	Remediation Status
	Number and proportion of buildings identified as having EWS life-critical fire-safety defects [Note 35] [Note 63] at the time of their most recent assessment, where remediation...
	…plans are unclear from survey		…works are planned		…has started		…has completed		... has completed and is awaiting sign-off by building control
	Number	Percentage	Number	Percentage‎	Number	Percentage	Number	Percentage‎	Number	Percentage‎
Total (All Providers)	544	29%	674	36%	562	30%	50	3%	58	3%
A2Dominion Housing Group Limited	0	0%	17	46%	7	19%	10	27%	3	8%
Abri Group Limited	0	0%	2	100%	0	0%	0	0%	0	0%
Accent Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Acis Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Agudas Israel Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Anchor Hanover Group	0	0%	4	40%	6	60%	0	0%	0	0%
Ashford Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Ashton Pioneer Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Aster Group Limited	0	0%	4	100%	0	0%	0	0%	0	0%
B3 Living Limited	5	100%	0	0%	0	0%	0	0%	0	0%
Beyond Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Birkenhead Forum Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Birmingham City Council	0	0%	7	32%	15	68%	0	0%	0	0%
Bolton at Home Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Bournemouth, Christchurch and Poole Council	0	0%	0	0%	0	0%	0	0%	0	0%
bpha Limited	2	100%	0	0%	0	0%	0	0%	0	0%
Brighter Places	0	0%	0	0%	0	0%	0	0%	0	0%
Brighton and Hove City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Bristol City Council	85	79%	13	12%	10	9%	0	0%	0	0%
Broadland Housing Association Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Bromford Housing Group Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Cambridge City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Central Bedfordshire Council	0	0%	1	100%	0	0%	0	0%	0	0%
Christian Action (Enfield) Housing Association Limited	3	100%	0	0%	0	0%	0	0%	0	0%
Citizen Housing Group Limited	0	0%	2	100%	0	0%	0	0%	0	0%
City of Doncaster Council	0	0%	0	0%	5	100%	0	0%	0	0%
City of London Corporation	0	0%	0	0%	0	0%	0	0%	0	0%
City of Westminster Council	1	100%	0	0%	0	0%	0	0%	0	0%
Clarion Housing Group Limited	0	0%	8	7%	99	87%	7	6%	0	0%
Curo Group (Albion) Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Dacorum Borough Council	2	50%	0	0%	2	50%	0	0%	0	0%
Dudley Metropolitan Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
East End Homes Limited	0	0%	5	83%	0	0%	0	0%	1	17%
Eastlight Community Homes Limited	0	0%	0	0%	0	0%	6	100%	0	0%
Ekaya Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Epping Forest District Council	0	0%	0	0%	0	0%	0	0%	0	0%
Estuary Housing Association Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Exeter City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Fairhazel Co-operative Limited	0	0%	0	0%	0	0%	0	0%	0	0%
First Choice Homes Oldham Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Flagship Housing Group Limited	0	0%	1	100%	0	0%	0	0%	0	0%
Folkestone and Hythe District Council	0	0%	0	0%	0	0%	0	0%	0	0%
ForHousing Limited	0	0%	5	100%	0	0%	0	0%	0	0%
Gateshead Metropolitan Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Gateway Housing Association Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Gentoo Group Limited	4	80%	0	0%	0	0%	0	0%	1	20%
Golding Homes Limited	1	33%	0	0%	2	67%	0	0%	0	0%
Gosport Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Gravesham Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Great Places Housing Group Limited	0	0%	4	100%	0	0%	0	0%	0	0%
GreenSquareAccord Limited	0	0%	0	0%	15	100%	0	0%	0	0%
Haringey London Borough Council	0	0%	8	17%	38	83%	0	0%	0	0%
Harlow District Council	0	0%	0	0%	0	0%	1	50%	1	50%
Hastoe Housing Association Limited	0	0%	2	67%	1	33%	0	0%	0	0%
Heart of Medway Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Hexagon Housing Association Limited	17	85%	1	5%	1	5%	0	0%	1	5%
HFL Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Hightown Housing Association Limited	1	50%	0	0%	1	50%	0	0%	0	0%
Home Group Limited	0	0%	11	46%	13	54%	0	0%	0	0%
Housing 21	0	0%	0	0%	0	0%	0	0%	0	0%
Housing For Women	0	0%	0	0%	0	0%	0	0%	0	0%
Hyde Housing Association Limited	0	0%	21	54%	6	15%	5	13%	7	18%
Incommunities Limited	11	100%	0	0%	0	0%	0	0%	0	0%
Irwell Valley Housing Association Limited	4	80%	1	20%	0	0%	0	0%	0	0%
Islington and Shoreditch Housing Association Limited	0	0%	7	100%	0	0%	0	0%	0	0%
Jigsaw Homes Group Limited	0	0%	2	22%	1	11%	0	0%	6	67%
Karbon Homes Limited	0	0%	14	93%	1	7%	0	0%	0	0%
Karibu Community Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Kingston upon Hull City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Kirklees Metropolitan Borough Council	0	0%	14	93%	1	7%	0	0%	0	0%
Lambeth and Southwark Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Leeds City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Legal & General Affordable Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Leicester City Council	0	0%	0	0%	0	0%	0	0%	0	0%
LiveWest Homes Limited	5	100%	0	0%	0	0%	0	0%	0	0%
Livv Housing Group	0	0%	0	0%	0	0%	0	0%	0	0%
London & Quadrant Housing Trust	35	49%	3	4%	17	24%	5	7%	11	15%
London Borough of Barking and Dagenham	2	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Barnet	0	0%	7	100%	0	0%	0	0%	0	0%
London Borough of Brent	1	25%	3	75%	0	0%	0	0%	0	0%
London Borough of Camden Council	0	0%	5	100%	0	0%	0	0%	0	0%
London Borough of Croydon	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Ealing	16	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Enfield	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Hackney	4	67%	0	0%	2	33%	0	0%	0	0%
London Borough of Hammersmith and Fulham	0	0%	4	57%	3	43%	0	0%	0	0%
London Borough of Havering Council	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Hillingdon	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Hounslow	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Islington	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Lambeth	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Lewisham	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Newham	44	90%	0	0%	5	10%	0	0%	0	0%
London Borough of Redbridge	0	0%	0	0%	0	0%	0	0%	0	0%
London Borough of Sutton	1	100%	0	0%	0	0%	0	0%	0	0%
London Borough of Tower Hamlets	4	15%	21	78%	2	7%	0	0%	0	0%
London Borough of Waltham Forest	17	74%	6	26%	0	0%	0	0%	0	0%
London Borough of Wandsworth	0	0%	2	100%	0	0%	0	0%	0	0%
Look Ahead Care and Support Limited	0	0%	0	0%	1	100%	0	0%	0	0%
Luton Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Magenta Living	0	0%	0	0%	3	100%	0	0%	0	0%
Manchester City Council	2	29%	5	71%	0	0%	0	0%	0	0%
Midland Heart Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Moat Homes Limited	0	0%	2	50%	2	50%	0	0%	0	0%
New Foundations Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Newark and Sherwood District Council	0	0%	0	0%	0	0%	0	0%	0	0%
Newcastle City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Newlon Housing Trust	0	0%	42	84%	6	12%	2	4%	0	0%
North London Muslim Housing Association Limited	0	0%	9	100%	0	0%	0	0%	0	0%
Norwich City Council	0	0%	0	0%	2	100%	0	0%	0	0%
Notting Hill Genesis	0	0%	0	0%	0	0%	0	0%	0	0%
Nottingham City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Nottingham Community Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Octavia Housing	34	100%	0	0%	0	0%	0	0%	0	0%
One Manchester Limited	0	0%	0	0%	0	0%	0	0%	0	0%
One Vision Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Onward Group Limited	0	0%	2	29%	5	71%	0	0%	0	0%
Orbit Group Limited	0	0%	0	0%	20	100%	0	0%	0	0%
Origin Housing Limited	4	25%	10	63%	2	13%	0	0%	0	0%
Oxford City Council	6	100%	0	0%	0	0%	0	0%	0	0%
P3 Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Paradigm Housing Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Paragon Asra Housing Limited	6	32%	10	53%	3	16%	0	0%	0	0%
Peabody Trust	73	39%	55	30%	38	21%	8	4%	11	6%
Phoenix Community Housing Association (Bellingham and Downham) Limited	0	0%	2	50%	2	50%	0	0%	0	0%
Pinnacle Spaces Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Places for People Group Limited	0	0%	3	75%	1	25%	0	0%	0	0%
Platform Housing Group Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Plus Dane Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Plymouth Community Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Poplar Housing And Regeneration Community Association Limited	0	0%	6	75%	2	25%	0	0%	0	0%
Portsmouth City Council	12	75%	4	25%	0	0%	0	0%	0	0%
Providence Row Housing Association	0	0%	0	0%	0	0%	0	0%	0	0%
Raven Housing Trust Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Reading Borough Council	0	0%	7	100%	0	0%	0	0%	0	0%
Regenda Limited	0	0%	1	33%	2	67%	0	0%	0	0%
Richmond Housing Partnership Limited	0	0%	5	28%	11	61%	0	0%	2	11%
Rochdale Boroughwide Housing Limited	0	0%	0	0%	7	100%	0	0%	0	0%
Rooftop Housing Group Limited	1	100%	0	0%	0	0%	0	0%	0	0%
Royal Borough of Greenwich	1	100%	0	0%	0	0%	0	0%	0	0%
Royal Borough of Kensington and Chelsea	1	25%	0	0%	1	25%	0	0%	2	50%
Royal Borough of Kingston Upon Thames	0	0%	0	0%	0	0%	0	0%	0	0%
Salix Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Salvation Army Housing Association	0	0%	0	0%	0	0%	0	0%	0	0%
Sanctuary Housing Association	1	2%	35	85%	5	12%	0	0%	0	0%
Sandwell Metropolitan Borough Council	0	0%	1	100%	0	0%	0	0%	0	0%
Sheffield City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Shepherds Bush Housing Association Limited	1	50%	0	0%	1	50%	0	0%	0	0%
Soho Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Solihull Metropolitan Borough Council	0	0%	11	69%	0	0%	0	0%	5	31%
Southampton City Council	0	0%	14	15%	81	85%	0	0%	0	0%
Southend on Sea City Council	0	0%	0	0%	0	0%	0	0%	0	0%
Southern Housing	6	5%	91	83%	10	9%	0	0%	3	3%
Southwark Council	0	0%	0	0%	0	0%	0	0%	0	0%
Southway Housing Trust (Manchester) Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Sovereign Housing Association Limited	17	27%	25	40%	18	29%	0	0%	2	3%
Spitalfields Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
St Mungo Community Housing Association	0	0%	0	0%	1	100%	0	0%	0	0%
Stevenage Borough Council	5	100%	0	0%	0	0%	0	0%	0	0%
Stockport Homes Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Stoke on Trent City Council	3	38%	3	38%	0	0%	0	0%	2	25%
Stonewater Limited	0	0%	3	75%	1	25%	0	0%	0	0%
Swindon Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Tamworth Borough Council	0	0%	0	0%	0	0%	0	0%	0	0%
Teign Housing	0	0%	1	100%	0	0%	0	0%	0	0%
Thames Valley Housing Association Limited	80	82%	0	0%	17	18%	0	0%	0	0%
Thanet District Council	0	0%	5	100%	0	0%	0	0%	0	0%
The ExtraCare Charitable Trust	0	0%	0	0%	0	0%	0	0%	0	0%
The Guinness Partnership Limited	4	31%	6	46%	3	23%	0	0%	0	0%
The Housing Plus Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
The Industrial Dwellings Society (1885) Limited	0	0%	0	0%	0	0%	0	0%	0	0%
The Riverside Group Limited	0	0%	69	76%	18	20%	4	4%	0	0%
Thirteen Housing Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Thurrock Council	0	0%	0	0%	0	0%	0	0%	0	0%
Together Housing Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Torus62 Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Tower Hamlets Community Housing	0	0%	3	20%	12	80%	0	0%	0	0%
Trident Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Vivid Housing Limited	1	50%	0	0%	1	50%	0	0%	0	0%
Wakefield And District Housing Limited	0	0%	4	100%	0	0%	0	0%	0	0%
Walsall Housing Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Wandle Housing Association Limited	0	0%	11	92%	1	8%	0	0%	0	0%
Warwick District Council	0	0%	5	100%	0	0%	0	0%	0	0%
Watford Community Housing Trust	0	0%	0	0%	0	0%	0	0%	0	0%
Watmos Community Homes	0	0%	0	0%	0	0%	0	0%	0	0%
West Hampstead Housing Co-operative Limited	0	0%	0	0%	0	0%	0	0%	0	0%
West Northamptonshire Council	0	0%	0	0%	8	100%	0	0%	0	0%
Wigan Council	0	0%	0	0%	0	0%	0	0%	0	0%
Woking Borough Council	0	0%	0	0%	14	100%	0	0%	0	0%
Wolverhampton City Council	0	0%	9	100%	0	0%	0	0%	0	0%
Women's Pioneer Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Worthing Homes Limited	0	0%	1	100%	0	0%	0	0%	0	0%
Wythenshawe Community Housing Group Limited	0	0%	0	0%	0	0%	0	0%	0	0%
YMCA St Paul's Group	0	0%	0	0%	0	0%	0	0%	0	0%
Yorkshire Housing Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Your Housing Group Limited	7	54%	5	38%	1	8%	0	0%	0	0%
Zebra Housing Association Limited	0	0%	0	0%	0	0%	0	0%	0	0%
Other RPs	9	38%	4	17%	9	38%	2	8%	0	0%

## Social_5
Remediation status of buildings with cladding defects monitored under the social housing surveys, time series, England, 30 June 2024
Back to Contents
This worksheet contains one table. All figures are for number of buildings or percentage of buildings.
Some cells refer to notes which can be found in the 'Notes' worksheet.

Remediation Category [Note 34] [Note 35] [Note 70]	Aug-23	Aug-232	Dec-23	Dec-232	Mar-24 [Note 68]	Mar-24 [Note 68]4	Jun-24	Jun-245
	Number	Percentage (%)	Number	Percentage (%)	Number	Percentage (%)	Number	Percentage (%)
Remediation complete [Note 37] [Note 54]	106	7%	204	10%	661	27%	703	28%
Remediation started	394	25%	525	27%	544	23%	565	23%
Remediation works planned	591	37%	658	34%	717	30%	699	28%
Remediation plans unclear from survey	510	32%	559	29%	488	20%	540	22%
Work is not required	7	0%	6	0%	0	0%	0	0%
Total buildings	1608	100%	1,952	100%	2,410	100%	2,507	100%

## Enforcement_1
Enforcement action taken by local authorities against 11m+ buildings under the Housing Act (2004) by remediation programme status, England, 23 August 2024
Back to Contents
This worksheet contains one table. All figures are for the number of enforcement actions by local authority and by the type of remediation programme each building is in [note_19].
Local Authority [note_2]	BSF or CSS only (non-ACM cladding only) / Number	ACM cladding only / Number	BSF or CSS (non-ACM) and ACM cladding / Number	Not in any remediation fund (non-ACM cladding only) / Number	Total / Number
Barking and Dagenham	1	0	0	2	3
Barnet	1	3	1	3	8
Birmingham	3	1	0	2	6
Bournemouth, Christchurch and Poole	2	2	0	1	5
Bradford	0	1	0	0	1
Brent	0	2	0	0	2
Brighton and Hove	0	0	0	0	0
Bristol, City of	6	1	0	3	10
Bromley	0	0	0	0	0
Calderdale	0	0	0	0	0
Camden	16	1	0	21	38
City of London	1	0	0	6	7
Croydon	3	0	1	1	5
Dacorum	0	0	0	0	0
Ealing	2	1	1	0	4
Gateshead	0	0	0	0	0
Greenwich	4	0	0	1	5
Hackney	4	3	2	4	13
Hammersmith and Fulham	9	1	2	31	43
Haringey	0	0	0	0	0
Harrow	0	0	0	0	0
Hillingdon	3	1	0	3	7
Hounslow	0	0	0	1	1
Ipswich	0	0	0	0	0
Islington	2	0	0	0	2
Kensington and Chelsea	0	0	0	0	0
Kingston upon Thames	0	0	0	0	0
Kirklees	0	0	0	0	0
Lambeth	2	2	0	0	4
Leeds	0	0	0	0	0
Leicester	0	0	0	0	0
Lewisham	0	0	0	0	0
Liverpool	3	2	4	1	10
Maidstone	0	0	0	0	0
Manchester	0	0	0	0	0
Medway	0	1	0	0	1
Merton	0	0	0	0	0
Milton Keynes	0	0	0	0	0
Newcastle upon Tyne	6	0	0	8	14
Newham	12	1	1	12	26
North Somerset	0	0	0	0	0
Norwich	0	0	0	0	0
Nottingham	2	1	0	1	4
Plymouth	1	0	0	0	1
Portsmouth	0	1	0	2	3
Reading	0	0	0	0	0
Redbridge	2	0	0	0	2
Salford	1	0	0	0	1
Sheffield	1	0	0	0	1
Slough	0	0	0	0	0
Southampton	3	0	0	0	3
Southwark	28	3	3	22	56
Sunderland	0	0	0	0	0
Sutton	0	0	1	0	1
Thanet	0	0	0	0	0
Tower Hamlets	18	0	5	12	35
Trafford	0	0	0	0	0
Waltham Forest	1	0	0	0	1
Wandsworth	1	2	1	0	4
Westminster	32	4	6	26	68
Windsor and Maidenhead	0	0	0	0	0
Others	15	0	2	18	35
Total	185	34	30	181	430

## Enforcement_2
Category rating of buildings inspected by local authorities, England, 23 August 2024
Back to Contents
This worksheet contains one table. All figures are for the number of inspections by type of rating outcome.
Local Authority [note_2]	Inspections with the building rated Category 1 [note_20] [note_69] / Number	Inspections with the building rated Category 2 [note_20] [note_69] / Number	Rating outcome to be confirmed / Number	Total / Number
Barking and Dagenham	1	2	0	3
Barnet	6	2	0	8
Birmingham	0	6	0	6
Bournemouth, Christchurch and Poole	5	0	0	5
Bradford	0	1	0	1
Brent	1	1	0	2
Brighton and Hove	0	0	0	0
Bristol, City of	0	2	8	10
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	0	37	1	38
City of London	4	2	1	7
Croydon	1	4	0	5
Dacorum	0	0	0	0
Ealing	1	3	0	4
Gateshead	0	0	0	0
Greenwich	2	1	2	5
Hackney	7	3	3	13
Hammersmith and Fulham	1	38	4	43
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	2	5	0	7
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	1	1	2
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	2	2	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	4	5	1	10
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	0	13	1	14
Newham	10	15	1	26
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	1	3	0	4
Plymouth	1	0	0	1
Portsmouth	0	1	2	3
Reading	0	0	0	0
Redbridge	1	1	0	2
Salford	0	1	0	1
Sheffield	0	0	1	1
Slough	0	0	0	0
Southampton	1	0	2	3
Southwark	26	26	4	56
Sunderland	0	0	0	0
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	7	19	9	35
Trafford	0	0	0	0
Waltham Forest	0	1	0	1
Wandsworth	1	3	0	4
Westminster	6	62	0	68
Windsor and Maidenhead	0	0	0	0
Others	12	20	3	35
Total	106	280	44	430

## Enforcement_3
Statutory notices served by local authorities under the Housing Act (2004), England, 23 August 2024
Back to Contents
This worksheet contains one table. All figures are for number of statutory notices served, broken down by type of notice, for each Local Authority.
Local Authority [note_2]	Improvement notices / Number	Hazard awareness notices / Number	Prohibition orders / Number	Total / Number
Barking and Dagenham	1	0	0	1
Barnet	8	0	0	8
Birmingham	4	0	0	4
Bournemouth, Christchurch and Poole	3	0	0	3
Bradford	1	0	0	1
Brent	0	0	0	0
Brighton and Hove	0	0	0	0
Bristol, City of	0	0	0	0
Bromley	0	0	0	0
Calderdale	0	0	0	0
Camden	11	3	0	14
City of London	2	0	0	2
Croydon	0	0	0	0
Dacorum	0	0	0	0
Ealing	2	0	0	2
Gateshead	0	0	0	0
Greenwich	2	0	0	2
Hackney	9	0	0	9
Hammersmith and Fulham	0	2	0	2
Haringey	0	0	0	0
Harrow	0	0	0	0
Hillingdon	4	1	0	5
Hounslow	1	0	0	1
Ipswich	0	0	0	0
Islington	0	0	0	0
Kensington and Chelsea	0	0	0	0
Kingston upon Thames	0	0	0	0
Kirklees	0	0	0	0
Lambeth	4	0	0	4
Leeds	0	0	0	0
Leicester	0	0	0	0
Lewisham	0	0	0	0
Liverpool	6	0	0	6
Maidstone	0	0	0	0
Manchester	0	0	0	0
Medway	1	0	0	1
Merton	0	0	0	0
Milton Keynes	0	0	0	0
Newcastle upon Tyne	2	4	0	6
Newham	19	0	0	19
North Somerset	0	0	0	0
Norwich	0	0	0	0
Nottingham	2	0	0	2
Plymouth	1	0	0	1
Portsmouth	1	0	0	1
Reading	0	0	0	0
Redbridge	0	0	0	0
Salford	0	0	0	0
Sheffield	0	0	0	0
Slough	0	0	0	0
Southampton	1	0	0	1
Southwark	20	1	0	21
Sunderland	0	0	0	0
Sutton	1	0	0	1
Thanet	0	0	0	0
Tower Hamlets	13	9	0	22
Trafford	0	0	0	0
Waltham Forest	1	0	0	1
Wandsworth	1	0	0	1
Westminster	1	16	1	18
Windsor and Maidenhead	0	0	0	0
Others	18	0	0	18
Total	140	36	1	177

## Enforcement_4
Number of building inspections by local authorities supported by the Joint Inspection Team, England, 23 August 2024
Back to Contents
This worksheet contains one table. All figures are for the number of inspections supported by the Joint Inspection Team.
Local Authority [note_2]	Inspections supported by the Joint Inspection Team [note_21] / Number
Barking and Dagenham	1
Barnet	4
Birmingham	5
Bournemouth, Christchurch and Poole	2
Bradford	0
Brent	2
Brighton and Hove	0
Bristol, City of	0
Bromley	0
Calderdale	0
Camden	6
City of London	0
Croydon	5
Dacorum	0
Ealing	4
Gateshead	0
Greenwich	5
Hackney	10
Hammersmith and Fulham	2
Haringey	0
Harrow	0
Hillingdon	2
Hounslow	1
Ipswich	0
Islington	2
Kensington and Chelsea	0
Kingston upon Thames	0
Kirklees	0
Lambeth	2
Leeds	0
Leicester	0
Lewisham	0
Liverpool	8
Maidstone	0
Manchester	0
Medway	0
Merton	0
Milton Keynes	0
Newcastle upon Tyne	1
Newham	23
North Somerset	0
Norwich	0
Nottingham	2
Plymouth	1
Portsmouth	2
Reading	0
Redbridge	2
Salford	1
Sheffield	1
Slough	0
Southampton	3
Southwark	3
Sunderland	0
Sutton	1
Thanet	0
Tower Hamlets	15
Trafford	0
Waltham Forest	1
Wandsworth	4
Westminster	2
Windsor and Maidenhead	0
Others	8
Total	131

## JIT_1
Number of Joint Inspection Team training sessions attended by local authorities, England, April 2021 - 31 August 2024
Back to Contents
This worksheet contains one table. All figures are for the number of Joint Inspection Team training sessions attended by local authority officers.
Local Authority [note_22]	Intro to Fire Safety (Level 1) Number	Intermediate Fire Safety: Theoretical HHSRS assessments (Level 2 Part 1) Number	Intermediate Fire Safety: Practical HHSRS assessments (Level 2 Part 2) Number
Barking and Dagenham	0	1	0
Barnet	4	3	3
Birmingham	10	6	7
Bournemouth, Christchurch and Poole	10	4	1
Bradford	24	4	1
Brent	1	4	0
Brighton and Hove	0	0	0
Bristol, City of	10	4	2
Bromley	3	0	0
Calderdale	3	1	0
Camden	16	12	5
City of London	8	4	1
Croydon	26	4	4
Dacorum	4	2	1
Ealing	10	4	2
Gateshead	6	3	0
Greenwich	2	5	5
Hackney	18	9	4
Hammersmith and Fulham	20	7	9
Haringey	4	2	0
Harrow	1	2	0
Hillingdon	3	2	0
Hounslow	4	4	0
Ipswich	0	0	0
Islington	11	8	1
Kensington and Chelsea	0	0	1
Kingston upon Thames	3	0	0
Kirklees	2	1	0
Lambeth	16	8	7
Leeds	6	1	1
Leicester	0	0	0
Lewisham	5	2	1
Liverpool	32	12	3
Maidstone	0	0	0
Manchester	8	4	1
Merton	6	4	0
Medway	12	5	0
Milton Keynes	6	4	3
Newcastle upon Tyne	6	3	2
Newham	10	7	0
North Somerset	8	3	2
Norwich	11	7	0
Nottingham	34	8	6
Plymouth	3	2	1
Portsmouth	2	5	0
Richmond and Wandsworth	8	6	4
Reading	15	4	1
Redbridge	4	2	1
Salford	11	7	0
Sheffield	0	0	0
Slough	5	7	0
Southampton	1	0	0
Southwark	7	1	0
Sunderland	3	3	2
Sutton	2	0	0
Thanet	2	2	0
Tower Hamlets	9	12	1
Trafford	7	3	0
Waltham Forest	6	4	3
Westminster	17	10	1
Windsor and Maidenhead	8	5	0
Others	414	143	58
Total	887	380	145