## Sheet1
		Nuclear Restoration Services Limited (Dounreay) - Procurement Plan October 2024
For further information contact Dounreay at commercial.services@dounreay.com

☆ Record Ref	Business Unit	Sourcing to Contract: Record Name	☆ Published Description	Procurement Route	Contract Type	Commercial Strategy	Desired Contract Start Date	Desired Contract End Date	Value Range	Previous Contract Ref	Ops Project Manager	Contract Owner
C1072	Balance of Site	Shaft and Silo Process Cell and Waste Transfer System	Shaft and Silo Process Cell and Waste Transfer System	Framework - Further Competition	Services		01/05/2025	29/09/2030	≥ £10m to <£25m		Iain Lyall	Kirstin Polson
C1073	FCA	Thorium Nitrate Drums Final Letter of Compliance	Thorium Nitrate Drums Final Letter of Compliance	Framework - Further Competition	Services		01/08/2025	01/05/2026	< £100k		Robert McKiddie	Sarah McCaughey
C1096	Balance of Site	Non Active Drain Effluent Treatment Plant Works	Non Active Drain Effluent Treatment Plant Works	Below Threshold - Competitive Tender	Works		28/02/2025	24/06/2025	≥ £1m to <£5m		Adreain Gill	Dawn Sewell
C1108	FCA	Thorium Nitrate Manufacture, Integrated Works Testing, Installation	Thorium Nitrate Manufacture, Integrated Works Testing, Installation and Commissioning	Framework - Further Competition	Works		01/08/2025	31/05/2026	≥ £500k to <£1m		Ewen Boyd	Sarah McCaughey
C1113	Site Services	Voidage and Container Assessments	Voidage and Container Assessments	Framework - Further Competition	Services	Not known	04/12/2024	30/09/2025	≥ £100k to <£500k		Stephen Mackie	Janet Brooke
C1114	Site Services	Low Level Waste Metals Diversion Projects	Low Level Waste Metals Diversion Projects	Framework - Further Competition	Services	Not known	31/01/2025	31/07/2025	≥ £100k to <£500k		Kerryn Sievewright	Hannah Budge
C1120	Site Services	Supply of Half Height ISO Low Level Waste Containers Framework Agreement	Framework Agreement for the Supply of Half Height ISO Low Level Waste Containers	Framework Agreement – Set up of a new Framework	Supplies	Re-procurement (same scope)	01/07/2025	30/06/2029	≥ £10m to <£25m	CFA/12/0048 - CFA/12/0049	Alistair Ross	Janet Brooke
C1122	Balance of Site	D3000 Switchboard	D3000 Switchboard	Open Procedure	Supplies		18/11/2024	27/06/2025	≥ £100k to <£500k		Morris Macleod	Lee Parnell
C11262	Capability	U4BW Software as a Service	Unit4 Business World (U4BW) Software as a Service (SaaS).	Framework - Direct Award	Services	Re-procurement (same scope)	01/07/2025	30/06/2028	≥ £500k to <£1m	3300026361	Amanda Petrie	Lynsey Will
C1128	FCA	D1217 - Cell Floor Block Lifting Bags	D1217 - Cell Floor Block Lifting Bags	Below Threshold - Competitive Tender	Supplies		03/02/2025	28/03/2025	< £100k		Leslie D M Mackay	Alex Wood
C1129	FCA	D1217 Cell Floor Equipment Manufacture, Concrete and Steel and Hire of Facility	D1217 Cell Floor Equipment Manufacture, Concrete and Steel and Hire of Facility for Testing	Below Threshold - Competitive Tender	Works	Not known	14/02/2025	30/03/2025	≥ £100k to <£500k		Leslie D M Mackay	Alex Wood
C1136	Reactors	Prototype Fast Reactor Delivery and Design of the Cold Trap Loop	Prototype Fast Reactor Delivery and Design Phase for the Prototype Fast Reactor Secondary Cold Trap Loop 1 and 2	Framework - Further Competition	Services		02/10/2026	30/06/2027	< £100k		James Campbell	Robert McDonald
C1142	Balance of Site	Manufacture and Design Ammonium Diuranate Floc Transport Stillage Lifting Beam	Manufacture and Design of Ammonium Diuranate Floc Transport Stillage Lifting Beam	Below Threshold - Competitive Tender	Services	Not known	24/06/2025	04/12/2026	≥ £100k to <£500k		Michael Gray	Sonja Sinclair
C1149	Site Services	Site Closure and Environmental Restoration - Peer Review	Site Closure and Environmental Restoration - Peer Review	Framework - Further Competition	Services	Not known	01/04/2025	31/12/2025	< £100k		Adreain Gill	Declan Gunn
C1150	Site Services	Development of Individual Component Environmental Safety Cases	Development of Individual Component Environmental Safety Cases	Framework - Further Competition	Services	Not known	01/04/2025	31/12/2025	< £100k		Adreain Gill	Declan Gunn
C1151	Site Services	Low Level Waste Pits - Review and development of the Environmental Safety Case	Low Level Waste Pits - Review and development of the Environmental Safety Case	Framework - Further Competition	Services	Not known	01/04/2025	31/03/2026	< £100k		Adreain Gill	Declan Gunn
C1155	Site Services	Supply of Heavy Weight Towing Vehicle	Supply of Heavy Weight Towing Vehicle	Open Procedure	Supplies	Re-procurement (same scope)	01/05/2025	01/04/2026	≥ £100k to <£500k	3300028934	Stephen Mackie	Janet Brooke
C1157	Site Services	Maintenance of Air Compressors	Maintenance of Air Compressors	Open Procedure	Services	Re-procurement (same scope)	03/03/2025	02/03/2029	≥ £500k to <£1m	3300024069	Laurence Campbell	Immi Smith
C1168	Portfolio & Support	Waste Optimisation - Waste Optimisation Improvements	Waste Optimisation - Waste Optimisation Improvements	Framework - Further Competition	Services	Not known	02/12/2024	31/10/2025	< £100k		Alan Mowat	Janet Brooke
C1172	Site Services	Reserved Procurement - Repair of Steelwork	Repair of Steelwork	Below Threshold - Competitive Tender	Works		30/11/2024	30/11/2025	≥ £100k to <£500k		Jason Park	Lauren J Mackay
C1173	Site Services	Design of Steelwork Repair	Design of Steelwork Repair	Framework - Further Competition	Services		30/11/2024	14/03/2025	≥ £100k to <£500k		Jason Park	Lauren J Mackay
C1177	FCA	Active Filter Change Robot Mechanical Modifications	Active Filter Change Robot Mechanical Modifications	Framework - Further Competition	Services	Not known	30/11/2024	02/11/2025	≥ £100k to <£500k		Michael L Tait	Alex Wood
C1211	Site Services	D1310 - Gas Chromatography - Mass Spectrometer	D1310 - Gas Chromatography - Mass Spectrometer	Below Threshold - Competitive Tender	Supplies		30/06/2025	17/11/2025	≥ £100k to <£500k		Jeremy Andrew	Hannah Budge
C1222	Reactors	Prototype Fast Reactor Transformers	Prototype Fast Reactor Transformers	Below Threshold - Competitive Tender	Supplies	Not known	03/02/2025	31/12/2025	≥ £100k to <£500k		Laurence Campbell	Fraser Bruce
C12385	Balance of Site	Dounreay Cementation Plant Peer Review	Dounreay Cementation Plant Peer Review	Framework - Further Competition	Services		03/02/2025	30/01/2026	< £100k		Frank Simmons	Erica Innes
C1246	Balance of Site	The supply of Cameras, Camera Encoders & Server Upgrade & supporting maintenance	- The supply and delivery of Cameras, Camera Encoders and Server Upgrade. / - Maintenance of Titan Vision Control Equipment.	Direct Award - PCR Single Source (Reg 32)	Supplies	Not known	01/01/2025	31/12/2029	≥ £1m to <£5m	N/A	Douglas Mackenzie	Declan Gunn
C1252	Finance	Programme Controls Support	Programme Controls Support	Direct Award - PCR Single Source (Reg 32)	Services	Re-procurement (same scope)	11/08/2025	11/08/2028	≥ £500k to <£1m	3300027789	Neil Cook	Ilona Unger-Russell
C1254	Site Services	D1215 Instrument Lab - Inductively Coupled Plasma - Mass Spectrometer	D1215 Instrument Lab - Inductively Coupled Plasma - Mass Spectrometer	Direct Award - Below Threshold	Supplies	Not known	14/11/2024	31/03/2025	≥ £100k to <£500k		Jeremy Andrew	Hannah Budge
C12555	EHSSQ	Purchase of Ambulance	Purchase of Ambulance	Below Threshold - Competitive Tender	Supplies		01/04/2026	31/03/2027	≥ £100k to <£500k		Richard Berry	Debbie Weir
C12623	EHSSQ	Firefighter and Officer Related Training	Firefighter and Officer Related Training	Below Threshold - 3 Quotes	Services		02/12/2024	19/12/2025	< £100k		Richard Berry	Debbie Weir
C12886	Balance of Site	D1215 / D1218 Ventilation System Electrical, Control and Instrumentation	D1215 / D1218 Ventilation System Electrical, Control and Instrumentation	Below Threshold - Competitive Tender	Services		02/12/2024	28/06/2025	< £100k		To be confirmed (TBC)	Lee Parnell
C12887	Balance of Site	D1215 Glove box Manufacturing and Delivery	D1215 Glove box Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		01/04/2025	31/10/2025	≥ £100k to <£500k		To be confirmed (TBC)	Lee Parnell
C12889	Balance of Site	Manufacturing and Delivery of the D1215 Red Extract System Filter Housings	Manufacturing and Delivery of the D1215 Red Extract System Filter Housings	Open Procedure	Services		01/04/2025	01/12/2025	≥ £100k to <£500k		To be confirmed (TBC)	Lee Parnell
C12890	Balance of Site	D1215 Ductwork Manufacturing and Delivery	D1215 Ductwork Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		01/04/2025	31/08/2025	≥ £100k to <£500k		To be confirmed (TBC)	Lee Parnell
C12892	Balance of Site	D1215 Panel Build & Factory Acceptance Testing of Panels for Red Extract System	D1215 Panel Build and Factory Acceptance Testing of Panels for Red Extract System	Below Threshold - Competitive Tender	Services		01/04/2025	31/10/2025	< £100k		To be confirmed (TBC)	Lee Parnell
C12893	Balance of Site	D1215 Fit-out and Commissioning of Glovebox and Extract Systems	Electrical, Control and Instrumentation Fit-out and Commissioning of Glovebox and Extract Systems	Open Procedure	Services		02/12/2024	12/12/2025	≥ £100k to <£500k		To be confirmed (TBC)	Lee Parnell
C12897	Balance of Site	D1215 Mechanical Fit-out and Commissioning of Glovebox and extract systems	D1215 Mechanical Fit-out and Commissioning of Glovebox and extract systems	Open Procedure	Services		01/04/2025	31/03/2026	≥ £100k to <£500k		To be confirmed (TBC)	Lee Parnell
C13963	EHSSQ	Fuel Cycle Area North Perimeter Fence Razor Wire Repair	Fuel Cycle Area North Perimeter Fence Razor Wire Repair	Below Threshold - Competitive Tender	Works	Not known	01/04/2025	31/05/2025	≥ £100k to <£500k		Richard Berry	Corrinda Pearson
C13986	Balance of Site	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Low Level Waste Effluent Treatment Plant Accommodation and Cladding	Below Threshold - Competitive Tender	Services		02/12/2024	30/05/2025	≥ £100k to <£500k		Morris Macleod	Lee Parnell
C13987	Balance of Site	D3000 Generator	D3000 Generator	Below Threshold - Competitive Tender	Supplies		02/12/2024	09/05/2025	< £100k		Morris Macleod	Lee Parnell
C13988	Balance of Site	Gravity Receipt Tank Ladder Replacement	Gravity Receipt Tank Ladder Replacement	Below Threshold - Competitive Tender	Works		08/07/2025	08/01/2026	< £100k		Morris Macleod	Lee Parnell
C13989	Balance of Site	Break Tank Improvements	Break Tank Improvements	Below Threshold - Competitive Tender	Works		02/09/2025	02/03/2026	< £100k		Morris Macleod	Lee Parnell
C14394	Portfolio & Support	Provision of Criticality Software MONK & Visual Workshop	Provision of Criticality Software MONK & Visual Workshop	Direct Award - PCR Single Source (Reg 32)	Services	Re-procurement (same scope)	01/04/2025	31/03/2030	≥ £100k to <£500k	3300031908	Mike Potts	Declan Gunn
C15129	EHSSQ	Supply of Electronic Personal Dosimeters 400no. + 400no.	Supply of Electronic Personal Dosimeters 400no. + 400no.	Direct Award - PCR Single Source (Reg 32)	Supplies	Not known	07/04/2025	31/03/2026	≥ £100k to <£500k		Anthony Ridgley	Fraser Bruce
C15131	Portfolio & Support	Framework Agreement for Provision of Design Services (Minor)	Framework Agreement for Provision of Design Services (Minor)	Framework Agreement – Set up of a new Framework	Services	Re-procurement (same scope)	01/05/2025	30/04/2029	≥ £1m to <£5m	CFA/21/0002-0010	Mike Potts	Lesley-Ann Crombie
C15173	Balance of Site	Reserved Procurement - D1310 Air Handling Unit Design	Reserved Procurement - D1310 Air Handling Unit Design	Below Threshold - Competitive Tender	Services		13/01/2025	28/03/2025	< £100k		Gary Armstrong	Lee Parnell
C15305	Balance of Site	Low Level Waste Pits - Resurfacing	Low Level Waste Pits - Resurfacing	Below Threshold - Competitive Tender	Works		03/03/2025	30/05/2025	≥ £100k to <£500k		Morris Macleod	Lee Parnell
C15329	Balance of Site	Shaft & Silo Waste Retrieval System	Procurement of a Silo Retrieval System for the Shaft & Silo programme - Detail Design, Manufacture, Installation & Commissioning,.	Restricted Procedure	Works		01/07/2026	15/01/2031	≥ £10m to <£25m		Grant Coghill	Lee Parnell
C16201	Site Services	Supply of 2 x new Tipper / Gritter Lorries	Supply of 2 x new Tipper / Gritter Lorries	Open Procedure	Supplies	Not known	29/11/2024	28/11/2025	≥ £100k to <£500k		Ian Mackay	Fraser Bruce
C16547	Balance of Site	Low Level Waste Pits - Provision of Cover Building	Low Level Waste Pits - Provision of Cover Building	Below Threshold - Competitive Tender	Supplies		03/03/2025	27/06/2025	< £100k		Morris Macleod	Lee Parnell
C16823	FCA	Procurement of a Non-Destructive Assay System (NDA 34 Replacement)	Procurement of a Non-Destructive Assay System	Open Procedure	Supplies	Not known	13/01/2025	31/07/2029	≥ £100k to <£500k	N/A	Ewen Boyd	Robert McDonald
C16843	Balance of Site	Low Level Waste Effluent Treatment Plant Accommodation Electrical Design	Low Level Waste Effluent Treatment Plant Accommodation Electrical Design	Framework - Further Competition	Services		18/11/2024	31/01/2025	< £100k		Morris Macleod	Lee Parnell
C16884	Reactors	Refit of IPM9 Monitor	Supply, Installation, Commissioning and Site Acceptance Testing of an IPM Rebuild Kit	Direct Award - Below Threshold	Works		04/12/2024	29/11/2024	< £100k		Chris Wratten	Jade Plowman
C16984	Balance of Site	Replacement of Wound Monitor and Supporting Equipment	This procurement is to supply a replacement Wound Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Below Threshold - Competitive Tender	Supplies	Not known	20/01/2025	23/06/2025	< £100k	N/A	Avril Fell	Dawn Sewell
C17121	Balance of Site	D1215 Dampers Manufacturing and Delivery	D1215 Dampers Manufacturing and Delivery	Below Threshold - Competitive Tender	Services		25/11/2024	25/04/2025	< £100k		Robert Spence	Lee Parnell
C17227	Capability	Internet Resilience Project for the Dounreay Site	Wide Area Network connectivity/ Internet Feeding requirement	Framework - Direct Award	Services		02/12/2024	20/01/2025	≥ £100k to <£500k		Calum Mackay	Ilona Unger-Russell
C17690	Portfolio & Support	Ongoing Support to SPOT Robot	Ongoing Support Contract for SPOT Robot System	Direct Award - Below Threshold	Services		20/12/2024	29/08/2025	< £100k		Heather Fairweather	Robert McDonald
C17834	People	Provision of Opticians Services - Reserved Procurement	Provision of Opticians Services - Reserved Procurement	Below Threshold - Competitive Tender	Services	Re-procurement (same scope)	01/05/2025	30/04/2030	< £100k	C0625	Kirsty McIntosh	Debbie Weir
C18787	Site Services	Gamma Spectroscopy Detector	Gamma Spectroscopy Detector	Direct Award - Below Threshold	Supplies	Not known	13/01/2025	30/04/2025	≥ £100k to <£500k		Ian Swainson	Hannah Budge
C18791	Site Services	Non Destructive Assay (NDA) 40 equipment and Software	Non Destructive Assay (NDA) 40 equipment and Software	Direct Award - Below Threshold	Supplies	Not known	30/11/2024	14/02/2025	≥ £100k to <£500k		Ian Swainson	Hannah Budge
C18805	Site Services	Shielded High Resolution Gamma Spectrometry System and Collimator	Shielded High Resolution Gamma Spectrometry System and Collimator	Direct Award - Below Threshold	Supplies		14/11/2024	07/03/2025	≥ £100k to <£500k		Jeremy Andrew	Immi Smith
C18809	Site Services	Supply of Cryocooler for D1310	Supply of Cryocooler for D1310	Direct Award - Below Threshold	Supplies	Not known	30/11/2024	01/03/2025	< £100k		Ian Swainson	Hannah Budge
C18811	Site Services	D1310 Total Organic Carbon backup	D1310 Total Organic Carbon backup	Below Threshold - 3 Quotes	Supplies	Not known	18/11/2024	28/02/2025	< £100k		Jeremy Andrew	Hannah Budge
C18812	Site Services	Portable X-Ray Radiography System	Portable X-Ray Radiography System	Below Threshold - Competitive Tender	Supplies		30/06/2025	01/08/2025	< £100k		Jeremy Andrew	Hannah Budge
C18813	Site Services	Dionex Ion Chromatography System (Effluent Lab)	Dionex Ion Chromatography System (Effluent Lab)	Direct Award - Below Threshold	Supplies		30/06/2025	01/09/2025	< £100k		Jeremy Andrew	Hannah Budge
C18814	Site Services	Supply of Easycount System for D2176	Supply of Easycount System for D2176	Direct Award - Below Threshold	Supplies		30/06/2025	01/10/2025	≥ £100k to <£500k		Jeremy Andrew	Hannah Budge
C18815	Site Services	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Alpha Spectrometry Analyst Floor Cabinet (48 Slots)	Direct Award - PCR Single Source (Reg 32)	Supplies	Not known	01/04/2026	01/08/2026	≥ £100k to <£500k		Ian Swainson	Hannah Budge
C18928	Portfolio & Support	Provision of Lifting Services	Provision of Lifting Services	Framework Agreement – Set up of a new Framework	Services	Re-procurement (same scope)	01/05/2025	30/04/2029	≥ £500k to <£1m	CFA/21/0011	Laurence Campbell	Janet Brooke
C19142	EHSSQ	Provision of Internal and Criticality Accident Dosimetry Service	Provision of Internal and Criticality Accident Dosimetry Service	Open Procedure	Services	Re-procurement (different scope)	01/04/2026	31/03/2030	≥ £1m to <£5m	3300008206	Anthony Ridgley	Fraser Bruce
C19455	Site Services	Provision of Grounds Maintenance on the Dounreay Estate	Provision of Grounds Maintenance on the Dounreay Estate	Open Procedure	Services	Re-procurement (same scope)	16/12/2024	15/12/2034	≥ £1m to <£5m	3300008447	Peter Swanson	Kelsey Bain
C19577	FCA	Safety Case Consultant to provide Safety Case support to D1203 and D2001	A Safety Case Consultant to provide Safety Case support to D1203 and D2001 decommissioning, and provide inventory support to the Irradiated Fuels Programme.	Framework - Further Competition	Services		18/11/2024	31/08/2026	≥ £100k to <£500k	3300032871	Ewen Boyd	Alex Wood
C19644	Portfolio & Support	Provision of Decommissioning Operatives	Provision of Decommissioning Operatives	Framework Agreement – Set up of a new Framework	Services	Re-procurement (same scope)	01/04/2026	31/03/2031	≥ £25m to <£50m	3300031138	Graeme Dunnett	Robert McDonald
C19906	Balance of Site	D1208 East Fire Escape Removal & Installation	Removal of the current and installation of a new D1208 Fire Escape Staircase	Below Threshold - Competitive Tender	Works		08/12/2024	12/05/2025	≥ £100k to <£500k		Michael Gray	Heidi Warner
C19908	Capability	Data Warehouse for Dounreay Site	Creation of a cohesive data ecosystem to eliminate fragmentation of information across Dounreay.	Framework - Further Competition	Services	Not known	02/12/2024	01/09/2025	≥ £100k to <£500k		Calum Mackay	Lynsey Will
C19935	Reactors	Prototype Fast Reactor Water Vapour Nitrogen System and Effluent Pump	A requirement has been identified requiring a Water Vapour Nitrogen injection point to be installed within the Prototype Fast Reactor reactor vessel as an addition to the current installation	Below Threshold - Competitive Tender	Supplies		28/04/2025	18/07/2025	< £100k		James Campbell	Kerrie Mackay
C19966	People	Outward Bound Experience	Outward Bound Experience	Framework - Further Competition	Services		02/06/2025	20/10/2025	< £100k		Rhona Gill	Debbie Weir
C19981	Site Services	Lynx II Digital Signal Analyser and Gamma Spec interfaces	Lynx II Digital Signal Analyser and Gamma Spec interfaces	Direct Award - Below Threshold	Supplies	Not known	02/12/2024	31/03/2025	< £100k		Ian Swainson	Hannah Budge
C20152	Capability	Checkpoint Firewall Replacement	Checkpoint Firewall Replacement	Framework - Further Competition	Services	Not known	01/01/2025	31/10/2025	≥ £100k to <£500k		Calum Mackay	Lynsey Will
C20153	Capability	Dounreay Electronic Document and Records Management System (EDRMS) Support	Dounreay Electronic Document and Records Management System (EDRMS) Support	Framework - Further Competition	Services	Not known	01/11/2024	31/10/2025	≥ £500k to <£1m		Calum Mackay	Lynsey Will
C20364	FCA	Provision of Breathing Air Panel	Provision of Breathing Air Panel	Direct Award - Below Threshold	Supplies		30/11/2024	31/05/2025	< £100k		Michael L Tait	Alex Wood
C20370	FCA	Provision of Safety Case Advisor	Provision of Safety Case Advisor	Framework - Further Competition	Services		16/12/2024	29/09/2025	< £100k		Ewen Boyd	Alex Wood
C20538	Reactors	Breeder Fast Reactor Senior Design Engineer Support	Breeder Fast Reactor Senior Design Engineer Support	Framework - Further Competition	Services	Not known	03/03/2025	30/09/2027	≥ £100k to <£500k		Magnus O'Brien	Kerrie Mackay
C20555	Balance of Site	Shaft Head Removal - Facility Hire & Construction of Mock Up Trials Rig	NRS looks to engage a contractor to provide the hire of a local facility, and the construction of a trials rig for the Shaft Head Removal Trials	Below Threshold - Competitive Tender	Works	New Requirement	01/08/2025	31/12/2025	≥ £100k to <£500k		Willie Ross	Kelsey Bain
C20641	EHSSQ	Call-off contract for ambulance training and Learning in Practice days	Call-off contract for ambulance training and Learning in Practice days	Direct Award - Below Threshold	Services		10/02/2025	07/08/2026	< £100k		John Dunnet	Debbie Weir
C20745	Portfolio & Support	Nuclear Restoration Services Limited (Dounreay) Excellence Plan	Nuclear Restoration Services Limited (Dounreay) Excellence Plan	Framework - Further Competition	Services	Not known	20/01/2025	31/12/2025	≥ £100k to <£500k		Fredric Stalin	Ilona Unger-Russell
C20778	People	Provision of Doctor's Services for Occupational Health Support	Provision of Doctor's Services for Occupational Health Support: health surveillance and case management with option for adhoc support.	Direct Award - Below Threshold	Services	Not known	12/11/2024	12/05/2026	< £100k		Kirsty McIntosh	Lauren J Mackay
C20814	Capability	Electric Vehicle Charging Off-Site (Design and Installation)	Electric Vehicle Charging Off-Site (Design and Installation)	Below Threshold - Competitive Tender	Works		07/04/2025	03/04/2026	≥ £100k to <£500k		Christopher Simpson	Debbie Weir
C20815	Capability	Water Meter Option Study	Water Meter Option Study	Framework - Further Competition	Services	Not known	07/04/2025	31/10/2025	< £100k		David Calder	Debbie Weir
C20817	Capability	Programme Carbon Consultancy Lifecycle Carbon Assessment	Programme Carbon Consultancy Lifecycle Carbon Assessment	Framework - Further Competition	Services		07/04/2025	02/04/2027	≥ £100k to <£500k		Christopher Simpson	Debbie Weir
C20891	Capability	Maintenance of the Dounreay Data Management System	Maintenance of the Dounreay Data Management System	To be confirmed (TBC)	Services	Re-procurement (same scope)	01/07/2025	30/06/2029	≥ £1m to <£5m	3300015868	Tracy Alexander	Lesley-Ann Crombie
C20938	Balance of Site	Faecal Lab Upgrade	Faecal Lab Upgrade	Below Threshold - Competitive Tender	Works		11/11/2024	31/03/2025	≥ £100k to <£500k		Gary Armstrong	Erica Innes
C21098	Reactors	Upgrades Prior to Fuel Repackaging	Prototype Fast Reactor Irradiated Fuel Cave Upgrades Prior to Fuel Repackaging (Electrical, Control & Instrumentation Upgrades)	Below Threshold - Competitive Tender	Works	Not known	25/03/2025	30/09/2025	≥ £500k to <£1m		Hamish Boyd	Robert McDonald
C21099	Reactors	Panel Upgrades	Prototype Fast Reactor Irradiated Fuel Cave Panel Upgrades	Below Threshold - Competitive Tender	Works	Not known	18/02/2025	01/09/2025	≥ £500k to <£1m		Hamish Boyd	Robert McDonald
C21101	Reactors	Pre Asbestos Clean Up	Prototype Fast Reactor Intermediate Level Waste Size Reduction Facility Pre Asbestos Clean Up	Open Procedure	Services		25/06/2025	30/06/2026	≥ £500k to <£1m		Chris Wratten	Robert McDonald
C21109	Reactors	Painting Accessible Areas of the Sphere	Painting Accessible Areas of the Dounreay Fast Reactor Sphere	Below Threshold - 3 Quotes	Services		11/03/2025	31/07/2025	≥ £100k to <£500k		Chris Wratten	Robert McDonald
C21237	Capability	LINC Opportunity 24- Network Cabling	Provision of upgrade to 40 network cabinets	Below Threshold - Competitive Tender	Works	Not known	18/12/2024	28/02/2025	≥ £100k to <£500k		Calum Mackay	Ilona Unger-Russell
C21282	Balance of Site	Procurement of X-Ray Equipment	NRS has a requirement for a contractor to undertake the design, manufacture, installation and commission of equipment to produce X-Rays to enhance their capability to calibrate Gamma Radiation Protection Instruments at high dose rate.	Open Procedure	Services		01/04/2025	31/10/2025	≥ £100k to <£500k		Bernie Jones	Kelsey Bain
C21291	Balance of Site	Non Active Drain Design Support CPS1-36274-2024	To review and update the current design and provide support during the procurement, installation and commissioning phase.	Framework - Direct Award	Services	New Requirement	11/11/2024	17/04/2026	≥ £100k to <£500k		Steve Efemey	Dawn Sewell
C21297	Balance of Site	Completion of Mechanical & Electrical Installation - Dounreay Cementation Plant Stores Extension	Nuclear Restoration Services Limited (Dounreay) intends to procure a contractor to complete the remaining mechanical and electrical (M&E) works for the Dounreay Cementation Plant Store Extension project at the Dounreay Nuclear site in Caithness, Scotland.	Below Threshold - Competitive Tender	Works	Re-procurement (same scope)	01/02/2025	31/07/2025	≥ £500k to <£1m	3300004730	Fiona Forbes	Sonja Sinclair
C21304	Reactors	Erection and Outfitting of DN026 Building	Erection and Outfitting of new DN026 Building including Services Racking & Access Platforms	Below Threshold - Competitive Tender	Works		01/12/2024	31/03/2025	≥ £1m to <£5m		Andy MacInnes	Jade Plowman
C21653	FCA	Licence Condition 15 periodic review of the ATO 52 Decommissioning Safety Case	License Condition 15 periodic review of the ATO 52 Decommissioning Safety Case	Framework - Further Competition	Services		17/02/2025	16/02/2028	≥ £500k to <£1m		Suzy Nellies	Sarah McCaughey
C21725	Site Services	Maintenance, Support & Development - Environment Sample Management System	Annual Maintenance, Support & Development of the Dounreay Environment Sample Management System	Open Procedure	Services	Re-procurement (same scope)	01/09/2025	31/08/2028	≥ £100k to <£500k	3300022841	Doug King	Declan Gunn
C21802	Site Services	Refurbishment of Flask Trailer	Refurbishment of Flask Trailer	Below Threshold - Competitive Tender	Services	Not known	03/02/2025	29/08/2025	≥ £100k to <£500k		Stephen Mackie	Janet Brooke
C21835	Balance of Site	Supply of a Whole Body Monitor System Replacement	This procurement is to supply a replacement Whole Body Monitor and all associated equipment. This shall include equipment installation, training, and verification to enable initial operation by the dosimetry team.	Open Procedure	Supplies	Not known	25/11/2024	25/04/2025	≥ £100k to <£500k	N/A	Gary Armstrong	Fraser Bruce
C22051	Site Services	Reserved Procurement - Stainless Steel Drums with Gaitor Attachment	Under PPN 11/20 this procurement is being Reserved to the county of Caithness. This procurement is for the manufacture and supply of stainless steel drums with a gaitor attachment.	Below Threshold - Competitive Tender	Supplies	Not known	20/12/2024	31/03/2025	< £100k		Michael Burrell	Jill Hannah
C22052	Site Services	Reserved Procurement - Stainless Steel Waste Drums with Solid Pintle	This procurement is for the manufacture, inspection, testing and delivery of stainless steel waste drums with solid pintle. Under PPN 11/20 this procurement is being Reserved to the county of Caithness.	Below Threshold - Competitive Tender	Supplies	Not known	20/12/2024	31/03/2025	< £100k		Michael Burrell	Jill Hannah
C22054	Site Services	Reserved Procurement - Mild Steel Waste Cans	Under PPN 11/20 this procurement is being Reserved to the county of Caithness. This procurement is for the manufacture and supply of mild steel waste cans.	Below Threshold - Competitive Tender	Supplies	Not known	20/12/2024	31/03/2025	< £100k		Michael Burrell	Jill Hannah
C22062	Balance of Site	D3100 Slope Maintenance	D3100 Slope Maintenance Site survey and geotechnical consultancy.	Framework - Further Competition	Services	Not known	05/05/2025	01/08/2025	< £100k		Jason Park	Lauren J Mackay
C22203	Reactors	Deterministic Fire Risk Assessment Peer Review	Prototype Fast Reactor Ventilation Upgrade Peer Review of Deterministic Fire Risk Assessment	Framework - Direct Award	Services	Extension	25/11/2024	20/12/2024	< £100k		Aly Mackay	Kate Thomson
C22205	Balance of Site	Gamma Calibration Facility Upgrade - X-ray System	A requirement for new equipment to produce X-Rays to enhance the capability to calibrate Gamma Radiation Protection Instruments (RPI) at high dose rates.	Direct Award - PCR Single Source (Reg 32)	Works	Extension	25/11/2024	31/03/2025	≥ £100k to <£500k		Bernie Jones	Dawn Sewell
C22228	Balance of Site	Shaft Monitoring Options Study	Shaft Monitoring Options Study	Below Threshold - Competitive Tender	Services	Not known	01/02/2025	31/03/2026	< £100k		Doug King	Kelsey Bain
C22243	FCA	Crane Control System Upgrade - D1206	Crane Control System Upgrade - D1206	Below Threshold - Competitive Tender	Services	Not known	17/02/2025	30/08/2025	< £100k		Alan J Farquhar	Alex Wood
C22280	Balance of Site	Production of LC15 Periodic Review	Production of LC15 Periodic Review	Framework - Further Competition	Services	Not known	09/12/2024	31/08/2026	≥ £500k to <£1m		Jared Fraser	Erica Innes
C22287	Capability	BT Migration to EE Mobile Sims	BT Migration to EE Mobile Sims	Framework - Direct Award	Services	Not known	02/12/2024	01/12/2025	≥ £100k to <£500k		Calum Mackay	Ilona Unger-Russell
C22295	Balance of Site	Legal compliance position statements	Legal compliance position statements	Below Threshold - 3 Quotes	Services	Not known	02/12/2024	31/05/2025	< £100k		Alex Proverbio	Erica Innes
C22296	Balance of Site	Costal erosion study and peer review	Costal erosion study and peer review	Framework - Further Competition	Services	Not known	09/12/2024	28/11/2025	< £100k		Alex Proverbio	Erica Innes
C22297	Balance of Site	Performance Assessment	Performance Assessment	Framework - Further Competition	Services	Not known	29/11/2024	29/05/2026	< £100k		Alex Proverbio	Erica Innes
C22302	Balance of Site	Geochemical And Near Field Evolution	Geochemical And Near Field Evolution	Framework - Further Competition	Services	Not known	16/12/2024	28/11/2025	< £100k		Alex Proverbio	Erica Innes
C22303	Balance of Site	Infield Investigation Planning	Infield Investigation Planning	Framework - Further Competition	Services	Not known	02/12/2024	16/07/2025	< £100k		Alex Proverbio	Erica Innes
C22324	FCA	LINC Opportunity 25 - D1201 Welfare facility upgrades - Phase 2	LINC Opportunity 25 - D1201 Welfare facility upgrades - Phase 2	Below Threshold - Competitive Tender	Works	Not known	25/11/2024	17/02/2025	< £100k		Jason Simpson	Kate Thomson
C22333	Reactors	Prototype Fast Reactor Vessel Residue Treatment	Prototype Fast Reactor (PFR) Reactor Vessel Residue Treatment	Below Threshold - Competitive Tender	Works	Not known	08/04/2025	16/09/2025	≥ £100k to <£500k		Andy MacInnes	Robert McDonald
C22335	Reactors	Prototype Fast Reactor Turbine Hall Bulk Sodium Treatment	Prototype Fast Reactor Turbine Hall Bulk Sodium Treatment	Below Threshold - 3 Quotes	Works	Not known	13/10/2025	14/05/2026	≥ £100k to <£500k		Andy MacInnes	Robert McDonald
C22337	Reactors	Dounreay Fast Reactor Facility Compliance and Maintenance	Dounreay Fast Reactor Facility Compliance and Maintenance	Below Threshold - 3 Quotes	Works	Not known	28/04/2025	30/10/2026	≥ £100k to <£500k		Claire Hughes	Robert McDonald
C22338	Reactors	Prototype Fast Reactor Facility Compliance and Maintenance	Prototype Fast Reactor Facility Compliance and Maintenance	Below Threshold - 3 Quotes	Works	Not known	02/05/2025	29/09/2025	≥ £100k to <£500k		Andy MacInnes	Robert McDonald
C22341	Reactors	Dounreay Fast Reactor Circuits and Dismantling	Dounreay Fast Reactor (DFR) Reactor and Circuits Dismantling, Decommissioning and Dismantling Documentation and Procurement	Below Threshold - 3 Quotes	Works	Not known	18/07/2025	25/02/2026	≥ £100k to <£500k		Claire Hughes	Robert McDonald
C22343	Reactors	Dounreay Fast Reactor Waste Processing Facility	Dounreay Fast Reactor Waste Processing Facility Concept Design Procurement	Below Threshold - 3 Quotes	Works	Not known	18/07/2025	25/02/2026	≥ £100k to <£500k		Claire Hughes	Robert McDonald
C22351	Reactors	Temporary Works Coordinator Personnel Requirement	The requirement of a temporary works coordinator to work in Reactors.	Direct Award - Below Threshold	Services		08/11/2024	31/10/2025	< £100k		Alisha Farquhar	Jade Plowman
C22423	EHSSQ	Supply, Delivery and Installation of 2 x Portacabins	Supply, Delivery and Installation of 2 x Portacabins	Below Threshold - 3 Quotes	Works	Not known	29/11/2024	31/03/2025	< £100k		Susan Mackay	Corrinda Pearson
C22433	Site Services	Vermin & Bird Control Services on Dounreay Site	Bird Hazzard Management Services & Vermin Management Services	Open Procedure	Services	Re-procurement (same scope)	01/01/2025	01/01/2035	≥ £1m to <£5m	3300024313; 3300038229	Laurence Campbell	Heidi Warner
C22505	EHSSQ	Automated Access Control System Replacement	Automated Access Control System Replacement	Open Procedure	Supplies	Re-procurement (same scope)	01/04/2025	31/12/2025	≥ £500k to <£1m	N/A	Richard Berry	Debbie Weir
C22521	Balance of Site	Shaft Head Removal - Concrete Cutting of Mock Up Trials Rig	NRS looks to engage a contractor to provide concrete cutting of the shaft headworks - Mock Up Trials Rig	Below Threshold - Competitive Tender	Works	New Requirement	01/04/2025	31/12/2025	≥ £500k to <£1m		Willie Ross	Kelsey Bain
C22528	Site Services	Supply and installation of an LB4200 gross alpha-beta counting system	Supply and installation of an LB4200 gross alpha-beta counting system	Direct Award - Below Threshold	Supplies	Not known	30/11/2024	20/04/2025	≥ £100k to <£500k		Ian Swainson	Hannah Budge
C8624	Balance of Site	Low Level Waste Effluent Treatment Plant Ventilation System Upgrade	Low Level Waste Effluent Treatment Plan Ventilation System Upgrade	Below Threshold - Competitive Tender	Works		09/12/2024	02/05/2025	< £100k		Morris Macleod	Lee Parnell
C8637	Balance of Site	Dounreay Cementation Plant Licence Condition 15 and Engineering Substantiation	Dounreay Cementation Plant Licence Condition 15 and Engineering Substantiation	Framework - Further Competition	Services		02/12/2024	19/12/2025	≥ £500k to <£1m		Frank Simmons	Erica Innes
C9673	Site Services	Telehandler	Telehandler	Below Threshold - Competitive Tender	Supplies	Not known	02/12/2024	31/03/2025	< £100k		Stephen Mackie	Janet Brooke
C9871	Balance of Site	Area 600 Caustic Line D2700 to DN253	Area 600 Caustic Line D2700 to DN253	Direct Award - Below Threshold	Works	Not known	06/06/2025	07/07/2025	< £100k		Michael Gray	Sonja Sinclair
C9875	Balance of Site	Area 600 - Internal Cement Powders Line and Caustic Line installation	Area 600 - Internal Cement Powders Line installation, internal and external Caustic Line installation and Phase 1 internal ventilation installation	Below Threshold - Competitive Tender	Works	Not known	01/04/2025	18/07/2025	≥ £100k to <£500k		Michael Gray	Sonja Sinclair
C9877	Balance of Site	Area 300 Main Immobilisation Line installation	Area 300 Main Immobilisation Line installation	Below Threshold - Competitive Tender	Works	Not known	24/10/2025	18/12/2026	≥ £100k to <£500k		Michael Gray	Sonja Sinclair
C9887	Balance of Site	Area 400 Internal Ventilation	To be coordinated with the installation of Area 300 and Area 400 Fan and Filter Rooms	Direct Award - Below Threshold	Works	Not known	18/06/2026	30/03/2026	< £100k		Michael Gray	Sonja Sinclair
C9890	Balance of Site	Stillage Transfer System- Gantry Crane & Frame	Works on the Stillage Transfer System- the Gantry Crane and Frame only	Below Threshold - Competitive Tender	Works	Not known	04/03/2026	19/02/2027	≥ £100k to <£500k		Michael Gray	Sonja Sinclair
C9903	Balance of Site	Electrical Control and Instrumentation Services	Electrical Control and Instrumentation Services	Open Procedure	Services		01/09/2025	31/03/2028	≥ £500k to <£1m		Michael Gray	Sonja Sinclair
C9905	Balance of Site	Mechanical Design Services	Mechanical Design Services	Open Procedure	Services		01/09/2025	31/03/2028	≥ £1m to <£5m		Michael Gray	Sonja Sinclair