## Detailed_Plan
Last Updated: / 27.09.24
Work Strand		October 2024 - December 2024 (No meetings in August & September)			January-April 2025 (No meeting in January)
	Tier 1: These are areas of work the Government has committed to do, either through primary legislation or through work programmes such as HMCTS Reform, or that the Committee is progressing at pace.
No.	FPRC Dates 2024	7 October 2024	4 November 2024 / Open Meeting	9 December 2024	3 February 2025	3 March 2025	7 April 2025
1	Private Law Demand (Early Resolution)	Item listed as a verbal update on the October agenda. Potential to discuss evaluation of the ER programme, need to ensure internal sign off for evaluation plans first, so subject to SCS discussion.	Item as a substantive item in November. Potential to discuss evaluation of the ER programme, need to ensure internal sign off for evaluation plans first, so subject to SCS discussion
2	Transparency orders / media reporting (roll out of pilot scheme)	Draft FPR and PD provision to be submitted to the Committee.
3	Service of Orders at refuges / confidentiality of refuge addresses	Update and final draft PD to be submitted to the Committee prior to the October FPRC meeting. The Rule amendments are scheduled to be laid in on the 11 October. The Rules will be send to the Committee for signing on the 27 September, and the PD Update will be sent to the PFD in parallel to this.
4	Parental Responsibility and Child Arrangements following imprisonment for murder of the other parent.	Update provided in matters arising.
Standing Items: Domestic Abuse Act Implementation
5	Cross Examination Provisions (Qualified Legal Representatives)		Update on QLR scheme
6	Domestic Abuse Protection Orders	Verbal update on DAPO launch
Tier 2: Substantive Items
7	Web Updates (inaccuracies on Justice.gov.uk).	Web updates are reviewed by the FPRC Secretariat on an ongoing basis.
8	Fast Track Procedure / – financial remedy applications.	The most recent working group meeting took place on 9 September, with the group considering a number of outstanding issues.	Plan to bring a substantive update with draft PD to be brought for discussion to the November or December meeting.
9	Modernisation of PD27A.	The public consultation on this item commenced on 9 September via email and was published online on 12 September. Consultation will close on 21 October, after which a substantive update will return to the Committee.
10	Deed Poll Name Changes.	MoJ in discussions with senior judiciary on child name change application reforms. Update will be provided once agreement has been reached on whether to progress reforms.
11	Forms Working Group (standing forms update with table of work).	The Forms Working Group consider provisions on an ongoing basis.
12	Permission to Appeal (PTA)	Draft rule amendments re PTA on TWM cases were agreed in the May meeting. Proposals in relation to lay justices were discussed at the June meeting. Item to return in October. Final proposal on workstream likely from Autumn.
13	Police Disclosure Orders in private law proceedings / New Protocol	The Committee considered FPR and PD amendments in May but have asked MoJ to work with the DA WG and the Disclosure Working Group to develop one template order. Matter to return to the Committee for an update in under matters arising.
15	Case Management and Intimate Images.	Substantive update will be provided from the Autumn.
16	Voice of the Child.	This item is led by Mrs Justice Knowles. Mrs Justice Knowles provided an update in May 2024 and may wish to give updates to subsequent meetings periodically.
17	Private law reform pilots – review of Child Arrangement Programme – including PD36Z (investigative approach) and PD36ZE (local flexibilities)			Throughout 2024 officials will continue to investigate the impacts of PD36ZE. An update was provided at the June meeting when the Committee agreed that future implementation updates will not be required. Matter to return to the Committee ahead of pilot PD expiry dates.
18	Mediation Vouchers (Pilot PD).			MoJ will update on progress of the pilot.
19	PD36ZF: Joint MoJ and DfE Pilot for Expert and Readiness Checklists.		Update to be provided to Committee on initial feedback on pilot and to outline plans for substantive update in Feb 2025 with a more detailed assessment and plans for next steps.		Substantive update to be provided to the Committee.
20	Disclosure of Respondent's Contact Details	Draft rule amendments approved. Will be included in SI when HMCTS confirm IT readiness.
21	Justice Legal Adviser Powers	Substantive paper to be provided on trainee legal adviser powers. / MoJ policy has also met with HHJ Suh to discuss legal adviser powers in public law cases and potential improvements to the public law file allocation system. This work is in the early stages and is not yet ready for triaging.
22	Financial remedies (FPR 28.3(4)(b)(ii))	Item was triaged in April and the Committee agreed to add it in tier 2. Priority level to be reviewed in January 2025.
23	Interim maintenance application (FPR 9.7)	Item was triaged in April and the Committee agreed to add it in tier 2. Priority level to be reviewed in January 2025.
24	Review of Practice Direction 12G.	An item on Disclosure to Police (Contempt of Court PD and committal proceedings, EBK v DLO 2023) was triaged in May and the Committee agreed that item should be added to the wider review of PD12G and moved to tier 2. The item will return to the Committee once wider work priorities are agreed.
Tier 3: Work with timings listed as TBC or with longer timescales
25	Review of PD12J (domestic abuse)					Committee agreed in May 2024 that updates need not return until March 2025 save for raising any substantive issues
26	Single Lawyer Models.	Item led by Mr Justice Peel/Single Lawyer Model Working Group. End date depends on any agreed next steps by the Working Group.
27	Review of the overriding objective, to include consideration of amendments relating to vulnerable parties and witnesses (FJC Report).	This workstream is not currently being progressed so an end date cannot be predicted.
28	Opposite sex civil partnerships Implementation: consequential amendments to the FPR 2010.	GEO aim to lay the regulations in Autumn 2024, subject to ministerial decision. MoJ Policy will confirm with GEO when this will return to the Committee.
29	Pension Sharing Orders.	Item was triaged in April with agreement it will be allocated to Tier 3. This will include responding to the recommendations made by the Pensions Advisory Group. It will return to the Committee when capacity permits.
30	Enforcement of Financial Remedy orders.	Item was triaged in April with agreement it will be allocated to Tier 3. This will include reviewing Rule 33.4(3) following the Gladwell v Gladwell judgment (2019). It will return to the Committee when capacity permits.
31	Applications for permission to revoke a placement order (G v H)	Item was triaged in May with agreement it should be in tier 3. / MoJ policy is now liaising with DfE, Cafcass Cymru, Cafcass and other stakeholders to inform our policy intention. Once this is confirmed we will return to the Committee to discuss potential FPR amendments.
32	Closed Material Proceedings (CMP)	The Committee agreed for this item to be paused whilst amendments to CMP are being made in Civil. MoJ colleagues would also require cross-department agreement before amendments can be made.
33	Disclosure of electronic records	This was triaged in May and the Committee agreed it should remain at tier 3.
34	Deprivation of Liberty	Item to remain in Tier 3.
34	Cape v Dring implications	The CPRC sub-committee have undergone a consultation from 19 February which closed on 8 April. They will be reviewing the responses and will provide a report to the CPRC. The report will be shared with the Committee at a later date.
35	Relationship between rules, PDs and guidance.	This item was triaged in May where the Committee agreed it should remain in tier 3. It will return to the Committee when capacity permits.
36	Financial position after an overseas divorce	This item was triaged in April with agreement it should be tier 3. It will return to the Committee when capacity permits.
37	Committal proceedings: 'Esper' judgment	This item was triaged in May where the Committee agreed it should be added to the Priorities Table in tier 3. It will return to the Committee when capacity permits.
38	Abduction: The role of a solicitor-guardian under FPR 16.6(1)	This item was triaged in June and the Committee agreed it should be added to the Priorities Table under tier 3.

	Annex A: Pending PD Changes / The changes below sets out the various PD-related projects that are underway or pending. When an entry relates to a project in the main table above, this is noted in the status column below.
	Subject	Practice Direction	Status	Timings of PD Update/ next due at Committee	Timescale for end of Work Strand
Action required mid 2024
A1	MIAMs	PD3A	See entry in main Table for Deed Polls.	TBC	Uncertain
A2	Online (a) private law proceedings (b) Part 4 FLA 1996 proceedings / (c) additional types of private law proceedings	PD36G and PD36ZD (pilots)	PD36G expires 31 March 2025 / PD36ZD came into force 20 April 2022. Expires 31 March 2025.	Awaiting confirmation from HMCTS of the timing and content of any further future IT releases, which will inform the timing of our bringing draft PD amendments to the Committee. In any event, return in February 2025 prior to respective expiry dates.	To be confirmed – depends on HMCTS rollout.
A3	Bundles	PD27A/ various pilot PDs	Modernisation to reflect increased use of electronic bundles. See item in main table. / Amendments may also be needed to PD36N, PD36P, PD36ZD and PD41D. / See entry in main Table.	Substantive item to July 2024 meeting. Consultation issued Sept 2024.	See entry in main table.
A5	REMOVE THIS ROW AS PD36P NOW REPLACED WITH PERMANENT PD41F.	PD36P (pilot)	Pilot PD ends 31 March 2024.	Future amendments dependent on any further developments to the online system, which will inform the / timing of bringing draft PD amendments to the Committee.	If pilot PD to be replaced with Part 41 permanent PD – paper to be put to March 2024 meeting.
A4	Piloting of investigative approach	PD36Z (annexes PD12B (Pilot))	PD expires various dates in 2025. / See main Table entry for Private Law Reform		See main table.
A5	Protocol Police disclosure in public and private law proceedings	TBC	Proposal to flag existence of new protocol in PD	See entry in main table. PD amendments on hold pending agreement of new template order.	Nov-24
A6	Online contested financial remedy	PD36N (pilot)	Amended via PD Update No. 5 of 2024. Expires 31 December 2024. / In future, will need to be extended, or replaced with permanent PD under Part 41 FPR.	November 2024 - / Prior to expiry date.	End of 2024 (if replaced by permanent PD) – or later if pilot PD extended further.
A9	Email communication with the court	PD5B	Minor amendment needed to link to new HMCTS guidance approved at November 2023 meeting.	Committee will be advised when PD amendment included in a future PD Update.	No ongoing call on Committee’s time.
Action required - late 2024/ early 2025
A7	Notification to police of Part 4 FLA orders	PD36ZA (pilot)	Came into force 28 February 2022. / Expires 28 February 2025.	Prior to expiry date. December 2024.	TBC depending on plans for the future of the notification system.
A8	Temporary modifications	PD36ZE (pilot) came into force 1 April 2023 (replacing PD36Y).	PD36ZE expires 28 February 2025 / See item for Private Law Reform in main table re. child arrangements programme (PD12B). / PD 36ZE provisions unrelated to PD12B will also need review.		See entry in main table.
A9	Transparency	PD12I	Practice Direction 12I to be updated to reference the Press Association’s Media Injunctions Alert Service.	TBC	TBC
A10	Justices’ Legal Advisers	PD2C			See entry in main table.
To return for review
A11	Mediation Vouchers	PD36V	See main table	Review ahead of expiry date of February 2025	See main table
A12	Enforcement	New Part 33 PD	Possible new PD to support simplified Part 33 FPR: see main table entry for enforcement	This item is triaged to Tier 3.	See main table
Timings to be confirmed
A13	Tracing through Government Departments	PD6C	New PD put in place January 2023. Further details may be added in due course	TBC	TBC

					Name of governing body for social workers requires updating	TBC	TBC