## Sheet1
[18 empty] | Season | Area | Days
| SNS ACTIVITY TRACKER | [16 empty] | summer | 27028 | 183
[18 empty] | winter | 12696 | 182
REFERENCE | APPLICATION STATUS | APROVAL DATE | REGULATOR | NAME OF PROJECT/ACTIVITY | OPERATOR/DEVELOPER | LOCATION QUAD/BLOCK | LOCATION CO-ORDINATES | APPLICATION EARLIEST START DATE | APPLICATION LATEST COMPLETION DATE | ACTUAL ACTIVITIES START DATE | ACTUAL ACTIVITIES END DATE | DATE OPERATIONS COMPLETED | DURATION OF ACTIVITY IN DAYS | DURATION OF ACTIVITY IMPACTING SAC IN DAYS | ACTIVITY TYPE | ACTIVITY SIZE Daily KM2 | MAGNITIUDE | LINK TO DECISION | DAILY THRESHOLD (summer) | SEASONAL THRESHOLD (summer)
| Proposed is included to highlight the potential activities but should not be used to in AA | [6 empty] | Initial start date within the Application - remains the same for Audit | Initial end date within the Application - remains the same for Audit | Refined start date of activities - updated once the final programme has been | Refined end date of activities - updated once the final programme has been | Update from notification of completion | The number of days the activity will take place | The number of days the activity will impact the SAC | Be clear on the impact to the SAC and any information that could assist in completing AA | Still in discussion on if it is within the SAC or average WCS | SEL, dB, cu, kg - depending on activity - put as much information as possible | Which season is impacted? | Only take into account the none greyed out figures | Only take into account the none greyed out figures
DCO/2013/00011 | Approved |  | MMO | Sofia Offshore Wind Farm Piling | Sofia Offshore Wind Farm Limited |  |  | 2024-01-01 | 2024-12-31 | 2024-05-17 | 2025-03-31 |  | 365 | 100 | Piling. Combined with DBB piling = daily maximum 16.39%. Activity size for x1 turbine: 1480, x2 turbines: 1995 | 1480 |  | Summer | 5.4758 | 1.54
DCO/2013/00011 | Approved |  | MMO | Sofia OWF Piling - Offshore Converter Platform (OCP) pin-pile installation | Sofia Offshore Wind Farm Limited |  |  | 2024-04-01 | 2024-09-30 | 2024-08-11 | 2024-09-30 |  | 8 | 8 | Piling | 133.37 |  | Summer | 0.49345 | 0.021572
EXE/2023/00009 | Completed |  | MMO | Sofia OWF - geophysical survey (export cable) | Sofia Offshore Wind Farm Limited |  |  | 2023-05-01 | 2023-07-31 |  |  |  | 80 | 20 | Geophysical Surveys |  |  |  | 0 | 0
EXE/2023/00009 | Completed |  | MMO | Sofia - geophysical survey (array) | Sofia Offshore Wind Farm Limited |  |  | 2023-07-01 | 2023-12-31 |  |  |  | 0 | 0 | Geophysical Surveys |  |  |  | 0 | 0
MLA/2020/00489 | Approved |  | MMO | Sofia OWF UXO Sidescan sonar, multibeam echo sounder and magnetometer equipment | RWE LTD | N/A |  | 2023-06-02 | 2028-05-31 | 2024-10-01 | 2028-05-31 |  |  |  | Geophysical Surveys | 133.37 |  | Summer | 0.49345 | 0
MLA/2023/00209 | Approved |  | MMO | East Anglia THREE - UXO Investigation and Clearance - High Order | Scottish Power |  | See applicaton | 2024-04-01 | 2024-09-30 | 2024-07-08 | 2024-09-30 |  |  | 3 | High Order UXO | 707 |  | Both | 2.6158 | 0.042882
MLA/2023/00209 | Approved |  | MMO | East Anglia THREE - UXO Investigation and Clearance - Low Order | Scottish Power |  |  | 2024-04-01 | 2024-10-31 | 2024-07-08 | 2024-09-30 |  |  | 73 | Low Order UXO | 79 |  | Both | 0.29229 | 0.1166
DCO/2016/00024 | Approved |  | MMO | Dogger Bank B | SSE |  |  | 2024-03-01 | 2024-08-31 | 2024-04-26 | 2024-10-21 |  | 214 | 95 | Piling. Combined with Sofia piling = daily maximum 16.39% | 2123.7 |  | Summer | 7.8574 | 4.079
MLA/2024/00088 | Submitted |  | MMO | Hornsea Three Landfall HDD UXO Inspection and Removal | ORSTED |  |  | 2024-08-01 | 2024-12-31 | 2024-09-16 | 2024-12-31 |  |  | 97 | Low Order UXO | 79 |  | Summer | 0.29229 | 0.15493
MLA/2024/00088 | Submitted |  | MMO | Hornsea Three Landfall HDD UXO Inspection and Removal | ORSTED |  |  | 2024-08-01 | 2024-12-31 | 2024-09-16 | 2024-12-31 |  | 153 | 3 | High Order UXO | 707 |  | Summer | 2.6158 | 0.042882
MLA/2023/00373 | Completed |  | MMO | NEUCONNECT BRITAIN LTD UXOs | NEUCONNECT BRITAIN LTD |  |  | 2024-04-01 | 2024-09-30 | 2024-07-31 | 2024-08-31 |  | 2 | 2 | Low Order UXO | 79 |  | Summer | 0.29229 | 0.0031944
MLA/2023/00373 | Completed |  | MMO | NEUCONNECT BRITAIN LTD UXOs | NEUCONNECT BRITAIN LTD |  |  | 2024-04-01 | 2024-09-30 | 2024-07-31 | 2024-08-31 |  | 0 | 0 | High Order UXO | 707 |  | Summer | 2.6158 | 0
GS/1605 | Completed |  | OPRED | NEP Expansion Survey (Phase 1) | BP EXPLORATION OPERATING COMPANY LIMITED | 44/21, 22, 26 and 27; 43/, 24, 25, 29 and 30 |  | 2024-04-01 | 2024-06-30 | 2024-06-10 |  |  | 40 | 40 | 2D seismic (160 cu inch); SBP and SSS. | 655 | SEL 214dB SPL 245dB | Summer | 2.4234 | 0.234
TBC | Cancelled | Resubmitting spring 2024 | OPRED | Q43 Lodestone West 2023- multi-client regional survey | CGG Services (UK) Limited | 41/11, 16, 21, 42/6 to 25, 43/6 to 25, 44/6, 11,16, 21 | See application- to be clarified | 01/09/2024 maybe october | 1905-07-17 |  |  |  | 114 | 114 | 3D high resolution seismic survey- some details to be clarified |  | 3390 (cu in); SEL 233 dB; SPL 254 dB | Summer & Winter | 0 | 0
GS/1680 | Cancelled |  | OPRED | UK SNS Transformation 3D | WesternGeco | 23/17 - 21; 23,25 and 29. 44/21-30 |  | 2024-03-25 | 2024-10-24 |  |  |  | 178 | not stated | Towed Streamer 3D Marine Seismic Survey in an area just south of the Dogger Bank shallows area in the UK Southern North Sea. The maximum survey area size is approximately 5,100sqkm. | 4.76 | 1090cu in |  | 0.017611 | #VALUE!
GS/1642 | Approved |  | OPRED | Baker Survey - Sub-bottom profiler. (Winter area only) | PETROGAS NORTH SEA LIMITED | 47/3 | see application - winter | 2023-09-18 | 2024-09-30 |  |  |  | 8 | 8 | SBP. |  |  | winter | 0 | 0
GS/1692 | Completed | 25/04/2024 | OPRED | NEP Expansion Survey: Phase 2 - 2D seismic | BP EXPLORATION OPERATING COMPANY LIMITED | 43/17, 43/21, 43/22 | See application | 2024-04-15 | 2024-07-16 | w/c 22/29 July |  | 2024-08-04 | 5 | 5 | 2D seismic | 817 |  | Summer | 3.0228 | 0.08259
GS/1682 | Completed | 01/02/2024 | OPRED | Katy KT, NW Bell ZX & Murdoch KM | Chrysaor Production (U.K) Limited | 44/19, 44/22, 49/22 | See applicaton | 2024-05-28 | 2024-08-31 |  |  |  | 3 | 1 | Sub-bottom profilling and other survey methods (echo-sounder, sidescan sonar, multibeam sonar) | 0.25 | SEL 232 dB SPL 250 dB | Both | 0.00092497 | 5.0545e-06
GS/1683 | Completed | 26/01/2024 | OPRED | Hunter, Rita, Johnston Wells Sub Bottom Profiler (SBP) Survey | Premier Oil | 44/23 | See applicaton | 2024-02-01 | 2024-09-30 |  |  |  | 5 | 5 | Geophysical survey using a passive magnetometer, MBES, SSS and SBP. | 0.75 | SEL 232 dB SPL 250 dB | Both | 0.0027749 | 7.5817e-05
GS/1689 | Completed | 22/02/2024 | OPRED | Crosgan 2D seismic | One Dyas UK Limited | 42/14 | See applicaton | 2024-03-01 | 2024-04-01 |  |  |  | 4 | 4 | 2D seismic (160 cu inch) and SBP. | 1 | 160 cu inch |  | 0.0036999 | 8.0871e-05
DR/2469 | Completed | 04/04/2024 | OPRED | Hewett Injectivity Testing | ENI UK Limited |  |  | 2024-04-05 | 2024-04-30 |  |  |  | 1 | 1 | Downhole perforation using explosives 3500ft below seabed. |  |  | Summer | 0 | 0
DCO/2016/00024 | Completed |  | MMO | Dogger Bank A - Axial Assessment | SSE |  |  | 2024-04-15 | 2024-09-30 | 2024-04-15 | 2024-04-15 | 2024-04-15 | 1 | 1 | Piling | 1864.06 |  | Summer | 6.8968 | 0.037687
GS/1769 | Approved |  | OPRED | Viking CCS survey | Harbour Energy | 48/17, 49/22 |  | 2024-06-06 | 2024-10-31 |  |  |  | 10 | 12 | 2D site survey. Site survey (2D seismic) outwith SNS SAC boundary but will impact. | 95.4 | 160 cu inch | Summer | 0.35297 | 0.023145
GS/1769 | Approved |  | OPRED | Viking CCS survey | Harbour Energy | 48/20,49/16,49/17, 49/22 |  | 2024-06-06 | 2024-10-31 |  |  |  | 12 | 10 | SBP route and site survey. | 35 | SEL = 228 dB re 1 μPa2s SPL = 250 dB re 1 μPa (peak) | Summer | 0.1295 | 0.0070762
GS/1794/0 | Submitted |  | OPRED | CS020 CCS well site survey | Neptune (ENI) | 43/19 43/20, 43/24 and 43/25 |  | 2024-08-01 | 2024-12-31 |  |  |  | 15 | 15 | Mini Ultra High Res seismic (10cu-inch airgun) and SBP. Survey of potential CCS drill site | 14 |  | Summer | 0.051798 | 0.0042457
ML/1161/0 | Completed |  | OPRED | Leman P&A (2 wells) | Petrodec | 49/27 |  | 2024-07-15 | 2025-11-30 |  |  |  | 1 | 1 | 1 activity for each of 2 days. Question - will the use of explosives be after Sept? | 78.5 |  | Summer | 0.29044 | 0.0015871
GS/1815/0 | Submitted |  | OPRED | CS008 CCS well site survey | ENI UK Limited | 48/30 |  | 2024-09-02 | 2024-10-31 |  |  |  | 7 | 7 | Mini Airgun Seismic survey of potential CCS drill site | 12.5 | 152cu inch. SEL218, SPL 249 | Summer | 2.2 - to be amended | #VALUE!
MLA/2021/00229/2 | Completed |  | MMO | Great Yarmouth O&M Sheet Piles | Norfolk County Council |  |  | 2023-11-03 | 2024-06-23 | 2024-04-29 | 2024-08-01 |  |  | 149 |  | 707 |  | Winter | 2.6158 | 2.1298
[19 empty] | 0 | 0
[19 empty] | 0 | 0