Business Case

Summary Sheet

Department CDD/Portfolio/ Business Plan Summary: / The DFID Research and Evidence Division (RED) contributes to the achievement of DFID’s Single Departmental Plan, to deliver the Sustainable Development Goals (SDGs) and is in line with the UK Aid Strategy and wider UK national security objectives. Over the period RED will ensure that DFID remains a global leader in knowledge, technology and innovation for development- funding high-quality, problem focused research that generates new technologies and knowledge, able to deliver tangible development impacts. / This programme directly contributes to DFID Single Departmental Plan objective 3.1 to “Harness digital technologies to drive inclusive economic growth and alleviate poverty, including through a technology accelerator programme to bring UK and African entrepreneurs together to learn from each other” This investment supports technological innovation, building evidence and ensuring new products and services can be scaled through strategic partnerships between entrepreneurs, the private sector and academics. The programme also aligns and delivers against the priorities set out in the 2016 DFID Research Review.

Title: Africa Technology and Innovation Partnerships
Programme summary (100 words maximum): / The Africa Technology and Innovation Partnerships (ATIP) programme will accelerate the growth of technological innovation in Nigeria, South Africa, Kenya and adjacent countries through strengthened networks between African policymakers, businesses, investors, innovators and relevant stakeholders with links to innovation stakeholders in the UK; an innovation fund for solutions to systemic barriers to scaling technological innovation in each setting and robust research on strengthening of innovation ecosystems. This will enable technology entrepreneurs to create sustainable businesses and new products and services with a wide range of beneficiaries.
What is the rationale for UK Aid spending? (200 words maximum): / The Africa Technology and Innovation Partnerships (ATIP) programme will create mutually beneficial and sustainable partnerships to accelerate the growth of promising technologies in Kenya, Nigeria and South Africa and countries in their regions. Technology has long been a driver of growth. Advances in technology have the potential to translate into increased productivity in all sectors of the economy and improved access to goods and services, in addition to supporting service delivery for the poor and underserved communities. / Using a whole of government approach, it will also help leverage wider UK expertise through the UK’s world-leading science, technology and development base to tackle global problems. With cutting-edge science and technology industries the UK has distinctive qualities and strengths to partner with African nations, for mutual benefit. These partnerships will not only accelerate innovation in partner African nations but also support the wider objectives of the UK’s Industrial Strategy. / In 2018, UK set out a new strategic partnership approach with Africa, committing to work alongside, invest in and partner with African nations for our mutual benefit. The Prime Minister announced a series of ambitious new innovation partnerships between the UK and Africa. The Africa Technology and Innovation Partnerships programme was one of those new innovation partnerships.
Programme Value: / £32m		Country/ Region or Sector: / Initial focus on Kenya, Nigeria and South Africa with extension to look for opportunities within other African countries as the programme develops.
Department/Country Office confirmation / Contact name / Before submission Department procedures for review of papers should be followed. Contact for CN may be author or other who leads on follow-up		Point of Contact for CN: Seb Mhatre
Threshold for Approval of Business Case: / Deputy Directors <£40m / Director £40m-£100m / Minister >£100m. List of Ministerial Portfolios for CNs available from Private Offices or BDD		Deputy Director
Date of Approval of Business Proposition:	13/08/2018	Name of Approver / Minister of State Baldwin
Date of Approval of Concept Note:	15/05/19	Name of Approver
Date of Approval of Business Case	04/12/2019y	Name of Approver / Charlotte Watts
Programme Code: 300704	Start Date: dd/mm/yyyy	End Date: 31/03/24
Overall programme risk rating: / Further details in “Risk” section	Moderate
Vault Number:

Strategic Case

Technological innovation is increasingly a fundamental driver of economic growth and human progress. Examples include mobile technologies and services that generated 8.6% of GDP in Sub-Saharan Africa, a contribution of over $144 billion of economic value added and supported almost 3.5 million jobs, in 2018. The development of the first ever rapid action drug to treat malaria in children led to 300 million treatments being delivered to 50 countries saving an estimated 750,000 lives. Off-grid solar lighting products have led to 108 million people with improved energy access. Two-thirds of Nigerian farmers adopted improved cassava varieties leading to an estimated 1.8 million people escaping poverty in 2015/16.

This programme is a core part of delivering DFID’s strategic direction for Harnessing Technological innovation For Development (HT4D). This programme will be a platform or ‘super connector’ to connect and strengthen national innovation ecosystems, connect UK ODA funded technology and innovation programmes and through a learning approach, help refine new approaches to scale transformative technologies. The importance of technological innovation[1] for prosperity, serving poor and marginalised populations and achieving the sustainable development goals has been clearly set out in a wide range of recent reports such as the World Development Reports (Digital Dividends and the Future of Work), Charting Pathways to Inclusive Growth and the UN’s High-Level Political Forum on Sustainable Development.
[1] “Technological innovations comprise new products and processes and significant technological changes of products and processes. An innovation has been implemented if it has been introduced on the market (product innovation).” OECD Statistical Glossary https://stats.oecd.org/glossary/detail.asp?ID=2688

“In a fast-changing world, technology affords us the opportunity to do more as individuals and in collaboration with others. Technology gives us the power to include, the power to reach, to inspire, to communicate, to educate, to change. Digital technologies offer an unprecedented opportunity to revolutionise the global development system, change lives, transform entire economies, stimulate growth and, ultimately, end reliance on aid.” DFID Digital Strategy 2018 to 2020: doing development in a digital world.

“We find ourselves in the midst of the greatest information and communications revolution in human history. More than 40 percent of the world’s population has access to the internet, with new users coming online every day. Among the poorest 20 percent of households, nearly 7 out of 10 have a mobile phone. The poorest households are more likely to have access to mobile phones than to toilets or clean water. We must take advantage of this rapid technological change to make the world more prosperous and inclusive.” Jim Yong Kim, Digital Dividends, World Development Report.

“Innovation will continue to accelerate but developing countries will need to take rapid action to ensure they can compete in the economy of the future. They will have to invest in their people with a fierce sense of urgency especially in health and education, which are the building blocks of human capital to harness the benefits of technology and to blunt its worst disruptions. But right now, too many countries are not making these critical investments.” Jim Yong Kim, Future of Work, World Development Report

“We are living through a moment in which new technologies are radically transforming lives across the world in ways that would have been difficult to imagine even a few years ago. The actions we take today will determine whether these technologies are ultimately an asset or a liability for people and economies in developing countries.” Charting Pathways to Inclusive Growth, Pathways for Prosperity Commission.

“These new technologies hold great promise for the Sustainable Development Goals. They could help eradicate poverty; bring high-quality education to all; help find cures for intractable diseases; expand mankind’s knowledge base; significantly improve resource efficiencies; improve governance, accountability and inclusion; and make a fully renewable, circular economy possible, thus fostering an era of abundance and cooperation rather than scarcity.” High Level Political Forum for the Sustainable Development

The ability of countries to bring innovative technologies to scale is determined by the strength of their innovation ecosystem. An innovation ecosystem is the interaction between multiple and interconnected actors such as governments, civil society, the private sector, universities, investors and individual entrepreneurs and the policy, infrastructure, cultural environment in which they operate. Figure 1 shows how a new idea or innovation goes through several stages of development, from basic research and testing through to being marketed at scale. It shows the interaction and stages when different actors play a predominant role[2].
[2] Figure 1 represents the ecosystem scaling as a linear process for simplicity, in reality not all ideas go through to scale and the process may involve several iterations.
Figure 1: Process of Scaling Innovation[3]
[3] https://www.idiainnovation.org/ecosystem-actors

A weak innovation ecosystem reduces the effectiveness of national efforts to take innovative technologies to scale. Building more effective innovation ecosystems that enable the scaling of new technologies means local innovators can address local problems through growing businesses providing solutions that fit the local context.

There is a broad consensus on the important factors for enabling the commercial scaling of new technologies. Published evidence and stakeholder feedback confirms the barriers to scaling technological to be substantial, interrelated and complex. This consensus is supported through the findings of a scoping exercise[4] conducted for this programme that consulted innovation ecosystem stakeholders in Nigeria, Kenya and South Africa.
[4] See Annex 1

“Without a strong innovation system, the UK would struggle to reap the returns from both its own investments in research and development (R&D) and the investments made by others, jeopardising economic growth, much-needed increases in productivity and the creation of high-value jobs.” https://www.raeng.org.uk/publications/reports/investing-in-innovation

“Despite all of the good work, there are still two major challenges cited in studies
referenced: financing and human capital. Despite the many financing options available,
there is a gap between supply and demand that needs to be resolved, particularly for
early-stage non-collateral-based equity and debt. There are also talent gaps, both in the
organizations providing services to SMEs and in senior roles in startups. These are
systemic issues that need to be considered.” The Entrepreneurship and Enterprise Growth
Landscape, Kenya, Aspen Network of Development Entrepreneurs. https://c.ymcdn.com/sites/www.andeglobal.org/resource/dynamic/forums/20160713_061617_17571.pdf

“These findings confirm the need for funders to help build local entrepreneurial ecosystems, particularly robust local capital pools, over the longer term. Building ecosystems can include supporting industry networks, engaging in policy advocacy to strengthen tax and regulatory environments, and building a pipeline of entrepreneurs through investments in universities and technical trainings… ANDE identifies eight features of an entrepreneurial ecosystem — business support, markets, finance, policy, human capital, research and development, infrastructure, and culture… Quantitative and qualitative data support the idea that these ecosystem features have a large effect on SGB performance.” USAID Accelerating Entrepreneurs report March 2018 https://www.usaid.gov/sites/default/files/documents/15396/PACE_Strategic_Review_Mar2018.pdf

“The factors holding back the South African ecosystem can be narrowed down to six areas. They are: Finance of new and growing firms, access to markets for firms both domestic and international, skills, education, networks and culture, and regulation.” The Entrepreneurial Ecosystem of South Africa, The Global Entrepreneurship and Development Institute. https://sabcms.blob.core.windows.net/wp-content/2017/03/GEDI-South-Africa-Analysis2.pdf

Figure 2: Gaps in the Lagos Entrepreneurial Ecosystem, Lagos Entrepreneurial Ecosystem Snapshot https://cdn.ymaws.com/www.andeglobal.org/resource/resmgr/west_africa/Lagos_Entrepreneurial_Ecosys.pdf

The main areas consistently identified in the literature as serving as either enablers or barriers to scaling technological innovation, and confirmed in the scoping study, are summarised in the table below.

Table 1: Technology and Innovation Ecosystem Enablers
Partnerships: Organisations are siloed geographically, sectorally and organisationally leading to reduced learning and reduced collaboration. Examples of ways to strengthen partnerships and networks include: / fostering trust and collaboration between researchers/universities and businesses to see greater opportunity for research to pull through to commercial ideas and development impact; / supporting pan-African and Africa-UK partnerships e.g. between tech hubs, between innovation agencies, between angel investor networks; allowing cross-fertilisation of ideas and new collaborations. / Supporting the engagement of the tech sector with civil society enabling the different groups to better understand the challenges the other is facing and leading to the development of technologies better informed by the needs of civil society.
Skills and Knowledge: The demand for skilled workers by technology businesses and need for research and innovation skills is greater than the supply. Examples of ways to strengthen skills include: / Building the local talent pool of deep 4IR expertise through partnerships between universities, innovation agencies and tech companies in the UK and Africa / Strengthening the capabilities of local the hubs / Building entrepreneurship and business skills through supporting mentorship from angel investors and successful startups and through improved university support for entrepreneurs.
Investment: Technology businesses struggle to raise funding and investors struggle to find a pipeline of businesses to invest in. Examples of ways to strengthen investment include: / Building local investment capacity through supporting the growth of Angel investor networks. / Working with investors, tech hubs and startups to provide technical support to the design and support innovative financing structures e.g. blended finance, crowdfunding mechanisms, matched funding or more patient capital.
Policy and Regulation: Policy and regulation are slow to adapt to technological innovation both in terms of realising opportunities to support innovation and in having the necessary safeguards in place to guard against risks, especially from emerging technologies, such as privacy, security, monopoly or exclusion. Examples of ways to strengthen policy and regulation include: / Working with regulatory bodies and tech businesses to develop policy and regulation sandboxes. / Supporting innovation agencies to run policy hackathons with other innovation ecosystem stakeholders to identify best practice for innovation policy. / Assess and diagnose policy and regulation bottlenecks though consultation with networks and detailed analysis; identification of best practice approaches and convening of discussions on practical actions to take forward.
Market Access: Technology entrepreneurs struggle to access customers and beneficiaries. Examples of ways to strengthen market access include: / Support the development of ‘one stop shops’ to simplify procedures for business registration. / Supporting government to match entrepreneurs with government services and supply chains. / Supporting corporates to match entrepreneurs with corporate services and supply chains.
Infrastructure – A lack of physical, digital, knowledge and institutional infrastructure prevents innovative R&D output from reaching a full development and commercialisation potential, products and services from reaching customers and beneficiaries, innovators from building new products and services. Examples of ways to strengthen infrastructure include: / Supporting the development of public good digital infrastructure (e.g. payments API’s, mobile services API’s, open data) that will lower the barriers to market entry for entrepreneurs and increase interoperability. / Supporting the development of institutional infrastructure that reduces barriers to market entry for entrepreneurs e.g. standardisation of legal framework for innovation such as IP, NDA’s, contracts, deal structures.

This programme aims to understand the critical barriers to scaling technological innovation in each of Kenya, Nigeria and South Africa’s innovation ecosystems It will work with local partners and decision makers to identify critical barriers that can be addressed and where UK HMG has a comparative advantage. Support will be provided in partnership with key players in the local ecosystem, who have the potential to be key enablers to the scaling of new and emerging technologies with the high potential for poverty reduction and inclusive growth.

The programme will focus on interventions in each setting based on a detailed and shared assessment of the barriers and context for change. Actions will include building and linking networks of entrepreneurs and ensuring linkages to early investment funding for promising technologies. There will be a focus on identifying best practice for innovation policy and supporting policy change and a strong focus on robust evidence and learning.

Digital innovation, the digital economy and clean energy will be key focus areas explored within each innovation ecosystem. The programme will work with existing centrally funded programmes such as the GSMA Mobile for Development Ecosystem Accelerator (supporting digital start-ups and entrepreneurs) and the Prosperity Fund Digital Access Programme through their Digital Tech Hubs. It will also work closely with clean energy programmes such as the Transforming Energy Access (TEA) and the recently announced Ayrton Fund to identify opportunities to support the innovation ecosystem in country to more effectively deliver clean energy objectives alongside scoping opportunities to connect with other DFID funded sectoral innovation programmes.

The expected high level results this programme will support are:

Impact: More effective innovation ecosystems that catalyse new technologies to scale in Nigeria, South Africa, Kenya and adjacent countries.

At an impact level, the programme will contribute towards achieving the overall ambition set out by the Nigerian, Kenyan and South African governments within their Science, Technology and Innovation strategies. Once the programme is operational and within the inception phase, we will agree a series of more tangible measures of impact linking to existing strategies. Finalising impact measures will also be supported by new research recently commissioned by the East Africa Research Fund to explore the metrics used by different initiatives to measure science, technology and innovation in Africa. This work will provide an assessment of the quality, completeness and appropriateness of measures and will inform the development of a scoreboard to track and monitor the science, technology and innovation ecosystem in Africa.

Outcome: Critical barriers to the inclusive scaling of new and emerging technologies analysed and addressed in Nigeria, South Africa, Kenya and adjacent countries.

Through strengthening the innovation ecosystem, the programme is an impact multiplier that augments UK and other investments in science, technology and innovation reducing the barriers to scaling innovation and maximising its social and economic impact. The programme also mitigates the risks from the harmful effects of technological disruption through better equipping countries to understand, anticipate and prepare for technological change.

The underlying Theory of Change is that that more technology businesses will pass through to the next stage of the pathway to scale in each ecosystem. At the same time ensuring new technologies reach the poorest and most marginalised people and create new jobs and economic growth. This ‘pull through’ of technology businesses and the improvement of innovation ecosystem enabling factors will be measured through robust methods and data collection developed through research commissioned under output 4 of the programme. This research will provide a public good that will be valuable to other HMG programmes working on technology and innovation in Nigeria, South Africa, Kenya and adjacent countries and other stakeholders in the innovation ecosystems.

The expected outputs are:

1. Larger and more effective networks of entrepreneurs and innovators building partnerships – For example in Kenya, the UK-Africa Knowledge Transfer Network and DCMS Techs Hubs (both co-funded through this programme) will form part of the HMG Innovation Cluster alongside the Global Innovation Fund tech hub and DFID Science, Technology and Innovation advisers.
2. Key barriers identified and addressed in each ecosystem- co-creating innovation ecosystem strengthening interventions with innovation ecosystem stakeholders to build sustainable solutions to key challenges (examples of types of challenge are shown in Table 1).
3. Strengthened technology and innovation policy and regulation - Engaging partner governments and the other stakeholders in the innovation ecosystem to diagnose challenges in policy and regulation and facilitate links to global networks of experts including the opportunity to draw on UK strength in innovation friendly policy and regulation. For example, this might include building on the Newton’s Fund Global Innovation Policy Accelerator or working with the UK’s Better Regulation Executive to support innovative regulatory pilots by African technology regulators.
4. Targeted research, analysis and learning on strengthening innovation ecosystems - Improving the evidence base to guide action on how to strengthen innovation ecosystem by commissioning targeted research, analysis and learning.

The exact indicators at output level will be informed by the commissioned research and determined in consultation with local stakeholders and national innovation strategies. The measurement framework will be agreed by the end of the programme’s inception phase. Example indicators include:

- Number of new IP/patents (through a simplified registration process)
- Increased speed in commercialisation of R&D
- Increased level of R&D investment
- Number of new market opportunities
- Innovations which are i) commercialised, ii) deployed and iii) scaled
- Increased investment and match funding (applications and receipt of funding from UK and elsewhere)

All outputs will be guided by the principle of ‘Leave No One Behind’. The programme will actively support greater inclusion and making sure that the innovation ecosystem works for everyone. This means supporting women and girls as innovators, as well as other groups who are under-represented in technology and innovation roles and will be vital in ensuring that solutions meet diverse needs and are responsive to the local context, conducting research and analysis specifically targeted at how to make technological innovation work for the most marginalised communities and linking to other DFID programmes that are supporting marginalised groups such as the new DFID programme ‘Assistive Technologies 2030’, ‘Mobile for Development’ and ‘Mobile for Humanitarian Innovation’ programme’s work on accelerating digital and financial inclusion for women, people with disabilities and refugees.

Through strengthening innovation ecosystems in Nigeria, Kenya, South Africa & adjacent countries, this programme will directly support the objectives of the science, technology and innovation enabler within the UK’s new approach to Africa. The long-term impact of the programme is increased development of emerging technologies, digital innovations and business models that support economic growth, jobs, trade, and development and contribute to the UK as a key partner to Africa for science, technology and innovation partnerships.

UK is well positioned to partner with governments and key stakeholders to strengthen innovation ecosystems in Nigeria, Kenya, South Africa & adjacent countries. UK is recognised as a thought leader in technology and innovation and can draw on a strong portfolio of existing technology and innovation programmes in these countries.

This programme is one of the commitments in the UK’s ‘International Research and Innovation Strategy’ that sets out how the UK will develop its international research and innovation partnerships to help achieve the targets in the UK’s modern Industrial Strategy. This programme will help to ensure that promising new innovations and technologies are better linked to entrepreneurs and policy makers on the ground in focus countries, and that local companies with potentially transformative innovations are given the tools and finance they need to scale. It will also address the SDG theme of building and investing in collaborative partnerships to tackle the greatest global challenges.

 Assurances

Table 2: Assurances
Gender Equality	The programme will fully comply with the Gender Equality Act, and partners will be required to demonstrate compliance. This will be monitored and reviewed annually. All data will be gender disaggregated. It will contribute to DFID’s strategic vision for girls and women, by increasing the ability of women and girls to be part of the innovation ecosystem as innovators and entrepreneurs; by supporting all innovators to consider the differing access to new technologies by women and men, and vulnerable populations and the differing effects of new technologies on women and men and vulnerable populations. As we finalise implementation arrangements for each element of this programme, we will ensure that those arrangements have the above considerations embedded within them and will be tracked as part of the results framework. The governance and operation of the programme will include women and girls as innovators, who are often under-represented in technology and innovation roles and will be vital in ensuring that solutions meet diverse needs and are responsive to the local context.
Counter Terrorist Financing	Support for partners will follow procedures established by the Civil Society Team and contained in DFID contracts and agreements for managing the risks associated with terrorism. DFID will ensure that the programme is consistent with relevant UK legislation, including the Terrorism Act (2000). Any suspicions of terrorism financing will be immediately reported to the Internal Audit Department.
Public Sector Equality Duty	This programme will support the advancement of equality of opportunity through ensuring women and girls, and other marginalised populations participate in innovation ecosystem as innovators and entrepreneurs. All programme workstreams will actively promote equality of opportunity and set out a PSED plan for annual review.
Climate and environment	This programme is not counted as climate finance, yet through removing barriers to scaling technological innovation, the programme will support new technologies that enable mitigation and adaptation to climate change and protect the environment. For example, this might involve supporting innovation policy and regulation that is climate smart.
Partnership Principles	There will be no direct funding to partner governments. In cases where this programme’s suppliers work with partner governments, we will ensure that an appropriate MOU that reflects relevant partnership principles is agreed
Disability	The programme will include support to tackle barriers to scaling technological innovation by people from the most marginalised communities, including those with disabilities and will address barriers to scaling of technological innovation that includes barriers to innovative assistive technologies.
Safeguarding	Safeguarding will be integrated into programme design and delivery to ensure that interventions that strengthen the technology innovation ecosystem do no harm e.g. perpetuate discrimination and inequality. DFID contracts, agreements and programme management will set out and assess safeguarding practices of partners, to check that the skills required to make such a judgement and the frequency with which organisational assessments are updated remain adequate and proportionate to the risks entailed

Appraisal Case

The strategic case sets out the importance of technological innovation for prosperity, serving poor and marginalised populations and achieving the sustainable development goals and the need to strengthen innovation ecosystems to catalyse and scale new technologies in Nigeria, South Africa, Kenya and adjacent countries.

This appraisal case sets out three thematic options and three delivery options for strengthening technology and innovation ecosystems in Nigeria, South Africa, Kenya and adjacent countries by tackling these barriers.

Thematic Options

1. Business as Usual (counterfactual). This scenario would mean the focus on African technology and innovation ecosystems would be through existing programmes.
2. Programme focuses on the partnerships and policy and regulation barriers –cross cutting barriers common to all three ecosystems
3. A programme with the scope and flexibility to identify and address critical barriers for each country based on opportunity, demand and UK comparative advantage in the innovation ecosystem. (Recommended)

Criteria

These options have been appraised against the following criteria:
- Does it address a critical gap, that is not addressed by the UK ODA portfolio or other funders?
- Does it have the appropriate breadth of scope vs depth of focus?
- Does it respond to context?

Thematic Appraisal

Option 1: There is a broad portfolio of UK ODA funded programmes that support technology and innovation in Africa (see Annex X). These programmes both centrally managed and country based are mostly focused on specific sectors such as education, agriculture, energy or financial inclusion or they are specific partnerships with organisations like the GSMA, (mobile operator industry body), Shell Foundation, Acumen or Unilever. There are also broader programmes like the Global Innovation Fund that provide support to innovators across sectors. Each programme has unique strengths that build a part of the technology and innovation ecosystem, but none look across the whole ecosystem and not all are in the programme’s focus countries; Nigeria, Kenya and South Africa.

There are two main gaps in the portfolio. The first is a focus on strengthening the enablers to scaling technological innovation. The current portfolio mostly focuses on early stage investment, mentoring and other support to early stage technology entrepreneurs rather than on wider systemic barriers and taking businesses through each stage of the innovation pathway. The second is that many programmes are sector specific, significantly limiting the opportunity ability to connect and learn across the portfolio or address higher-level barriers.

The ‘business as usual’ option would avoid the cost of setting up a new programme. It would not focus on the specific ecosystems of Nigeria, Kenya and South Africa or enable a look across sectors, geographies and technologies and flexibly identify gaps and address barriers. Without a programme looking across the technology and innovation ecosystem and actively connecting similar initiatives, there will be a lack of focus on barriers to scaling technological innovation in that context, increasing the chance of duplication and lost opportunities for learning.

Option 2: Focusing the programme on new partnerships and networks across sectors, geographies and technologies in each context to stimulate collaboration, learning and business opportunities between stakeholders. Partnerships and networks are a well-recognised enabler for addressing other problems within the technology and innovation ecosystem. Policy and regulation are similarly also cross cutting themes for each context, as lack of effective policy and regulation are key blockers across skills, market access, infrastructure and investment. The specific policy and regulatory barriers will be different in each setting. Focusing on the two areas of networks and policy and regulation would enable this programme to go deeper into solving those challenges than focusing on all six of the barriers identified in Table 2.

The increased depth could potentially lead to increased ability to create change leading to significantly better partnerships, networks, policy and regulation than a broader approach. Although this programme would address two areas of key enablers for ecosystems it would not be able to respond to issues arising around other barriers. This would limit the overall opportunity for impact because these issues may not be the critical barriers in the context. Given the complexity and quickly changing nature of technological innovation and the political, economic and social context, it is important to understand the political economy for change in order to predict what opportunities will be the most tractable and require support.

Option 3: A programme with the scope and flexibility to identify and address critical barriers in the innovation ecosystem (across partnerships, skills and knowledge, investment, policy and regulation, market access and infrastructure) based on opportunity, demand and UK comparative advantage would ensure that it was context specific and responding to local need. Being able to react to a complex and changing technological, political, economic and social context across barriers makes it more likely that the programme will be able to support solutions that are best able to deliver tangible results. The programme would also be able to respond flexibly within each context to the major barriers and not duplicate existing programmes on the ground. Addressing critical barriers in response to the context requires engaging and connecting a wider range of stakeholders, leading to a larger network and increasing the potential for learning and collaboration. Addressing critical barriers for the context means being able to take advantage of synergies between solutions. For example, solving the problem of a lack of investment in early stage tech start-ups might require an approach that considers regulation, finance, skills and infrastructure together. Taking a whole system approach and connecting across initiatives and sectors is especially important at a time when we are seeing a proliferation of technology and innovation projects.

The risks of this approach are that the greater scope could reduce the depth into which the programme can tackle each barrier and it increases the complexity of monitoring programme performance. Having a greater scope could reduce the chance of delivering results. It also means that to successfully deliver the programme requires a wider range of expertise, which are likely to increase programme costs. Careful prioritisation of critical barriers which are tractable to change in each setting will be required to mitigate these risks.

Thematic Choice: Options 2 and 3 are preferred to option 1 (‘do nothing’) because there is a gap in the UK ODA technology and innovation portfolio that focuses on strengthening technology and innovation ecosystems in the three focus countries.

Option 3 is recommended because taking an approach that addresses critical and tractable barriers in each context:
- Addresses the gap in the UK ODA portfolio of a programme that strengthens the enablers to scaling technological innovation and connects across technology, innovation and investment programmes at a time when there are a growing number of technology, innovation and investment initiatives.
- Responds flexibly to technological, political, economic and social context and develops synergies between different problems in the technology innovation ecosystem.
- The benefits of responding to context in greater flexibility and ability to connect different innovation ecosystem strengthening initiatives outweigh the risk that insufficient depth of resources and focus on a particular barrier will prevent delivery of results.

Delivery Options
Three delivery options were considered for thematic option 3:
1. A managed fund that would fund sustainable solutions with innovation ecosystem stakeholders in focus countries to strengthen the enablers of technological innovation. This means working with stakeholders such as policymakers, tech hubs, entrepreneurs, investors or universities to design and implement interventions that can strengthen the innovation ecosystem enablers.
2. Partnership with UK programmes that would address a specific area of the technology and innovation ecosystem This will include:
  1. Growing networks and building partnerships through Innovate UK’s Knowledge Transfer Network (KTN), a large, established network of UK innovation stakeholders working with more than 37,000 organisations and 92,000 individuals from large and small companies, government agencies, research and innovation organisations, funding bodies and private investors in the UK. DFID partnership with KTN will enable effective linkages to in depth country experience and connections through DFID’s country offices in Nigeria, Kenya and South Africa, strengthened by new science, technology and innovation teams, and by synergies with the other elements of this programme.
  2. Supporting digital skills development and particularly for women through the Department for Digital, Culture, Media and Sport (DCMS) Tech Hubs which based in South Africa, Nigeria and Kenya.
  3. Further potential partnerships include with the Newton Fund, Innovate UK and the Science and Innovation Network on their Global Innovation Policy Accelerator and the Better Regulation Executive on their Regulator’s Pioneer Fund. These will be scoped out during the first 6 month of the programme.
Alongside this the programme will include
  1. Strengthening technology and innovation policy and regulation through a competitively procured specialist team;
2. Mixed approach – Ensuring a mixed portfolio of ‘quick wins’ through partnership with specialist UK expertise in specific areas of the technology, innovation and investment system and alongside this having a flexible responsive fund to cover key critical barriers identified for each setting (recommended).

Standard economic appraisal methods, such as cost-benefit analysis, require the identification, quantification and assignment of monetary value to at least some costs and benefits. Technology and innovation system strengthening does not lend itself to formal cost benefit analysis for the following reasons:
- The total number of ultimate beneficiaries cannot be identified at the start of the programme because while we expect the programme to lead to improvements to the technology and innovation ecosystem, we do not know at this stage what these improvements will be and who they will affect. The Theory of Change is based on increasing the numbers of businesses passing through to the next stage of the innovation pathway. Measuring this is complex and underlines the need for a robust research and monitoring component.
- The impacts of system strengthening on technologies scaling are likely to take many years;
- The technology and innovation ecosystem and results chain are complex, and change relies on multiple factors (including political and economic environment).

Due to these challenges there is no reasonable methodology to conduct a detailed cost-benefits analysis of the options, the aim of which would be to select a preferred option by comparing the ratio of benefits to costs for each option. Instead we select a preferred option based on an appraisal of the relative strengths of each option according to a set of explicit criteria.

Criteria

Ability to engage local stakeholders: The ability to sustain engagement with innovation ecosystem stakeholders is key to success in strengthening the innovation ecosystem enablers. It is only through engaging local stakeholders that we can navigate the incentives for stakeholders to support or block reform, draw upon their experience and networks and collaborate to leverage additional resources.
- Ability to leverage UK expertise and networks: The UK has significant strength in technology and innovation within UK business, academia and government. Successfully leveraging this strength, through connecting with existing UK innovation networks, would enable win-win partnerships with stakeholders in the technology and innovation ecosystems in Kenya, Nigeria, South Africa and adjacent countries.
- Control over risk and delivery: What are the opportunities available to measure and manage performance and delivery risk?
- Timing: How long before the programme can start?
- Social and poverty impacts:
- Gender equality:

Each criterion is weighted (all criteria sum to 100) and scored in the table below.

Table 3: Criteria
Criteria	Managed Fund	Specialist teams	Mixed Approach
Ability to engage local stakeholders (Weight: 30)	A managed fund approach is well suited to testing innovative ideas through locally led, designed and owned solutions that leverages local expertise, influence and resources. (25)	There are activities necessary to strengthen technology and innovation ecosystems which are better served by long term specialist engagement and relationship building than more rapid testing. Examples of such activities are building networks and partnerships; research, learning and analysis and engagement with policymakers and regulators. (20)	Would balance the benefits of a managed fund with those of specialist teams for long term engagement at the cost of designing and managing a more complex programme. (30)
Ability to leverage UK expertise and networks (Weight: 20)	Leveraging UK expertise and networks would be more challenging with a managed fund approach. It would also potentially duplicate existing initiatives from Innovate UK and DCMS in Nigeria, Kenya and South Africa. (5)	Co-funding and working with existing initiatives that can leverage UK expertise, funding and networks such as KTN and the DCMS tech hubs would increase VfM and enable us to develop a more ambitious programme, aligned with a one HMG fusion approach. (20)	Would enable the programme to leverage UK expertise, funding and networks such as KTN and the DCMS tech hubs but not with as much depth as the specialist teams approach. (15)
Control over risk and delivery (Weight: 10)	DFID has less direct control over delivery and risk as there is an extra layer in the delivery chain. (0)	Greater control over delivery and risk as DFID has a direct relationship with the implementing supplier. (10)	Harder to manage multiple teams and get coherence across the programme. (5)
Timing (Weight: 10)	Slower as there is a need to contract the fund supplier and then design and set up the fund before being able to start implementation of innovation ecosystem strengthening solutions (0)	Faster start for KTN and DCMS as they could be allocated funding through an MOU. (10)	Staggered approach is useful as the networks built by KTN and DCMS will be needed by the managed fund and other specialist teams. (10)
Social and poverty impacts (Weight: 20)	Social and poverty impact are likely to similar between the managed fund and specialist teams approach. / Managed Fund: Greater flexibility and being more locally led would enable greater ability to draw upon local stakeholder experience and networks and collaborate to leverage additional resources. In the commissioning model we can set criteria for the funding to ensure that they target social and poverty impacts and monitor delivery against them (10) / Specialist teams: Long-term engagement and specialist expertise in building networks, research and in policy and regulation would enable greater continuity, relationship building and learning in these areas. (10)		Likely to have the greatest social and poverty impacts as the benefits of the managed fund approach and the benefits of specialist teams complement one another (20)
Gender equality / (Weight: 10)	Gender equality impact is likely to similar between the managed fund and specialist teams approach. / Managed Fund: In the commissioning model we can set criteria for the funding windows to ensure that the managed fund increases female participation in the innovation ecosystem. (5) / Specialist teams will build expertise in how to increase female participation in the technology and innovation ecosystem and the differing effects of new technologies on women and men. (5)		Likely to have the greatest ability to affect gender equality as it can increase inclusion both through locally led projects and through a longer-term focus on research, policy and networks. (10)
Total Score	45	75	90 (preferred option)

Preferred Option

The preferred option is for thematic option 3 (addressing all six barriers in Table 2) and delivery option 3; to combine a managed fund approach with procurement of specialist teams for partnerships, research, analysis and learning and policy and regulation.

Thematic option 3 was chosen because the benefits of responding flexibly to the context and the enhanced opportunities to develop synergies between different enablers in the technology innovation ecosystem outweigh the risk that insufficient depth of resources and focus on a particular barrier will prevent delivery of results.

Delivery option 3 was chosen as it scored highest against the criteria and balances the benefits of the managed fund approach i.e. testing locally led solutions that leverage expertise, networks and resources from stakeholders in the innovation ecosystem; with the benefits of specialist teams with a long-term commitment to specific functions such as commissioning research, building networks and engaging policy makers and regulators. It takes advantage of the UK-Africa Knowledge Transfer Network that builds on the existing expertise in developing technology and innovation networks and has an extensive network of innovation stakeholders in the UK. It also takes advantage of the DCMS Tech Hubs existing digital projects and networks in the South Africa, Kenya and Nigeria.

This delivery option involves a more complicated management process to ensure coordinated activity, but the risks can be mitigated by the strength of DFID science, technology and innovation teams on the ground in Kenya, Nigeria and South Africa and a programme funded post that will focus on coordination between the different teams.

Theory of Change for Preferred Option

Situation Analysis

The importance of new technologies in Africa is increasing both in terms of opportunities for inclusive, sustainable growth and risks of increased inequality, marginalisation and exclusion. The rate of change of the emergence and adoption of new technologies is increasing which means that countries will have decreasing windows of time to adapt. South Africa, Kenya and Nigeria are regional hubs for technology and innovation. These countries are at the forefront of testing out new approaches and dealing with systemic problems in the technology and innovation ecosystem. The strength of their technology and innovation ecosystems e.g. their ability to invest in or regulate promising new technologies, will affect their ability to realise the opportunities and protect against the risks of technological change. Despite the rapid growth in technology businesses there are still significant barriers to taking technological innovation to scale. The Theory of Change of this programme is based on understanding those barriers and enablers in the innovation ecosystem. Each geographic setting requires research, analysis and engaging with local technology and innovation ecosystem stakeholders to identify and map what existing initiatives are underway and then catalyse action in areas where gaps remain and where action is tractable.

An underlying assumption is that taking on and solving all barriers is beyond the ability of this programme in isolation but that it is possible for well targeted catalytic funding and actions to drive change. This programme will act as a super-connector linking and supporting other initiatives that are addressing barriers to technological innovation by connecting them and by identifying and developing solutions to unaddressed problems. This will include partnering closely with DFID country offices and other parts of HMG to ensure a joined-up approach. In each focus country, the programme will work closely with sectoral initiatives like Transforming Energy Access (TEA), Ayrton Fund, EdTech Hub, Enhancing Digital and Innovation for Agrifood Systems and Livelihoods (eDial) and Financial Sector Deepening Africa and will take a structured approach to mapping the breadth and depth of both the HMG portfolio and wider initiatives in order to provide a solid foundation for partnering and collaboration.

Figure 3: Theory of Change Diagram
This programme will respond to the country context including other relevant initiatives and the political, economic and social environment. Therefore, it is not feasible to state which barriers will be addressed in which country/region up front. Instead the programme will implement a structured, multi-stakeholder process[5] that engages a broad range of innovation ecosystem stakeholders in developing a shared understanding, vision and plan to catalyse wider efforts in strengthening the innovation ecosystem enablers.
[5] See https://www.pmsdroadmap.org/ for information on multi-stakeholder processes being used for participatory market system development.

There are three stages to the multi-stakeholder process:
- Preparation –build a clear picture of the innovation ecosystem to facilitate the consultation stage. This will involve analysis to better understand the key stakeholders and relationships, the structure and main characteristics of the ecosystem and the systemic enablers, opportunities and risks (Output 4). It will also involve building working relationships with key stakeholders to partner on the consultation and action stages (Output 1).
- Consultation – facilitate dialogue between stakeholders to develop a shared understanding of the innovation ecosystem and develop a shared vision and plan for action. This will involve a series of workshops in Kenya, Nigeria, South Africa and adjacent countries; each building on the last. It will explore alternative approaches to facilitate dialogue such as online engagement tools (Output 1). This will identify key sectors and opportunities for strengthening the innovation ecosystem, including assessments of their potential impact.
- Action – catalyse wider efforts in strengthening the innovation ecosystem enablers through four grouped outputs informed by the shared vision and plan.
  - Output 1: Growing networks and building partnerships - to enhance learning, collaboration and investment opportunities. This means working with partners in country to strengthen the networks of innovation ecosystem stakeholders that connect those stakeholders across geographical and sectoral silos; including with the UK innovation ecosystem.
  - Output 2: Innovation ecosystem strengthening projects and platforms - co-creating innovation ecosystem strengthening projects and platforms with innovation ecosystem stakeholders to build sustainable solutions to key challenges. This means working with stakeholders such as policymakers, tech hubs, entrepreneurs, investors or universities to design and implement projects that can strengthen the innovation ecosystem enablers
  - Output 3: Strengthen technology and innovation policy and regulation - Engage partner governments and the other stakeholders in the innovation ecosystem to diagnose challenges in policy and regulation. Facilitate links to global networks of experts including the opportunity to draw on UK strength in innovation friendly policy and regulation. Support the testing of new policy and regulation.
  - Output 4: Research, analysis and learning - Improve the evidence base to guide action on how to strengthen innovation ecosystem by commissioning targeted research, analysis and learning.

The multi-stakeholder process is a cycle with the learning from the outputs continuing the development of our understanding of the innovation ecosystem and informing future consultation with key stakeholders. The 6-month inception phase will include the initial consultation phase, the detailed assessment of country innovation ecosystems and the planned future interventions for innovation system strengthening and will be agreed with the high level steering group.

All outputs will be guided by the following principles:
- Leave No One Behind – making sure the innovation ecosystem works for everyone. This will include:
  - Connecting civil society groups with other stakeholders in the innovation ecosystem through developing new networks and partnerships.
  - Innovation ecosystem strengthening projects that will focus on supporting women and girls as innovators, as well as other groups who are under-represented in technology and innovation roles and will be vital in ensuring that solutions meet diverse needs and are responsive to the local context.
  - Research and analysis specifically targeted at how to make technological innovation work for the most marginalised communities.
  - Linking to other DFID programmes that are supporting marginalised groups such as the new DFID programme ‘Assistive Technologies 2030’ and the ‘Mobile for Development’ programme’s work on accelerating digital and financial inclusion for women.

- Adapting to context
  - Making sure we get the buy-in of local innovation ecosystem stakeholders is critical to the success of the programme. Only by working with them will we understand what will work by drawing on their skills, experience and networks and magnify the impact of the programme by leveraging existing resources.
  - Linking and working with other development programmes that aim to strengthen the innovation ecosystem. There are many existing programmes that work on some aspect of innovation ecosystem strengthening. This programme will reach out to other initiatives to ensure greater collaboration and synergy.

What measures can be used to assess Value for Money (VfM)?

Table 4: VfM Metrics
VFM Metrics	How VFM is assessed/measured
Economy –whether the project has bought inputs of the appropriate quality at the right price?	The main cost drivers for projects supported by this business case are: / Labour costs, particularly linked to technical support, data collection; supervision and mentoring / Travel and subsistence, and costs of meeting / Other system development costs, including equipment / Overheads / Admin and running costs associated with managing research activities and ecosystem strengthening pilots. / The preferred option comprises two delivery routes: / DFID will run an open competition for a supplier or consortium to deliver the managed fund, research, analysis and learning activities and policy and regulation capacity building. We will work closely with PCD to design a procurement strategy that considers mechanisms to support successful delivery to the right standard, within budget, and on time (e.g. strategic oversight, clarity on deliverables, risk management, financial management, Key Performance Indicators, and monitoring of performance). Suppliers will be asked to prepare a full technical and commercial proposal based on maximum results for a stated budget. Bidders will be encouraged to form consortia where this strengthens the offer, with a clearly designated Lead Supplier who will be responsible for overall delivery and technical oversight. / An MOU with Innovate UK for the UK-Africa Knowledge Transfer Network will build on the established governance and administrative processes they already have with Innovate UK to ensure they are in accordance with DFID Smart Rules and are driving economy in the cost drivers for the UK-Africa Knowledge Transfer Network. / An MOU with the Digital Access Programme for the DCMS Tech Hubs will use established governance and administrative arrangements DCMS tech hubs have with the Digital Access Programme that are already in accordance with DFID Smart Rules.
Efficiency- how well the project is converting inputs into outputs? (‘Spending well’)	The exact indicators at output level will be informed by the commissioned research and determined in consultation with local stakeholders and national innovation strategies. The measurement framework will be agreed by the end of the programme’s inception phase. Example indicators include: / Output 1 - Larger and more effective networks of entrepreneurs and innovators building partnerships - This will be measured by: / Increase in size of technology, innovation and investment stakeholder networks; / Increase in the effectiveness of networks through the number of new stakeholder partnerships facilitated; / Output 2 - Critical (or key) barriers identified and addressed in each ecosystem- co-creating innovation ecosystem strengthening projects with innovation ecosystem stakeholders to build sustainable solutions to key challenges. This will be measured by: / Number of critical barriers identified then competitions and/or sustainable projects supporting innovation ecosystem enablers completed. Each project will have its own performance metrics, including on improving access for disadvantaged groups. For example, a project strengthening skills might have the number of people trained who find jobs in the innovation ecosystem. / Number of detailed case studies assessing pathway to impacts for projects tackling a critical enabling factor in the innovation ecosystem. / Number of documented case studies demonstrating sustainable projects that have increased the inclusiveness of the innovation ecosystem e.g. women supported to participate in the innovation ecosystem. / Output 3 - Strengthened technology and innovation policy and regulation - Engaging partner governments and the other stakeholders in the innovation ecosystem to diagnose challenges in policy and regulation and facilitate links to global networks of experts including the opportunity to draw on UK strength in innovation friendly policy and regulation. This will be measured by: / Number of documented diagnostic analyses of policy and regulatory systems. / Number of policymakers supported to enact evidence-based innovation policy, with documented case studies of change / Number of documented case studies of improved technology and innovation policy and regulation. / Output 4 - Targeted research, analysis and learning on strengthened innovation ecosystem - Improving the evidence base to guide action on how to strengthen innovation ecosystem by commissioning targeted research, analysis and learning. This will be measured by: / Number of case studies demonstrating influence of commissioned research projects in changing behaviours in the innovation ecosystem; / Milestone based improvements in the frameworks and tools for monitoring country technology and innovation portfolios and mapping innovation ecosystem activity. / A robust methodology and data collection mechanism for measuring the improvement of the enabling factors in the innovation ecosystem will be developed. This will be developed in partnership with other stakeholders and become a public good providing insight to stakeholders across the innovation ecosystem. / Number of learning and analytical reports commissioned and communicated across the innovation ecosystem; / In addition, to output performance metrics, each supplier will develop a monitoring strategy with more detailed performance metrics. The DFID management team will review the monitoring strategy to ensure that the programme remains on track to deliver the outputs. / A comparison will be run on quantity, quality and timeliness of outputs with comparable interventions such as funds or research commissioning programmes. / The programme will measure the amount of funds leveraged from other organisations. Under the preferred option DFID funds support the UK-Africa Knowledge Transfer Network that will be co-financed by the Global Challenges Research Fund through Innovate UK.
Effectiveness- how well the outputs produced have had the intended effect/ achieved the outcome? (‘Spending wisely’)	The strength and efficacy of technology and innovation system strength outcomes are difficult to measure as there are many factors that determine it. The programme will take both a top down and a bottom up approach to assessing VfM. In the top down approach, we can use established metrics like the Global Competitiveness Index or Global Innovation Index. The bottom up approach will monitor the output level indicators for programme activities such as pilots, workshops, research, learning and analytical reports. There will be specific performance indicators for each activity / This programme will support the development of tools and frameworks for assessing the strength of the technology and innovation ecosystem within the first year of the programme and use those tools and frameworks to determine the contribution and influence of the programme. Through a survey of stakeholders in the technology and innovation ecosystem we will estimate the contribution of programme outputs to outcomes.
Equity - ensuring that the programme is inclusive.	The principle of leave no one behind will be embedded across the programme. This will be assessed through both qualitative and quantitative metrics such as: / the number of research and analytical reports that improve understanding of what works in making innovation ecosystems more inclusive e.g. an analysis of the barriers for women innovators and entrepreneurs. / Criteria within managed fund selection process that increases participation of marginalised groups. / the number of innovation ecosystem strengthening projects that improve access to the innovation ecosystem for marginalised groups. / the number of new innovations that target marginalised groups or involve marginalised groups in their design. / The programme will increase the ability of women and girls to be part of the innovation ecosystem by supporting all stakeholders in the innovation ecosystem to consider the differing access to and the differing effects of new technologies on women and men. For example, the managed fund will require that all applications for funding set out how they increase the ability of women and girls to be part of the innovation ecosystem. / This will be tracked as part of the results framework. For example, within the logframe there will be a performance indicator that tracks the number of documented case studies demonstrating co-created sustainable projects that have increased the inclusiveness of the innovation ecosystem, e.g. women supported to participate in the innovation ecosystem. / The governance and operation of the programme will include women and girls as innovators, who are often under-represented in technology and innovation roles and will be vital in ensuring that solutions meet diverse needs and are responsive to the local context.

Summary value for money statement

“Innovation is a complex process. It starts with the generation of ideas, some of which lead to inventions, and only a few of which are ever commercialised. Innovations enhance economic productivity only if they reach the desired markets and achieve commercial success. Innovation takes place within an ecosystem of multiple factors. Any factor missing from the innovation ecosystem can prevent new ideas from being generated or evolving into viable commercial products.”[6]
[6] http://www3.weforum.org/docs/GCR2018/05FullReport/TheGlobalCompetitivenessReport2018.pdf

This programme will achieve VfM by supporting the enabling factors at each stage of the journey from idea to scaled commercial technology. Through new partnerships, pilot projects, better evidence on what works and improved policy and regulation, the programme will address those points of failure in the process that would otherwise lead to the attrition of promising new technology products and services. This will lead to more businesses at each stage of the pathway to scale enabling new technologies to reach the poorest and most marginalised people and creating new jobs and economic growth.

There are a number of feedback loops that if established will create even greater VfM:
- Innovators and businesses that take a technology to scale learn a lot in the process. New innovators and businesses are more likely to be successful if they have access to the experience of those that have already achieved success. This can happen through mentorship or employees starting their own businesses.
- Successful commercial technology products and services generate capital and provide a demonstration effect. This leads to increased investment in technological innovation and sends a signal to government, banks, corporates, investors and would be entrepreneurs that it is possible to create a business that can successfully grow and scale through the smart use of technology.

The programme will take both a top down and a bottom up approach to assessing VfM. In the top down approach, we will use established metrics like the Global Competitiveness Index or Global Innovation Index and complement those indices with analysis that tracks technologies through the pathway to scale.
- The Global Competitiveness Index has a range of indicators that assess an economy’s innovation ecosystem under its Innovation capability and Business dynamism pillars.
- The Global Innovation Index provides 80 detailed metrics on the multidimensional facets of innovation-driven growth. It is an annual ranking of countries by their capacity for, and success in, innovation.
- The programme will commission the development of a robust methodology and data collection mechanism for measuring the improvement of the enabling factors in the innovation ecosystem. This will be developed in partnership with other stakeholders and become a public good providing insight to stakeholders across the innovation ecosystem. This analysis will enable the assessment of outcome level indicators of innovation ecosystem health.

The bottom up approach will monitor the output level indicators at both programme level through the logframe (see Annex 2) and through more detailed monitoring strategies with each partner and supplier that will be agreed at the design stage.

Commercial Case

Why is the proposed funding mechanism/form of arrangement the right one for this intervention, with this development partner?

The recommended option involves a combination of procurement routes:
1. Innovation Ecosystem Partnerships through MOUs. This includes MOUs with:
  1. Innovate UK to fund the UK-Africa Knowledge Transfer Network;
  2. The Digital Access Programme to fund the DCMS Tech Hubs.
2. Direct procurement of a supplier/consortium to deliver:
  1. An Innovation Ecosystem Fund – a managed fund for funding and co-creating sustainable solutions with innovation ecosystem stakeholders to barriers to technological innovation.
  2. Technology and Innovation Policy and Regulation strengthening.
  3. Innovation Ecosystem Research, Analysis and Learning– funding research, analysis and learning to inform the strengthening of innovation ecosystems.
3. A programme funded Knowledge Coordination manager to sit within one of the programme suppliers. The location will be determined in consultation with key programme stakeholders within the first six months.

MOU with Innovate UK to fund the UK-Africa Knowledge Transfer Network

The BEIS-led Global Challenges Research Fund (GCRF) through Innovate UK as part of UK Research and Innovation has awarded £5m over 6 years to develop the UK-Africa Knowledge Transfer Network. DFID will provide £5 million as co-funding UK-Africa KTN with Innovate UK to deliver a more ambitious project extending the approach in Africa and aligned with a one-HMG fusion approach. DFID’s funding ensures effective linkages to in depth country experience and connections through its country offices in Nigeria, Kenya and South Africa and this will be strengthened by new science, technology and innovation teams and by the other elements of this programme. This will prove invaluable to UK-Africa KTN in understanding and engaging with both the local and the international development actors and context. This partnership brings together DFID’s experience and networks in international development and Innovate UK’s experience and networks in technology and innovation.

Co-funding the UK-Africa Knowledge Transfer Network with Innovate UK will:
- utilise the Knowledge Transfer Network’s expertise in building innovation networks and large existing network of UK innovation stakeholders. KTN works with more than 37,000 organisations and 92,000 individuals from large and small companies, government agencies, research and innovation organisations, funding bodies and private investors. This makes KTN uniquely placed to develop and empower new country-based knowledge transfer networks and act as the bridge between UK innovation stakeholders and those in African innovation ecosystems.
- enable DFID to draw upon Innovate UK’s expertise and networks in technology and innovation.
- Increase the ambition of the UK-Africa Knowledge Transfer Network and ensure alignment with the one HMG fusion approach.

Working in partnership with the key national research and innovation government stakeholders to agree a clear shared vision and objectives and building on existing research and innovation relationships created and managed across HMG, UK-Africa KTN will engage innovation stakeholders to build a network capable of enabling knowledge transfer between stakeholders. The funding will enable UK-Africa Knowledge Transfer Network teams based in Kenya, Nigeria, South Africa to deliver the following activities:

- the development of this network in three countries in Africa provides an opportunity for research and innovation collaboration between African countries through targeted matchmaking between stakeholders leading to new business to business and business to research innovation dialogues, collaboration and partnerships generated between innovation stakeholders; to develop innovation, prosperity and investment partnerships.
- convene innovation stakeholders at events to enable increased networking and collaboration;
- provide case studies, share cross-sector and innovation intelligence, publish insights reports and success stories.
- provide strategic analysis & mapping of the innovation ecosystem in partnership with local key stakeholders;
In addition, this will provide country-based innovation stakeholders, including DFID country offices, with effective access to the entirety of UK’s innovation network.

DFID will sign an MoU with Innovate UK, one of the constituent councils of UK Research and Innovation, an executive non-departmental public body (NDPB). This approach, in accordance with DFID Smart Rules, is consistent with current DFID joint initiatives, such as with Innovate UK and Agri-Tech, Innovate UK and the Energy Catalyst and with the Research Councils (for example EPSRC).

How will the Partners be managed?

Under the MoU, Innovate UK will manage and administer funds on DFID’s behalf in accordance with their rules and regulations. The MoU will cover and govern the implementation of this component of the Africa Technology and Innovation Partnerships programme including formal reporting requirements of partners so that the DFID management team has a clear line of sight on progress against proposed outputs, outcomes and project managerial and financial information. A joint DFID and Innovate UK project management board will meet quarterly to approve high level strategies, work plans and budgets and maintain oversight of the programme’s implementation and performance. Innovate UK has demonstrated its track record in managing and disbursing funds through the Knowledge Transfer Network, including having robust financial forecasting and reporting mechanisms in place.

MOU with Digital Access Programme to fund the DCMS tech hubs

The ATIP Programme will establish a collaborative partnership with the Prosperity Fund Digital Access Programme (DAP), through its Tech Hub component as this offers a platform for the two interventions to work together and complement each other in strengthening the tech and digital ecosystems and promoting tech and digital for development in Kenya, Nigeria and South Africa.

The Digital Access Programme is led by DFID and delivered in partnership with FCO and DCMS. With a total budget of up to £82.5m over four years, it aims to catalyse inclusive, affordable, safe and secure digital access for excluded or underserved populations in Kenya, Nigeria, South Africa, Brazil and Indonesia; and to use digital inclusion as a basis for a more thriving digital ecosystem that will stimulate innovations for local development challenges, create local skilled jobs and generate opportunities for business partnerships. The programme is articulated into three interconnected pillars and coordinated through one programme governance structure. The DCMS-led Pillar 3 ‘Sustainable Digital Ecosystems’ (up to £7.5m) will stimulate local digital economies and support local tech entrepreneurs to find innovative solutions to local development challenges (‘tech for good’) and forge partnerships between local start-ups and international businesses (including UK firms) through a Tech Hub network to drive inclusive and sustainable economic growth.

DFID will provide up to £3m as co-funding to the DCMS Tech Hubs, bringing the total across the two programmes to £10.5m. The partnership, also working with the UK-Africa KTN, will enable wider networks, shared learning and a more joined up approach to engaging the innovation ecosystem stakeholders. DFID co-funding will enable the DCMS tech hubs to scale up projects that support both the DCMS tech hub and ATIP objectives such as in the areas of digital skills building and sharing UK expertise and best practice to equip entrepreneurs, start-ups and established companies with the right skills, preparation, mentoring and introductions to grow and go global through partnership with UK and other international companies. This will allow both ATIP and the DAP to deliver greater impact.

How will the Partners be managed?

Under the MoU, DCMS will manage and administer funds on DFID’s behalf in accordance with their rules and regulations. The MoU will cover and govern the implementation of this component of the Africa Technology and Innovation Partnerships programme including formal reporting requirements of partners so that the DFID management team has a clear line of sight on progress against proposed outputs, outcomes and project managerial and financial information. A joint ATIP and DAP project management board will meet quarterly to approve high level strategies, work plans and budgets and maintain oversight of the programme’s implementation and performance.

Direct procurement of suppliers/consortium

The recommended option includes direct procurement through a competitive process for suppliers or a consortium to deliver against the following strands of work:
  1. An Innovation Ecosystem Fund - co-creating and funding sustainable solutions with innovation ecosystem stakeholders to barriers to technological innovation.
  2. Technology and innovation policy and regulation strengthening;
  3. Innovation Ecosystem Research, Analysis and Learning– funding research, analysis and learning to inform the strengthening of innovation ecosystems.
  4. There is an additional component under the Business Proposition included up to £200k for initial design, scoping and consultation.

Initial conversations with suppliers suggest there are enough suppliers capable of delivering these projects to suggest a competitive procurement route. DFID will run an early market engagement event to confirm whether this is the case and what the best procurement strategy to deliver them is.

The Innovation Ecosystem Fund will be key to addressing Output 2, ‘Critical barriers identified and addressed in each ecosystem - co-creating innovation ecosystem strengthening projects with innovation ecosystem stakeholders to build sustainable solutions to key challenges.’ To successfully achieve this the managed fund will need to work with and alongside local innovation ecosystem stakeholders both to understand what will work by drawing on their skills, experience and networks and to magnify the impact of the programme by partnering with them and leveraging existing resources. The Innovation Ecosystem Fund will ensure that the projects selected can build upon each other and actively identify synergies to become more than the sum of their parts through targeted joint workshops.

The Innovation Ecosystem Fund will also address Output 3: ‘Strengthened technology and innovation policy and regulation - Engaging partner governments and the other stakeholders in the innovation ecosystem to diagnose challenges in policy and regulation and facilitate links to global networks of experts including the opportunity to draw on UK strength in innovation friendly policy and regulation’ by managing project(s) focused on this output. Examples of UK strength in innovation friendly policy and regulation include the ‘Better Regulation Executive’ in the Department for Business, Energy and Industrial Strategy and UK standards institutes and agencies.

DFID funding will cover both administration costs for running the programme and programme costs for managing and deploying the fund. This will involve consultation and co-creation with innovation stakeholders and supporting and providing oversight of the selected projects. The supplier will develop/refine projects agreed through the consultation and prioritisation process. These will be reviewed by independent experts and the in-country advisory group. The overarching governance body will approve allocation of funding. As part of the fund design, there will be a 6-month inception phase. This will enable the winning supplier to invest in further design, conduct further consultation with key stakeholders (including DFID country offices), and prepare a detailed work-plan that sets out key milestones. After the six-month inception phase there will be a break point. The assessment of the country innovation ecosystems and the planned interventions for innovation ecosystem strengthening will be agreed by a high-level steering group. Provided the supplier meets all expected standards, and DFID considers that there is still value in the programme approach, the contract will continue with the agreed funds for the next stage of work. All elements of the programme should be extensible and scalable if successful; both through future UK ODA funding and through funding from other donors.

Innovation Ecosystem Research and Analysis will be key to addressing Output 4: Research, analysis and learning’. There is limited evidence of what works in strengthening the enablers of technological innovation due to the complexity of innovation ecosystems and rapid changes in technological context. A research partner or consortium will be procured through a competitive grant process to develop a programme of applied research across the three countries to build the evidence base of what works, looking particularly at how to assess impact. In addition to research and analysis, the research partner/consortium will also provide independent advice on the monitoring of the programme, embedding analysis within this to help measure the project outcome and advising on the quality and scope of monitoring for each component. DFID funding will cover both administration costs for running the programme and programme costs for commissioning and managing the research and analysis projects.

Scoping and consultation include the initial testing of the approach and consultation with innovation ecosystem stakeholders and mapping of the ecosystem prior to the start of the other programme strands. There will also be a need for a small amount of additional scoping and consultation throughout the programme duration to be responsive to the needs of HMG country-based science, technology and innovation teams.

We will work closely with PCD to design a procurement strategy that considers mechanisms to support successful delivery to the right standard, within budget, and on time (e.g. strategic oversight, clarity on deliverables, risk management, financial management, Key Performance Indicators, and monitoring of performance). Suppliers will be asked to prepare full technical and commercial proposals based on maximum results for a stated budget. Bidders will be encouraged to form consortia where this strengthens the offer, with a clearly designated Lead Supplier who will be responsible for overall delivery and technical oversight. Once the preferred bids have been selected, DFID will undertake a Due Diligence assessment of the suppliers, who will hold the contract with DFID, and are ultimately responsible for the delivery of the contract.

Where there is a consortium, the Lead Supplier will be accountable for the overall performance and delivery of the contract. They will have responsibility for coordinating other partners, overall strategy and vision, timely delivery, and efficiency in programme administration. The Lead Supplier will provide DFID spending teams with appropriate financial and corporate reporting as required and is required to conduct its own due diligence assessment of any junior partners in the consortium prior to sub-contracting. The Lead Supplier will have final responsibility for all performance (including financial performance) of its partners when accounting to DFID and will have duty of care for all consortium members unless otherwise agreed in contracts between the Lead Supplier and other organisations or individuals. Any changes in the composition of the consortium (dropping or adding consortium members or substantially revising responsibilities) will require DFID’s approval.

The full proposals for the Innovation Ecosystem Fund and the Innovation Ecosystem Research and Analysis will be assessed against published criteria. These criteria will be finalised in discussion with DFID’s Procurement and Commercial Department (PCD) and published in the Terms of Reference. They will be outlined in detail during the procurement process.

DFID will run an early market engagement exercise to test the market capability to deliver this component and will advertise the contract requirement on the DFID supplier portal. It will be tendered in line with the EU Treaty Principles of fairness and transparency. We will publish a Prior Information Notice, the TORs and application on several forums including the DFID supplier portal to help prepare the market for the upcoming call.

How will the Partners be managed?

The partners will be managed based on agreed work plans for each of the contracts, with clear deliverables. The DFID programme management team (PMT) will monitor progress against work plan milestones to ensure that the programme is on track to achieve expected outcomes within anticipated timeframes. This will be supported by robust financial monitoring at regular intervals (including monthly forecasting updates) to ensure that the programme continues to offer good VfM for DFID. We will work closely with PCD on both the procurement of the Innovation Ecosystem Fund and the Innovation Ecosystem Research and Analysis component to determine if there are suitable mechanisms to link payment to performance or delivery in some way such as milestones or other appropriate performance indicators.

DFID and the parties to the agreements and contracts will establish clear mechanisms for regular informal and formal dialogue (see Management Case). The programme will be managed using the principles of flexible and adaptive programming ensuring that there is significant flexibility for DFID to shape the milestones and/or output indicators to ensure these are stretching targets, to defer/cancel payments if quality is not satisfactory, and to accelerate certain activities in response to opportunities and UK policy priorities.

Knowledge Coordination Manager

The Knowledge Coordination Manager will be seconded to sit within one of the programme suppliers. The location will be determined in consultation with key programme stakeholders within the first six months. The Knowledge Coordination Manager will ensure that the learning emerging from different programme strands is being effectively shared both between those programme strands and with DFID. Having a dedicated Knowledge Coordination Manager will improve both the programme performance through faster diffusion of learning and of the wider DFID portfolio of technology and innovation programmes. The Knowledge Coordination Manager will be managed by the A2 SRO/Technical Adviser for the ATIP programme.

Timelines

The Africa Technology and Innovation Partnerships programme will be for 5 years. The MOU with Innovate UK for KTN and Digital Access Programme will commence early 2020. It is anticipated that the Innovation Ecosystem Fund and Innovation Ecosystem Research and Analysis will commence in 2020/21, following tender and contracting. There will be a six month inception phase to undertake assessments of the country innovation ecosystems and develop an innovation ecosystem strengthening implementation plan.

Financial Case

Overview of costs

As outlined in the Commercial Case, DFID will sign an MOU with Innovate UK and DCMS and go through a competitive process for the Innovation Ecosystem Fund and Innovation Ecosystem Research and Analysis delivery strands. Funds will be disbursed as per the terms of the respective agreements. A DFID Programme Manager will be responsible for ensuring due diligence in the disbursement of funds. The UK-Africa Knowledge Transfer Network will receive funding of £5m over 6 years from the Global Challenges Research Fund and £5m over 5 years from DFID. DCMS Tech Hubs are receiving funding of up to £7.5m over four years from the Prosperity Fund and up to £3m from DFID.

The proposed costs are up to £32 million over 5 years. An indicative outline budget for the programme is given below. The FY18/19 costs are part of the scoping budget and take place before the programme start. Expenditure forecasting will be an important task for the service providers, which DFID will monitor closely.

Procurement route (£ thousands )	18/19	19/20	20/21	21/22	22/23	23/24	Total
Innovation Ecosystem Partnerships			£1,500	£2,500	£3,000	£3,000	£10,000
Direct procurement			£2,000	£6,500	£6,500	£6,500	£21,500
Knowledge Coordination Manager			£60	£60	£60	£60	£240
Scoping and convening	£30	£50	£60	£40	£40	£40	£260
Total	£30	£50	£3,620	£9,100	£9,600	£9,600	£32,000

These are an estimate of the costs to be incurred directly by DFID. The estimates are based on the costs of similar DFID programmes. Detailed estimates for the breakdown of funding for the direct procurement will be created after the early market engagement and updated during the 6-month design phase prior to the first breakpoint.

Does the project involve financial aid to governments? If so, please define the arrangements in detail.

The project does not involve financial aid to governments.

ODA Eligibility

All funding is ODA eligible.

Is the required funding available through current resource allocation or via a bid from contingency? Will it be funded through capital/programme/admin?

The Innovation Ecosystem Analysis and Research is funded from CDEL (approx. £3m total) with the rest of the programme being funded by RDEL. The programme funding is covered through the from the Africa Regional Department as part of the new approach to Africa.

How will you work to ensure accurate forecasting?

The DFID Programme Manager will ensure accurate forecasting through developing a strong working relationship with the partners and enabling effective engagement on programme issues including financial management issues. Expenditure monitoring will be undertaken by DFID, based on regular quarterly expenditure forecasts made in accordance with the MoU with Innovate UK and the contract with the lead supplier. The accuracy of the financial profile and forecasting will be closely assessed by the DFID Programme Management Team as part of the quarterly and Annual programme reviews. DFID will conduct Annual Reviews and a Project Completion Report against the log frame.

DFID will disburse funds (GBP sterling) to Innovate UK and DCMS quarterly and in arrears on receipt and approval of a quarterly statement of expenditure and report. DFID will disburse funds (GBP sterling) to the lead suppliers on the Innovation Ecosystem Fund and the Innovation Ecosystem Research and Analysis component in accordance with the contract.

Financial Risk
Fiduciary risk is medium. The Knowledge Transfer Network has an existing relationship with Innovate UK with established procedures and accounting provisions. The contract with the lead supplier will mitigate financial risk through a due diligence check by PCD before contract award. Any organisation failing to meet the required standard will not be contracted. The standard terms and conditions of the contract also make specific reference to fraud and corruption. As DFID makes payments in arrears based on actual deliverables this helps mitigate against the threat of financial risk and fraud in the programme.

The Knowledge Transfer Network and the selected lead supplier will be responsible for ensuring a strong financial management and fraud risk frameworks are in place for any other partners that are sub-contracted. This will include robust arrangements for due diligence checks on potential technology providers and pilot and research grant recipients. DFID will review this as part of the Annual Review and Project Completion Review process. DFID has a zero-tolerance policy on fraud and will apply standard measures to ensure this policy is adhered to.

Management Case

What are the management arrangements for implementing the intervention?

The management arrangements for Africa Technology and Innovation Partnerships programme are designed to ensure appropriate oversight, to enable effective steering of the programme, and to maximise synergies across the components. Figure 3 presents an overview of the management arrangements, described in more detail below.

Figure 4: Management overview

Overview of Africa Technology and Innovation Partnerships programme management arrangements

Direct programme management for directly procured suppliers or consortia will be comprised of DFID’s management team. The Innovation Ecosystem Fund will report to a high-level steering committee. The high-level steering group will be created in early 2020 with an initial meeting at the start of the Innovation Ecosystem Fund inception phase and a second meeting at the end of the inception phase. The high-level steering group will review the inception analysis and agree the proposed innovation ecosystem strengthening implementation plan. The final governance arrangements will be developed during the design phase.

The Programme Management Board for the UK-Africa KTN will be comprised of DFID’s and Innovate UK’s management team. It will meet quarterly and approve high level strategies, work plans and budgets and maintain oversight of the programme’s implementation and performance.

The Programme Management Board for ATIP support to the DCMS tech hubs will be comprised of DFID’s (both ATIP and Digital Access Programme) and DCMS’s management team. It will meet quarterly and approve high level strategies, work plans and budgets and maintain oversight of the programme’s implementation and performance.

The DFID ATIP management team will consist of an A2 SRO/Technical Adviser and a B1 programme manager. The SRO/Technical Adviser will be responsible for strategic direction and implementing the high-level strategic decisions agreed by the programme steering committee. The SRO will be also be accountable for the overall performance of the programme against expectations, linking the programme to wider UK strategy on science, technology and innovation and ensuring the programme can work effectively with other UK ODA funded programmes. The Programme Manager will be responsible for corporate compliance on all aspects of the programme. Through DFID’s programme management we will track management and operational costs, and work to decrease them over the lifetime of the programme where possible. The Annual Review process will assess the technical progress, management processes and Value for Money across the 4 Es of the programme.

DFID Science, Technology and Innovation Teams in Kenya, Nigeria and South Africa will provide an important advisory role to all programme strands in each country, ensuring the programme can work effectively with other UK ODA funded programmes and linking the programme to wider UK strategy on science, technology and innovation in country. The DFID Science, Technology and Innovation Teams will also play a role in connecting and engaging with the local network to ensure consistency in our engagement.

The Country Strategic Advisory Panel will consist of a mix of internal HMG staff in country who will advise on links to the country business plan and relevant UK ODA funded programmes and external experts and stakeholders who will provide an independent expert challenge function to the programme including peer-review and advice on the strategies, research and outreach to policy makers being proposed and undertaken by each programme strand. The panels will include a representative from both the DFID Science, Technology and Innovation Team and the DCMS Tech Hubs. An early programme objective will be to create a Country Strategic Advisory Panel in Kenya, Nigeria and South Africa. The panels will be expected to meet twice a year.

The Knowledge Coordination Manager will be managed by the A2 SRO/Technical Adviser for the ATIP programme. This post will conform to DFID rules on Programme Funded Posts as set out in SMART Rules.

Monitoring and Evaluation

The programme will monitor performance on several different levels:

- Impact level: the strength of the innovation ecosystems in Kenya, South Africa, Nigeria and adjacent countries will be tracked with established metrics like the Global Competitiveness Index’s Innovation Ecosystem category or the Global Innovation Index.
- Outcome level: a robust methodology and data collection mechanism for measuring this programme’s contribution to the improvement of the enabling factors in the innovation ecosystem in Kenya, South Africa, Nigeria and adjacent countries will be developed. This will be developed in the first year of implementation and in partnership with other stakeholders. The methods and data will be a useful public good providing insight to stakeholders across the innovation ecosystem.
- Output level: Output indicators that will form the core of the Annual Review scoring process are set out in the logframe (see Annex 2). Milestones will be updated at the end of the first-year inception phase.
- Work stream level: Each workstream will set out its own monitoring and learning strategy during their design phase that will enable course correction of the work stream and ongoing learning. These monitoring learning strategies will be reviewed annually by the DFID programme management team.

The programme will continue to strengthen measurement frameworks and to strengthen evidence base of what works through a range of research, analysis and learning activities throughout the lifetime of the programme.

The DFID programme management team will monitor progress all levels to ensure that the programme is on track to achieve expected results. The Knowledge Transfer Network, DCMS Tech Hubs and the selected suppliers will report annually against agreed work plans and provide more quarterly formal updates and informal updates to be agreed with each partner. Reporting schedules will be aligned with DFID financial year and reporting requirements, wherever possible, to reduce transaction costs for the DFID programme management team.

The DFID programme management team will undertake Annual Performance Reviews and, at the end, a Project Completion Report in accordance with DFID requirements. Partners will report performance against separate logframes with specific indicators, which will be incorporated within a single logframe that will be used during DFID monitoring and Annual Review processes.

Evaluations

Instead of commissioning programme evaluations, this programme will have an in-built learning function. This will enable the programme to learn lessons about the quality of implementation throughout the programme lifetime and how the programme is contributing to the programme outcomes. There will be an annual learning report that will summarise learning from across the programme activities. This learning function will be supported with research that improves the evidence about what works in strengthening innovation ecosystems and the link between innovation ecosystems and development impact. This continuous approach is likely to be more effective and efficient than an evaluation because it will inform decision making throughout the programme’s implementation and will be better able to gather the needed data.

What are the risks and how will these be managed?

The overall risk is Moderate at the programme level. DFID’s Due Diligence assessments on known partners have provided reasonable assurances that they have the policies, processes and procedures in place for effective risk management. These assessments will be refreshed as required. As per DFID guidance, an enhanced safeguarding pillar of the Due Diligence process will be undertaken on partners prior to any new agreements being signed. Project leads for the individual components will be required to raise material risks as a matter of urgency with the SRO. Any significant increase in risk rating on any risk will be elevated by the SRO to team and RED management for advice.

The risk category is moderate, which is within the risk appetite for the Research and Evidence Division and is considered manageable with potential high returns. The rating stems from the inherent uncertainty in funding the strengthening of technology and innovation ecosystems due to a weak evidence base on what works and the political and economic risks that can affect the overall climate for the commercial success of new technology products and services. However, the risk will be mitigated through building the evidence base on what works and taking a flexible approach that can adapt quickly to the political and economic context and respond to learning. Risk will be proactively managed throughout programme delivery with regular reporting to DFID and an active risk matrix (see Table 3 below).

Risk	Probability	Impact	Gross risk	Mitigating measures	Residual risk
Delivery
Delivery partners unable to identify opportunities with greatest impact potential.	Unlikely	Moderate	Moderate	Mitigation measures involve ensuring high quality delivery partners, maximising synergies between delivery partners and drawing on external expertise. / Ensure partner selection process includes criterion for experience in assessing technology and innovation ecosystems. / Regular meetings between delivery partners and DFID’s science, technology and innovation team in country and a programme-funded post will provide DFID will pipeline oversight and enable DFID to shape direction of investments. / Delivery partners will work together and be able to access each other’s expertise. / Working closely with external experts and stakeholders and other HMG programmes operating in the technology and innovation ecosystem will enable delivery partners to draw on additional expertise. / Building the evidence base for what works in strengthening technology and innovation ecosystems will include assessing impact potential.	Minor
Lack of sufficient engagement with local stakeholders leads to a negative perception of the programme	Unlikely	Major	Major	Initial consultation indicates that the programme would be positively received. The programme will prioritise engaging and consulting local stakeholders on the direction of the programme. This will be supported by a country based external advisory group made up of actors with expertise on the country technology and innovation ecosystem including representation from the national innovation agency.	Moderate
Operational
Coordination between multiple suppliers reduces effectiveness of programme.	Possible	Moderate	Major	The DFID management team will consist of a Technology and Innovation Adviser and a Deputy Programme Manager in the Director of Research Team. This will be supported in each focus country by a DFID Science, Technology and Innovation team. / Recruiting a programme-funded post to focus on coordination will release resource within the core PMT to focus on contract management.	Moderate
Safeguarding
Inadequate oversight leads to safeguarding concerns, such as violations of human rights and discrimination.	Unlikely	Major	Major	Through Enhanced Due Diligence assessments on Safeguarding, partners will be required to demonstrate robust measures are in place. / All partners to carry out their own due diligence on potential downstream Partners before committing any funds.	Moderate
Fiduciary
Corruption in delivery chain; funds are not used for the intended purposes.	Unlikely	Major	Major	The terms and conditions of the contract with delivery partners and MOU will include specific requirements around protections against fraud and corruption. This will include a policy for assessing and mitigating risks of corruption in downstream partners. Financial and fiduciary risk will be assessed during quarterly meetings and as part of the Annual Review and Project Completion Report processes.	Moderate
Reputational
UK public opinion opposes systems building without clear development impact	Possible	Major	Major	Work closely with DFID Comms division to ensure that the positive impacts of the new technologies and stronger technology and innovation systems for the poor are effectively communicated to the public.	Moderate
Contextual
Political, social and economic shocks or change in focus countries affect the performance and ability to deliver of the programme.	Unlikely	Major	Major	The programme will take a flexible approach that can adapt quickly to the political and economic context and respond to learning. / Ensure contingency plans with other partners in place to mitigate risks.	Moderate

Partnership Principles and other conditions
 The programme does not involve financial aid to governments. It will work in partnership with government agencies such as innovation agencies or regulatory bodies. We hope that these agencies will be represented on (and possibly chair) country steering boards. It is also likely that technical assistance will be provided through some of the funded interventions. For all interactions the DFID management team will follow DFID country offices guidance on working with government and to the Partnership Principles

Annex

Annex 1 – Scoping exercise (double click on image to see PowerPoint)

Annex 2 - Logframe
The initial output indicators that will form the core of the Annual Review scoring process are set out in the logframe below. The exact indicators at output level will be informed by the commissioned research and determined in consultation with local stakeholders and national innovation strategies. The measurement framework will be agreed by the end of the programme’s inception phase.
PROJECT TITLE: Africa Technology and Innovation Partnerships (ATIP)
IMPACT	Impact Indicator 1		Baseline	Milestone 1	Milestone 2	Target (date)
More effective innovation ecosystems that catalyse new technologies to scale in Nigeria, South Africa, Kenya and adjacent countries.	Global Competitiveness Index: Innovation Ecosystem category - Score and Ranking for Kenya, Nigeria and South Africa	Planned	GCI 2019 not yet published
		Achieved
			Source
			https://www.weforum.org/reports/global-competitiveness-report-2019
	Outcome Indicator 2		Baseline	Milestone 1	Milestone 2	Target (date)
	Global Innovation Index - Score and Rank for Kenya, Nigeria and South Africa	Planned	Kenya - Score 31.1, Rank 77 South Africa - Score 34, Rank 63 Nigeria - Score 23.9, Rank 114
		Achieved
			Source
			https://www.globalinnovationindex.org/gii-2019-report

OUTCOME	Outcome Indicator 1		Baseline	Milestone 1	Milestone 2	Target (date)
Critical barriers to the inclusive scaling of new and emerging technologies analysed and addressed in Nigeria, South Africa, Kenya and adjacent countries.	Outcome metric to be determined through research and data collection in output 4 (indicator 4.3).	Planned	tbd	tbd	tbd
		Achieved
			Source

INPUTS (HR)	DFID (FTEs)

OUTPUT 1	Output Indicator 1.1		Baseline	Milestone 1	Milestone 2	Target (date)
Larger and more effective networks of entrepreneurs and innovators building partnerships	Increased networks (#members; #sectors covered) - Number of technology and innovation partnerships brokered through effective knowledge transfer and network building.	Planned	0	tbd
		Achieved
		Source

	Output Indicator 2.2
	Increased effectiveness through # new stakeholder partnerships facilitated - Number of technology and innovation partnerships brokered through effective knowledge transfer and network building.	Planned	0	tbd
		Achieved
		Source

IMPACT WEIGHTING (%)
INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 2	Output Indicator 2.1		Baseline	Milestone 1	Milestone 2	Target (date)
Critical barriers identified and addressed in each ecosystem	# critical barriers identified then competitions and projects completed	Planned	0	Agreement on governance, design and scope of innovation ecosystem fund.	tbd	tbd
		Achieved
		Source

	Output Indicator 2.2		Baseline	Milestone 1	Milestone 2	Target (date)
	# detailed case studies assessing pathway to impacts for co-created projects on a critical enabling factor in the innovation ecosystem.	Planned	0	0	1	4
		Achieved
		Source

IMPACT WEIGHTING (%)	Output Indicator 2.3		Baseline	Milestone 1	Milestone 2	Target (date)
	# documented case studies demonstrating sustainable projects that have increased the inclusiveness of the innovation ecosystem	Planned	0	0	1	4
		Achieved
		Source

INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 3	Output Indicator 3.1		Baseline	Milestone 1	Milestone 2	Target (date)
Strengthened technology and innovation policy and regulation	# Diagnostic analyses of policy and regulatory systems.	Planned	0	0	3	9
		Achieved
		Source

	Output Indicator 3.2		Baseline	Milestone 1	Milestone 2	Target (date)
	# policymakers with analysis and knowledge to enact evidence-based innovation policy	Planned	0	0	30	60
		Achieved
		Source

IMPACT WEIGHTING (%)	Output Indicator 3.3
	# documented case studies of improved technology and innovation policy and regulation.	Planned	0	0	0	2

INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)

OUTPUT 4	Output Indicator 4.1		Baseline	Milestone 1	Milestone 2	Target (date)
Targeted research, analysis and learning on strengthened innovation ecosystem	# research projects completed and disseminated effectively	Planned	0	0	1	3
		Achieved
		Source

	Output Indicator 4.2		Baseline	Milestone 1	Milestone 2	Target (date)
	Frameworks and tools for mapping and enhanced monitoring of country technology and innovation portfolios	Planned	No clear methods or tools for monitoring country technology and innovation portfolios.	Development of initial framework for monitoring country technology and innovation portfolios and mapping innovation ecosystem activity. Basic innovation ecosystem mapping completed	Prototypes of tools for improved monitoring of country technology and innovation portfolios and mapping innovation ecosystem activity tested. Detailed innovation ecosystem mapping completed	tbd
		Achieved
		Source
	Output Indicator 4.3		Baseline	Milestone 1	Milestone 2	Target (date)
	Robust methodology for measuring the effectiveness of the innovation ecosystem and improvement of the enabling factors developed.	Planned	Not started	Initial research into measuring improvement of the enabling factors in the innovation ecosystem completed	1st data collection and analysis in Kenya, South Africa and Nigeria.	2nd data collection and analysis in Kenya, South Africa and Nigeria.
		Achieved
		Source

IMPACT WEIGHTING (%)	Output Indicator 4.3		Baseline	Milestone 1	Milestone 2	Target (date)
	# learning and analytical reports commissioned and communicated across the innovation ecosystem	Planned	0	1	4	7
		Achieved
		Source

INPUTS (£)	DFID (£)		Govt (£)	Other (£)	Total (£)	DFID SHARE (%)

INPUTS (HR)	DFID (FTEs)