Annual Review/Programme Completion Review (21/22)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK

Programme Title	Pakistan Regional Stability Programme (PRSP)
Programme ID	C-SAA-0019 - Pakistan Regional Stability Programme (PRSP)
Country and Region	Pakistan, / Afghanistan Pakistan Directorate (APD)
IATI Unique ID	CSSF-09-000010
HMG Partners / (Lead in bold)	Jinnah Institute (JI), Pakistan Afghanistan Joint Chambers of Commerce and Industry (PAJCCI), International Institute of Strategic Studies (IISS), Council for Defence and Strategic Studies (CSDR), / Centre for Research and Security Studies (CRSS), ALCIS, Regional Peace Institute (RPI)
Total Budget	ODA: £2.37m	Non-ODA: £0.14m
Budget this FY	ODA: £2.37m	Non-ODA: £0.14m
Spend this FY	ODA: £1.87m	Non-ODA: £0.13m
Time Frame	Start Date:1/4/21	End Date:31/3/22

Outputs			Individual Output Rating
Output 1: Engagements between Pakistan and Afghanistan and India and Pakistan designed and conducted based on improved context and stakeholder analysis​			3
Output 2: Engagements between India and Pakistan and Pakistan and Afghanistan on FCDO prioritised thematic areas pursued through various platforms/spaces/mechanisms ​			3
Output 3: High level engagement through Defence (MOD)-RCDS​			3
Overall Rating of Output Delivery			3
Outcome Assessment	The Programme met or exceeded some of its outcomes however, progress on the Afghanistan-Pakistan & the UK Ministry of Defence (MOD) components was hampered by external factors such as the fallout from Covid-19, Taliban takeover of Afghanistan and the war in Ukraine. Although out of the programme’s control, these factors contributed to the non-achievement of some planned outputs. / The achievement of dialogues on the India-Pakistan side and the continued engagement on Af-Pak issues by continuing the Pakistan leg of activities and planning the meetings in the border areas to facilitate exchange with the Afghan business communities are some key outputs achieved despite the above mentioned hurdles during the review period. The high-level dialogues are long running but remain significant given the lack of engagement between India and Pakistan. / Overall, even though the programme met or exceeded its expectations for some of the outputs, the programme/ policy teams should work with partners in designing better attributable interventions that can demonstrate continuous stakeholder engagement and ensure progress.
Overall Outcome Progress Rating:		Amber
Overall Risk Rating:		High

Year	2021/22
Programme Rating	3	Amber
Risk Rating	High

What Support Did the UK Provide in FY 21/22?

Pakistan’s Regional Stability Programme (PRSP) launched in 2021, was designed taking account of the experience gained from its predecessor, the CSSF Regional Programme. Activities undertaken by the programme comprise of Track 1.5 and Track 2 dialogues addressing bilateral deadlocks and potential for engagement, support to economic connectivity including addressing barriers to trade, specific engagement on nuclear issues, research to underpin other components and supporting engagement between UK and Pakistani Military through initiatives such as participation of Pakistani Military officers on the UK’s Royal College of Defence Studies (RCDS) course and the flagship annual Regional Stability Conference.

The new programme, aimed to increase regional stability by reducing the potential for conflict by facilitating a) dialogue processes in areas of mutual concern between Afghanistan, India and Pakistan; and b) unofficial interactions between non-state Pakistani and Indian parties to develop strategies and ideas in ways that may contribute to the peaceful handling of disputes.  On Afghanistan-Pakistan, it aimed to assist the deepening of economic connectivity to create opportunities for increased revenue so that the costs to both countries of failing to peacefully manage future challenges increases.

It is critical to note the various factors that impacted the delivery of the programme significantly in the financial year. Firstly, Covid-19 was still prominent during the year in the region meaning that face-to-face meetings were partially curtailed. This is relevant to the dialogues that need physical presence to establish, build and sustain trust even among participants known to each other. Secondly, the arrival of the Taliban meant that a major adjustment had to be made to a programme that had just been set-up months earlier. Thirdly, the events in Afghanistan created a huge effort for the FCDO across the network that required staff to be repositioned to work on the crisis response. In addition, a policy gap on Afghanistan as HMG adjusted to the fall of Kabul. This in turn resulted in less clarity for the programme design process than would have been optimal. Programme staff were abstracted to address urgent crisis responses meaning less attention could be paid to programme management consequently. Staff turnover was also a disruptive factor with the programme having three SROs within the year under review. Finally, the programme’s financial management had additional problems caused by the recurring inability of MOD systems to align fully with CSSF requirements.

The cumulative effect of these factors was significant, and it is a testament to staff particularly in the programme team that so much positive work was achieved, and the programme continued delivery.

Output 1 - Engagements between Pakistan and Afghanistan, and between India and Pakistan designed and conducted on the basis of improved context and stakeholder analysis.

Outputs 1 and 2 were delivered through five implementing partners, the financial information is below:

Partner	Budget FY 2021-22	Actual Spend FY 2021-22
IISS	£487,808	£475,903
Jinnah Institute	£193,850	£146,015
CSDR	£187,701	£135,798
CRSS	£351,442	£226,992
PAJCCI	£468,635	£312,652
MOD (ODA + Non-ODA)	£499,000	£419,336
Staff costs	£179,197	£140,436
M&E costs	£26,530	£24,117
Research (pilot activities)	£251,872	£119,742
Total	£2,646,035 / (Contract costs + budgeted)	£2,000,991(Actual Spend)

In addition, Implementing Partners had some conversations with FCDO to ensure policy relevance and, in some cases, consult on those invited to dialogues. However, this was not consistent across dialogues or IPs, with some IPs receiving mixed engagement from FCDO.

Output 2 – Engagements between India and Pakistan, and between Pakistan and Afghanistan on FCDO prioritised thematic areas pursued through various platforms / spaces / mechanisms.

This output covered a range of Track 1.5 dialogue activity on security issues plus crisis management. Further details are detailed below.

Output 3 – High level engagement through Defence (MOD) - Royal College of Defence Studies.

This component was only funded by CSSF until September 2021 after which MOD took over full responsibility. During the time that CSSF was applicable, three candidates were selected for the three places on the RCDS course and began professional development. The annual Regional Stability Conference was cancelled in March owing to the Russia-Ukraine crisis and could not be delivered.

Key Results for FY 21/22:

It should be noted that the AR, had to be completed virtually due to the inability to travel to the BHC Islamabad on account of visas not being issued. This resulted in the AR evidence being gathered over a compressed four-day period which was sub-optimal compared to the wider opportunities afforded by a country visit. The observations are offered on the basis that further time would have allowed for a more robust review than was the case in practice and based on Programme Team’s inputs.

Overall, the AR team found widespread support for both the programme concept and for the value of the engagements created. FCDO policy staff appreciated the opportunities afforded by the programme for access to influential people with associated messaging opportunities that benefited the range of other BHC efforts in Islamabad and Delhi. Given the significance of the influence effect, it is suggested that consideration be given to tracking this issue in the results framework. Claiming attribution from dialogue processes over time is problematic and will be referred to later.

The AR team noted a greater awareness than before on the need for alignment of understanding on what the activities could achieve across the policy / programme teams. However, it is suggested that there is potential within HMG to develop an enhanced understanding internally on what the programme should be doing. Getting regular FCDO policy staff involvement in formulating dialogue agendas and nominating participants would be a useful step towards improving impact and usefulness.

India-Pakistan achievements

The following events were held: Two Track 1.5 Regional Security Dialogues, one Track 2 Chao Track India Pakistan Dialogue, one Crisis Management Workshop between India and Pakistan, and four India-Pakistan Policy Relevant Roundtable meetings held in India and Pakistan. It was noted that over 30% participants for Track 1.5 dialogues were serving government officials from India and Pakistan. ​

Some key dialogue participants included then Serving National Security Adviser (NSA) of Pakistan, the Taliban’s Ambassador - designate to the UN, Suhail Shaheen (virtually).​The dialogue provided Pakistan’s NSA an opportunity to meet Indian counterparts in person to discuss matters of interest.

In the absence of an official dialogue between the two governments, the backchannel dialogues by the programme served as established institutionalised mechanisms to support bilateral conversations. The communication channel initiated between the security establishments of Pakistan and India through post dialogue advocacy with the Pakistan NSA and the Indian Deputy NSAs is a great example of such an effort. Even though the content of the post dialogue discussions and side-line meetings during the dialogue are sensitive, confidential and off-the-record, partners reported that their efforts have helped a great deal in bridging communication and building trust between the two nuclear rivals.

Afghanistan-Pakistan achievements

Despite the Afghanistan component having to cease following the fall of Kabul, the following progress was reported as a result of programme initiatives:
​
The Pakistan government’s decision to ease Afghan visa policy resulted in an online visa process opening to facilitate visiting Afghans and extending visa validity up to 3 years. This is a result of the Focus Group Discussions organised by the CRSS in October 2021 where in visiting Afghan traders (participants) expressed their issues around Government of Pakistan’s Afghan visa policy directly to concerned officials who also attended the consultation and took cognizance of these recommendations. CRSS also had done meticulous advocacy with the officials to follow up on the issue until a resolution was sought. ​

The mechanism developed through the implementing partner, Pakistan-Afghanistan Joint Chamber of Commerce (PAJCCI), to facilitate bilateral trade issues at Pakistan-Afghan border earned them membership of the Pakistan-Afghanistan Inter-ministerial Coordination cell and Parliamentary Friendship group, both high level bodies formed to address issues of trade at Pak/Afghan borders. This has been the most significant development to date in securing such senior representation in policy fora.
 ​
Pakistan agreed entry of around one hundred Afghan patients every day, along with the issuance of on-arrival visas for all Afghan passengers trying to visit Pakistan at Torkham border crossing. Pakistan also agreed a reduction of Pakistani Kinnows (mandarins) tariffs by 67%, abolishing sales tax for Afghan fresh fruits and vegetables exports which furthered the trade relations between the two countries. ​Recognition of the programme’s work on economic connectivity was evidenced by the appointments of the PAJCCI Chairman and Co-Chairman from both countries to the High Economic Council Board appointed by Taliban in Afghanistan and apex committee formed by Pakistan to govern trade relations with Afghanistan. This headway has given PAJCCI an opportunity to address and resolve several trade related issues and to advocate meaningful solutions. In the present iteration of the programme, PAJCCI is currently in the process of developing a TOR with GOP on barter system as an alternative payment mechanism to help trade continuity in the absence of formal trade which is about to be piloted and tested for feasibility. Thus, the appointment has helped the IP to address various operational issues at the Pak/Af border and to manage the abeyance due to regime change in Afghanistan and the expiry of Afghanistan Pakistan Trade Transit agreement (APTTA) during this period.

It is important to note, however, that these programme interventions are largely expected to demonstrate impact in the long term given the sensitivity of bilateral relationships and the resulting slow-paced progression towards desired results. Nonetheless, the programme team engages implementing partners to adopt various methods of tracking post intervention impact such as outcome harvesting to ensure they continue to engage stakeholders and demonstrate progress.
Key Lessons

The staffing of the programme team has been variable throughout the year for reasons already stated. The consequence of staff gaps impeded the programme team from covering the full spectrum of management responsibilities. This has been managed in the current programme period as the staff positions are all filled, and the staff roles and objectives are clarified by systematic approach using a thematic delivery and road mapping method.

A significant feature of the new programme is the extent to which security organisations have been included in the dialogues (also part of the Programme Completion Report recommendations from the previous iteration of this programme). The programme has ensured it through improving the security participation and representation at the Track 1.5 Regional security dialogue which was attended by participants from India and Pakistan which is seen as a major enabler to sustaining the credibility of the process. Also, the future programme will ensure the participation of key Track II and Track 1.5 actors from the security agencies of India and Pakistan.

A major learning experience for the programme in the period was also to innovate & be agile. For instance, despite the immediate discontinuation of fund flows and programme activities in Afghanistan owing to the unclear HMG strategy towards engagement with the Taliban, the programme continued the Pakistan component of Afghanistan - Pakistan activities to sustain momentum. This included shifting programme engagement with trade communities and civil society to the border areas and the selection of alternate locations in Pakistan to support the participation of Afghan delegations in project activities.

Recommendations for FY 21/22

Based on the evidence collected during the review, the AR team is confident that if adopted, the recommendations could assist the programme and policy staff to improve the coherence of the programme overall and to assist in the forward look process already initiated.

Funding: In a longer run, the programme should be assessed a) for its appropriateness to sit under CSSF and b) how it (or elements) could transition from CSSF to FCDO baseline and what timeline would be suitable based on the mission priorities (through JACS review).The programme team should consider a review to address this recommendation in collaboration with relevant policy stakeholders before the next iteration of the programme is in place that is October 2022.
Engaging Policy colleagues in dialogue designing and formalising the process of participation selection and agenda formulation- FCDO policy staff are involved in the programme but their level of engagement should be increased especially in designing these dialogues from agenda formulation to participant selection where feasible.
Delivery partner co-ordination – Additional ways should be identified to bring together Policy/Programme/Delivery Partners to analyse content of dialogues and improve co-ordination. Joint workshops have been suggested for the programme team to consider for the next iteration of the programme post October 22.
Monitoring, Evaluation and Learning: The programme team should consider how best to measure the impact of dialogue-based activities, working alongside Joint Funds Unit. MEL related activities should focus on what is directly attributable to the programme vs which outcomes it is making a contribution towards.
Whilst acknowledging that accounting for CSSF within MOD Departmental systems is not straightforward, better reporting and timeliness for spend is essential for good programme management. The new CSSF hub within MOD are encouraged to assist.
There is potential for the programme to facilitate greater engagements between security officials and the programme team should consider compiling an Overseas Security and Justice Assessment (OSJA) to manage risks efficiently.