Annual Review (21/22)

A. Summary Sheet
Programme Title	Open Societies Programme
Programme ID	C-SAA-0014 - Pakistan - Open Societies Programme (OSP)
Country and Region	Pakistan, APD
IATI Unique ID	CSSF-09-000009
HMG Partners (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO)
Total Budget	ODA: £4.2 million	Non-ODA: £0
Budget this FY	ODA: £2.7 million	Non-ODA: £0
Spend this FY	ODA: £2.62million	Non-ODA: £0
Time Frame	Start Date: April 2021	End Date: March 2025

Outputs	Individual Output Rating
Support and response mechanism for victims of forced conversion is integrated (at least partially) within the Gender Based Violence (GBV) response framework	3
Improved capacity of federal and provincial government to implement GBV legislation for human right complaint response to GBV survivors	4
Selected journalists and media outlets produce quality public interest reporting on targeted issues including women, inclusion, and minority rights	3
Federal and provincial governments and assemblies support new legislation on safety of journalists and take at least one additional legislation/executive action to enhance civic space	4
Overall Rating of Output Delivery	4

Outcome Assessment	The Open Societies Programme (OSP) has two outcomes: / Outcome 1: Policy makers, response providers and target communities are more aware of, sensitive to, and inclusive of, the rights of vulnerable groups (women, girls, and religious minorities). / Outcome 2: A more conducive operating environment for civil society and media to: / a) exercise civil and political rights; and b) act as protector and promote of the rights of vulnerable groups (women, girls, and religious minorities). / The programme was designed as a high-risk intervention to test how to create a more conducive environment in Pakistan for the protection of the rights of vulnerable groups. The complex mix of stakeholders, advocacy in a shrinking civic space, the COVID-19 pandemic, and internal HMG restructuring made for a challenging operating space. The programme worked with civil society to strengthen the Pakistan Federal Government’s implementation of recent Anti-Rape legislation, engagement on NGO registration, and efforts to raise the quality of journalism associated with reporting on issues affecting women and minorities. Implementing partners needed to be opportunistic and capitalised on emerging opportunities to challenge or reset institutional norms. / The programme has delivered well overall. The outputs were catalytic, delivered the conditions for outcome-level change and the desired changes at outcome level were achieved. The programme contributed to an improved legislative environment (creating more favourable conditions for key players – justice actors, journalists and CSOs) through the passage of journalist protection legislation at the federal level and enactment of the anti-rape legislation. The programme worked to build the capacity for communities to sustainably engage on these laws. The results from multiple interventions need to be consolidated, but evidence from the breadth of engagement represents a ‘chipping away’ at the rules, behaviours and practices that undermine the rights of vulnerable groups which, ultimately, bodes well for a more open and inclusive Pakistan.
Overall Outcome Progress Rating:		GREEN
Overall Risk Rating:		Major

Summary of Programme Performance
Year	2021/22		2022/23		2023/242
Programme Rating	4	Green
Risk Rating	MAJOR
Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?
Funding to four (4) Pakistani non-governmental organisations and one (1) commercial firm for operational activities, Technical Assistance and research as follows:

Partners	Project Title	Activity focus
Group Development Pakistan (GDP) – Focused on the Federal level and KP province	"Urdh Ja" - Promoting and Protecting the Welfare of Women and Girls (PPWWG)	The project aimed to improve the structural, institutional, and socio-cultural response to sexual and gender-based violence (SGBV) in Pakistan to better promote and protect women's and girls’ rights - including girls from religious minorities, through advocacy, capacity building and strategic engagement with senior judiciary, police, and key government institutions such as Ministry of Law and Justice (MoLJ) and Council of Islamic Ideology (CII).
Legal Aid Society (LAS) – Sindh and Islamabad Capital Territory (ICT)	Strengthening the Criminal Justice System Response to Sexual Violence in Sindh and Islamabad Capital Territory (ICT)	The project aimed to improve the experience of victims and survivors of sexual and Gender Based Violence, with the criminal justice institutions with focus on victim-centric service provision through training of judicial actors, advocacy for improved facilities in courts, and measures these improvements through the lens of survivors.
National Dialogue Forum (NDF) – Nationwide	Freedom for Religion or Belief (FoRB) Research Study	A research study aimed at better understanding socio-political conditions for improving religious minority rights, with emphasis on forced conversions and hate speech, with possible entry points for future programming.
Trust for Democratic Education and Accountability (TDEA) – Nationwide	Strengthening Media Freedom and Civic Space in Pakistan	The project aimed to contribute to the freedom of the press, expression, and civic space through establishing synergies between media and CSOs, positioning and training of both to engage policy makers on the issues of vulnerable groups.
Media Matters for Democracy (MMfD) – Karachi and Islamabad	Actions for Free Inclusive and Resilient Media	Project aimed to improve the skills of digital media journalists (especially women journalists) and media houses though fellowships, training, and the development of safety protocols to enable them to undertake public interest reporting on vulnerable groups without compromising on their safety.
Other (MEL; PM support; salary of staff members.

Key Results for FY 21/22:
- Enactment of the anti-rape legislation, and submission of the final draft of a policy on the Protection of the Rights of Transgender People;
- Legally binding jurisprudence acknowledging child marriage as a form of child abuse and advising the state to legislate and put 18 as the minimum age of marriage for girls
- Increased knowledge and skills of courts and Investigating Officers (with over 80 individuals comprising of judges and magistrates trained) for better handling of GBV cases, alongside newly developed guidelines and a performance management framework;
- Provision of Special Protection Measures to protect victims and survivors of GBV from additional trauma in the justice process;
- Notification of 288 police Investigating Officers (IO) as a specialised cadre trained to conduct GBV investigations in ICT and Sind. Through effective advocacy, four specialised GBV Magistrates were nominated by the District & Sessions Judge, Karachi East to adjudicate GBV cases;
- The Government of Pakistan adopted 20 of the Pakistan Federal Union of Journalists (PFUJ)’s proposed amendments in its newly-passed Protection of Journalists and Media Professionals Bill, 2021.Data collection and research in 35 districts across Pakistan produced four pandemic governance monitoring reports, the findings of which were used in an intensive advocacy campaign leading to one federal level and 12 district level official notifications/actions to effectively manage the pandemic.
- The Khyber Pakhtunkhwa Transgender Persons Welfare Endowment Fund Bill, 2021 was approved by the Cabinet for the protection of the rights of the transgender community;
- 119 journalists received training including women in media, transgender women, women with disabilities, women from religious minority groups and women from remote areas who were supported to create digital content, allowing them to self-represent in a male-dominated digital space;
- First representation ever of Pakistan in the World Congress on Justice with Children and first ever participation of Pakistani children in drafting General Comments of the United Nations Convention on the Rights of the Child (UNCRC) (#25 on children rights and the digital space, and #26 on children rights and the environment);
- Additionally, there were wider and unintended effects realised by the programme outside of the target activities such as 97 additional initiatives undertaken by the state to counter SGBV to protect minority rights as a consequence of advocacy campaigns and behind-the scene engagements.

Key Lessons
- Despite sharing a common problem, civil society and lobby groups are not always willing to collaborate as they compete for donor funding, particularly in controversial thematic areas. Collaboration can be built into performance frameworks to ensure synergies and efficiencies.
- The communication and stakeholder engagement strategies applied have been effective in sustaining the social, institutional, and political buy-in of projects and the overall objective of the programme. That goodwill and those strategies must be capitalised upon and consolidated as they have constituted important and successful elements of managing potential conflict triggers in Pakistan.
- Federal and provincial level advocacy are not mutually exclusive – both are necessary to secure the progress needed on sensitive issue areas. However, it requires a keen eye on resources, political economy, and staff welfare to avoid overstretch and be equally effective in both spheres.
- ‘Chipping away’ is a proven concept; implementation must remain flexible and adaptive as circumstances change; take advantage of emerging opportunities and make evidence-based decisions on discontinuing interventions that show no promise of delivery. For example, the pandemic presented opportunities to work on misinformation and to use networks built for political participation to track and report on service delivery. At the same time, ideas such as the social research labs were dropped as there was not enough time to secure traction.
- Adequate consideration should be given to partner’s capacity and system when selecting programme implementors. Although, there are only a handful of implementors operating in the media space, but a more objective assessment should be made when selecting a partner. If their systems and processes are not robust enough, the programme teams should not hesitate to go back to the drawing board and revisit the deliverables or select strong partner rather than taking on additional transaction of cost of capacitating a weak partner.

Key Recommendations for FY 22/23
- The need to push against harmful (ingrained) behaviours, particularly those with a religious basis, requires sustained advocacy. FCDO should explore brokering partnerships between key actors and other programmes/donors who have strong contacts and credibility within Government and who can bring their resources to improve & enforce the regulatory framework to counter GBV (including rape, child marriage and forced conversion) at both national and local levels. Action: CG5 to continue to refine advocacy plans to capitalise on the work done so far (August 22).
- As the programme narrows its scope to the digital space, digital technology/platforms should be used to track and report cases of GBV and demonstrate the linkages between disinformation, hate speech and GBV. Action: The SRO has commissioned a desk research and scoping contract to be followed by more detailed primary research that should be instructive in this regard. (Contract awaiting to be signed, with research to completed by Dec 22)
- The first year of the programme has created the space to be even more ambitious; it has shown what is possible with tactical, sustained advocacy (versus confrontational approaches) and similar principles should be maintained going forward. Action: Team to review against this principle once design for years 2-4 is in place.
- The Human Rights and AAWAZ II[1] teams will need to be deliberate in how they exploit synergies that will be created by the OSP, by leveraging the impact and partners working in the digital space and by using their platforms to amplify OSP’s work[2]. This will ensure that OSP’s legacy in broader thematic areas is not lost, and that successful initiatives and the various consultative mechanisms which gave voice to marginalised groups are sustained. Many of these mechanisms were pioneering ways of engagement and a febrile political context can lead to stillbirth of these platforms. The political dynamics could also shift in favour of a more conducive operating space. This second possibility will demand strategic conversations, backchanneling and coordination, and a clear mix of technical and political skills, but the Campaign Goal framework should facilitate this. Action: CG5/SRO to set up internal engagement forum to ensure that synergies are exploited (Aug 22).
  [1] AAWAZ II works with local communities in Khyber Pakhtunkhwa (KP) and Punjab to promote the rights of children, women, youth, and other marginalised groups to strengthen and facilitate their development.
  [2] The team should also consider how programming by other development partners and like-minded organisations is aligned with the revised scope of the OSP and seek to influence how the focus of the programme might be amplified and built on, beyond HMG-funded initiatives.