Annual Review/Programme Completion Review (21/22)

Programme Title	International Prevent programme (IPP)
Programme ID	C-CTP-0008
Country and Region	Multi-region
IATI Unique ID	CSSF-01-000015
HMG Partners / (Lead in bold)	CONTEST Unit (CU), Home Office (HO), Foreign, Commonwealth & Development Office (FCDO), Cabinet Office (CO)
Total Budget	ODA: £40.61m*	Non-ODA: £25.79m*
Budget this FY	ODA: £20.5m*	Non-ODA: £12.72m*
Spend this FY	ODA: £18.79m*	Non-ODA: £13.76m*
Time Frame	Start Date: 1 April 2021	End Date: 31 March 2022

* Financial information below Portfolio level is not published for security reasons.

Outputs	Output Rating
Overall Rating of Output Delivery	3

Outcome Assessment	In FY21/22 International Prevent made positive efforts to co-ordinate activity with the Enablers and Strategic Drivers and Counter Daesh Communications Cell programmes to better align activities across these programmes; the mapping exercise undertaken as part of this process has been noted by the review team as a practical lesson to learn for the CTPf portfolio as a whole in the capping paper’s strategic recommendations. This strategic refocus is clear. / While there were issues with some inconsistent reporting and lack of target setting for some indicators the review team have taken account of progress made by Q4 – and how this has continued into the following FY.
Overall Outcome Progress Rating:		Green
Overall Risk Rating:		High

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	A	A	Green / (Aa)	3 / (Aa)	3	Green
Risk Rating	High		High		High

Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?
In FY 21/22, the IPP delivered 17 projects. The programme effectively targeted and worked with identified cohorts in priority countries that posed risks to the UK and UK interests.

The IPP effectively delivered projects in countries that posed terrorist risks to UK interests, and to support partners overseas. The IPP is designed to reduce the likelihood of individuals or groups from engaging in terrorism. The programme advanced this objective through: (1) working with identified at risk individuals, or those showing early signs of radicalisation; (2) countering radicalising influences into the UK; and (3) disengaging, reintegrating and rehabilitating offenders including violent extremist offenders. It achieved these objectives through direct work with at-risk groups and through capacity building with partner governments.

Key Results for FY 21/22
- Reduced risk of vulnerable individuals re-engaging in extremist activities as a consequence of vocational training and other support.
- Improved partner ability to assess risk and deliver responses around disengagement and reintegration.
- Strengthened partner capacity to identify and provide support to individuals or groups at risk, or those showing early signs of radicalisation and recruitment leading to terrorism.
- Improved understanding of radicalisation influences between the UK and partner countries.
- Strengthened relationships with CT partners.

Key Lessons
- Strategic patience – ensure effective evaluation of the institutionalisation of Prevent approaches.
- Greater collaboration with other donors to maximise CT effect.
- Barriers to change and enhanced performance include working culture, equipment or resources to implement standards.
- Multi-agency working is essential for effective work to prevent violent extremism.

Key Recommendations for FY 21/22
- As in 20/21 recommendations, continue to encourage co-development of solutions, to avoid delays, lack of acceptance, adaptation to local contexts or existing practice or ownership of host government partners. This will also enhance ownership and likelihood of formal approval and implementation.
- Enable some element of peer to peer learning, to ensure that products, practice and learning developed – for example in important reintegration work – can be shared and benefit other projects.