Annual Review/Programme Completion Review (21/22)

A. Summary Sheet
NB: Summary Sheets Will Be Published on GOV.UK
Programme Title	CSSF Cyber & Tech Security Programme 2021-22
Programme ID	C-CYB-0001
Country and Region	Global
IATI Unique ID	CSSF-14-000001
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO) / Home Office / NCA / DCMS / NCSC / DIT / MoD / Government Communication Services (International)
Total Budget	ODA: £7,144,000	Non-ODA: £5,656,000
Budget this FY	ODA: £7,144,000	Non-ODA: £5,656,000
Spend this FY	ODA: £7,452,868	Non-ODA: £5,928,241
Time Frame	Start Date: April 2021	End Date: March 2022

Outcome Assessment	Outcome 1: Evidence of governments better protecting critical national infrastructure from cyber-attacks: AMBER: On track but some doubts that outcome targets will be met. / Outcome 2: Improved cybersecurity attitudes among private citizens, including employing secure online practices: GREEN: Fully on track to meet or exceed outcome targets. / Outcome 3: The private sector includes cyber security as part of all operational practices: AMBER/RED: Off-track, outcome targets unlikely to be met without action. / Outcome 4: Increased Criminal Justice System capability to investigate and prosecute cybercrimes: GREEN: Fully on track to meet or exceed outcome targets.
Overall Outcome Progress Rating:		AMBER
Overall Risk Rating:		Medium/High

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	N/A	N/A	N/A	N/A	3	AMBER
Risk Rating	N/A		Medium/High		Medium/High

Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?

The programme delivered 40 projects with a total value of £14,286,714. This provided national cyber authorities around the world with capacity building, legislative support, and access to threat intelligence and an international peer community. It also generated essential research and scoping to inform future work.

The programme’s relatively small Ukraine focused activities became useful in shaping the new CSSF Ukraine Cyber Programme as a direct response to Russia’s invasion of Ukraine.

The programme shifted its funding allocation from predominantly ODA to non-ODA in Financial Year (FY) 21/22, which enabled a greater breadth of projects, including projects that contributed to countering hostile state activity.

Key Results for FY 21/22:

Cybersecurity attitudes have improved among private citizens as a result of the programme. Over 18,500 people gained new cyber hygiene skills via Get Safe Online campaigns and the Ambassador Scheme. Survey results indicate significant improvement in cyber hygiene.

Several governments have increasingly protected their critical national infrastructure from cyber-attacks. Three countries (Nigeria, Botswana and Zambia) conducted National Cyber Risk Assessments with the support of the Home Office, seven Association of South East Asian Nations (ASEAN) member states gained awareness of the benefits of a Critical National Infrastructure Dependency project, and two countries (Morocco and Rwanda) received a Joint Integrated Cyber Analysis. In addition, India and Sri Lanka took part in incident response threat exercises, with a multi Cyber Security Incident Response Team (CSIRT) Commonwealth exercise was also delivered.

Cybercrime has also been directly addressed in the programme. A project in Africa with Interpol known as Operation Falcon II, supported the arrests of 11 suspected members of a prolific international cybercrime network in Nigeria. Interpol referenced Foreign Commonwealth and Development Office (FCDO) funding in their public reporting of the operation.

Key Lessons:

The programme could target more activity towards engagement with the private sector. The programme could adopt a similar approach to the Digital Access Programme, where projects have regularly brought the private sector in, especially in key Critical National Infrastructure sectors.

Key Recommendations for FY 22/23

The programme should consider revamping the Monitoring, Evaluation and Learning (MEL) approach and designing a more streamlined and smaller programme answering to the four portfolio outcomes. This should include fewer projects overall, with each project clearly working towards one of these outcomes.

A review should be done to decide which geographical areas the programme will focus on. And then to ensure that this matches wider UK cyber country prioritisation, including de conflicting with existing programmes operating in these specific countries/regions. This has begun with the development of dedicated regional programming from FY22/23, but successor programming should consider how a global programme with few projects complements this.

There should be consideration given to developing a new information management system showing programme and project outcome aims, outputs, spend and country coverage covering whole portfolio. This is already underway, but should be finalised as soon as possible.

Design a new process for this programme to engage the FCDO’s international cyber network and programme staff overseas prior to commissioning new projects, and ensure lessons learned from previous programming are integrated into new programme design.

The programme should work with the new Cyber Monitoring, Evaluation and Learning (MEL) contractor to ensure a clearer process is developed to monitor how projects are furthering specific outcomes. It should also explore a more in depth look at sustainability across the programme and review overall programme management, particularly reporting processes.

In the medium term, the programme should give further consideration to narrow the scope of the programme, in light of Portfolio reprioritisation since February 2022 and the creation of a new and separate Ukraine Cyber Programme. The programme scope should be clearly aligned to both the National Cyber Strategy Global Leadership pillar and all four portfolio level outcomes. This will give the programme more of a niche direction and identity alongside new regional CSSF cyber programmes.
There is also an opportunity to raise ambition on gender and social inclusion, and develop a more cohesive approach.