Annual Review (FY 21/22)

A. Summary Sheet
Programme Title	CSSF Ukraine Programme
Programme ID	C-EEA-005
Country and Region	Ukraine, Eastern Europe and Central Asia (EECAD)
IATI Unique ID	CSSF-05-000004
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), Ministry of Defence (MOD), Her Majesty’s Revenue and Customs (HMRC), National Crime Agency (NCA)
Total Budget	ODA: £20.994m	Non-ODA: £29.142m
Budget this FY	ODA: £20.994m	Non-ODA: £29.142m
Spend this FY	ODA: £22.723m	Non-ODA: £31.352m
Time Frame	Start Date: April 2021	End Date: March 2022

Outcome Assessment	Outcomes scored were variable with mostly 4s. As per the Annual Review TOR, projects are scored solely on whether they were ‘on track’ pre-full-scale invasion. Indicators directly interrupted by the full-scale invasion have been marked as ‘NA’ and removed from scoring calculations. Most of the confidence statements underlying the outcome assessment are rated medium with one poor and one good.
Overall Outcome Progress Rating:		3.84
Overall Risk Rating:		Medium/High

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c*		2021/22
Programme Rating	B	B	B	A	A	A	A	4 / (A)	Amber (B)	Outcome: Green	Output:3.84
Risk Rating	Medium	Medium		Medium		Medium/ High		Medium/ High		Medium/High (Pre-invasion)

What Support Did the UK Provide in FY 21/22?
In FY 21/22, the Ukraine CSSF Programme continued to support the delivery of the Russia and Ukraine HMG Strategies to ensure a united, stable, sovereign and resilient Ukraine. In total, the programme provided over £50m of support focused on the following priority areas: to end the (2014) conflict and defend human rights; to address structural instability (anti-corruption); build capability of security and defence sectors; and tackle gender inequality. In complement to the full spectrum of HMG initiatives, the CSSF Ukraine Programme was actively supporting the independence, sovereignty, and defence capability of the Ukrainian state.

Key Lessons from FY 21/22
The lessons learned are internal to the Embassy and are in hindsight of the full-scale invasion’s effects on overall programme preparedness to manage projects and continue delivery:
Contingency Planning: The full-scale invasion underlined the importance of contingency planning. Overall, it is this review’s opinion that the Embassy’s contingency plans were well executed. Pre-full-scale invasion contingency planning allowed for deployment and immediate use of technical advisers such as (special defence and humanitarian advisers) which supported the immediate response to the full-scale invasion and helped manage the extreme workload within the Embassy. Pre-existing CSSF Ukraine Programme governance systems (i.e., Post Project Boards (PPB)) were increased in frequency from monthly to weekly. Post project boards allowed for co-ordination and decision making. They directly resulted in successful project pivots and responsiveness under the CSSF.
- Financial Management: Agile budget management practices have proved critical in allowing the CSSF Ukraine Programme to pivot during the full-scale invasion. The Embassy staff creatively made use of budget management tools and systems within the CSSF such as the use of no-cost extensions and 5% discretionary spend of project values. This allowed individual projects the space to pivot and change their interventions in direct response to the full-scale invasion.
- Humanitarian Activity: In hindsight, the ability of the CSSF Ukraine Programme to quickly respond to new and emergent humanitarian needs is in part due to the experience and pre-existing humanitarian project partners - even though the humanitarian programme ended in March 2021 and prior to the full-scale invasion the Embassy had started to de-prioritise humanitarian spending in order to hone the CSSF’s focus on stabilisation. In certain projects, CSSF Ukraine programme has stepped up post-full-scale invasion to respond to humanitarian demands despite their distance from original remits and frameworks.
- Leadership and Culture: The importance of embassy, EECAD, Joint Funds Unit (JFU) and programme leadership must be recognised. Political acumen, dedication and leadership set a cultural standard of excellence and mutual support. This particularly enabled CSSF Ukraine Programme’s success through a clearly articulated vision and its’ strategic direction in response to the full-scale invasion. Supported by effective pre-planning, the CSSF Ukraine Programme impressively managed to regroup, pivot and respond to the unprovoked Russian full-scale invasion with continuous, adaptive and responsive support to Ukraine at all levels of engagement.

Key Recommendations for FY 22/23
Recommendation Summary	Owner	Timeline for Action
Future Contingency Planning: While there was a culture of support and concern for staff welfare within the Embassy, the personal toll on all the Embassy staff has been immense, with many colleagues working beyond capacities in uncertain circumstances. Bespoke counselling and well-being support to the Embassy staff was established. It is recommended that there is further exploration of how best to mitigate capacity gaps in advance and ensure support from outside the Embassy is tailored to meet specific post requirements.	Ukraine Programme Team (UPT)	31 March 2023
Share Lessons Learned with EECAD’s Ukraine Humanitarian Team: The CSSF Ukraine Programme should remain connected to any future UK funded humanitarian response programming, with close-working and co-ordination. It is recommended that at minimum the CSSF Ukraine Programme Team share lessons learnt on immediate crisis response with EECAD’s Ukraine Humanitarian Team. An important lesson to share includes the localised response of CSSF Ukraine programme’s civil society partners who pivoted to humanitarian assistance with remarkable speed, reach and resilience.	UPT	31 March 2023
Highlight the CSSF Ukraine Programme’s unique role and build on programming strengths in the context of the full-scale invasion: FY 21/22 programming has provided the groundwork for the CSSF Ukraine Programme to provide unique support within an increasingly crowded donor landscape. The multi-donor Partnership Fund for a Resilient Ukraine (PFRU) is the only political stabilisation tool in operation in Ukraine and a strong example of the benefits of CSSF’s high risk appetite. The CSSF has a war crimes and accountability sub-programme operating and joining up efforts at the international, national, and local levels. It is recommended that the Embassy should continue to hone and articulate the UK’s unique role in the context of a significant uplift in international support for Ukraine.	UPT	Continue within FY 22/23
Strictly rationalise the CSSF Ukraine Programme’s focus and only fund projects that are relevant to embassy objectives: the Embassy should consider how best it strikes the right balance between responding to the ongoing full-scale invasion and rationalizing the CSSF Ukraine Programme’s focus. The Delivery Working Groups (DWGs) are an important innovation, enabling cross-FCDO and cross-sectoral collaboration to deliver recently defined six-monthly objectives. It is strongly recommended that it should be a strict requirement of PPB to interrogate project relevance very critically to these objectives, before granting approvals.	UPT working / with DWGs and London Team	Start within FY 22/23
Mainstream Gender, Equality and Social Inclusion (GESI) into individual project design and delivery: All projects should be required to meet a minimum GESI Marker Category C, while striving to increase the number of Category E projects. An updated GESI (as opposed to Gender Equality Marker) programme stocktake is recommended.	UPT / with London Team	Continue within FY 22/23
Risk Appetite: The CSSF Ukraine Programme’s heightened risk appetite has enabled a flexible response to the full-scale invasion. Looking forward, it is recommended that the programme conduct a refreshed and strategic assessment of its risk appetite and tolerance to ensure future project activities sit within agreed and acceptable bounds.	UPT	31 March 2023