Annual Review (21/22)

Summary Sheet
Programme Title	Central Asia
Programme ID	C-EEA-0001
Country and Region	Central Asia (Kazakhstan, Kyrgyzstan, Tajikistan, Turkmenistan and Uzbekistan)
IATI Unique ID	CSSF-05-000001
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office, Ministry of Defence, National Crime Agency
Total Budget	ODA: £2.085 million	Non-ODA: £0.3 million
Budget this FY	ODA: £2.085 million	Non-ODA: £0.3 million
Spend this FY	ODA: £2.080 million	Non-ODA: £0.202 million
Time Frame	Start Date: 01 April 2021	End Date: 31 March 2022

Outcome Assessment	The overall outcome score for the Central Asia programme is Amber. The individual projects have (or will, in instances where extensions were granted) largely achieve their stated outcomes which are, for the most part, focused on increasing individual or institutional capacity and capability. The relevance, delivery and overall management of the programme by the Programme Hub has ensured it continues to be strategic, supported by teams across HMG and FCDO and is responsive to and well informed by changes in context.
Overall Outcome Progress Rating:		3
Overall Risk Rating:		Medium

Summary of Programme Performance
Year	2016/17a	2017/18b		2018/19b		2019/20b		2020/21c		2021/22
Programme Rating	B	A	B	A	B	A	B	4	Amber	3	Amber
Risk Rating	Low/Medium	Low/Medium		Low/Medium		Low/Medium		Low/Medium		Medium
Programme changes during this period
Note: a output scores; b output / outcome scores; c scale of output delivery / outcome progress rating

What Support Did the UK Provide in FY 21/22?

The programme funded various projects which were primarily focused on improving the capacity of media, supporting the prevention and response to gender based violence (GBV), developing policy action on climate & improving UK defence partnerships.

Key Results for FY 21/22:

- The UN Population Fund (UNFPA) rapidly established shelters in Kyrgyzstan and delivered dignity kits to Afghan refugees following the fall of Kabul
- The Tajik Family Planning Association engaged female as well as male religious leaders in highlighting gender norms to help prevent violence against women
- Demonstrated progress on the national provision of multi-sectoral, survivor-centred Gender Based Violence (GBV) services to vulnerable women and girls in all five Central Asian Republics
- All countries are engaged in the preparation for COP27
- Regional collaboration on workshops in Kyrgyzstan and Tajikistan, to raise awareness of climate change amongst young people.
- The Institute for War and Peace Reporting (IWPR) project developed a New Media Handbook, supporting journalists to use digital tools and methods in their work.
- A total of 2999 (2240 female and 759 male) students and tutors of journalism departments in all CARs attended the courses on new media, including skills on conflict and gender-sensitive reporting, and delivering COVID-19 messaging.

Key Lessons

- The programme notably responded well to the changing global and regional contexts throughout the year including events in Kazakhstan, Afghanistan and Ukraine which showcased both resilience and agility.
- Project colleagues were able to work in close collaboration with project implementers and utilised adaptable and agile programming well to deliver.
- The effective management of the programme including using evidence and analysis in programme redesign and building good relationships with partners/implementers has been noted as a good learning tool for other programmes.

Key Recommendations for FY 22/23

- Share the Theory of Change and results framework for the new programme with Eastern Europe and Central Asia Directorate (EECAD) and their Monitoring and Evaluation (contractor), including for quality assurance or ongoing support needs.
- Bring together implementing partners on a regular basis (such as quarterly or biannually) to encourage sharing of technical expertise, achievements and challenges, opportunities for collaboration and capacity building.
- Arrange an annual programme conference or gathering to address topical or timely needs for the team on different processes of themes.
- Explore opportunities to align admin spend with the CSSF requirement of 5% to ensure the best value for money, following any realignment to the programme team structure.
- Work with partners to consider opportunities for proactive and reactive political/diplomatic engagement to support the delivery of individual projects.
- Consider ways to communicate the programme results across EECAD and the wider CSSF Network.