Annual Review/Programme Completion Review (21/22)

A. Summary Sheet

Programme Title	Eastern Neighbourhood
Programme ID	C-EEA-0003
Country and Region	Armenia, Azerbaijan, Belarus, Georgia and Moldova, Eastern Europe and Central Asia (EECAD)
IATI Unique ID	CSSF-05-000002
HMG Partners / (Lead in bold)	Foreign, Commonwealth and Development Office (FCDO), Ministry of Defence (MOD)
Total Budget	ODA: £7.102m	Non-ODA: £1.031m
Budget this FY	ODA: £7.102m	Non-ODA: £1.031m
Spend this FY	ODA: £6.711m	Non-ODA: £0.654m
Time Frame	Start Date: 1st April 2021	End Date: 31st March 2022

Outcome Assessment	Outcomes scored were variable; some outcomes achieved considerable success, whilst others did not deliver anticipated results. Part of this was due to the context, which rendered a number of the outcomes unreachable, however there were also issues with both measurement and uncaptured successes.
Overall Outcome Progress Rating:		2
Overall Risk Rating:		High

Summary of Programme Performance
Year	2019/20		2020/21		2021/22
Programme Rating	A	A	2	Amber/Red	2	Amber/Red
Risk Rating	Medium		High		High
Programme changes during this period
Note: Output / Outcome score

What Support Did the UK Provide in FY 21/22?
- Armenia: Strengthened the resilience of communities along the Armenia/Azerbaijan border and delivered disaster risk management training to conflict affected communities.
- Azerbaijan: Supported women resource centres with psychological, educational, legal and economic assistance and delivered de-mining support in conflict-affected areas.
- Georgia: Supported women’s participation in decision-making processes and English language learning in conflict affected areas of the country. Contributed to the clearance of unexploded objects within Abkhazia and provided support to Abkhazia citizens through businesses and NGO’s.
- Enabled the continuation of a shelter for survivors of domestic violence in Transnistrian region of Moldova. Facilitated policy exchanges between gender-based violence experts in Moldova and Transnistria and embedded international standards for domestic violence response in Transnistria’s health sector and police forces.

Key Results for FY 21/22:

- Improved resilience within Armenia to respond to emergencies with clear disaster risk management plans; Armenian government developing a register of emergency foster families and social services helpline in use across the country.
- Recognition of the UK’s contribution to demining in Azerbaijan at the highest levels of Government, enabling economic development of cleared areas; increasing focus of gender UNDP engagement with key interlocutors, aimed at strengthening delivery of gender-responsive services; and women provided with psychological, legal, economic and social support to enable them to play a more active role in society.
- Significant contribution to the development of Georgia’s national action plan on gender, adopting a far more participatory approach; over 400 explosives cleared in Abkhazia in 2021/22; 3) developing sustainable businesses in Abkhazia through economic support, whilst developing business links between Abkhazia and other regions in the country; 4) planning and designing of a new Georgia cyber security centre.
- Increase in contact and exchange between gender-based violence experts in Moldova and Transnistria; increase in police officers and health officials’ knowledge of gender-based violence in Transnistria, leading to an increase in effective referrals to the shelter; recognition of the UK with both the de facto authorities and people of Transnistria for supporting transformation on an issue of social importance; trained the Transnistrian de facto authorities’ to assist Ukrainian refugees in recognising domestic violence and human trafficking risks.

Key Lessons

- The UK is playing a leading role in the region on issues such as gender and cyber security, through high quality projects and output level successes.
- The programme has had more difficulty demonstrating outcome level change, partly due to the deterioration in the context in FY 2012/22 but also as the change delivered by some partners is difficult to evidence.
- The shift in strategic focus during the review period created uncertainty for the programme. The link between high-level policy direction and programming implications was not sufficiently bridged, leading to confusion on strategic direction within and outside the programme team.
- Current governance structures need to be refreshed to improve the decision-making processes within the programme, and to facilitate discussion on core programme issues including risk, monitoring and evaluation and Value for Money (VfM).

Key Recommendations for FY 22/23

Strategic Fit
- Additional policy resource is needed to provide the bridge between strategic direction and programme operations.
- Programme stakeholders having a clearer understanding of roles and responsibilities of both Programme, Results and Advisory Group (PARG) and Joint Funds Unit (JFU) should facilitate better discussions and decision making.
- Country posts, the Hub and UK based teams need to recognise that the programme pivot will take time to adapt. Allocating a proportion of the budget to smaller, more innovative methods of combatting state threats would help, although this is also dependent on having clear evidence and policy direction.

Governance
- Additional support for the Senior Reporting Officer to support the delivery of a programme that is both complex in its remit and contextual environment.
- Terms of Reference for each board and clear lines of escalation to ensure decisions are made at the appropriate level and complimentary governance calendars to ensure sequencing of decisions. This will also help to support risk reviews at the appropriate level.
- A dedicated operational programme board to be set up to manage the delivery of the Eastern Neighbourhood (EN) Programme, which feeds into the EN Strategy Board.
- The Hub model should be more aligned to that of a programme management office and should include a secretariat, risk management and reporting function.

Monitoring and Evaluation
Develop a programme-wide results framework that accurately reflects the breadth of work, whilst remaining usable by stakeholders improve the programme’s ability to record and measure change at outcome level, including through effective baselining. Have results frameworks in place and agreed by the programme hub for all projects.