Annual Review (21/22)
Programme Title			CSSF Lake Chad Basin Programme
Programme ID			C-AFR-0011
Country and Region			Nigeria, Cameroon, Niger and Chad
IATI Unique ID
HMG Partners (Lead in bold)			Foreign, Commonwealth and Development Office (FCDO), Ministry of Defence (MOD)
Total Budget			ODA: £23.7m			Non-ODA: £24.9m
Budget this FY			ODA: £9.0m			Non-ODA: £6.6m
Spend this FY			ODA: £8.7m			Non-ODA: £5.9m
Time Frame			Start Date: 01 April 2021			End Date: 31 March 2024
Outputs								Individual Output Rating
Enhanced capacity and political will of regional governments to develop inclusive roadmap for peace.								4
Improved conduct and performance of regional military forces; and improved Nigerian military and Multinational Joint Task Force (MNJTF) operational and strategic capability.								2
Former low risk Violent Extremist Organisations cadres de-radicalised and reintegrated.								N/A
Improved civ-mil coordination and human rights compliance of security forces.								3
Area-based stabilisation improves security, services and livelihood options for all civilians.								4
Improved capability of State Governors to deliver benefits for at-risk communities.								3
Enhanced programme coherence, and mainstreaming of Monitoring, Evaluation & Learning (MEL), gender and value for money.								3
Overall Rating of Output Delivery								3
Outcome Assessment	In its first year, the LCB programme exceeded expectations in delivering progress towards a peaceful political settlement, making the most of conducive external conditions. Defence cooperation elements faced challenges in achieving the scale of change desired, although current work to refine the scope of defence activity will seek to solidify pockets of progress. Programme ambitions on social cohesion, security and justice are being met, with an increase in perceptions of safety and security within areas of north-east Nigeria and success in supporting civil military relations. Work to improve service delivery and accountability at community level also saw good progress with increased community access to basic services in areas of north-east Nigeria and initial work to develop a delivery unit in Borno State. / The broader achievement of some outcomes will be highly dependent on programme activity that had yet to start, including Disarmament, Demobilisation, and Reintegration (DDR) and transitional justice projects, due to begin after the March 2022 Wilton Park Conference. Given the operating context, progress will remain vulnerable to events on the ground, such as future VEO incursions and defections, fluctuating political will and cooperation from partner governments and services and the outcome of the 2022 elections.
Overall Outcome Progress Rating:							Amber
Overall Risk Rating:							High
Summary of Programme Performance
Year		2020/21			2022/23				2023/24
Programme Rating		3		Amber
Risk Rating		High

What Support Did the UK Provide in FY 21/22
Defence training and capacity building within the Nigerian armed forces, Cameroon Bataillon d’Intervention Rapide (BIR), Directorate General for External Research (DGRE), and the Multinational Joint Task Force (MNJTF). Training and support of defence activity in Cameroon led to substantial engagement with partner forces and insight into the Cameroonian military system.
Organisation and delivery of a Wilton Park conference, bringing together key regional stakeholders on Transitional Justice (TJ) and DDR. This demonstrated federal and regional commitments to DDR and TJ, and laid foundations for subsequent interventions in both areas.

Design and initiation of the Lake Chad Basin Support Framework to embed UK advisers in north-east Nigeria and relevant organisations.

Support to the Centre for Civilians in Conflict (CIVIC), a CSO facilitating dialogue between communities and security services and providing training on the protection of civilians. This provided a range of examples where community protection committees have raised security concerns with security forces and state administrators, and action has been taken in response.

Financial support, stabilisation expertise, and third-party monitoring contributions to the Regional Stabilisation Facility (RSF), reinforcing the UK’s reputation as a trusted and well-informed partner. RSF interventions also led to an increase in perceptions of security in Nigerian locations, broadly attributed to the Nigerian government.

Support to the development of a Borno State Delivery Unit (BSDU) and funding for a pilot project to provide a durable resettlement model for displaced people in Adamawa state.

Key Lessons
The programme's influence on overall national and regional military effectiveness relies on the commitment of national militaries and their willingness to cooperate. Without this programme scope within Nigeria is limited.

Broader UK effort has been essential to progress allowing the UK to drive political and donor cohesion through the north-east Ambassadors group and other forums. Close engagement between the political and CSSF teams and alignment with the High Commission’s priorities has provided important benefits in areas of the programme dependent on political buy-in.

Individuals have been instrumental in tackling organisational and institutional challenges between CSSF and MOD. More formal arrangements should be put in place to support these relationships, such as a Service Level Agreement (SLA).

Internal approval processes can take longer than anticipated, impacting delivery. The complexity and risks warrant serious attention but need to be balanced against the impact of not delivering support.

The programme should build in more focus on gender equality and social inclusion in its results, developing a gender specific project, underpinned by gender analysis.
Key Recommendations for FY 22/23
- New coordination arrangements between MoD and FCDO need to be designed to support cross team and departmental relationships, formalised through a jointly agreed SLA.
- Op TURUS (MOD) should retain a clear focus on Human Security, given the UK’s prioritisation of Nigeria as a focus country for Women, Peace and Security.
- The programme should work closely with the BSDU to identify projects where its capabilities will be applied– the focus must be on demonstrating the benefits of a delivery led approach to the wider Borno State Government.
- All projects need to ensure compliance with fund gender requirements.