Annual Review (21/22)
Programme Title			CSSF Sahel Security & Stabilisation Programme
Programme ID			C-AFR-0023
Country and Region			Mali, Niger (the Sahel)
IATI Unique ID			CSSF-03-000024
HMG Partners (Lead in bold)			Foreign, Commonwealth and Development Office (FCDO), National Crime Agency (NCA)
Total Budget			ODA: £13.272m			Non-ODA: £7.9m
Budget this FY			ODA: £6.272m			Non-ODA: £3.0m
Spend this FY			ODA: £5.7m			Non-ODA: £1.92m
Time Frame			Start Date: April 2021			End Date: March 2024
Outputs								Individual Output Rating
Stabilisation: Better co-ordinated, more civ-mil integrated, politically informed UK support for national and international stabilisation efforts in Multidimensional Integrated Stabilisation Mission in Mali (MINUSMA), UK deployment area of operation and wider Sahel								3
Women, Peace and Security (WPS): Increased involvement of women in community- based organisations and peace processes leads to more inclusive stabilisation activities								3
Civilian-Military: Increased UK support to improve civ-mil coordination in MINUSMA, UK deployment area of operation and wider Sahel								3
Security Partnerships: Enhanced capacities of Malian and other regional security partners in communicating effectively and providing human rights/IHL compliant security								2
Threat detection: Enhanced capacities of Sahelian military and intelligence actors to detect and tackle threats								3
Overall Rating of Output Delivery								3
Outcome Assessment		While the outcomes represent a credible approach to stabilisation, they are too broad and complex for successful delivery by the programme. Some activity areas are not a strong fit for the programme’s core aims, with insufficient links between what is being delivered and measured. / Activity to reduce community-level violence is unlikely to achieve the desired results and relies on survey data which is sufficiently rigorous. / The links from WPS and humanitarian activity political settlement outcomes are insufficient. WPS work is better seen as contributing to reducing community-level violence and humanitarian should no longer be supported by this programme. International stabilisation activity needs significant strengthening, including increasing the numbers reached, better evidence, analysis and coordination.
Overall Outcome Progress Rating:							Amber
Overall Risk Rating:							High
Summary of Programme Performance
Year	2019/20				2020/21				2021/22
Programme Rating	N/A			N/A	N/A			N/A	3	Amber
Risk Rating	N/A				N/A				High

What Support Did the UK Provide in FY 21/22
Stabilisation in north-east Mali: the Gao Stabilisation Fund linked to the UK’s deployment to MINUSMA in and around the Gao and Ménaka region. This supported five projects operating in the Gao region including activity on community resilience, youth employment, countering misinformation and WPS. A Sahel Stabilisation Network to exchange and coordinate advisory experience and capacity. Support to the MINUSMA Trust Fund in and around the Gao region and support to third party monitoring.

Other Stabilisation Support: support to prevent the further spread of inter-ethnic violence in central Mali; funding of local government strategic communications support to stabilisation activities; funding of a land governance programme supporting village land commissions. Support to the Government of Niger’s stabilisation agency, targeting communities at risk of radicalisation or instability.

Civ-Mil Coordination: support of the UN Office for the Coordination of Humanitarian Affairs (OCHA); support to safeguard humanitarian access in central Sahel.

Threat detection: NCA support to enhance capacities of Sahelian security actors to detect and tackle threats, disrupt human trafficking networks and protect victims by support to counter serious and organised crime in the Gao region of Mali.
Support to the Nigerien National Stabilisation Agency to fund community dialogues and micro-projects to strengthen livelihoods, promote community engagement and strengthen the presence of the state.

Key Lessons
The programme’s ambition levels are unrealistic in the difficult and dynamic context and given limited team capacity. Building in a realistic inception phase can help to manage expectations and enable adapt.
The programme tools and frameworks should be adapted to ensure they provide the most benefit to the team in implementing programme activities and identifying results.

Given the operating context, a more systematic approach to analysing and responding to context trends will benefit more strategic prioritisation and implementation.
Key Recommendations for FY 22/23
- Adapting the programme to make it more focused including planning for the end of the UK MINUSMA deployment in the next FY. A more focused programme would likely have a smaller budget and a reduced number of interventions. The theory of change should be updated following any changes to the overall approach.
- Refocus activity on the tri-border area between Mali, Niger and Burkina Faso to reflect the key risk to the region and the UK of regional ‘contagion’ of extremist groups into coastal West African states.
- A strategy should be developed to shape and support the team’s ability to use the programme to influence national, regional and international stakeholders.
- Given the dynamic context, the programme team should review trends each quarter to make necessary adjustments to activity.
- Consider whether there should be a different balance of effort between supporting standalone projects and reforming and strengthening broader existing structures such as the MINUSMA Trust Fund or the UNDP Regional Stabilisation Fund (RSF).
- Value for Money (VFM): The programme needs to more systematically capture, analyse and present its wider effect and set this out in terms of VFM.