Annual Review
Programme Title	CSSF Somalia Programme
Programme ID	C-AFR-0025
Country and Region	Somalia
IATI Unique ID
HMG Partners / (Lead in bold)	Ministry of Defence (MOD), Foreign, Commonwealth & Development Office (FCDO)
Total Budget	ODA: £9.762m	Non-ODA: £14.273m
Budget this FY	ODA: £9.762m	Non-ODA: £14.273m
Spend this FY	ODA: £10.643m	Non-ODA: £13.088m
Time Frame	Start Date: 1 April 2021	End Date: 31 March 2022

Outputs	Scale of Deliver
The Somali National Army (SNA) demonstrate improved operational capability and new approaches to address community protection are tested.	3
Civilian oversight structures in Federal Government of Somalia (FGS) and Federal Member State (FMS) Institutions are strengthened and demonstrate improved capacity and capability to plan for and deliver security transition.	3
Transition operations in targeted locations are increasingly well-coordinated between the African Union Mission in Somalia (AMISOM) and Somali security architecture.	2
FGS and select FMSs have improved capability to plan, coordinate and implement stabilisation efforts in a gender and conflict sensitive way, with the engagement of local communities.	3
Inclusive community and civil society-led stabilisation and security activities build social cohesion in select districts and provide greater understanding on how to engage women in these processes.	3
Religious leaders have the tools and capacity to counter al Shabaab (AS) narratives and approaches are identified to counter AS financial access.	3
FGS have the capacity to deliver activities that support inclusive alternatives (including women and girls) for low level defection and mechanisms to support high level defection are identified.	3
Overall Scale of Output Delivery	3

Outcome Assessment	The programme operates in a high risk and challenging operating environment, but the overarching strategic aims of this programme are the right ones to help achieve the overarching goals. In some instances, the delivery methods may need to adapt to context – and it is key that the programme team continue to capture lessons on how to operate in Somalia. Despite the changes in circumstances such as delayed general elections, a new Government and the transition from AMISOM and African Union Transition Mission (ATMIS), the programme is likely to deliver against the intended targets as set out in the results framework by the end of the programme cycle. Most projects have either achieved or overachieved against their targets. Further work should be done on the outcome indicators to ensure these can adequately capture outcome level change.
Overall Outcome Progress Rating:						Amber
Overall Risk Rating:						High
Summary of Programme Performance
Year	2016/17	2017/18		2018/19		2019/20			2020/21		2021/22*
Programme Rating	N/A	N/A		N/A		N/A			N/A		3	Amber
Risk Rating						High
Programme changes during this period	Elections did not happen when anticipated during this reporting cycle. Stalled elections impacted on the political buy-in and mandate to enable the required institutional changes. / There were minor changes to intended activity at project level: not including Darwish training as part of the security work; Counter AS finances work was still being scoped, so not delivered against.
Note: First year of programme delivery. Output / outcome progress ratings.

What Support Did the UK Provide in FY 20/21?
The programme delivered activity covering security governance, early recovery, transition and Women Peace & Security (WPS) that supported the policy objective of Somalia having capable and accountable security forces and institutions to take greater responsibility for security as the AMISOM evolves.
The activity included UK military training and support to the Somali National Army (SNA) and support to other security actors, liaison, mentoring and advice to the AMISOM mission and the UN support mission, civilian advisory support to Somali Ministries and security institutions, support for effective and accountable government control in areas recovered from AS and countering AS through support to address the AS threat and reduce AS’s capability.
The programme adapted to the context and continued to deliver against project level activity during a very difficult and uncertain period around general elections. This complicated delivery and slowed across several areas. The Early Recovery project delivers effectively against CSSF key principles of being agile, taking risks with new approaches and having catalytic affect by building further support. The Security Governance strand has played a key role in enabling the UK to be able to deliver against UK objectives.
Key Lessons
- While there are risks of capacity substitution, having embedded advisors supporting the Somalia government has been crucial to navigate challenges and provide access to the British Embassy Mogadishu to influence direction where they would otherwise be unable to gain access.
- Gender sensitivity is in a much better place with key pieces of work (GESI analysis and GESI strategy) undertaken to help understand the centrality of gender dynamics to the conflict.
- Op Tangham and Security Team recognise that a more effective delivery model should be developed which they should seek to proactively drive forward.
Key Recommendations for FY 21/22
- Reframe the Results Framework and especially outcome level indicators to better monitor higher level change across project strands. Ensure that key cross-cutting themes are captured across these strands.
- Strategy: the programme would benefit from greater clarity from policy leads of the priorities it should address, given the multiple UK strategies in play (the “hierarchy of objectives). Priorities and their evolution need to be communicated clearly to the programme team to help shape practical options.
- Wider HMG and International activity: Greater consideration should be taken to ensure that the CSSF programme docks into other HMG activity.
- Further action should be taken to address implementing partner performance in some areas. The programme team need to be propositional to take the lead and try new implementation approaches.
- The team should look at scope to consolidate the number of implementing partners or look at using consortiums as contracts end.